## GRNRegister638581911111111958_0
GRN Register
From 01-07-2024 To 31-07-2024
Page 1 of 1
Total Records: 155 Records 1 to 155
Project_Name | Supplier_Name | Material_Name | Received_Store | GRN_No | GRN_Date | GRNType | Recd_Qty | Amount | PO_SrNo | PO_Qty | Rate | Challan_No | Challan_Date | Status | VehicleNo | Billing_Status | GRN_Remark
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239555 | 2024-07-29 16:36 | Purchase | 6.5 | 22160.593 | 69326 | 54.7 | 4022.9999 | 051437 | 2024-07-28 | Normal | MH12KP7715 | Billed | Gate No.17509 Dt.28/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239589 | 2024-07-30 15:03 | Purchase | 6 | 20455.932 | 69326 | 54.7 | 4022.9999 | 052365 | 2024-07-29 | Normal | MH12KP7717 | Billed | Issue No.17517 Dt.29/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239590 | 2024-07-30 15:04 | Purchase | 6 | 20455.932 | 69326 | 54.7 | 4022.9999 | 052392 | 2024-07-29 | Normal | MH11AL5997 | Billed | Issue No.17518 Dt.30/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239591 | 2024-07-30 15:27 | Purchase | 6 | 20455.932 | 69267 | 31.995 | 4022.9998 | 052415 | 2024-07-30 | Normal | MH11AL5998 | Billed | Gate No.17519 Dt.30/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239592 | 2024-07-30 15:28 | Purchase | 6 | 20455.932 | 69267 | 31.995 | 4022.9998 | 2609 | 2024-07-30 | Normal | MH12KP7717 | Unbilled | Gate No.17520 Dt.30/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239593 | 2024-07-30 15:30 | Purchase | 6 | 20455.932 | 69326 | 54.7 | 4022.9999 | 2610 | 2024-07-30 | Normal | MH11AL5997 | Unbilled | Gate No.17521 Dt.30/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239410 | 2024-07-23 19:01 | Purchase | 6.5 | 22160.593 | 69267 | 31.995 | 4022.9998 | 049387 | 2024-07-22 | Normal | MH11AL5997 | Billed | Gate No.17447 Dt.22/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239411 | 2024-07-23 19:05 | Purchase | 6 | 20455.932 | 69267 | 31.995 | 4022.9998 | 049412 | 2024-07-22 | Normal | MH12HD4699 | Billed | Gate No.17448 Dt.23/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239412 | 2024-07-23 19:06 | Purchase | 6 | 20455.932 | 69267 | 31.995 | 4022.9998 | 049441 | 2024-07-23 | Normal | MH12KP7719 | Billed | Gate No.17449 Dt.23/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239422 | 2024-07-24 12:52 | Purchase | 6.5 | 22160.593 | 69317 | 15.058 | 4022.9998 | 049899 | 2024-07-23 | Normal | MH12VF4144 | Billed | Gate No.17456 Dt.23/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239423 | 2024-07-24 12:55 | Purchase | 6.5 | 22160.593 | 69317 | 15.058 | 4022.9998 | 049911 | 2024-07-23 | Normal | MH12VF4123 | Billed | Gate No.17457 Dt.24/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239424 | 2024-07-24 12:57 | Purchase | 2.058 | 7016.3847 | 69317 | 15.058 | 4022.9998 | 049926 | 2024-07-24 | Normal | MH12UM4090 | Billed | Gate No.17458 Dt.24/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239425 | 2024-07-24 12:59 | Purchase | 4.942 | 16848.8693 | 69326 | 54.7 | 4022.9999 | 049926. | 2024-07-24 | Normal | MH12UM4090 | Billed | Gate No.17458 Dt.24/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Downpour) | GDT/AGGE | 239426 | 2024-07-24 13:01 | Purchase | 6 | 20455.932 | 69326 | 54.7 | 4022.9999 | 049939 | 2024-07-24 | Normal | MH12VF2666 | Billed | Gate No.17459 Dt.24/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239558 | 2024-07-29 16:42 | Purchase | 6.5 | 23400 | 69253 | 86.374 | 4248.0001 | 051409 | 2024-07-27 | Normal | MH11AL5997 | Billed | Gate No.17503 Dt.27/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239559 | 2024-07-29 16:46 | Purchase | 6.5 | 23400 | 69253 | 86.374 | 4248.0001 | 051412 | 2024-07-27 | Normal | MH12RN4287 | Billed | Gate No.17504 Dt.27/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239560 | 2024-07-29 16:52 | Purchase | 6.5 | 23400 | 69253 | 86.374 | 4248.0001 | 051419 | 2024-07-27 | Normal | MH12KP7719 | Billed | Gate No.17506 Dt.28/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239561 | 2024-07-29 16:53 | Purchase | 6.5 | 23400 | 69253 | 86.374 | 4248.0001 | 051422 | 2024-07-27 | Normal | MH12KP7719 | Billed | Gate No.17507 Dt.27/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239562 | 2024-07-29 16:55 | Purchase | 6 | 21600 | 69253 | 86.374 | 4248.0001 | 051426 | 2024-07-27 | Normal | MH12HD4699 | Billed | Gate No.17508 Dt.28/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239563 | 2024-07-29 16:57 | Purchase | 6.5 | 23400 | 69253 | 86.374 | 4248.0001 | 051444 | 2024-07-28 | Normal | MH11AL5997 | Billed | Gate No.17510 Dt.28/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239564 | 2024-07-29 16:58 | Purchase | 6.5 | 23400 | 69253 | 86.374 | 4248.0001 | 18979 | 2024-07-28 | Normal | MH12KP7717 | Unbilled | Gate No.17511 Dt.28/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239565 | 2024-07-29 17:00 | Purchase | 4.5 | 16200 | 69253 | 86.374 | 4248.0001 | 051448 | 2024-07-28 | Normal | MH11AL5998 | Billed | Gate No.17512 Dt.28/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239566 | 2024-07-29 17:02 | Purchase | 5.5 | 19800 | 69342 | 26.45 | 4248 | 051447 | 2024-07-28 | Normal | MH12UM4090 | Unbilled | Gate No.17513 Dt.28/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239149 | 2024-07-16 15:01 | Purchase | 6 | 21600 | 69253 | 86.374 | 4248.0001 | 140 | 2024-07-15 | Normal | MH11AL5998 | Billed | Gate No.17409 Dt.16/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239150 | 2024-07-16 15:03 | Purchase | 6 | 21600 | 69253 | 86.374 | 4248.0001 | 141 | 2024-07-15 | Normal | MH12KP7717 | Billed | Issue No.17410 Dt.15/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239151 | 2024-07-16 15:06 | Purchase | 6 | 21600 | 69253 | 86.374 | 4248.0001 | 142 | 2024-07-15 | Normal | MH14KQ0859 | Billed | Issue No.17412 Dt.16/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239152 | 2024-07-16 15:07 | Purchase | 6 | 21600 | 69253 | 86.374 | 4248.0001 | 143 | 2024-07-16 | Normal | MH11AL5998 | Billed | Issue No.17413 Dt.16/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239153 | 2024-07-16 15:09 | Purchase | 6 | 21600 | 69253 | 86.374 | 4248.0001 | 144 | 2024-07-16 | Normal | MH12KP7717 | Billed | Issue No.17414 Dt.16/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M25 (Pumpable) | GDT/AGGE | 239154 | 2024-07-16 15:11 | Purchase | 6 | 21600 | 69253 | 86.374 | 4248.0001 | 145 | 2024-07-16 | Normal | MH14KQ0859 | Billed | Issue No.17415 Dt.16/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M35 (Downpour) | GDT/AGGE | 239405 | 2024-07-23 18:54 | Purchase | 6.5 | 22160.58 | 69317 | 27 | 4022.9978 | 2540 | 2024-07-23 | Normal | MH12KP7717 | Billed | Gate No.17450 Dt.23/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M35 (Downpour) | GDT/AGGE | 239406 | 2024-07-23 18:57 | Purchase | 6 | 20455.92 | 69317 | 27 | 4022.9978 | 2541 | 2024-07-23 | Normal | MH11AL5998 | Billed | Gate No.17451 Dt.23/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M35 (Downpour) | GDT/AGGE | 239408 | 2024-07-23 18:59 | Purchase | 6.5 | 22160.58 | 69317 | 27 | 4022.9978 | 2542 | 2024-07-23 | Normal | MH11AL5997 | Billed | Gate No.17452 Dt.23/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Downpour) | GDT/AGGE | 239165 | 2024-07-16 17:40 | Purchase | 6 | 21549.15 | 69273 | 18.4655 | 4237.9998 | 046270 | 2024-07-15 | Normal | MH12KP7717 | Billed | Gate No.17411 Dt.16/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Downpour) | GDT/AGGE | 239556 | 2024-07-29 16:38 | Purchase | 6 | 21549.15 | 69273 | 18.4655 | 4237.9998 | 051399 | 2024-07-27 | Normal | MH12KP7715 | Billed | Gate No.17502 Dt.27/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Downpour) | GDT/AGGE | 239557 | 2024-07-29 16:40 | Purchase | 6 | 21549.15 | 69273 | 18.4655 | 4237.9998 | 051414 | 2024-07-27 | Normal | MH11AL5998 | Billed | Gate No.17505 Dt.27/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239651 | 2024-07-31 18:14 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 052920 | 2024-07-30 | Normal | MH12KP7717 | Billed | Gate No.17527 Dt.30/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239652 | 2024-07-31 18:16 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 052928 | 2024-07-30 | Normal | MH12KP7715 | Billed | Gate No.17528 Dt.30/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239653 | 2024-07-31 18:17 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 052930 | 2024-07-30 | Normal | MH12KP7719 | Billed | Gate No.17530 Dt.30/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239659 | 2024-07-31 18:20 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 052966 | 2024-07-31 | Normal | MH14KQ0859 | Billed | Gate No.17531 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239660 | 2024-07-31 18:22 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 052965 | 2024-07-31 | Normal | MH12PQ2677 | Billed | Gate No.17532 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239661 | 2024-07-31 18:23 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 052971 | 2024-07-31 | Normal | MH12RN4287 | Billed | Gate No.17533 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239662 | 2024-07-31 18:24 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 052973 | 2024-07-31 | Normal | MH11AL5997 | Billed | Gate No.17534 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239663 | 2024-07-31 18:26 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 052976 | 2024-07-31 | Normal | MH11AL5998 | Billed | Gate No.17535 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239664 | 2024-07-31 18:27 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 052975 | 2024-07-31 | Normal | MH12VF4123 | Billed | Gate No.17536 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239665 | 2024-07-31 18:29 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 052978 | 2024-07-31 | Normal | MH12HD4699 | Billed | Gate No.17537 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239666 | 2024-07-31 18:30 | Purchase | 5 | 18911.015 | 69228 | 166.8625 | 4462.9996 | 052969 | 2024-07-31 | Normal | MH14GD4951 | Billed | Gate No.17538 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239667 | 2024-07-31 18:31 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 052979 | 2024-07-31 | Normal | MH12KP7717 | Billed | Gate No.17539 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239668 | 2024-07-31 18:33 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 052981 | 2024-07-31 | Normal | MH12KP7715 | Billed | Gate No.17540 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239669 | 2024-07-31 18:36 | Purchase | 3.705 | 14013.0621 | 69228 | 166.8625 | 4462.9996 | 052982 | 2024-07-31 | Normal | MH12VF2662 | Billed | Gate No.17541 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239670 | 2024-07-31 18:37 | Purchase | 2.795 | 10571.2574 | 69261 | 303.095 | 4462.9995 | 052982. | 2024-07-31 | Normal | MH12VF2662 | Billed | Gate No.17541 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239671 | 2024-07-31 18:38 | Purchase | 6 | 22693.218 | 69261 | 303.095 | 4462.9995 | 052983 | 2024-07-31 | Normal | MH12KP7719 | Billed | Gate No.17542 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239672 | 2024-07-31 18:40 | Purchase | 6.5 | 24584.3195 | 69261 | 303.095 | 4462.9995 | 052985 | 2024-07-31 | Normal | MH12VF2666 | Billed | Gate No.17543 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239673 | 2024-07-31 18:41 | Purchase | 6.5 | 24584.3195 | 69261 | 303.095 | 4462.9995 | 052990 | 2024-07-31 | Normal | MH12PQ2677 | Billed | Gate No.17544 Dt.31/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239522 | 2024-07-27 17:14 | Purchase | 6 | 22693.218 | 69261 | 303.095 | 4462.9995 | 050984 | 2024-07-26 | Normal | MH11AL5997 | Billed | Gate No.17484 Dt.26/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239523 | 2024-07-27 17:16 | Purchase | 6.5 | 24584.3195 | 69261 | 303.095 | 4462.9995 | 051001 | 2024-07-26 | Normal | MH12VF4123 | Billed | Gate No.17485 Dt.26/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239524 | 2024-07-27 17:17 | Purchase | 6.5 | 24584.3195 | 69261 | 303.095 | 4462.9995 | 051016 | 2024-07-26 | Normal | MH12VF4144 | Billed | Gate No.17486 Dt.26/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239525 | 2024-07-27 17:19 | Purchase | 6.5 | 24584.3195 | 69261 | 303.095 | 4462.9995 | 051002 | 2024-07-26 | Normal | MH12KP7719 | Billed | Gate No.17490 Dt.27/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239526 | 2024-07-27 17:21 | Purchase | 6 | 22693.218 | 69261 | 303.095 | 4462.9995 | 051020 | 2024-07-26 | Normal | MH12HD4699 | Billed | Gate No.17491 Dt.27/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239527 | 2024-07-27 17:22 | Purchase | 6.5 | 24584.3195 | 69261 | 303.095 | 4462.9995 | 21166 | 2024-07-26 | Normal | MH12VF2662 | Unbilled | Gate No.17492 Dt.27/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239528 | 2024-07-27 17:24 | Purchase | 6.5 | 24584.3195 | 69261 | 303.095 | 4462.9995 | 051022 | 2024-07-26 | Normal | MH12KP7715 | Billed | Gate No.17494 Dt.27/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239448 | 2024-07-25 15:25 | Purchase | 4.3425 | 16424.2165 | 69204 | 149.8425 | 4462.9996 | 2561 | 2024-07-24 | Normal | MH12KP7715 | Billed | Gate No.17468 Dt.24/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239449 | 2024-07-25 15:28 | Purchase | 2.1575 | 8160.103 | 69228 | 166.8625 | 4462.9996 | 2561. | 2024-07-24 | Normal | MH12KP7715 | Billed | Gate No.17468 Dt.24/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239450 | 2024-07-25 15:30 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 21144 | 2024-07-24 | Normal | MH12VF4123 | Unbilled | Gate No.17469 Dt.24/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239451 | 2024-07-25 15:32 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 21145 | 2024-07-24 | Normal | MH12VF2662 | Unbilled | Gate No.17470 Dt.24/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239452 | 2024-07-25 15:35 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 229 | 2024-07-24 | Normal | MH14KQ0859 | Unbilled | Gate No.17471 Dt.24/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239453 | 2024-07-25 15:37 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 228 | 2024-07-24 | Normal | MH14GD4951 | Unbilled | Gate No.17472 Dt.24/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239454 | 2024-07-25 15:39 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 2562 | 2024-07-25 | Normal | MH12HD4699 | Billed | Gate No.17470 Dt.25/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239455 | 2024-07-25 15:41 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 21146 | 2024-07-25 | Normal | MH12RN4287 | Unbilled | Gate No.17474 Dt.25/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239456 | 2024-07-25 15:43 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 21147 | 2024-07-25 | Normal | MH12VF4144 | Unbilled | Gate No.17475 Dt.25/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239457 | 2024-07-25 15:45 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 21148 | 2024-07-25 | Normal | MH12UM4090 | Unbilled | Gate No.17476 Dt.25/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239458 | 2024-07-25 15:46 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 21149 | 2024-07-25 | Normal | MH12VF2666 | Unbilled | Gate No.17477 Dt.25/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239459 | 2024-07-25 15:47 | Purchase | 6 | 22693.218 | 69228 | 166.8625 | 4462.9996 | 21150 | 2024-07-25 | Normal | MH12PQ2677 | Unbilled | Gate No.17478 Dt.25/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239463 | 2024-07-25 15:49 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 21151 | 2024-07-25 | Normal | MH12VF4123 | Unbilled | Gate No.17479 Dt.25/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239464 | 2024-07-25 15:51 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 21152 | 2024-07-25 | Normal | MH12VF2662 | Unbilled | Gate No.17480 Dt.25/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239465 | 2024-07-25 15:53 | Purchase | 6.5 | 24584.3195 | 69228 | 166.8625 | 4462.9996 | 21153 | 2024-07-25 | Normal | MH12RN4287 | Unbilled | Gate No.17481 Dt.25/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239089 | 2024-07-15 16:24 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 045572 | 2024-07-13 | Normal | MH12K7717 | Billed | Gate No.17380 Dt.13/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239092 | 2024-07-15 16:44 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 045573 | 2024-07-13 | Normal | MH12HD4699 | Billed | Gate No.17381 Dt.13/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239093 | 2024-07-15 16:45 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 045578 | 2024-07-13 | Normal | MH12KP7719 | Billed | Gate No.17382 Dt.13/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239094 | 2024-07-15 16:47 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 045593 | 2024-07-13 | Normal | MH11AL5997 | Billed | Gate No.17383 Dt.13/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239095 | 2024-07-15 16:49 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 131 | 2024-07-13 | Normal | MH12VT4110 | Billed | Gate No.17384 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239096 | 2024-07-15 16:52 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 045596 | 2024-07-14 | Normal | MH12KP7715 | Billed | Gate No.17385 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239097 | 2024-07-15 16:54 | Purchase | 6.5 | 24584.3195 | 69204 | 149.8425 | 4462.9996 | 045598 | 2024-07-14 | Normal | MH12VF2662 | Billed | Gate No.17386 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239098 | 2024-07-15 16:55 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 132 | 2024-07-14 | Normal | MH12UM9335 | Billed | Gate No.17387 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239099 | 2024-07-15 16:58 | Purchase | 6.5 | 24584.3195 | 69204 | 149.8425 | 4462.9996 | 045599 | 2024-07-14 | Normal | MH12VF2666 | Billed | Gate No.17388 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239100 | 2024-07-15 16:59 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 133 | 2024-07-14 | Normal | MH12HD4150 | Billed | Gate No.17389 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239101 | 2024-07-15 17:01 | Purchase | 6.5 | 24584.3195 | 69204 | 149.8425 | 4462.9996 | 045600 | 2024-07-14 | Normal | MH12VF4144 | Billed | Gate No.17390 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239102 | 2024-07-15 17:03 | Purchase | 5 | 18911.015 | 69204 | 149.8425 | 4462.9996 | 134 | 2024-07-14 | Normal | MH14DM5661 | Billed | Gate No.17391 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239103 | 2024-07-15 17:06 | Purchase | 6.5 | 24584.3195 | 69204 | 149.8425 | 4462.9996 | 045607 | 2024-07-14 | Normal | MH12UM4090 | Billed | Gate No.17392 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239104 | 2024-07-15 17:10 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 045612 | 2024-07-14 | Normal | MH11AL5998 | Billed | Gate No.17393 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239105 | 2024-07-15 17:12 | Purchase | 6.5 | 24584.3195 | 69204 | 149.8425 | 4462.9996 | 045613 | 2024-07-14 | Normal | MH12RN4287 | Billed | Gate No.17394 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239106 | 2024-07-15 17:15 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 135 | 2024-07-14 | Normal | MH12VT5274 | Billed | Gate No.17395 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239107 | 2024-07-15 17:16 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 136 | 2024-07-14 | Normal | MH12UM9331 | Billed | Gate No.17396 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239108 | 2024-07-15 17:18 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 137 | 2024-07-14 | Normal | MH12UM9335 | Billed | Gate No.17397 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239109 | 2024-07-15 17:21 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 045622 | 2024-07-14 | Normal | MH12PQ2677 | Billed | Gate No.17398 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239110 | 2024-07-15 17:22 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 138 | 2024-07-14 | Normal | MH12VT4110 | Billed | Gate No.17399 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239111 | 2024-07-15 17:24 | Purchase | 6 | 22693.218 | 69204 | 149.8425 | 4462.9996 | 045624 | 2024-07-14 | Normal | MH12HD4699 | Billed | Gate No.17400 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239112 | 2024-07-15 17:29 | Purchase | 6.5 | 24584.3195 | 69204 | 149.8425 | 4462.9996 | 045625 | 2024-07-14 | Normal | MH12VF2662 | Billed | Gate No.17401 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239113 | 2024-07-15 17:31 | Purchase | 6.5 | 24584.3195 | 69204 | 149.8425 | 4462.9996 | 045627 | 2024-07-14 | Normal | MH12VF2666 | Billed | Gate No.17402 Dt.14/07/2024
GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | Sand-Metal Mix M50 Easycrete (Pumpable) | GDT/AGGE | 239114 | 2024-07-15 17:33 | Purchase | 5 | 18911.015 | 69204 | 149.8425 | 4462.9996 | 139 | 2024-07-14 | Normal | MH14DM5661 | Billed | Gate No.17403 Dt.14/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-15 Downpour | GDT/AGGE | 239370 | 2024-07-20 19:08 | Purchase | 8 | 34088.128 | 69316 | 8 | 5027.9985 | S/2063 | 2024-07-19 | Normal | MH12WJ6713 | Unbilled | Gate No.17438 Dt.19/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-15 Grade( PUMPABLE) | GDT/AGGE | 238889 | 2024-07-10 16:26 | Purchase | 8 | 35311.84 | 69176 | 50.17 | 5208.4962 | S/1905 | 2024-07-10 | Normal | MH12WJ6714 | Billed | Gate No.17342 Dt.10/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-15 Grade( PUMPABLE) | GDT/AGGE | 238890 | 2024-07-10 16:29 | Purchase | 8 | 35311.84 | 69176 | 50.17 | 5208.4962 | S/1906 | 2024-07-10 | Normal | MH12WJ6712 | Billed | Gate No.17343 Dt.10/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-15 Grade( PUMPABLE) | GDT/AGGE | 238903 | 2024-07-10 17:22 | Purchase | 8 | 35311.84 | 69176 | 50.17 | 5208.4962 | S/1899 | 2024-07-09 | Normal | MH12WJ6715 | Billed | Gate No.17336 Dt.09/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-15 Grade( PUMPABLE) | GDT/AGGE | 238905 | 2024-07-10 17:24 | Purchase | 8 | 35311.84 | 69176 | 50.17 | 5208.4962 | S/1900 | 2024-07-09 | Normal | MH12WJ6711 | Billed | Gate No.17337 Dt.09/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-15 Grade( PUMPABLE) | GDT/AGGE | 238955 | 2024-07-11 12:42 | Purchase | 8 | 35311.84 | 69176 | 50.17 | 5208.4962 | S/1408 | 2024-06-07 | Normal | MH12WJ6712 | Billed | Gate No.17323 Dt.11/07/2024-Due to time leps, TM rejected & converted in to M-50 to M-15
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238891 | 2024-07-10 16:38 | Purchase | 6 | 30551.7 | 69173 | 78 | 6008.501 | S/1896 | 2024-07-09 | Normal | MH12KP9216 | Billed | Gate No.17333 Dt.09/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238892 | 2024-07-10 16:40 | Purchase | 8 | 40735.6 | 69173 | 78 | 6008.501 | S/1898 | 2024-07-09 | Normal | MH12WJ6713 | Billed | Gate No.17335 Dt.09/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238893 | 2024-07-10 16:42 | Purchase | 6 | 30551.7 | 69173 | 78 | 6008.501 | S/1901 | 2024-07-09 | Normal | MH12QW4549 | Billed | Gate No.17338 Dt.09/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238894 | 2024-07-10 16:43 | Purchase | 6 | 30551.7 | 69173 | 78 | 6008.501 | S/1902 | 2024-07-09 | Normal | MH12NX5548 | Billed | Gate No.17339 Dt.09/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238895 | 2024-07-10 16:56 | Purchase | 6 | 30551.7 | 69173 | 78 | 6008.501 | S/1903 | 2024-07-10 | Normal | MH12KP9215 | Billed | Gate No.17340 Dt.10/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238896 | 2024-07-10 16:59 | Purchase | 6 | 30551.7 | 69173 | 78 | 6008.501 | 1904 | 2024-07-10 | Normal | MH12KP9216 | Billed | Gate No.17341 Dt.10/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238897 | 2024-07-10 17:01 | Purchase | 8 | 40735.6 | 69173 | 78 | 6008.501 | S/1907 | 2024-07-10 | Normal | MH12WJ6713 | Billed | Gate No.17344 Dt.10/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238898 | 2024-07-10 17:07 | Purchase | 6 | 30551.7 | 69173 | 78 | 6008.501 | S/1908 | 2024-07-10 | Normal | MH12QW4549 | Billed | Gate No.17345 Dt.10/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238899 | 2024-07-10 17:08 | Purchase | 6 | 30551.7 | 69173 | 78 | 6008.501 | S/1909 | 2024-07-10 | Normal | MH12NX5548 | Billed | Gate No.17346 Dt.10/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238900 | 2024-07-10 17:10 | Purchase | 6 | 30551.7 | 69173 | 78 | 6008.501 | S/1910 | 2024-07-10 | Normal | MH12KP9215 | Billed | Gate No.17347 Dt.10/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238901 | 2024-07-10 17:11 | Purchase | 6 | 30551.7 | 69173 | 78 | 6008.501 | S/1911 | 2024-07-10 | Normal | MH12KP9216 | Billed | Gate No.17348 Dt.10/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Pumpable) | GDT/AGGE | 238902 | 2024-07-10 17:17 | Purchase | 8 | 40735.6 | 69173 | 78 | 6008.501 | S/1897 | 2024-07-09 | Normal | MH12WJ6712 | Billed | Gate No.17334 Dt.09/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239046 | 2024-07-13 12:55 | Purchase | 8 | 42159.28 | 69173 | 213.91 | 6218.4938 | S/1958 | 2024-07-12 | Normal | MH12WJ6711 | Billed | Gate No.17364 Dt.12/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239047 | 2024-07-13 12:58 | Purchase | 6 | 31619.46 | 69173 | 213.91 | 6218.4938 | S/1959 | 2024-07-12 | Normal | MH12KP9216 | Billed | Gate No.17365 Dt.12/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239048 | 2024-07-13 13:00 | Purchase | 6 | 31619.46 | 69173 | 213.91 | 6218.4938 | S/1960 | 2024-07-12 | Normal | MH12NX5548 | Billed | Gate No.17366 Dt.12/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239049 | 2024-07-13 13:01 | Purchase | 6 | 31619.46 | 69173 | 213.91 | 6218.4938 | S/1961 | 2024-07-12 | Normal | MH12NX5548 | Billed | Gate No.17367 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239050 | 2024-07-13 13:03 | Purchase | 6 | 31619.46 | 69173 | 213.91 | 6218.4938 | S/1962 | 2024-07-12 | Normal | MH12QW4549 | Billed | Gate No.17368 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239053 | 2024-07-13 15:20 | Purchase | 6 | 31619.46 | 69173 | 213.91 | 6218.4938 | S/1963 | 2024-07-12 | Normal | MH12KP9218 | Billed | Gate No.17369 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239054 | 2024-07-13 15:23 | Purchase | 8 | 42159.28 | 69173 | 213.91 | 6218.4938 | S/1964 | 2024-07-13 | Normal | MH12WJ6714 | Billed | Gate No.17370 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239055 | 2024-07-13 15:25 | Purchase | 8 | 42159.28 | 69173 | 213.91 | 6218.4938 | S/1965 | 2024-07-13 | Normal | MH12WJ6714 | Billed | Gate No.17371 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239056 | 2024-07-13 15:27 | Purchase | 8 | 42159.28 | 69173 | 213.91 | 6218.4938 | S/1966 | 2024-07-13 | Normal | MH12WJ6715 | Billed | Gate No.17372 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239057 | 2024-07-13 15:28 | Purchase | 8 | 42159.28 | 69173 | 213.91 | 6218.4938 | S/1967 | 2024-07-13 | Normal | MH12WJ6711 | Billed | Gate No.17373 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239058 | 2024-07-13 15:30 | Purchase | 6 | 31619.46 | 69173 | 213.91 | 6218.4938 | S/1968 | 2024-07-13 | Normal | MH12KP9216 | Billed | Gate No.17374 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239059 | 2024-07-13 15:31 | Purchase | 6 | 31619.46 | 69173 | 213.91 | 6218.4938 | S/1969 | 2024-07-13 | Normal | MH12NX5548 | Billed | Gate No.17375 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239060 | 2024-07-13 15:33 | Purchase | 6 | 31619.46 | 69173 | 213.91 | 6218.4938 | S/1970 | 2024-07-13 | Normal | MH12KP9215 | Billed | Gate No.17376 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239061 | 2024-07-13 15:34 | Purchase | 6 | 31619.46 | 69173 | 213.91 | 6218.4938 | S/1971 | 2024-07-13 | Normal | MH12QW4549 | Billed | Gate No.17377 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade PT (Pumpable) Without Fly Ash | GDT/AGGE | 239062 | 2024-07-13 15:36 | Purchase | 7 | 36889.37 | 69173 | 213.91 | 6218.4938 | S/1972 | 2024-07-13 | Normal | MH12WJ6714 | Billed | Gate No.17378 Dt.13/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239225 | 2024-07-17 15:42 | Purchase | 6 | 31566.096 | 69275 | 100 | 6207.9988 | S/2013 | 2024-07-16 | Normal | MH12KP9218 | Unbilled | Gate No.17418 Dt.16/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239226 | 2024-07-17 15:44 | Purchase | 8 | 42088.128 | 69275 | 100 | 6207.9988 | S/2014 | 2024-07-16 | Normal | MH12WJ6712 | Unbilled | Gate No.17419 Dt.16/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239227 | 2024-07-17 15:46 | Purchase | 8 | 42088.128 | 69275 | 100 | 6207.9988 | S/2016 | 2024-07-16 | Normal | MH12WJ6715 | Unbilled | Gate No.17420 Dt.16/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239228 | 2024-07-17 15:48 | Purchase | 6 | 31566.096 | 69275 | 100 | 6207.9988 | S/2018 | 2024-07-16 | Normal | MH12KP9215 | Unbilled | Gate No.17421 Dt.17/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239229 | 2024-07-17 15:50 | Purchase | 8 | 42088.128 | 69275 | 100 | 6207.9988 | S/2019 | 2024-07-17 | Normal | MH12WJ6713 | Unbilled | Gate No.17422 Dt.17/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239230 | 2024-07-17 15:52 | Purchase | 6 | 31566.096 | 69275 | 100 | 6207.9988 | S/2020 | 2024-07-17 | Normal | MH12KP9216 | Unbilled | Gate No.17423 Dt.17/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239231 | 2024-07-17 15:54 | Purchase | 8 | 42088.128 | 69275 | 100 | 6207.9988 | S/2021 | 2024-07-17 | Normal | MH12WJ6714 | Unbilled | Gate No.17424 Dt.17/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239232 | 2024-07-17 15:56 | Purchase | 8 | 42088.128 | 69275 | 100 | 6207.9988 | S/2023 | 2024-07-17 | Normal | MH12WJ6711 | Unbilled | Gate No.17425 Dt.17/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239233 | 2024-07-17 15:58 | Purchase | 6 | 31566.096 | 69275 | 100 | 6207.9988 | S/2022 | 2024-07-17 | Normal | MH12NX5548 | Unbilled | Gate No.17426 Dt.17/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239234 | 2024-07-17 15:59 | Purchase | 8 | 42088.128 | 69275 | 100 | 6207.9988 | S/2024 | 2024-07-17 | Normal | MH12WJ6712 | Unbilled | Gate No.17427 Dt.17/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239235 | 2024-07-17 16:01 | Purchase | 6 | 31566.096 | 69275 | 100 | 6207.9988 | S/2025 | 2024-07-17 | Normal | MH12KP9218 | Unbilled | Gate No.17428 Dt.17/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239237 | 2024-07-17 16:03 | Purchase | 8 | 42088.128 | 69275 | 100 | 6207.9988 | S/2026 | 2024-07-17 | Normal | MH12WJ6715 | Unbilled | Gate No.17429 Dt.17/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239238 | 2024-07-17 16:05 | Purchase | 6 | 31566.096 | 69275 | 100 | 6207.9988 | S/2027 | 2024-07-17 | Normal | MH12KP9215 | Unbilled | Gate No.17430 Dt.17/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-40 Grade (Pumpable) | GDT/AGGE | 239239 | 2024-07-17 16:08 | Purchase | 8 | 42088.128 | 69275 | 100 | 6207.9988 | S/2028 | 2024-07-17 | Normal | MH12WJ6713 | Unbilled | Gate No.17432 Dt.17/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M25 Regular Downpour | GDT/AGGE | 239367 | 2024-07-20 19:04 | Purchase | 8 | 37139.008 | 69316 | 16 | 5478.0035 | S/2065 | 2024-07-20 | Normal | MH12WJ6714 | Unbilled | Gate No.17441 Dt.20/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M25 Regular Downpour | GDT/AGGE | 239368 | 2024-07-20 19:06 | Purchase | 8 | 37139.008 | 69316 | 16 | 5478.0035 | S/2067 | 2024-07-20 | Normal | MH12WJ6715 | Unbilled | Gate No.17443 Dt.20/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M25 Regular Pumpable | GDT/AGGE | 239362 | 2024-07-20 18:57 | Purchase | 6 | 28769.496 | 69314 | 14 | 5658.001 | S/2062 | 2024-07-19 | Normal | MH12KP9218 | Unbilled | Gate No.17439 Dt.19/07/2024
GANGA DHAM TOWERS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M25 Regular Pumpable | GDT/AGGE | 239364 | 2024-07-20 18:58 | Purchase | 8 | 38359.328 | 69314 | 14 | 5658.001 | S/2064 | 2024-07-19 | Normal | MH12WJ6711 | Unbilled | Gate No.17440 Dt.19/07/2024
GANGA DHAM TOWERS | PROTON READY MIX CONCRETE PRIVATE LIMITED | Ready Mix Concrete M-15 Downpour | GDT/AGGE | 239646 | 2024-07-31 17:45 | Purchase | 8 | 33762.64 | 69355 | 27.9 | 4979.9895 | 3686 | 2024-07-30 | Normal | MH12WX0036 | Unbilled | Gate No.17529 Dt.30/07/2024
GANGA DHAM TOWERS | PROTON READY MIX CONCRETE PRIVATE LIMITED | Ready Mix Concrete M-15 Grade( PUMPABLE) | GDT/AGGE | 239518 | 2024-07-27 16:59 | Purchase | 7 | 30592.94 | 69341 | 70 | 5157.0957 | 3644 | 2024-07-26 | Normal | MH12RN2359 | Unbilled | Gate No.17489 Dt.27/07/2024
GANGA DHAM TOWERS | PROTON READY MIX CONCRETE PRIVATE LIMITED | Ready Mix Concrete M-15 Grade( PUMPABLE) | GDT/AGGE | 239519 | 2024-07-27 17:02 | Purchase | 9.5 | 41518.99 | 69341 | 70 | 5157.0957 | 3645 | 2024-07-27 | Normal | MH12WX0036 | Unbilled | Gate No.17493 Dt.27/07/2024
GANGA DHAM TOWERS | PROTON READY MIX CONCRETE PRIVATE LIMITED | Ready Mix Concrete M-15 Grade( PUMPABLE) | GDT/AGGE | 239520 | 2024-07-27 17:05 | Purchase | 9.5 | 41518.99 | 69341 | 70 | 5157.0957 | 3646 | 2024-07-27 | Normal | MH12WX0180 | Unbilled | Gate No.17495 Dt.27/07/2024
GANGA DHAM TOWERS | PROTON READY MIX CONCRETE PRIVATE LIMITED | Ready Mix Concrete M-15 Grade( PUMPABLE) | GDT/AGGE | 239521 | 2024-07-27 17:08 | Purchase | 9.5 | 41518.99 | 69341 | 70 | 5157.0957 | 3647 | 2024-07-27 | Normal | MH12WX0180 | Unbilled | Gate No.17496 Dt.27/07/2024