## GRNRegister638591691100205354_0
GRN Register
From 13-07-2024 To 13-08-2024
Page 1 of 1
Total Records: 198 Records 1 to 198
Project_Name | Supplier_Name | Material_Name | Received_Store | GRN_No | GRN_Date | GRNType | Recd_Qty | Amount | PO_SrNo | PO_Qty | Rate | Challan_No | Challan_Date | Status | VehicleNo | Billing_Status | GRN_Remark
GANGA ALTUS | AGARWAL AGENCIES | Aqua water -20lit | ALTUS CENTRAL STORE | 239372 | 2024-07-20 19:23 | Purchase | 28 | 980 | 68932 | 200 | 35 | 797 | 2024-07-20 | Normal | MH12DG1273 | Billed | G E NO.8529 DT.20.07.2024
GANGA ALTUS | AGARWAL AGENCIES | Aqua water -20lit | ALTUS CENTRAL STORE | 239756 | 2024-08-02 19:27 | Purchase | 28 | 980 | 68932 | 200 | 35 | 820 | 2024-08-02 | Normal | MH12DG1273 | Billed | G E NO.8571 DT.02/08/2024
GANGA ALTUS | ANANDI ENTERPRISES | Ball bearing | ALTUS CENTRAL STORE | 239292 | 2024-07-18 19:11 | Purchase | 2 | 2139 | 69268 | 2 | 1262.01 | 14/24-25 | 2024-07-18 | Normal | MH 12RY9695 | Billed | G E NO.8506 DT.18.07.2024
GANGA ALTUS | ANANDI ENTERPRISES | Bearing | ALTUS CENTRAL STORE | 239293 | 2024-07-18 19:11 | Purchase | 3 | 15345 | 69268 | 3 | 6035.7 | 14/24-25 | 2024-07-18 | Normal | MH 12RY9695 | Billed | G E NO.8506 DT.18.07.2024
GANGA ALTUS | ANANDI ENTERPRISES | Bearing | ALTUS CENTRAL STORE | 239298 | 2024-07-18 19:22 | Purchase | 1 | 5580 | 69281 | 1 | 6584.4 | 15/24-25 | 2024-07-18 | Normal | MH 12RY9695 | Billed | G E NO.8507 DT.18.07.2024
GANGA ALTUS | ANANDI ENTERPRISES | Gearbox Fitting Charges | ALTUS CENTRAL STORE | 239294 | 2024-07-18 19:11 | Purchase | 1 | 4650 | 69268 | 1 | 5487 | 14/24-25 | 2024-07-18 | Normal | MH 12RY9695 | Billed | G E NO.8506 DT.18.07.2024
GANGA ALTUS | ANANDI ENTERPRISES | Oil Seal - 80 x 140 x 13 | ALTUS CENTRAL STORE | 239295 | 2024-07-18 19:11 | Purchase | 4 | 1302 | 69268 | 4 | 384.09 | 14/24-25 | 2024-07-18 | Normal | MH 12RY9695 | Billed | G E NO.8506 DT.18.07.2024
GANGA ALTUS | ANANDI ENTERPRISES | Service Charges | ALTUS CENTRAL STORE | 239296 | 2024-07-18 19:11 | Purchase | 1 | 4650 | 69268 | 1 | 5487 | 14/24-25 | 2024-07-18 | Normal | MH 12RY9695 | Billed | G E NO.8506 DT.18.07.2024
GANGA ALTUS | ANANDI ENTERPRISES | Transport Charges | ALTUS CENTRAL STORE | 239297 | 2024-07-18 19:11 | Purchase | 2 | 1860 | 69268 | 2 | 1097.4 | 14/24-25 | 2024-07-18 | Normal | MH 12RY9695 | Billed | G E NO.8506 DT.18.07.2024
GANGA ALTUS | AONE ENTERPRISES | 2MP IP Bullet camera | ASSET & FURNITURE | 239549 | 2024-07-29 16:05 | Purchase | 8 | 20457.76 | 68898 | 8 | 3017.52 | 13 | 2024-06-21 | Normal | BY HAND | Unbilled | G E NO.8441 DT.02/07/2024 GRN LATE WRONGE CHALLAN RECEIVED
GANGA ALTUS | AONE ENTERPRISES | 2U Rack - No. | ASSET & FURNITURE | 239550 | 2024-07-29 16:05 | Purchase | 1 | 1058.16 | 68898 | 1 | 1248.62 | 13 | 2024-06-21 | Normal | BY HAND | Unbilled | G E NO.8441 DT.02/07/2024 GRN LATE WRONGE CHALLAN RECEIVED
GANGA ALTUS | AONE ENTERPRISES | 32 Channel NVR CP PLUS | ASSET & FURNITURE | 239551 | 2024-07-29 16:05 | Purchase | 1 | 12000 | 68898 | 1 | 14160 | 13 | 2024-06-21 | Normal | BY HAND | Unbilled | G E NO.8441 DT.02/07/2024 GRN LATE WRONGE CHALLAN RECEIVED
GANGA ALTUS | AONE ENTERPRISES | 4+2 POE Switch | ASSET & FURNITURE | 239552 | 2024-07-29 16:05 | Purchase | 1 | 5731.7 | 68898 | 1 | 6763.4 | 13 | 2024-06-21 | Normal | BY HAND | Unbilled | G E NO.8441 DT.02/07/2024 GRN LATE WRONGE CHALLAN RECEIVED
GANGA ALTUS | AONE ENTERPRISES | PVC Box 4x4 | ASSET & FURNITURE | 239553 | 2024-07-29 16:05 | Purchase | 8 | 2469.04 | 68898 | 8 | 364.1825 | 13 | 2024-06-21 | Normal | BY HAND | Unbilled | G E NO.8441 DT.02/07/2024 GRN LATE WRONGE CHALLAN RECEIVED
GANGA ALTUS | AONE ENTERPRISES | UPS | ASSET & FURNITURE | 239554 | 2024-07-29 16:05 | Purchase | 1 | 2821.76 | 68898 | 1 | 3329.68 | 13 | 2024-06-21 | Normal | BY HAND | Unbilled | G E NO.8441 DT.02/07/2024 GRN LATE WRONGE CHALLAN RECEIVED
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | Biotile | ALTUS CENTRAL STORE | 239635 | 2024-07-31 17:19 | Purchase | 447 | 169860 | 69110 | 455.866 | 448.4 | 24-25/2194 | 2024-07-30 | Normal | MH12UM8979 | Billed | G E NO.8563 DT.31/07/2024
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | Biotile | ALTUS CENTRAL STORE | 239637 | 2024-07-31 17:30 | Purchase | 601 | 228380 | 69276 | 601.51 | 448.4 | 24-25/2193 | 2024-07-30 | Normal | MH12UM8979 | Billed | G E NO.8562 DT.31/07/2024
GANGA ALTUS | AQUAPROOF & ANCHORING SYSTEMS | Nitobond SBR (Latex) | ALTUS CENTRAL STORE | 239250 | 2024-07-17 18:11 | Purchase | 200 | 38000 | 67836 | 200 | 224.2 | 24-25/1981 | 2024-07-17 | Normal | MH12KP5947 | Billed | G E NO.8504 DT.17.07.2024
GANGA ALTUS | ASH CONCEPTS | RCC Chamber Cover with Frame 24"x36" (HD) | ALTUS CENTRAL STORE | 239825 | 2024-08-07 11:38 | Purchase | 1 | 2738.36 | 69292 | 15 | 3231.2653 | 956 | 2024-08-03 | Normal | MH05DK2184 | Billed | G E NO.8575 DT.03/08/2024 GRN LATE HIGHRISE ISSUE
GANGA ALTUS | ASH CONCEPTS | RCC Chamber Cover with Frame 24"x36" (HD) | ALTUS CENTRAL STORE | 239594 | 2024-07-30 16:50 | Purchase | 14 | 38337.04 | 69292 | 15 | 3231.2653 | 954 | 2024-07-27 | Normal | MH12QW4220 | Billed | G E NO.8550 DT.27/07/2024
GANGA ALTUS | ASH CONCEPTS | RCC NP2 Class Pipe 12" | ALTUS CENTRAL STORE | 239751 | 2024-08-02 17:56 | Purchase | 50 | 20375 | 69292 | 776 | 480.85 | 219. | 2024-07-22 | Normal | MH12QG2751 | Billed | G E NO.8536 DT.22.07.2024 GRN LATE W QTY PUNCH
GANGA ALTUS | ASH CONCEPTS | RCC NP2 Class Pipe 12" | ALTUS CENTRAL STORE | 239391 | 2024-07-22 19:11 | Purchase | 50 | 20375 | 69292 | 776 | 480.85 | 219 | 2024-07-22 | Normal | MH12QG2751 | Billed | G E NO.8536 DT.22.07.2024
GANGA ALTUS | ASH CONCEPTS | Rcc Round Chamber Cover with Frame 24" HD | ALTUS CENTRAL STORE | 239499 | 2024-07-26 18:42 | Purchase | 29 | 53263.72 | 69297 | 29 | 2167.2821 | 952 | 2024-07-26 | Normal | MH12QW4220 | Billed | G E NO.8547 DT.26/07/2024
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Arrow Chips (300x300) Code - T816129FA | ALTUS CENTRAL STORE | 239299 | 2024-07-18 19:52 | Purchase | 30.75 | 912.045 | 69295 | 30.75 | 34.9985 | 25/GST2455 | 2024-07-06 | Normal | RJ52GA9828 | Billed | G E NO. 8471 DT.09.07.2024
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Arrow Chips DK (300x600) Code -T816029DA | ALTUS CENTRAL STORE | 239137 | 2024-07-15 19:33 | Purchase | 145.28 | 4554.0922 | 69229 | 542.8 | 36.9894 | 24-25/GST2628 | 2024-07-13 | Normal | MH12NX2278 | Billed | G E NO.8500 DT.15.07.2024
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Arrow Chips DK (300x600) Code -T816029DA | ALTUS CENTRAL STORE | 239240 | 2024-07-17 16:38 | Purchase | 9.69 | 303.7524 | 69229 | 542.8 | 36.9894 | 24-25/GST2455 | 2024-07-06 | Normal | RJ52GA9828 | Billed | G E NO.8471 DT.09.07.2024
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Arrow Chips DK (300x600) Code -T816029DA | ALTUS CENTRAL STORE | 239869 | 2024-08-08 17:28 | Purchase | 387.83 | 12157.307 | 69229 | 542.8 | 36.9894 | 24-25/GST3095 | 2024-08-01 | Normal |  | Billed | G E NO.8574 DT.03/08/2024 GRN LATE HIGHRISE ISSUE
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Arrow Chips DK (300x600) Code - T816129DA | ALTUS CENTRAL STORE | 239870 | 2024-08-08 17:28 | Purchase | 56.45 | 1769.7075 | 69229 | 56.45 | 36.9929 | 24-25/GST3095 | 2024-08-01 | Normal |  | Billed | G E NO.8574 DT.03/08/2024 GRN LATE HIGHRISE ISSUE
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Arrow Chips DK (300x600) Code - T816129DA | ALTUS CENTRAL STORE | 239887 | 2024-08-09 12:08 | Purchase | 20.6 | 645.81 | 69441 | 20.6 | 36.9927 | 24-25/GST3095 | 2024-08-01 | Normal | MH12SX1451 | Billed | G E NO.8574 DT.03/08/2024 GRN LATE HIGHRISE ISSUE
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Arrow Chips LT (300x600) Code - T816129LA | ALTUS CENTRAL STORE | 239300 | 2024-07-18 19:52 | Purchase | 95.1 | 2981.385 | 69295 | 95.1 | 36.9931 | 25/GST2455 | 2024-07-06 | Normal | RJ52GA9828 | Billed | G E NO. 8471 DT.09.07.2024
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Arrow Chips LT (300x600) Code - T816129LA | ALTUS CENTRAL STORE | 239242 | 2024-07-17 16:45 | Purchase | 9706.13 | 304287.1755 | 69218 | 9706.13 | 36.993 | 24-25/GST2455 | 2024-07-06 | Normal | RJ52GA9828 | Billed | G E NO.8471 DT.09.07.2024
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Calyx Blue (300x300) Code - T813125FA | ALTUS CENTRAL STORE | 239871 | 2024-08-08 17:28 | Purchase | 1181.92 | 35055.7472 | 69229 | 1323.49 | 34.9988 | 24-25/GST3095 | 2024-08-01 | Normal |  | Billed | G E NO.8574 DT.03/08/2024 GRN LATE HIGHRISE ISSUE
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Calyx Blue (300x300) Code - T813125FA | ALTUS CENTRAL STORE | 239241 | 2024-07-17 16:38 | Purchase | 141.57 | 4198.9662 | 69229 | 1323.49 | 34.9988 | 24-25/GST2455 | 2024-07-06 | Normal | RJ52GA9828 | Billed | G E NO.8471 DT.09.07.2024
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Calyx Blue (300x300) Code - T813125FA | ALTUS CENTRAL STORE | 239888 | 2024-08-09 12:08 | Purchase | 143.4 | 4253.244 | 69441 | 143.4 | 34.9988 | 24-25/GST3095 | 2024-08-01 | Normal | MH12SX1451 | Billed | G E NO.8574 DT.03/08/2024 GRN LATE HIGHRISE ISSUE
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Lucia (300x300) Code - T816081FA | ALTUS CENTRAL STORE | 239301 | 2024-07-18 19:52 | Purchase | 73.73 | 2186.8318 | 69295 | 73.73 | 34.9987 | 25/GST2455 | 2024-07-06 | Normal | RJ52GA9828 | Billed | G E NO. 8471 DT.09.07.2024
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Lucia LT (300x600) Code - T816081LA | ALTUS CENTRAL STORE | 239243 | 2024-07-17 16:45 | Purchase | 3389.75 | 106268.6625 | 69218 | 3442.7 | 36.993 | 24-25/GST2455 | 2024-07-06 | Normal | RJ52GA9828 | Billed | G E NO.8471 DT.09.07.2024
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Lucia LT (300x600) Code - T816081LA | ALTUS CENTRAL STORE | 239872 | 2024-08-08 17:28 | Purchase | 7002.26 | 219520.851 | 69229 | 7116.888 | 36.993 | 24-25/GST3095 | 2024-08-01 | Normal |  | Billed | G E NO.8574 DT.03/08/2024 GRN LATE HIGHRISE ISSUE
GANGA ALTUS | CERATEC TILES INDIA PVT LTD. | Prism Terra HL (300x600) Code - T816174HA | ALTUS CENTRAL STORE | 239138 | 2024-07-15 19:33 | Purchase | 445.52 | 13967.052 | 69229 | 474.79 | 36.993 | 24-25/GST2628 | 2024-07-13 | Normal | MH12NX2278 | Billed | G E NO.8500 DT.15.07.2024
GANGA ALTUS | EASY FUEL PRIVATE LIMITED | Diesel | ALTUS CENTRAL STORE | 239115 | 2024-07-15 18:07 | Purchase | 1000 | 91520 | 69234 | 1000 | 91.52 | 938 | 2024-07-13 | Normal | MH12VT3546 | Billed | G E NO.8501 DT.15.07.2024
GANGA ALTUS | EASY FUEL PRIVATE LIMITED | Diesel | ALTUS CENTRAL STORE | 239820 | 2024-08-06 18:56 | Purchase | 1000 | 91520 | 69392 | 1000 | 91.52 | 1147 | 2024-08-05 | Normal | MH14 LL4672 | Billed | G E NO.8592 DT.06.08.2024
GANGA ALTUS | HOUSE OF CONSTRUCTION MATERIAL | Bleaching Powder | ALTUS CENTRAL STORE | 239373 | 2024-07-20 19:25 | Purchase | 200 | 5200 | 69302 | 200 | 30.68 | 8898 | 2024-07-20 | Normal | MH12QR2101 | Billed | G E NO.8523 DT.20.07.2024
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | CYLINDRICAL 60/70MMBS CA5122 US32D | ALTUS CENTRAL STORE | 240037 | 2024-08-13 17:28 | Purchase | 5 | 2450 | 69077 | 165 | 578.2 | IDPPL-16286 | 2024-08-10 | Normal | MH14 LB3441 | Unbilled | G E NO.8609 DT.13.08.2024
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | Cylindrical Lock with Key - Yale (CA5147 US32D) | ALTUS CENTRAL STORE | 240038 | 2024-08-13 17:28 | Purchase | 5 | 2225 | 69077 | 241 | 525.1 | IDPPL-16286 | 2024-08-10 | Normal | MH14 LB3441 | Unbilled | G E NO.8609 DT.13.08.2024
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | Eye piece V0401A US15 | ALTUS CENTRAL STORE | 240039 | 2024-08-13 17:28 | Purchase | 79 | 26070 | 69077 | 224 | 389.4 | IDPPL-16286 | 2024-08-10 | Normal | MH14 LB3441 | Unbilled | G E NO.8609 DT.13.08.2024
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | Handle D-Type YEH-11B-300 | ALTUS CENTRAL STORE | 240036 | 2024-08-13 17:22 | Purchase | 92 | 86020 | 69077 | 122 | 1103.3 | IDPPL-16264 | 2024-08-10 | Normal | MH14 LB3441 | Unbilled | G E NO.8610 DT.13.08.2024
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | Magnetic Catcher Yale (YMDC-20-SS) | ALTUS CENTRAL STORE | 240040 | 2024-08-13 17:28 | Purchase | 45 | 7875 | 69077 | 656 | 206.5 | IDPPL-16286 | 2024-08-10 | Normal | MH14 LB3441 | Unbilled | G E NO.8609 DT.13.08.2024
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | Main Door Shutter (35mm) 2225mm(H)x1050mm(W) | ALTUS CENTRAL STORE | 239500 | 2024-07-26 18:49 | Purchase | 30 | 189925.71 | 63050 | 200 | 7470.4113 | IDPPL-15992 | 2024-07-26 | Normal | MH14 LB3441 | Billed | G E NO.8548 DT.26/07/2024
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | Toilet Door Shutter (35mm) 2250mm(H)x750mm(W) | ALTUS CENTRAL STORE | 239501 | 2024-07-26 18:52 | Purchase | 1 | 4572.8535 | 63050 | 400 | 5395.9672 | IDPPL-15556 | 2024-06-29 | Normal | MH14 LB3441 | Billed | G E NO.8549 DT.26/07/2024
GANGA ALTUS | INNOVADOOR PRODUCTS PRIVATE LIMITED | Toilet Door Shutter (35mm) 2250mm(H)x750mm(W) | ALTUS CENTRAL STORE | 240034 | 2024-08-13 16:56 | Purchase | 36 | 164622.726 | 63050 | 400 | 5395.9672 | IDPPL-16305 | 2024-08-13 | Normal | MH14JL7905 | Unbilled | G E NO.8611 DT.13.08.2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Aggregate 10mm cft | ALTUS CENTRAL STORE | 239071 | 2024-07-13 18:11 | Purchase | 584 | 18104 | 69195 | 1018.34 | 32.55 | DC/24-25/2503 | 2024-07-13 | Normal | MH12VF0191 | Billed | G E NO.8497 DT.13.07.2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Crush Sand | ALTUS CENTRAL STORE | 239267 | 2024-07-18 17:50 | Purchase | 583 | 19822 | 69092 | 2142.5518 | 35.7 | DC/24-25/2671 | 2024-07-18 | Normal | MH12 VF0194 | Billed | G E NO.8505 DT.18.07.2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Crush Sand | ALTUS CENTRAL STORE | 239441 | 2024-07-24 18:14 | Purchase | 378.4918 | 12868.7212 | 69092 | 2142.5518 | 35.7 | DC-24-25/2798 | 2024-07-22 | Normal | MH12VF0190. | Billed | G E NO.8542 DT.23/07/2024 GRN LATE SHORT QTY
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Crush Sand | ALTUS CENTRAL STORE | 239444 | 2024-07-24 18:25 | Purchase | 220.5082 | 7497.2788 | 69332 | 2366.0349 | 35.7 | DC/24-25/2798 | 2024-07-22 | Normal | MH12VF0190. | Billed | G E NO.8542 DT.23/07/2024 GRN LATE SHORT QTY
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Crush Sand | ALTUS CENTRAL STORE | 239785 | 2024-08-03 18:53 | Purchase | 613 | 20842 | 69332 | 2366.0349 | 35.7 | DC/24-25/3121 | 2024-08-03 | Normal | MH12VF0193 | Unbilled | G E NO.8576 DT.03/08/2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Crush Sand | ALTUS CENTRAL STORE | 239976 | 2024-08-10 19:51 | Purchase | 581 | 19754 | 69332 | 2366.0349 | 35.7 | DC/24-25/3271 | 2024-08-09 | Normal | MH12VF0190. | Unbilled | G E NO.8599 DT.10/08/2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-15 Downpour | ALTUS CENTRAL STORE | 239386 | 2024-07-21 17:15 | Purchase | 6 | 22255.92 | 68513 | 38.97 | 4376.9977 | S/2081 | 2024-07-21 | Deleted | MH12KP9216 | Unbilled | G E NO.8532 DT.21.07.2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-15 Grade( D/P) - | ALTUS CENTRAL STORE | 239430 | 2024-07-24 17:34 | Purchase | 5 | 19669.49 | 69328 | 23.85 | 4641.9995 | S/2114 | 2024-07-20 | Normal | MH12WJ6711 | Billed | G E NO.8538 DT.23/07/2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-15 Grade( D/P) - | ALTUS CENTRAL STORE | 240027 | 2024-08-13 11:50 | Purchase | 6 | 23603.388 | 69328 | 23.85 | 4641.9995 | S/2081 | 2024-07-21 | Normal | MH12KP9216 | Billed | G E NO.8532 DT.21.07.2024 GRN LATE WRONG RATE
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-30 Grade FF (Pumpable) | ALTUS CENTRAL STORE | 239883 | 2024-08-08 19:00 | Purchase | 8 | 37776.264 | 69227 | 77 | 5571.999 | S/2314 | 2024-08-07 | Normal | MH12WJ6715 | Unbilled | G E NO.8594 DT.07/08/2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-30 Grade FF (Pumpable) | ALTUS CENTRAL STORE | 239884 | 2024-08-08 19:02 | Purchase | 8 | 37776.264 | 69227 | 77 | 5571.999 | S/2308 | 2024-08-07 | Normal | MH12WJ6713 | Unbilled | G E NO.8593 DT.07/08/2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-30 Grade FF (Pumpable) | ALTUS CENTRAL STORE | 239885 | 2024-08-08 19:03 | Purchase | 3 | 14166.099 | 69227 | 77 | 5571.999 | S/2317 | 2024-08-07 | Normal | MH12WJ6712 | Unbilled | G E NO.8595 DT.07/08/2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Downpour) | ALTUS CENTRAL STORE | 239969 | 2024-08-10 19:29 | Purchase | 3.5 | 16141.524 | 69395 | 12.73 | 5441.9991 | S/2363 | 2024-08-10 | Normal | MH12KP9215 | Unbilled | G E NO.8600 DT.10/08/2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Downpour) | ALTUS CENTRAL STORE | 239823 | 2024-08-07 10:56 | Purchase | 4 | 18447.456 | 69395 | 12.73 | 5441.9991 | S/2071 | 2024-07-20 | Normal | MH12KP9218 | Billed | G E NO.8524 DT.20/07/2024 GRN LSTE Deo to estimation revise pending
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M-35 Grade (Downpour) | ALTUS CENTRAL STORE | 239824 | 2024-08-07 10:59 | Purchase | 3 | 13835.592 | 69395 | 12.73 | 5441.9991 | S/2239 | 2024-08-02 | Normal | MH12QW4549 | Unbilled | G E NO.8570 DT.02/08/2024 GRN LATE DEO TO ESTIMATION REVISE PENDING
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M25 Regular Downpour | ALTUS CENTRAL STORE | 239432 | 2024-07-24 17:37 | Purchase | 4 | 17261.016 | 69259 | 18 | 5091.9996 | S/2116 | 2024-07-23 | Normal | MH12KP9215 | Billed | G E NO.8540 DT.23/07/2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M25 Regular Downpour | ALTUS CENTRAL STORE | 239384 | 2024-07-21 17:09 | Purchase | 3 | 12945.762 | 69259 | 18 | 5091.9996 | S/2077 | 2024-07-20 | Normal | MH12KP9216 | Billed | G E NO.8531 DT.20.07.2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M25 Regular Downpour | ALTUS CENTRAL STORE | 239385 | 2024-07-21 17:11 | Purchase | 3 | 12945.762 | 69259 | 18 | 5091.9996 | S/2083 | 2024-07-21 | Normal | MH12KP9218 | Billed | G E NO.8534 DT.21.07.2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M25 Regular Downpour | ALTUS CENTRAL STORE | 239131 | 2024-07-15 18:48 | Purchase | 3 | 12945.762 | 69259 | 18 | 5091.9996 | S/1890 | 2024-07-09 | Normal | MH12KP9216 | Billed | G E NO.8470 DT.09.07.2024
GANGA ALTUS | INNOVEN INFRACON PVT LTD LIMITED | Ready Mix Concrete M25 Regular Downpour | ALTUS CENTRAL STORE | 239132 | 2024-07-15 18:51 | Purchase | 5 | 21576.27 | 69259 | 18 | 5091.9996 | S/1951 | 2024-07-12 | Normal | MH12NX5548 | Billed | G E NO.8493 DT.12.07.2024
GANGA ALTUS | K K MARKETING | ASTM Ball Valve 1-1/2" | ALTUS CENTRAL STORE | 239324 | 2024-07-19 18:52 | Purchase | 4 | 696 | 68891 | 9 | 205.32 | KKM/0262/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8518 DT.19.07.2024
GANGA ALTUS | K K MARKETING | ASTM Ball Valve 1/2" | ALTUS CENTRAL STORE | 239343 | 2024-07-19 19:28 | Purchase | 33 | 1512.06 | 67967 | 580 | 54.0676 | KKM/0260/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8516 DT.19.07.2024
GANGA ALTUS | K K MARKETING | ASTM Brass FTA 1 1/2" | ALTUS CENTRAL STORE | 239271 | 2024-07-18 18:49 | Purchase | 96 | 16442.304 | 69170 | 96 | 202.1034 | KKM/0246/2024-25 | 2024-07-17 | Normal | MH12TV8018 | Billed | G E NO.8510 DT.18.07.2024
GANGA ALTUS | K K MARKETING | ASTM Brass MTA 1-1/4" | ALTUS CENTRAL STORE | 239272 | 2024-07-18 18:49 | Purchase | 32 | 5671.936 | 69170 | 32 | 209.1524 | KKM/0246/2024-25 | 2024-07-17 | Normal | MH12TV8018 | Billed | G E NO.8510 DT.18.07.2024
GANGA ALTUS | K K MARKETING | ASTM Elbow 11/4" | ALTUS CENTRAL STORE | 239325 | 2024-07-19 18:52 | Purchase | 57 | 1137.264 | 68891 | 110 | 23.5433 | KKM/0262/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8518 DT.19.07.2024
GANGA ALTUS | K K MARKETING | ASTM Pipe 1-1/2" x 10fts | ALTUS CENTRAL STORE | 239282 | 2024-07-18 18:58 | Purchase | 91 | 36726.963 | 68891 | 244 | 476.2397 | KKM/0252/2024-25 | 2024-07-18 | Normal | MH12TV8018 | Billed | G E NO.8513 DT.18.07.2024
GANGA ALTUS | K K MARKETING | ASTM Pipe 1/2" x 10 fts | ALTUS CENTRAL STORE | 239273 | 2024-07-18 18:49 | Purchase | 58 | 7362.114 | 69170 | 58 | 149.7809 | KKM/0246/2024-25 | 2024-07-17 | Normal | MH12TV8018 | Billed | G E NO.8510 DT.18.07.2024
GANGA ALTUS | K K MARKETING | ASTM Red. Bush 1-1/2" x 1-1/4" | ALTUS CENTRAL STORE | 239326 | 2024-07-19 18:52 | Purchase | 9 | 50.373 | 68891 | 24 | 6.6045 | KKM/0262/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8518 DT.19.07.2024
GANGA ALTUS | K K MARKETING | ASTM Red. Bush 11/4" x 3/4" | ALTUS CENTRAL STORE | 239327 | 2024-07-19 18:52 | Purchase | 28 | 194.88 | 68891 | 28 | 8.2129 | KKM/0262/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8518 DT.19.07.2024
GANGA ALTUS | K K MARKETING | ASTM Reducer Bushing 1 1/4" x 1 1/2" | ALTUS CENTRAL STORE | 239274 | 2024-07-18 18:49 | Purchase | 96 | 559.584 | 69170 | 96 | 6.8782 | KKM/0246/2024-25 | 2024-07-17 | Normal | MH12TV8018 | Billed | G E NO.8510 DT.18.07.2024
GANGA ALTUS | K K MARKETING | ASTM Reducer Tee 11/4" x 1/2" | ALTUS CENTRAL STORE | 239328 | 2024-07-19 18:52 | Purchase | 72 | 1941.84 | 68891 | 94 | 31.8247 | KKM/0262/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8518 DT.19.07.2024
GANGA ALTUS | K K MARKETING | ASTM Shoe Bend 1 1/4" (32mm) | ALTUS CENTRAL STORE | 239339 | 2024-07-19 19:18 | Purchase | 12 | 188.964 | 68532 | 192 | 18.5815 | KKM/0261/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8517 DT.19.07.2024
GANGA ALTUS | K K MARKETING | ASTM Solvent Cement 717 Black - 946 ml | ALTUS CENTRAL STORE | 239335 | 2024-07-19 18:56 | Purchase | 15 | 14624.7 | 67568 | 37 | 1150.4762 | KKM/0265/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8521 DT.19.07.2024
GANGA ALTUS | K K MARKETING | ASTM Tee 11/4" | ALTUS CENTRAL STORE | 239340 | 2024-07-19 19:18 | Purchase | 2 | 50.344 | 68532 | 2 | 29.702 | KKM/0261/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8517 DT.19.07.2024
GANGA ALTUS | K K MARKETING | PVC Elbow 1 1/2 " | ALTUS CENTRAL STORE | 239336 | 2024-07-19 19:03 | Purchase | 90 | 1187.55 | 69200 | 191 | 15.5701 | KKM/0264/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8520 DT.19.07.2024
GANGA ALTUS | K K MARKETING | PVC Elbow 3" | ALTUS CENTRAL STORE | 239329 | 2024-07-19 18:52 | Purchase | 4 | 162.4 | 68891 | 4 | 47.91 | KKM/0262/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8518 DT.19.07.2024
GANGA ALTUS | K K MARKETING | PVC Lubricant (1kg) - No. | ALTUS CENTRAL STORE | 239337 | 2024-07-19 19:06 | Purchase | 20 | 4442.8 | 69170 | 20 | 262.125 | KKM/0263/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8519 DT.19.07.2024
GANGA ALTUS | K K MARKETING | PVC Nahani Trap 4"X 3" | ALTUS CENTRAL STORE | 239338 | 2024-07-19 19:08 | Purchase | 19 | 1245.26 | 69170 | 96 | 77.3373 | KKM/0263/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8519 DT.19.07.2024
GANGA ALTUS | K K MARKETING | PVC Pipe 11/2"x 10 ft | ALTUS CENTRAL STORE | 239291 | 2024-07-18 19:00 | Purchase | 20 | 2227.2 | 69200 | 20 | 131.405 | KKM/0245/2024-25 | 2024-07-17 | Normal | MH12TV8018 | Billed | G E NO.8509 DT.18.07.2024
GANGA ALTUS | K K MARKETING | PVC Pipe 3" 6Ft Long D/S | ALTUS CENTRAL STORE | 239270 | 2024-07-18 18:42 | Purchase | 47 | 12893.98 | 69047 | 125 | 323.7213 | KKM/0249/2024-25 | 2024-07-18 | Normal | MH12WJ1445 | Billed | G E NO.8511 DT.18.07.2024
GANGA ALTUS | K K MARKETING | PVC Shoe Bend 1-1/4" | ALTUS CENTRAL STORE | 239330 | 2024-07-19 18:52 | Purchase | 192 | 3251.712 | 68891 | 192 | 19.9844 | KKM/0262/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8518 DT.19.07.2024
GANGA ALTUS | K K MARKETING | PVC Shoe Bend 3" | ALTUS CENTRAL STORE | 239331 | 2024-07-19 18:52 | Purchase | 24 | 890.88 | 68891 | 144 | 43.8017 | KKM/0262/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8518 DT.19.07.2024
GANGA ALTUS | K K MARKETING | PVC Shoe Bend 50mm | ALTUS CENTRAL STORE | 239332 | 2024-07-19 18:52 | Purchase | 16 | 403.68 | 68891 | 16 | 29.7713 | KKM/0262/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8518 DT.19.07.2024
GANGA ALTUS | K K MARKETING | PVC Single Y 3" | ALTUS CENTRAL STORE | 239341 | 2024-07-19 19:18 | Purchase | 1 | 66.7 | 68532 | 1 | 78.7 | KKM/0261/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8517 DT.19.07.2024
GANGA ALTUS | K K MARKETING | PVC Socket 4" | ALTUS CENTRAL STORE | 239342 | 2024-07-19 19:18 | Purchase | 9 | 454.14 | 68532 | 96 | 59.5427 | KKM/0261/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8517 DT.19.07.2024
GANGA ALTUS | K K MARKETING | PVC Solvent (500 ml.) - | ALTUS CENTRAL STORE | 239333 | 2024-07-19 18:52 | Purchase | 1 | 250.56 | 68891 | 50 | 295.6608 | KKM/0262/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8518 DT.19.07.2024
GANGA ALTUS | K K MARKETING | SWR Silent Aerator 4" (70001576) | ALTUS CENTRAL STORE | 239283 | 2024-07-18 18:58 | Purchase | 193 | 276491.8 | 68891 | 200 | 1690.468 | KKM/0252/2024-25 | 2024-07-18 | Normal | MH12TV8018 | Billed | G E NO.8513 DT.18.07.2024
GANGA ALTUS | K K MARKETING | SWR Silent Coupler 8" | ALTUS CENTRAL STORE | 239350 | 2024-07-19 19:53 | Purchase | 4 | 1787.8 | 68802 | 8 | 527.4 | KKM/0259/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8515 DT.19.07.2024
GANGA ALTUS | K K MARKETING | SWR Silent Pipe 4" x 10 ft S/S | ALTUS CENTRAL STORE | 239284 | 2024-07-18 18:58 | Purchase | 295 | 298569.5 | 68891 | 332 | 1194.278 | KKM/0252/2024-25 | 2024-07-18 | Normal | MH12TV8018 | Billed | G E NO.8513 DT.18.07.2024
GANGA ALTUS | K K MARKETING | SWR Silent Plug Bend 4" (70001521) | ALTUS CENTRAL STORE | 239334 | 2024-07-19 18:52 | Purchase | 19 | 3504.36 | 68891 | 40 | 217.639 | KKM/0262/2024-25 | 2024-07-19 | Normal | MH12WJ1445 | Billed | G E NO.8518 DT.19.07.2024
GANGA ALTUS | K K MARKETING | SWR Silent Shoe Bend 4" | ALTUS CENTRAL STORE | 239275 | 2024-07-18 18:52 | Purchase | 363 | 46108.26 | 68887 | 632 | 149.8836 | KKM/0251/2024-25 | 2024-07-18 | Normal | MH12TV8018 | Billed | G E NO.8512 DT.18.07.2024
GANGA ALTUS | K K MARKETING | SWR Silent Shoe Bend 4" | ALTUS CENTRAL STORE | 239344 | 2024-07-19 19:43 | Purchase | 3 | 381.06 | 68887 | 632 | 149.8836 | KKM/0258/2024-25 | 2024-07-18 | Normal | MH12WJ1445 | Unbilled | G E NO.8514 DT.19.07.2024
GANGA ALTUS | K K MARKETING | SWR Silent Shoe Bend 6" | ALTUS CENTRAL STORE | 239345 | 2024-07-19 19:43 | Purchase | 19 | 7185.04 | 68887 | 90 | 446.2289 | KKM/0258/2024-25 | 2024-07-18 | Normal | MH12WJ1445 | Unbilled | G E NO.8514 DT.19.07.2024
GANGA ALTUS | K K MARKETING | SWR Silent Socket 4" (Coupler) | ALTUS CENTRAL STORE | 239346 | 2024-07-19 19:43 | Purchase | 10 | 980.2 | 68887 | 55 | 115.6636 | KKM/0258/2024-25 | 2024-07-18 | Normal | MH12WJ1445 | Unbilled | G E NO.8514 DT.19.07.2024
GANGA ALTUS | KANAD ELECTRICAL SERVICES | Common Meter panel | ALTUS CENTRAL STORE | 239170 | 2024-07-16 18:28 | Purchase | 1 | 133087.5 | 66717 | 1 | 157043.26 | 29/KES/JULY24-25 | 2024-07-15 | Normal | MH12VT2833 | Billed | G E NO.8502 DT.16.07.2024
GANGA ALTUS | KANAD ELECTRICAL SERVICES | DG Distribution Panel | ALTUS CENTRAL STORE | 240031 | 2024-08-13 15:39 | Purchase | 1 | 635000 | 69194 | 1 | 749300 | 33/KES/JULY24-25 | 2024-08-10 | Normal | MH 12 RN3859 | Unbilled | G E NO.8607 DT.12.08.2024
GANGA ALTUS | KANAD ELECTRICAL SERVICES | Mini Feeder Pillar with Stand 200 AMP (HRC) | ALTUS CENTRAL STORE | 239323 | 2024-07-19 18:41 | Purchase | 2 | 37000 | 69294 | 2 | 21830 | 31/KES/JULY24-25 | 2024-07-19 | Normal | MH12 SX9958 | Billed | G E NO.8522 DT.19.07.2024
GANGA ALTUS | LEO ASSOCIATES | Mcon NSA Grey (Gold) 50kg | ALTUS CENTRAL STORE | 239821 | 2024-08-06 19:46 | Purchase | 190 | 145540 | 68146 | 600 | 903.88 | 304 | 2024-08-03 | Normal | MH12HD0959 | Billed | G E NO.8589 DT.06.08.2024
GANGA ALTUS | MACHINE TOOLS HARDWARE & APPLIANCES | OBD PAINT WHITE COLOUR - | ALTUS CENTRAL STORE | 239415 | 2024-07-23 19:41 | Purchase | 1050 | 38559.15 | 67859 | 2941.8017 | 43.3331 | 3622 | 2024-07-20 | Normal | MH 16AE 8796 | Billed | G E NO.8544 DT.23.07.2024
GANGA ALTUS | MACHINE TOOLS HARDWARE & APPLIANCES | Primer (Water base) | ALTUS CENTRAL STORE | 239416 | 2024-07-23 19:44 | Purchase | 400 | 38472 | 67575 | 2329.24 | 113.4924 | 3623 | 2024-07-20 | Normal | MH 16AE 8796 | Billed | G E NO.8543 DT.23.07.2024
GANGA ALTUS | MAIL TECH STATIONERY | Box File lamina | ALTUS CENTRAL STORE | 239223 | 2024-07-17 12:33 | Purchase | 60 | 3480 | 69225 | 84 | 68.44 | 3200 | 2024-06-19 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Box File lamina | ALTUS CENTRAL STORE | 239212 | 2024-07-17 12:24 | Purchase | 24 | 1392 | 69225 | 84 | 68.44 | 3179 | 2024-06-04 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Box File Voucher Lamina | ALTUS CENTRAL STORE | 239217 | 2024-07-17 12:33 | Purchase | 36 | 2052 | 69225 | 36 | 67.26 | 3200 | 2024-06-19 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Cloth Cover 10x12 | ALTUS CENTRAL STORE | 239216 | 2024-07-17 12:33 | Purchase | 200 | 2800 | 69225 | 200 | 16.52 | 3200 | 2024-06-19 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Copy Power A3 | ALTUS CENTRAL STORE | 239220 | 2024-07-17 12:33 | Purchase | 5 | 3900 | 69225 | 5 | 873.6 | 3200 | 2024-06-19 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Copy Power A4 | ALTUS CENTRAL STORE | 239208 | 2024-07-17 12:24 | Purchase | 64 | 16640 | 69225 | 104 | 291.2 | 3179 | 2024-06-04 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Copy Power A4 | ALTUS CENTRAL STORE | 239219 | 2024-07-17 12:33 | Purchase | 40 | 10400 | 69225 | 104 | 291.2 | 3200 | 2024-06-19 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Copy Power F/S | ALTUS CENTRAL STORE | 239215 | 2024-07-17 12:33 | Purchase | 10 | 4800 | 69225 | 10 | 537.6 | 3200 | 2024-06-19 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Envelop 9.5X4.5-100GSM | ALTUS CENTRAL STORE | 239211 | 2024-07-17 12:24 | Purchase | 100 | 150 | 69225 | 100 | 1.77 | 3179 | 2024-06-04 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Excel Bond Paper A3 | ALTUS CENTRAL STORE | 239221 | 2024-07-17 12:33 | Purchase | 5 | 3900 | 69225 | 5 | 873.6 | 3200 | 2024-06-19 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Excel Pro A/4 Paper | ALTUS CENTRAL STORE | 239214 | 2024-07-17 12:33 | Purchase | 5 | 2900 | 69225 | 5 | 649.6 | 3200 | 2024-06-19 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Maxwell Battery Lr 1130 | ALTUS CENTRAL STORE | 239213 | 2024-07-17 12:27 | Purchase | 20 | 600 | 69225 | 20 | 35.4 | 3197 | 2024-06-15 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Pagoda Folder File | ALTUS CENTRAL STORE | 239218 | 2024-07-17 12:33 | Purchase | 500 | 11000 | 69225 | 500 | 25.96 | 3200 | 2024-06-19 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Permenant Marker | ALTUS CENTRAL STORE | 239209 | 2024-07-17 12:24 | Purchase | 10 | 180 | 69225 | 10 | 20.16 | 3179 | 2024-06-04 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Register 200 Pages | ALTUS CENTRAL STORE | 239222 | 2024-07-17 12:33 | Purchase | 24 | 1560 | 69225 | 24 | 76.7 | 3200 | 2024-06-19 | Normal | BY HAND | Billed
GANGA ALTUS | MAIL TECH STATIONERY | Stapler Pin Small | ALTUS CENTRAL STORE | 239210 | 2024-07-17 12:24 | Purchase | 10 | 2100 | 69225 | 10 | 247.8 | 3179 | 2024-06-04 | Normal | BY HAND | Billed
GANGA ALTUS | N. M. SERVICE STATION | Diesel | ALTUS CENTRAL STORE | 239258 | 2024-07-18 14:29 | Purchase | 146.61 | 13235.9508 | 69289 | 146.61 | 90.28 | 1193 | 2024-07-15 | Normal | BY HAND | Billed
GANGA ALTUS | N. M. SERVICE STATION | Diesel | ALTUS CENTRAL STORE | 239965 | 2024-08-10 18:38 | Purchase | 182.61 | 16486.0308 | 69469 | 182.61 | 90.28 | 1366 | 2024-07-31 | Normal | BY HAND | Billed
GANGA ALTUS | N. M. SERVICE STATION | Petrol | ALTUS CENTRAL STORE | 239259 | 2024-07-18 14:29 | Purchase | 372.82 | 38676.3468 | 69289 | 372.82 | 103.74 | 1193 | 2024-07-15 | Normal | BY HAND | Billed
GANGA ALTUS | N. M. SERVICE STATION | Petrol | ALTUS CENTRAL STORE | 239964 | 2024-08-10 18:38 | Purchase | 414 | 42948.36 | 69469 | 414 | 103.74 | 1366 | 2024-07-31 | Normal | BY HAND | Billed
GANGA ALTUS | PATEL CERAMICS. | Jointing Mortar | ALTUS CENTRAL STORE | 239375 | 2024-07-20 19:35 | Purchase | 1030.2404 | 10817.5242 | 69098 | 1030.2404 | 12.39 | 3322 | 2024-07-20 | Normal | MH42BF4352 | Billed | G E NO.8526 DT.20.07.2024
GANGA ALTUS | PATEL CERAMICS. | Jointing Mortar | ALTUS CENTRAL STORE | 239376 | 2024-07-20 19:37 | Purchase | 165.83 | 1741.215 | 69288 | 165.83 | 12.39 | 3322 | 2024-07-20 | Normal | MH42BF4352 | Billed | G E NO.8526 DT.20.07.2024
GANGA ALTUS | PATEL CERAMICS. | Jointing Mortar | ALTUS CENTRAL STORE | 239468 | 2024-07-25 17:40 | Purchase | 3.9296 | 41.2608 | 69336 | 3.9296 | 12.3882 | 3322 | 2024-07-20 | Normal | MH42BF4352 | Billed | G E NO.8526 DT.20.07.2024 GRN LATE SHORT QTY
GANGA ALTUS | SA BUILDING SOLUTIONS | AAC Block 650x240x100 - No. | ALTUS CENTRAL STORE | 239379 | 2024-07-21 16:54 | Purchase | 451 | 26383.5 | 68747 | 451 | 65.52 | 1854 | 2024-07-21 | Normal | MH14BJ1791 | Billed | G E NO.8533 DT.21.07.2024
GANGA ALTUS | SA BUILDING SOLUTIONS | AAC Block 650x240x125 | ALTUS CENTRAL STORE | 239380 | 2024-07-21 16:54 | Purchase | 425 | 31078.125 | 68747 | 425 | 81.9 | 1854 | 2024-07-21 | Normal | MH14BJ1791 | Billed | G E NO.8533 DT.21.07.2024
GANGA ALTUS | SA BUILDING SOLUTIONS | AAC Block 650x240x125 | ALTUS CENTRAL STORE | 239381 | 2024-07-21 16:57 | Purchase | 195 | 14259.375 | 68500 | 1495 | 81.9 | 1854 | 2024-07-21 | Normal | MH14BJ1791 | Billed | G E NO.8533 DT.21.07.2024
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | Angle Cock (F1015201-Cera) | ALTUS CENTRAL STORE | 239623 | 2024-07-31 12:11 | Purchase | 50 | 23310 | 68946 | 480 | 550.116 | 12506199 | 2024-07-30 | Normal | MH 12 KP 4754 | Billed | G E NO.8560 DT.31/07/2024
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | Bath Spout (F1015661-Cera) | ALTUS CENTRAL STORE | 239624 | 2024-07-31 12:11 | Purchase | 50 | 27389.25 | 68946 | 192 | 646.3863 | 12506199 | 2024-07-30 | Normal | MH 12 KP 4754 | Billed | G E NO.8560 DT.31/07/2024
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | Cera Garnet Bib Cock (F2002153) | ALTUS CENTRAL STORE | 239625 | 2024-07-31 12:11 | Purchase | 20 | 10256.4 | 68946 | 107 | 605.1277 | 12506199 | 2024-07-30 | Normal | MH 12 KP 4754 | Billed | G E NO.8560 DT.31/07/2024
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | CP Extension Piece 1/2" x 1" | ALTUS CENTRAL STORE | 239626 | 2024-07-31 12:11 | Purchase | 280 | 15276.8 | 68946 | 480 | 64.3808 | 12506199 | 2024-07-30 | Normal | MH 12 KP 4754 | Billed | G E NO.8560 DT.31/07/2024
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | Pillar Cock (F1015101-Cera) | ALTUS CENTRAL STORE | 239627 | 2024-07-31 12:11 | Purchase | 97 | 66249.351 | 68946 | 192 | 805.92 | 12506199 | 2024-07-30 | Normal | MH 12 KP 4754 | Billed | G E NO.8560 DT.31/07/2024
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | RAGBOLTS For Wallhung | ALTUS CENTRAL STORE | 239631 | 2024-07-31 12:14 | Purchase | 144 | 51408 | 68947 | 192 | 421.26 | 12506201 | 2024-07-30 | Normal | MH 12 KP 4754 | Billed | G E NO.8561 DT.31/07/2024
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | Shower Arm (F7040101-Cera) | ALTUS CENTRAL STORE | 239628 | 2024-07-31 12:11 | Purchase | 50 | 7692.3 | 68946 | 192 | 181.5383 | 12506199 | 2024-07-30 | Normal | MH 12 KP 4754 | Billed | G E NO.8560 DT.31/07/2024
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | Shower Rose (7020305-Cera) | ALTUS CENTRAL STORE | 239629 | 2024-07-31 12:11 | Purchase | 100 | 58974.3 | 68946 | 192 | 695.8968 | 12506199 | 2024-07-30 | Normal | MH 12 KP 4754 | Billed | G E NO.8560 DT.31/07/2024
GANGA ALTUS | SAPPHIRE SALES CORPORATION PRIVATE LIMITED | Sink Cock (F1015251-Cera) | ALTUS CENTRAL STORE | 239630 | 2024-07-31 12:11 | Purchase | 20 | 15384.6 | 68946 | 104 | 907.6913 | 12506199 | 2024-07-30 | Normal | MH 12 KP 4754 | Billed | G E NO.8560 DT.31/07/2024
GANGA ALTUS | SATAV STONE CO. PVT. LTD. | M Sand | ALTUS CENTRAL STORE | 239249 | 2024-07-17 17:55 | Purchase | 720 | 44640 | 69284 | 1181.42 | 65.1 | 24-25/12730 | 2024-07-17 | Normal | MH12SX8541 | Billed | G E NO.8503 DT.17.07.2024
GANGA ALTUS | SATAV STONE CO. PVT. LTD. | M Sand | ALTUS CENTRAL STORE | 239407 | 2024-07-23 18:59 | Purchase | 653 | 40486 | 69169 | 1955.1087 | 65.1 | 24-25/13651 | 2024-07-23 | Normal | MH12SX8541 | Billed | G E NO.8539 DT.23.07.2024
GANGA ALTUS | SATAV STONE CO. PVT. LTD. | M Sand | ALTUS CENTRAL STORE | 239409 | 2024-07-23 19:00 | Purchase | 67 | 4154 | 69284 | 1181.42 | 65.1 | 24-25/13651 | 2024-07-23 | Normal | MH12SX8541 | Billed | G E NO.8539 DT.23.07.2024
GANGA ALTUS | SATAV STONE CO. PVT. LTD. | M Sand | ALTUS CENTRAL STORE | 239812 | 2024-08-06 17:40 | Purchase | 651 | 40362 | 69398 | 4568.5184 | 65.1 | 24-25/15446 | 2024-08-06 | Normal | MH12UM1141 | Billed | G E NO.8588 DT.06.08.2024
GANGA ALTUS | SEJAL ENTERPRISES | Anchor Fastner 10mmx75mm | ALTUS CENTRAL STORE | 239063 | 2024-07-13 16:07 | Purchase | 70 | 980 | 69220 | 70 | 16.52 | 3313 | 2024-07-12 | Normal | MH 12 QE 4587 | Billed | G E NO.8495 DT.13.07.2024
GANGA ALTUS | SEJAL ENTERPRISES | GI C- Bracket 6" x 8" | ALTUS CENTRAL STORE | 240017 | 2024-08-12 19:20 | Purchase | 216 | 15120 | 69443 | 216 | 82.6 | 3377 | 2024-08-12 | Normal | MH 12 QE 4587 | Unbilled | GE NO 8606 DT 12.08.24
GANGA ALTUS | SEJAL ENTERPRISES | GI U Clamps 4" | ALTUS CENTRAL STORE | 239064 | 2024-07-13 16:07 | Purchase | 434 | 5425 | 69220 | 434 | 14.75 | 3313 | 2024-07-12 | Normal | MH 12 QE 4587 | Billed | G E NO.8495 DT.13.07.2024
GANGA ALTUS | SHANTI SALES | GI Clip 11/4" | ALTUS CENTRAL STORE | 239067 | 2024-07-13 18:01 | Purchase | 400 | 1200 | 67926 | 400 | 3.54 | SS/34861/24-25 | 2024-07-12 | Normal | MH14AZ5609 | Billed | G E NO.8496 DT.13.07.2024
GANGA ALTUS | SHANTI SALES | GI U Clamps 1/2" - | ALTUS CENTRAL STORE | 239068 | 2024-07-13 18:01 | Purchase | 120 | 636 | 67926 | 120 | 6.254 | SS/34861/24-25 | 2024-07-12 | Normal | MH14AZ5609 | Billed | G E NO.8496 DT.13.07.2024
GANGA ALTUS | SHANTI SALES | GI U Clamps 2" | ALTUS CENTRAL STORE | 239069 | 2024-07-13 18:01 | Purchase | 528 | 4752 | 67926 | 528 | 10.62 | SS/34861/24-25 | 2024-07-12 | Normal | MH14AZ5609 | Billed | G E NO.8496 DT.13.07.2024
GANGA ALTUS | SHANTI SALES | GI Z Bracket 4" x 4 FT | ALTUS CENTRAL STORE | 239070 | 2024-07-13 18:01 | Purchase | 220 | 50600 | 67926 | 520 | 271.4 | SS/34861/24-25 | 2024-07-12 | Normal | MH14AZ5609 | Billed | G E NO.8496 DT.13.07.2024
GANGA ALTUS | SHANTI SALES | GI Z Bracket 4" x 4 FT | ALTUS CENTRAL STORE | 239128 | 2024-07-15 18:33 | Purchase | 300 | 69000 | 67926 | 520 | 271.4 | SS/34895/24-25 | 2024-07-15 | Normal | MH14AZ5609 | Billed | G E NO.8499 DT.15.07.2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 12 Module C1 1112 Support Frame with Cover Plate | ALTUS CENTRAL STORE | 239713 | 2024-08-01 18:43 | Purchase | 13 | 1825.2 | 69157 | 13 | 165.6723 | 51016 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8565 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 12 Module C1 1112 Support Frame with Cover Plate | ALTUS CENTRAL STORE | 239724 | 2024-08-01 18:57 | Purchase | 16 | 2246.4 | 67935 | 28 | 165.6721 | 51018 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8567 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 12 Module Plate 1112 | ALTUS CENTRAL STORE | 239714 | 2024-08-01 18:43 | Purchase | 7 | 982.8 | 69157 | 7 | 165.6714 | 51016 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8565 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 16 Amp. Socket with shutter (1057) | ALTUS CENTRAL STORE | 239715 | 2024-08-01 18:43 | Purchase | 10 | 1017 | 69157 | 10 | 120.006 | 51016 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8565 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 16 Amp. Switch with indicator (1052) | ALTUS CENTRAL STORE | 239716 | 2024-08-01 18:43 | Purchase | 2 | 175.5 | 69157 | 2 | 103.55 | 51016 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8565 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 3 Module C1 1103 Support Frame with Cover Plate | ALTUS CENTRAL STORE | 239717 | 2024-08-01 18:43 | Purchase | 44 | 2316.6 | 69157 | 138 | 62.127 | 51016 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8565 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 4 Module C1 1104 Support Frame with Cover Plate | ALTUS CENTRAL STORE | 239718 | 2024-08-01 18:43 | Purchase | 19 | 1162.8 | 69157 | 19 | 72.2158 | 51016 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8565 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 6 Module C1 1106 Support Frame with Cover Plate | ALTUS CENTRAL STORE | 239719 | 2024-08-01 18:43 | Purchase | 20 | 1791 | 69157 | 33 | 105.6688 | 51016 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8565 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 6 Module Plate 1106 | ALTUS CENTRAL STORE | 239722 | 2024-08-01 18:50 | Purchase | 22 | 1970.1 | 69157 | 23 | 105.6691 | 51016. | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8565 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 6A Two way Switch (1002) - No. | ALTUS CENTRAL STORE | 239725 | 2024-08-01 19:08 | Purchase | 6 | 378 | 66677 | 6 | 74.34 | 51021 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8568 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 6A Two way Switch (1002) - No. | ALTUS CENTRAL STORE | 239852 | 2024-08-08 11:58 | Purchase | 61 | 3843 | 69431 | 61 | 74.34 | 51021 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8568 DT.01/08/2024 GRN LATE SHORT QTY
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 8 Module C1 H-1108 Support Frame with Cover Plate - No. | ALTUS CENTRAL STORE | 239720 | 2024-08-01 18:43 | Purchase | 12 | 1544.4 | 69157 | 12 | 151.8667 | 51016 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8565 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | 8M Plate (Hzl) H1108 | ALTUS CENTRAL STORE | 239721 | 2024-08-01 18:43 | Purchase | 8 | 1029.6 | 69157 | 8 | 151.865 | 51016 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8565 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | Fan step Regulator (1075) | ALTUS CENTRAL STORE | 239723 | 2024-08-01 18:55 | Purchase | 19 | 4232.25 | 69164 | 19 | 262.8447 | 51017 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8566 DT.01/08/2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | MCB 32 Amp. 4 Pole | ALTUS CENTRAL STORE | 240032 | 2024-08-13 16:09 | Purchase | 6 | 6463.8 | 69313 | 6 | 1271.2133 | 51383 | 2024-08-12 | Normal | MH12JF0977 | Unbilled | G E NO.8608 DT.12.08.2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | MCB 63 amp 4 pole | ALTUS CENTRAL STORE | 240033 | 2024-08-13 16:09 | Purchase | 2 | 3081.96 | 69313 | 2 | 1818.36 | 51383 | 2024-08-12 | Normal | MH12JF0977 | Unbilled | G E NO.8608 DT.12.08.2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | PVC Copper Wire 1.5 Sqmm yellow | ALTUS CENTRAL STORE | 239224 | 2024-07-17 12:53 | Purchase | 49.06 | 757.4815 | 69280 | 50 | 18.2191 | 50478 | 2024-07-11 | Normal | MH12FD7617 | Billed | G E NO.8487 DT.11.07.2024
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | Rubber Matt 1MTR X2MTR X 10MM Thick | ALTUS CENTRAL STORE | 239755 | 2024-08-02 19:22 | Purchase | 6 | 16200 | 69359 | 6 | 3186 | 51023 | 2024-08-01 | Normal | MH12FD7617 | Billed | G E NO.8569 DT.01/08/2024 GRN LATE HIGHRISE ISSUE
GANGA ALTUS | SHRI RUSHABH ELECTRA AND CABLES PVT LTD | Single Phase Energy Meter | ALTUS CENTRAL STORE | 239377 | 2024-07-20 19:47 | Purchase | 10 | 4800 | 69298 | 10 | 566.4 | 50723 | 2024-07-19 | Normal | MH12FD7617 | Billed | G E NO.8530 DT.20.07.2024
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | Wall Putty (Rakshak) Cement Based | ALTUS CENTRAL STORE | 239413 | 2024-07-23 19:07 | Purchase | 1200 | 15000 | 68742 | 30585.4908 | 14.75 | SPPL/2276/24-25 | 2024-07-23 | Normal | MH12 WJ6787 | Billed | G E NO.8541 DT.23.07.2024
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | Wall Putty (Rakshak) Cement Based | ALTUS CENTRAL STORE | 239595 | 2024-07-30 16:55 | Purchase | 1600 | 20000 | 68675 | 10000 | 14.75 | SPPL/2332/24-25 | 2024-07-30 | Normal | MH12VT4363 | Billed | G E NO.8558 DT.30/07/2024
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | Wall Putty (Rakshak) Cement Based | ALTUS CENTRAL STORE | 239596 | 2024-07-30 16:58 | Purchase | 1000 | 12500 | 68675 | 10000 | 14.75 | SPPL/2343/24-25 | 2024-07-30 | Normal | MH12VT5247 | Billed | G E NO.8559 DT.30/07/2024
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | Wall Putty (Rakshak) Cement Based | ALTUS CENTRAL STORE | 239633 | 2024-07-31 17:14 | Purchase | 600 | 7500 | 68675 | 10000 | 14.75 | SPPL/2363/24-25 | 2024-07-31 | Normal | MH12 WJ6787 | Billed | G E NO.85645 DT.31/07/2024
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | Wall Putty (Rakshak) Cement Based | ALTUS CENTRAL STORE | 239634 | 2024-07-31 17:16 | Purchase | 1400 | 17500 | 68742 | 30585.4908 | 14.75 | SPPL/2363/24-25 | 2024-07-31 | Normal | MH12 WJ6787 | Billed | G E NO.8564 DT.31/07/2024
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | Wall Putty (Rakshak) Cement Based | ALTUS CENTRAL STORE | 239797 | 2024-08-05 17:50 | Purchase | 2800 | 35000 | 68742 | 30585.4908 | 14.75 | SPPL/2418/24-25 | 2024-08-05 | Normal | MH12 WJ6787 | Billed | G E NO.8583 DT.05.08.2024
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | Wall Putty (Rakshak) Cement Based | ALTUS CENTRAL STORE | 239798 | 2024-08-05 17:54 | Purchase | 1000 | 12500 | 68742 | 30585.4908 | 14.75 | SPPL/2408/24-25 | 2024-08-05 | Normal | MH12UM4628 | Billed | G E NO.8581 DT.05.08.2024
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | Wall Putty (Rakshak) Cement Based | ALTUS CENTRAL STORE | 239819 | 2024-08-06 18:49 | Purchase | 1200 | 15000 | 68742 | 30585.4908 | 14.75 | SPPL/2430/24-25 | 2024-08-06 | Normal | MH12 WJ6787 | Billed | G E NO.8591 DT.06.08.2024
GANGA ALTUS | SKCO PAINTS PRIVATE LIMITED | Wall Putty (Rakshak) Cement Based | ALTUS CENTRAL STORE | 239953 | 2024-08-09 18:49 | Purchase | 2000 | 25000 | 68742 | 30585.4908 | 14.75 | SPPL/2481/24-25 | 2024-08-09 | Normal | MH12 WJ6787 | Billed | G E NO.8598 DT.09/08/2024
GANGA ALTUS | SPARTAN ENGINEERING INDUSTRIES PVT. LTD | Cabin Light for SPM200L | ALTUS CENTRAL STORE | 239469 | 2024-07-25 17:45 | Purchase | 1 | 2730 | 68771 | 1 | 3221.4 | KS/SI/24-25/757 | 2024-06-06 | Normal | BY HAND | Billed | G E NO.8546 DT.25/07/2025
GANGA ALTUS | SUNSHINE ASSOCIATES | Potato Greece | ALTUS CENTRAL STORE | 239952 | 2024-08-09 18:46 | Purchase | 180 | 23940 | 69445 | 180 | 156.94 | SA/174/24-25 | 2024-08-09 | Normal | MH12SK0595 | Billed | G E NO.8596 DT.09/08/2024
GANGA ALTUS | SUPERMIX RMC INDIA | Sand-Metal Mix M25 (Downpour) | ALTUS CENTRAL STORE | 239675 | 2024-07-31 18:49 | Purchase | 7 | 20169.492 | 69217 | 11 | 3400.0001 | 2150 | 2024-07-30 | Normal | MH12SX1739 | Billed | G E NO..8556 DT.30/07/2024
GANGA ALTUS | SUPERMIX RMC INDIA | Sand-Metal Mix M25 (Downpour) | ALTUS CENTRAL STORE | 239822 | 2024-08-07 10:14 | Purchase | 4 | 11525.424 | 69217 | 11 | 3400.0001 | 2184 | 2024-08-06 | Normal | MH12UM8788 | Unbilled | G E NO.8590 DT.06/08/2024
GANGA ALTUS | SUPERMIX RMC INDIA | Sand-Metal Mix M25 (Pumpable) | ALTUS CENTRAL STORE | 239382 | 2024-07-21 17:03 | Purchase | 7 | 20169.492 | 69217 | 33 | 3399.9999 | 2121 | 2024-07-20 | Normal | MH12UM8788 | Billed | G E NO.8525 DT.20.07.2024
GANGA ALTUS | SUPERMIX RMC INDIA | Sand-Metal Mix M25 (Pumpable) | ALTUS CENTRAL STORE | 239383 | 2024-07-21 17:04 | Purchase | 7 | 20169.492 | 69217 | 33 | 3399.9999 | 2122 | 2024-07-20 | Normal | MH12SF4609 | Billed | G E NO.8528 DT.20.07.2024
GANGA ALTUS | ULTRATECH CEMENT LTD | Cement 43 Grade | ALTUS CENTRAL STORE | 239544 | 2024-07-29 11:41 | Purchase | 600 | 159375 | 69246 | 600 | 340 | 8930552190 | 2024-07-26 | Normal | MH13CU2718 | Billed | G E NO 8554 DT.29/07/2024
GANGA ALTUS | ULTRATECH CEMENT LTD | Cement 43 Grade | ALTUS CENTRAL STORE | 239967 | 2024-08-10 19:20 | Purchase | 600 | 159375 | 69423 | 600 | 340 | 8930553150 | 2024-08-09 | Normal | MH12QG0755 | Unbilled | G E NO.8602 DT.10/08/2024 UNLOADING ASMI SITE
GANGA ALTUS | ULTRATECH CEMENT LTD | Cement 43 Grade | ALTUS CENTRAL STORE | 239968 | 2024-08-10 19:26 | Purchase | 500 | 132812.5 | 69422 | 600 | 340 | 8930553151 | 2024-08-09 | Normal | MH43BP3127 | Unbilled | G E NO.8603 DT.10/08/2024 ALTUS
GANGA ALTUS | V H ENTERPRISES | 2 POLE 40 AMP MCB (IH22P0C040) | ALTUS CENTRAL STORE | 239530 | 2024-07-27 18:32 | Purchase | 60 | 25584 | 68111 | 210 | 503.152 | 966 | 2024-07-26 | Normal | MH14KV5285 | Unbilled | G E NO.8552 DT.27/07/2024
GANGA ALTUS | V H ENTERPRISES | 4 POLE 40AMP 30MA RCCB (IH2R440030) | ALTUS CENTRAL STORE | 239531 | 2024-07-27 18:32 | Purchase | 58 | 83195.2 | 68111 | 190 | 1692.592 | 966 | 2024-07-26 | Normal | MH14KV5285 | Unbilled | G E NO.8552 DT.27/07/2024
GANGA ALTUS | V H ENTERPRISES | 4 POLE 40AMP MCB (IH24P0C040) | ALTUS CENTRAL STORE | 239532 | 2024-07-27 18:32 | Purchase | 7 | 6115.2 | 68111 | 190 | 1030.848 | 966 | 2024-07-26 | Normal | MH14KV5285 | Unbilled | G E NO.8552 DT.27/07/2024
GANGA ALTUS | V H ENTERPRISES | 4 Way TPN DB DD 8 WAY In comer 1.2 Thick with TV Tele. | ALTUS CENTRAL STORE | 239533 | 2024-07-27 18:33 | Purchase | 4 | 11618 | 67716 | 15 | 3427.3107 | 966 | 2024-07-26 | Normal | MH14KV5285 | Unbilled | G E NO.8552 DT.27/07/2024
GANGA ALTUS | V H ENTERPRISES | SPN DB DD 12 Way IHPSPNDD012 | ALTUS CENTRAL STORE | 239529 | 2024-07-27 18:30 | Purchase | 2 | 2542.96 | 69174 | 4 | 1500.345 | 966 | 2024-07-26 | Normal | MH14KV5285 | Unbilled | G E NO.8552 DT.27/07/2024