## GRNRegisteritemwise638579360006
Material Wise GRN Report
From 01-01-2014 To 30-07-2024
Page 1 of 1
Total Records: 10 Records 1 to 10
Project_Name | Material_Category1 | Material_Name | Brand | GRN_No | GRN_Date | GRNType | Supplier_Issue_Store | Good_Qty | Unit_Name | Received_Store | Amount | Tax_Amount | PO_SrNo | PO_Qty | Rate | Others_Amount | Others_Tax | Challan_No | Challan_Date | Challan_Qty | Use_Challan_Qty | ChallanAmount | Bill_No | Bill_date | Billing_Status | VehicleNo | GateReg_No | GateReg date | GateReg Time | GateReg Out Date | GateReg Out Time | Po_Date | GRN_Remark | GRN_Status | Material_Category2 | GTN_SrNo | Created_By | Created_Date | Approved_By | Approved_Date | Accepted_Qty
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Dry Balcony Door) (Size at Actual) |  | 228774 | 2023-09-25 19:16 | Purchase | GREENCON INFRATECH SOLUTIONS | 5 | No. | GDT/COMM | 51750 | 9315 | 66658 | 5 | 10350 | 0 | 0 | 3091 | 2023-09-23 | 5 | 0 | 51750 | GIS/288/23-24/M | 2023-09-25 | Billed | MH16CD6207 | 15980 | 2023-09-25 19:15 | 7:15 PM | 1900-01-01 | 12:00 AM | 2023-09-23 15:42 | Gate No.15980 Dt.25/09/2023 | Approved |  | 66658 | rushikesh.hadke | 2023-09-25 19:16 |  |  | 5
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Dry Balcony Door) (Size at Actual) |  | 228495 | 2023-09-18 16:37 | Purchase | GREENCON INFRATECH SOLUTIONS | 3 | No. | GDT/COMM | 31050 | 5589 | 66596 | 4 | 10350 | 0 | 0 | 3074. | 2023-09-07 | 3 | 0 | 31050 | GIS/276/23-24/M | 2023-09-20 | Billed | MH12TB2013 | 15931 | 2023-09-18 16:37 | 4:37 PM | 1900-01-01 | 12:00 AM | 2023-09-18 14:08 | Gate No.15931 Dt.18/09/2023-A Bldg. | Approved |  | 66596 | rushikesh.hadke | 2023-09-18 16:37 |  |  | 3
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Dry Balcony Door) (Size at Actual) |  | 228490 | 2023-09-18 16:32 | Purchase | GREENCON INFRATECH SOLUTIONS | 17 | No. | GDT/COMM | 175950 | 31671 | 66408 | 19 | 10350 | 0 | 0 | 3074 | 2023-09-07 | 17 | 0 | 175950 | GIS/276/23-24/M | 2023-09-20 | Billed | MH12TB2013 | 15931 | 2023-09-18 16:28 | 4:28 PM | 1900-01-01 | 12:00 AM | 2023-08-30 17:49 | Gate No.15931 Dt.18/09/2023 | Approved |  | 66408 | rushikesh.hadke | 2023-09-18 16:32 |  |  | 17
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Dry Balcony Door) (Size at Actual) |  | 228488 | 2023-09-18 16:27 | Purchase | GREENCON INFRATECH SOLUTIONS | 1 | No. | GDT/COMM | 10350 | 1863 | 66596 | 4 | 10350 | 0 | 0 | 3073 | 2023-09-07 | 1 | 0 | 10350 | GIS/275/23-24/M | 2023-09-20 | Billed | MH12TB2013 | 15930 | 2023-09-18 16:21 | 4:21 PM | 1900-01-01 | 12:00 AM | 2023-09-18 14:08 | Gate No.15930 Dt.18/09/2023 | Approved |  | 66596 | rushikesh.hadke | 2023-09-18 16:27 |  |  | 1
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Dry Balcony Door) (Size at Actual) |  | 227367 | 2023-08-31 12:54 | Purchase | GREENCON INFRATECH SOLUTIONS | 2 | No. | GDT/COMM | 20700 | 3726 | 66408 | 19 | 10350 | 0 | 0 | 3058. | 2023-08-28 | 2 | 0 | 20700 | GIS/228/23-24/M | 2023-08-30 | Billed | MH12UM7726 | 15771 | 2023-08-28 12:51 | 12:51 PM | 1900-01-01 | 12:00 AM | 2023-08-30 17:49 | Gate No.15771 Dt.28/08/2023-B Bldg. (PO Not Available) | Approved |  | 66408 | RUSHIKESH.HADKE | 2023-08-31 12:54 |  |  | 2
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Dry Balcony Door) (Size at Actual) |  | 227074 | 2023-08-24 19:26 | Purchase | GREENCON INFRATECH SOLUTIONS | 17 | No. | GDT/COMM | 175950 | 31671 | 64745 | 26 | 10350 | 0 | 0 | 3055 | 2023-08-24 | 17 | 0 | 175950 | GIS/222/23-24/M | 2023-08-24 | Billed | MH12UM7726 | 15734 | 2023-08-24 19:21 | 7:21 PM | 1900-01-01 | 12:00 AM | 2023-02-20 18:31 | Gate No.15734 Dt.24/08/2023 | Approved |  | 64745 | rushikesh.hadke | 2023-08-24 19:26 |  |  | 17
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Dry Balcony Door) (Size at Actual) |  | 222741 | 2023-04-12 19:04 | Purchase | GREENCON INFRATECH SOLUTIONS | 9 | No. | GDT/COMM | 93150 | 16767 | 64745 | 26 | 10350 | 0 | 0 | 2669 | 2023-04-12 | 9 | 0 | 93150 | GIS/023/23-24/M | 2023-04-12 | Billed | MH12SX8637 | 15041 | 2023-04-12 17:58 | 5:58 PM | 1900-01-01 | 12:00 AM | 2023-02-20 18:31 | Gate No.15041 Dt.12/04/2023-A Bldg. | Approved |  | 64745 | rushikesh.hadke | 2023-04-12 19:04 |  |  | 9
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Dry Balcony Door) (Size at Actual) |  | 200544 | 2021-03-30 14:46 | Purchase | GREENCON INFRATECH SOLUTIONS | 2 | No. | GDT/COMM | 16200 | 2916 | 57573 | 28 | 8100 | 0 | 0 | 771 | 2021-03-29 | 2 | 0 | 16200 | GIS/473/20-21/M | 2021-03-31 | Billed | BY HAND | 11306 | 2021-03-30 14:39 | 2:39 PM | 1900-01-01 | 12:00 AM | 2020-10-29 19:43 | Gate No.11306 Dt.30/03/2021-A-301/302/303/304 | Approved |  | 57573 | rushikeshh | 2021-03-30 14:46 |  |  | 2
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Dry Balcony Door) (Size at Actual) |  | 200527 | 2021-03-30 14:27 | Purchase | GREENCON INFRATECH SOLUTIONS | 1 | No. | GDT/COMM | 8100 | 1458 | 57573 | 28 | 8100 | 0 | 0 | 758 | 2021-03-30 | 1 | 0 | 8100 | GIS/478/20-21/M | 2021-03-31 | Billed | BY HAND | 11304 | 2021-03-30 14:23 | 2:23 PM | 1900-01-01 | 12:00 AM | 2020-10-29 19:43 | Gate No.11304 Dt.30/03/2021-B-301/302 | Approved |  | 57573 | rushikeshh | 2021-03-30 14:27 |  |  | 1
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Dry Balcony Door) (Size at Actual) |  | 200122 | 2021-03-13 19:39 | Purchase | GREENCON INFRATECH SOLUTIONS | 25 | No. | GDT/COMM | 202500 | 36450 | 57573 | 28 | 8100 | 0 | 0 | 696 | 2021-03-13 | 25 | 0 | 202500 | GIS/429/20-21/M | 2021-03-17 | Billed | MH42AQ4697 | 11204 | 2021-03-13 19:27 | 7:27 PM | 1900-01-01 | 12:00 AM | 2020-10-29 19:43 | Gate No.11204 Dt.13/03/2021 | Approved |  | 57573 | rushikeshh | 2021-03-13 19:39 |  |  | 25