## GRNRegisteritemwise638579362721
Material Wise GRN Report
From 01-01-2014 To 30-07-2024
Page 1 of 1
Total Records: 18 Records 1 to 18
Project_Name | Material_Category1 | Material_Name | Brand | GRN_No | GRN_Date | GRNType | Supplier_Issue_Store | Good_Qty | Unit_Name | Received_Store | Amount | Tax_Amount | PO_SrNo | PO_Qty | Rate | Others_Amount | Others_Tax | Challan_No | Challan_Date | Challan_Qty | Use_Challan_Qty | ChallanAmount | Bill_No | Bill_date | Billing_Status | VehicleNo | GateReg_No | GateReg date | GateReg Time | GateReg Out Date | GateReg Out Time | Po_Date | GRN_Remark | GRN_Status | Material_Category2 | GTN_SrNo | Created_By | Created_Date | Approved_By | Approved_Date | Accepted_Qty
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 235868 | 2024-03-23 18:32 | Purchase | GREENCON INFRATECH SOLUTIONS | 14 | No. | GDT/AGGE | 144900 | 26082 | 68290 | 14 | 10350 | 0 | 0 | 3703 | 2024-03-18 | 14 | 0 | 144900 | GIS/541/23-24 | 2024-03-26 | Billed | MH12SX8637 | 16910 | 2024-03-23 18:20 | 6:20 PM | 2024-03-23 18:20 | 6:20 PM | 2024-03-23 16:11 | Gate No.16910 Dt.23/03/2024 | Approved |  | 68290 | Rushikesh.Hadke | 2024-03-23 18:32 |  |  | 14
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 229780 | 2023-10-23 15:47 | Purchase | GREENCON INFRATECH SOLUTIONS | 15 | No. | GDT/COMM | 155250 | 27945 | 66964 | 15 | 10350 | 0 | 0 | 3171 | 2023-10-23 | 15 | 0 | 155250 | GIS/329/23-24/M | 2023-10-23 | Billed | MH12RN0996 | 16158 | 2023-10-23 15:40 | 3:40 PM | 1900-01-01 | 12:00 AM | 2023-10-23 11:45 | Gate No.16158 Dt.23/10/2023 | Approved |  | 66964 | rushikesh.hadke | 2023-10-23 15:47 |  |  | 15
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 228775 | 2023-09-25 19:16 | Purchase | GREENCON INFRATECH SOLUTIONS | 2 | No. | GDT/COMM | 20700 | 3726 | 66658 | 2 | 10350 | 0 | 0 | 3091 | 2023-09-23 | 2 | 0 | 20700 | GIS/288/23-24/M | 2023-09-25 | Billed | MH16CD6207 | 15980 | 2023-09-25 19:15 | 7:15 PM | 1900-01-01 | 12:00 AM | 2023-09-23 15:42 | Gate No.15980 Dt.25/09/2023 | Approved |  | 66658 | rushikesh.hadke | 2023-09-25 19:16 |  |  | 2
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 228492 | 2023-09-18 16:36 | Purchase | GREENCON INFRATECH SOLUTIONS | 16 | No. | GDT/COMM | 165600 | 29808 | 66596 | 21 | 10350 | 0 | 0 | 3074 | 2023-09-07 | 16 | 0 | 165600 | GIS/276/23-24/M | 2023-09-20 | Billed | MH12TB2013 | 15931 | 2023-09-18 16:33 | 4:33 PM | 1900-01-01 | 12:00 AM | 2023-09-18 14:08 | Gate No.15931 Dt.18/09/2023-A Bldg. | Approved |  | 66596 | rushikesh.hadke | 2023-09-18 16:36 |  |  | 16
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 228487 | 2023-09-18 16:27 | Purchase | GREENCON INFRATECH SOLUTIONS | 5 | No. | GDT/COMM | 51750 | 9315 | 66596 | 21 | 10350 | 0 | 0 | 3073 | 2023-09-07 | 5 | 0 | 51750 | GIS/275/23-24/M | 2023-09-20 | Billed | MH12TB2013 | 15930 | 2023-09-18 16:21 | 4:21 PM | 1900-01-01 | 12:00 AM | 2023-09-18 14:08 | Gate No.15930 Dt.18/09/2023 | Approved |  | 66596 | rushikesh.hadke | 2023-09-18 16:27 |  |  | 5
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 227481 | 2023-09-02 18:18 | Purchase | GREENCON INFRATECH SOLUTIONS | 64 | No. | GDT/COMM | 662400 | 119232 | 66434 | 64 | 10350 | 0 | 0 | 3062. | 2023-08-30 | 64 | 0 | 662400 | GIS/240/23-24/M | 2023-09-04 | Billed | MH12SX8367 | 15807 | 2023-09-02 18:17 | 6:17 PM | 1900-01-01 | 12:00 AM | 2023-09-01 13:00 | Gate No.15807 Dt.02/09/2023 | Approved |  | 66434 | rushikesh.hadke | 2023-09-02 18:18 |  |  | 64
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 227476 | 2023-09-02 18:12 | Purchase | GREENCON INFRATECH SOLUTIONS | 46 | No. | GDT/COMM | 476100 | 85698 | 66408 | 107 | 10350 | 0 | 0 | 3062 | 2023-08-30 | 46 | 0 | 476100 | GIS/240/23-24/M | 2023-09-04 | Billed | MH12SX8367 | 15807 | 2023-09-02 18:09 | 6:09 PM | 1900-01-01 | 12:00 AM | 2023-08-30 17:49 | Gate No.15807 Dt.02/09/2023 | Approved |  | 66408 | rushikesh.hadke | 2023-09-02 18:12 |  |  | 46
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 227396 | 2023-08-31 18:48 | Purchase | GREENCON INFRATECH SOLUTIONS | 4 | No. | GDT/COMM | 41400 | 7452 | 66408 | 107 | 10350 | 0 | 0 | 3061 | 2023-08-30 | 4 | 0 | 41400 | GIS/238/23-24/M | 2023-09-02 | Billed | MH12VF6439 | 15798 | 2023-08-31 18:44 | 6:44 PM | 1900-01-01 | 12:00 AM | 2023-08-30 17:49 | Gate No.15798 Dt.31/08/2023 | Approved |  | 66408 | RUSHIKESH.HADKE | 2023-08-31 18:48 |  |  | 4
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 227368 | 2023-08-31 12:54 | Purchase | GREENCON INFRATECH SOLUTIONS | 57 | No. | GDT/COMM | 589950 | 106191 | 66408 | 107 | 10350 | 0 | 0 | 3058. | 2023-08-28 | 57 | 0 | 589950 | GIS/228/23-24/M | 2023-08-30 | Billed | MH12UM7726 | 15771 | 2023-08-28 12:51 | 12:51 PM | 1900-01-01 | 12:00 AM | 2023-08-30 17:49 | Gate No.15771 Dt.28/08/2023-B Bldg. (PO Not Available) | Approved |  | 66408 | RUSHIKESH.HADKE | 2023-08-31 12:54 |  |  | 57
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 227070 | 2023-08-24 19:26 | Purchase | GREENCON INFRATECH SOLUTIONS | 93 | No. | GDT/COMM | 962550 | 173259 | 64745 | 210 | 10350 | 0 | 0 | 3055 | 2023-08-24 | 93 | 0 | 962550 | GIS/222/23-24/M | 2023-08-24 | Billed | MH12UM7726 | 15734 | 2023-08-24 19:21 | 7:21 PM | 1900-01-01 | 12:00 AM | 2023-02-20 18:31 | Gate No.15734 Dt.24/08/2023 | Approved |  | 64745 | rushikesh.hadke | 2023-08-24 19:26 |  |  | 93
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 224526 | 2023-06-12 16:50 | Purchase | GREENCON INFRATECH SOLUTIONS | 8 | No. | GDT/COMM | 82800 | 14904 | 64745 | 210 | 10350 | 0 | 0 | 2878 | 2023-06-12 | 8 | 0 | 82800 | GIS/101/23-24/M | 2023-06-12 | Billed | MH14KA9475 | 15361 | 2023-06-12 16:45 | 4:45 PM | 1900-01-01 | 12:00 AM | 2023-02-20 18:31 | Gate No.15361 Dt.12/06/2023-B Bldg | Approved |  | 64745 | rushikesh.hadke | 2023-06-12 16:50 |  |  | 8
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 224264 | 2023-06-03 19:44 | Purchase | GREENCON INFRATECH SOLUTIONS | 10 | No. | GDT/COMM | 103500 | 18630 | 64745 | 210 | 10350 | 0 | 0 | 2857 | 2023-06-03 | 10 | 0 | 103500 | GIS/089/23-24/M | 2023-06-03 | Billed | MH12UM7726 | 15308 | 2023-06-03 19:39 | 7:39 PM | 1900-01-01 | 12:00 AM | 2023-02-20 18:31 | Gate No.15308 Dt.03/06/2023- A Bldg | Approved |  | 64745 | rushikesh.hadke | 2023-06-03 19:44 |  |  | 10
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 222742 | 2023-04-12 19:07 | Purchase | GREENCON INFRATECH SOLUTIONS | 44 | No. | GDT/COMM | 455400 | 81972 | 64745 | 210 | 10350 | 0 | 0 | 2670 | 2023-04-12 | 44 | 0 | 455400 | GIS/023/23-24/M | 2023-04-12 | Billed | MH12SX8637 | 15042 | 2023-04-12 19:04 | 7:04 PM | 1900-01-01 | 12:00 AM | 2023-02-20 18:31 | Gate No.15042 Dt.12/04/2023-A Bldg. | Approved |  | 64745 | rushikesh.hadke | 2023-04-12 19:07 |  |  | 44
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 222738 | 2023-04-12 19:04 | Purchase | GREENCON INFRATECH SOLUTIONS | 55 | No. | GDT/COMM | 569250 | 102465 | 64745 | 210 | 10350 | 0 | 0 | 2669 | 2023-04-12 | 55 | 0 | 569250 | GIS/023/23-24/M | 2023-04-12 | Billed | MH12SX8637 | 15041 | 2023-04-12 17:58 | 5:58 PM | 1900-01-01 | 12:00 AM | 2023-02-20 18:31 | Gate No.15041 Dt.12/04/2023-A Bldg. | Approved |  | 64745 | rushikesh.hadke | 2023-04-12 19:04 |  |  | 55
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 200547 | 2021-03-30 14:46 | Purchase | GREENCON INFRATECH SOLUTIONS | 5 | No. | GDT/COMM | 40500 | 7290 | 57573 | 83 | 8100 | 0 | 0 | 771 | 2021-03-29 | 5 | 0 | 40500 | GIS/473/20-21/M | 2021-03-31 | Billed | BY HAND | 11306 | 2021-03-30 14:39 | 2:39 PM | 1900-01-01 | 12:00 AM | 2020-10-29 19:43 | Gate No.11306 Dt.30/03/2021-A-301/302/303/304 | Approved |  | 57573 | rushikeshh | 2021-03-30 14:46 |  |  | 5
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 200520 | 2021-03-30 14:23 | Purchase | GREENCON INFRATECH SOLUTIONS | 6 | No. | GDT/COMM | 48600 | 8748 | 57573 | 83 | 8100 | 0 | 0 | 757 | 2021-03-30 | 6 | 0 | 48600 | GIS/479/20-21/M | 2021-03-31 | Billed | BY HAND | 11303 | 2021-03-30 14:17 | 2:17 PM | 1900-01-01 | 12:00 AM | 2020-10-29 19:43 | Gate No.11303 Dt.30/03/2021-B-301/302 | Approved |  | 57573 | rushikeshh | 2021-03-30 14:23 |  |  | 6
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 200125 | 2021-03-13 19:39 | Purchase | GREENCON INFRATECH SOLUTIONS | 72 | No. | GDT/COMM | 583200 | 104976 | 57573 | 83 | 8100 | 0 | 0 | 696 | 2021-03-13 | 72 | 0 | 583200 | GIS/429/20-21/M | 2021-03-17 | Billed | MH42AQ4697 | 11204 | 2021-03-13 19:27 | 7:27 PM | 1900-01-01 | 12:00 AM | 2020-10-29 19:43 | Gate No.11204 Dt.13/03/2021 | Approved |  | 57573 | rushikeshh | 2021-03-13 19:39 |  |  | 72
GANGA DHAM TOWERS | DOORS & WINDOWS | Veneer Door Shutter (Toilet Door) (Size at Actual) |  | 199043 | 2021-02-01 19:08 | Purchase | GREENCON INFRATECH SOLUTIONS | 4 | No. | GDT/COMM | 32400 | 5832 | 57913 | 4 | 8100 | 0 | 0 | 331 | 2021-01-27 | 4 | 0 | 32400 | GIS/342/20-21/M | 2021-02-13 | Billed | MH12KP4021 | 11028 | 2021-02-01 19:05 | 7:05 PM | 1900-01-01 | 12:00 AM | 2020-12-12 19:16 | Gate No.11028 Dt.01/02/2021 | Approved |  | 57913 | rushikeshh | 2021-02-01 19:08 |  |  | 4