## GRNRegisteritemwise638580421716
Material Wise GRN Report
From 01-07-2024 To 31-07-2024
Page 1 of 1
Total Records: 31 Records 1 to 31
Project_Name | Material_Category1 | Material_Name | Brand | GRN_No | GRN_Date | GRNType | Supplier_Issue_Store | Good_Qty | Unit_Name | Received_Store | Amount | Tax_Amount | PO_SrNo | PO_Qty | Rate | Others_Amount | Others_Tax | Challan_No | Challan_Date | Challan_Qty | Use_Challan_Qty | ChallanAmount | Bill_No | Bill_date | Billing_Status | VehicleNo | GateReg_No | GateReg date | GateReg Time | GateReg Out Date | GateReg Out Time | Po_Date | GRN_Remark | GRN_Status | Material_Category2 | GTN_SrNo | Created_By | Created_Date | Approved_By | Approved_Date | Accepted_Qty
GANGA ALTUS | RMC | Ready Mix Concrete M25 Regular Downpour |  | 239432 | 2024-07-24 17:37 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 4 | Cu.Mtrs | ALTUS CENTRAL STORE | 17261.016 | 3106.98 | 69259 | 25 | 4315.254 | 0 | 0 | S/2116 | 2024-07-23 | 4 | 0 | 17261.016 | 0 |  | Unbilled | MH12KP9215 | 8540 | 2024-07-23 17:18 | 5:18 PM | 2024-07-23 17:18 | 5:18 PM | 2024-07-15 13:11 | G E NO.8540 DT.23/07/2024 | Approved |  | 69259 | ANIL BHOSALE | 2024-07-24 17:37 |  |  | 4
GANGA ALTUS | RMC | Ready Mix Concrete M-15 Grade( D/P) - |  | 239430 | 2024-07-24 17:34 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 5 | Cu.Mtrs | ALTUS CENTRAL STORE | 19669.49 | 3540.5 | 69328 | 23.85 | 3933.898 | 0 | 0 | S/2114 | 2024-07-20 | 5 | 0 | 19669.49 | 0 |  | Unbilled | MH12WJ6711 | 8538 | 2024-07-20 17:18 | 5:18 PM | 2024-07-20 17:18 | 5:18 PM | 2024-07-23 18:08 | G E NO.8538 DT.23/07/2024 | Approved | D | 69328 | ANIL BHOSALE | 2024-07-24 17:34 |  |  | 5
GANGA ALTUS | RMC | Ready Mix Concrete M-15 Downpour |  | 239386 | 2024-07-21 17:15 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 22255.92 | 4006.06 | 68513 | 38.97 | 3709.32 | 0 | 0 | S/2081 | 2024-07-21 | 6 | 0 | 22255.92 | 0 |  | Unbilled | MH12KP9216 | 8532 | 2024-07-21 16:50 | 4:50 PM | 2024-07-21 16:50 | 4:50 PM | 2024-04-22 14:19 | G E NO.8532 DT.21.07.2024 | Approved |  | 68513 | ANIL BHOSALE | 2024-07-21 17:15 |  |  | 6
GANGA ALTUS | RMC | Ready Mix Concrete M25 Regular Downpour |  | 239385 | 2024-07-21 17:11 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 3 | Cu.Mtrs | ALTUS CENTRAL STORE | 12945.762 | 2330.24 | 69259 | 25 | 4315.254 | 0 | 0 | S/2083 | 2024-07-21 | 3 | 0 | 12945.762 | 0 |  | Unbilled | MH12KP9218 | 8534 | 2024-07-21 16:50 | 4:50 PM | 2024-07-21 16:50 | 4:50 PM | 2024-07-15 13:11 | G E NO.8534 DT.21.07.2024 | Approved |  | 69259 | ANIL BHOSALE | 2024-07-21 17:11 |  |  | 3
GANGA ALTUS | RMC | Ready Mix Concrete M25 Regular Downpour |  | 239384 | 2024-07-21 17:09 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 3 | Cu.Mtrs | ALTUS CENTRAL STORE | 12945.762 | 2330.24 | 69259 | 25 | 4315.254 | 0 | 0 | S/2077 | 2024-07-20 | 3 | 0 | 12945.762 | 0 |  | Unbilled | MH12KP9216 | 8531 | 2024-07-20 16:50 | 4:50 PM | 2024-07-20 16:50 | 4:50 PM | 2024-07-15 13:11 | G E NO.8531 DT.20.07.2024 | Approved |  | 69259 | ANIL BHOSALE | 2024-07-21 17:09 |  |  | 3
GANGA ALTUS | RMC | Sand-Metal Mix M25 (Pumpable) |  | 239383 | 2024-07-21 17:04 | Purchase | SUPERMIX RMC INDIA | 7 | Cu.Mtrs | ALTUS CENTRAL STORE | 20169.492 | 3630.5 | 69217 | 35.735 | 2881.356 | 0 | 0 | 2122 | 2024-07-20 | 7 | 0 | 20169.492 | 0 |  | Unbilled | MH12SF4609 | 8528 | 2024-07-20 16:50 | 4:50 PM | 2024-07-20 16:50 | 4:50 PM | 2024-07-11 15:32 | G E NO.8528 DT.20.07.2024 | Approved |  | 69217 | ANIL BHOSALE | 2024-07-21 17:04 |  |  | 7
GANGA ALTUS | RMC | Sand-Metal Mix M25 (Pumpable) |  | 239382 | 2024-07-21 17:03 | Purchase | SUPERMIX RMC INDIA | 7 | Cu.Mtrs | ALTUS CENTRAL STORE | 20169.492 | 3630.5 | 69217 | 35.735 | 2881.356 | 0 | 0 | 2121 | 2024-07-20 | 7 | 0 | 20169.492 | 0 |  | Unbilled | MH12UM8788 | 8525 | 2024-07-20 16:50 | 4:50 PM | 2024-07-20 16:50 | 4:50 PM | 2024-07-11 15:32 | G E NO.8525 DT.20.07.2024 | Approved |  | 69217 | ANIL BHOSALE | 2024-07-21 17:03 |  |  | 7
GANGA ALTUS | RMC | Ready Mix Concrete M25 Regular Downpour |  | 239132 | 2024-07-15 18:51 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 5 | Cu.Mtrs | ALTUS CENTRAL STORE | 21576.27 | 3883.72 | 69259 | 25 | 4315.254 | 0 | 0 | S/1951 | 2024-07-12 | 5 | 0 | 21576.27 | INV/24-25/00165 | 2024-07-17 | Billed | MH12NX5548 | 8493 | 2024-07-12 18:31 | 6:31 PM | 2024-07-12 18:31 | 6:31 PM | 2024-07-15 13:11 | G E NO.8493 DT.12.07.2024 | Approved |  | 69259 | ANIL BHOSALE | 2024-07-15 18:51 |  |  | 5
GANGA ALTUS | RMC | Ready Mix Concrete M25 Regular Downpour |  | 239131 | 2024-07-15 18:48 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 3 | Cu.Mtrs | ALTUS CENTRAL STORE | 12945.762 | 2330.24 | 69259 | 25 | 4315.254 | 0 | 0 | S/1890 | 2024-07-09 | 3 | 0 | 12945.762 | INV/24-25/00165 | 2024-07-17 | Billed | MH12KP9216 | 8470 | 2024-07-09 18:31 | 6:31 PM | 2024-07-09 18:31 | 6:31 PM | 2024-07-15 13:11 | G E NO.8470 DT.09.07.2024 | Approved |  | 69259 | ANIL BHOSALE | 2024-07-15 18:48 |  |  | 3
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 239020 | 2024-07-12 17:23 | Purchase | SUPERMIX RMC INDIA | 6.5 | Cu.Mtrs | ALTUS CENTRAL STORE | 15947.75 | 2870.6 | 69202 | 148 | 2453.5 | 0 | 0 | 2045 | 2024-07-10 | 6.5 | 0 | 15947.75 | SRI/TI/091 | 2024-07-17 | Billed | MH12UM8788 | 8479 | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 18:09 | G E NO.8479 DT.10.07.2024 | Approved |  | 69202 | ANIL BHOSALE | 2024-07-12 17:23 |  |  | 6.5
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 239019 | 2024-07-12 17:20 | Purchase | SUPERMIX RMC INDIA | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 14721 | 2649.78 | 69202 | 148 | 2453.5 | 0 | 0 | 2046 | 2024-07-10 | 6 | 0 | 14721 | SRI/TI/091 | 2024-07-17 | Billed | MH12SF4609 | 8480 | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 18:09 | G E NO.8480 DT.10.07.2024 | Approved |  | 69202 | ANIL BHOSALE | 2024-07-12 17:20 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 239018 | 2024-07-12 17:18 | Purchase | SUPERMIX RMC INDIA | 4 | Cu.Mtrs | ALTUS CENTRAL STORE | 9814 | 1766.52 | 69202 | 148 | 2453.5 | 0 | 0 | 2047 | 2024-07-10 | 4 | 0 | 9814 | SRI/TI/091 | 2024-07-17 | Billed | MH12SX6159 | 8482 | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 18:09 | G E NO.8482 DT.10.07.2024 | Approved |  | 69202 | ANIL BHOSALE | 2024-07-12 17:18 |  |  | 4
GANGA ALTUS | RMC | Ready Mix Concrete M-30 Grade FF (Pumpable) |  | 239016 | 2024-07-12 16:44 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 8 | Cu.Mtrs | ALTUS CENTRAL STORE | 37776.264 | 6799.72 | 69227 | 77 | 4722.033 | 0 | 0 | S/1946 | 2024-07-11 | 8 | 0 | 37776.264 | INV/24-25/00165 | 2024-07-17 | Billed | MH12WJ6713 | 8490 | 2024-07-11 16:23 | 4:23 PM | 2024-07-11 16:23 | 4:23 PM | 2024-07-12 10:36 | G E NO.8490 DT.11.07.2024 | Approved |  | 69227 | ANIL BHOSALE | 2024-07-12 16:44 |  |  | 8
GANGA ALTUS | RMC | Ready Mix Concrete M-30 Grade FF (Pumpable) |  | 239015 | 2024-07-12 16:41 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 8 | Cu.Mtrs | ALTUS CENTRAL STORE | 37776.264 | 6799.72 | 69227 | 77 | 4722.033 | 0 | 0 | S/1945 | 2024-07-11 | 8 | 0 | 37776.264 | INV/24-25/00165 | 2024-07-17 | Billed | MH12WJ6712 | 8489 | 2024-07-11 16:23 | 4:23 PM | 2024-07-11 16:23 | 4:23 PM | 2024-07-12 10:36 | G E NO.8489 DT.11.07.2024 | Approved |  | 69227 | ANIL BHOSALE | 2024-07-12 16:41 |  |  | 8
GANGA ALTUS | RMC | Ready Mix Concrete M-30 Grade FF (Pumpable) |  | 239014 | 2024-07-12 16:40 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 8 | Cu.Mtrs | ALTUS CENTRAL STORE | 37776.264 | 6799.72 | 69227 | 77 | 4722.033 | 0 | 0 | S/1940 | 2024-07-11 | 8 | 0 | 37776.264 | INV/24-25/00165 | 2024-07-17 | Billed | MH12WJ6715 | 8486 | 2024-07-11 16:23 | 4:23 PM | 2024-07-11 16:23 | 4:23 PM | 2024-07-12 10:36 | G E NO.8486 DT.11.07.2024 | Approved |  | 69227 | ANIL BHOSALE | 2024-07-12 16:40 |  |  | 8
GANGA ALTUS | RMC | Ready Mix Concrete M-30 Grade FF (Pumpable) |  | 238998 | 2024-07-12 16:38 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 28332.198 | 5099.8 | 69196 | 40.44 | 4722.033 | 0 | 0 | S/1937 | 2024-07-11 | 6 | 0 | 28332.198 | INV/24-25/00165 | 2024-07-17 | Billed | MH12QW4549 | 8485 | 2024-07-11 16:23 | 4:23 PM | 2024-07-11 16:23 | 4:23 PM | 2024-07-10 15:26 | G E NO.8485 DT.11.07.2024 | Approved |  | 69196 | ANIL BHOSALE | 2024-07-12 16:38 |  |  | 6
GANGA ALTUS | RMC | Ready Mix Concrete M-30 Grade FF (Pumpable) |  | 238997 | 2024-07-12 16:35 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 28332.198 | 5099.8 | 69196 | 40.44 | 4722.033 | 0 | 0 | S/1935 | 2024-07-11 | 6 | 0 | 28332.198 | INV/24-25/00165 | 2024-07-17 | Billed | MH12KP9215 | 8483 | 2024-07-11 16:23 | 4:23 PM | 2024-07-11 16:23 | 4:23 PM | 2024-07-10 15:26 | G E NO.8483 DT.11.07.2024 | Approved |  | 69196 | ANIL BHOSALE | 2024-07-12 16:35 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 238992 | 2024-07-11 19:37 | Purchase | SUPERMIX RMC INDIA | 7.5 | Cu.Mtrs | ALTUS CENTRAL STORE | 18401.25 | 3312.22 | 69202 | 148 | 2453.5 | 0 | 0 | 2039 | 2024-07-10 | 7.5 | 0 | 18401.25 | SRI/TI/091 | 2024-07-17 | Billed | MH12SF4609 | 8474 | 2024-07-10 19:12 | 7:12 PM | 2024-07-10 19:12 | 7:12 PM | 2024-07-10 18:09 | G E NO.8474 DT.10.07.2024 | Approved |  | 69202 | ANIL BHOSALE | 2024-07-11 19:37 |  |  | 7.5
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 238991 | 2024-07-11 19:35 | Purchase | SUPERMIX RMC INDIA | 7.5 | Cu.Mtrs | ALTUS CENTRAL STORE | 18401.25 | 3312.22 | 69202 | 148 | 2453.5 | 0 | 0 | 2041 | 2024-07-10 | 7.5 | 0 | 18401.25 | SRI/TI/091 | 2024-07-17 | Billed | MH12SF4609 | 8475 | 2024-07-10 19:12 | 7:12 PM | 2024-07-10 19:12 | 7:12 PM | 2024-07-10 18:09 | G E NO.8475 DT.10.07.2024 | Approved |  | 69202 | ANIL BHOSALE | 2024-07-11 19:35 |  |  | 7.5
GANGA ALTUS | RMC | Ready Mix Concrete M-30 Grade FF (Pumpable) |  | 238966 | 2024-07-11 17:33 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 8 | Cu.Mtrs | ALTUS CENTRAL STORE | 37776.264 | 6799.72 | 69196 | 40.44 | 4722.033 | 0 | 0 | S/1925 | 2024-07-10 | 8 | 0 | 37776.264 | INV/24-25/00165 | 2024-07-17 | Billed | MH12WJ6715 | 8481 | 2024-07-10 16:57 | 4:57 PM | 2024-07-10 16:57 | 4:57 PM | 2024-07-10 15:26 | G E NO.8481 DT.10.07.2024 | Approved |  | 69196 | ANIL BHOSALE | 2024-07-11 17:33 |  |  | 8
GANGA ALTUS | RMC | Ready Mix Concrete M-30 Grade FF (Pumpable) |  | 238965 | 2024-07-11 17:31 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 8 | Cu.Mtrs | ALTUS CENTRAL STORE | 37776.264 | 6799.72 | 69196 | 40.44 | 4722.033 | 0 | 0 | S/1921 | 2024-07-10 | 8 | 0 | 37776.264 | INV/24-25/00165 | 2024-07-17 | Billed | MH12WJ6712 | 8478 | 2024-07-10 16:57 | 4:57 PM | 2024-07-10 16:57 | 4:57 PM | 2024-07-10 15:26 | G E NO.8478 DT.10.07.2024 | Approved |  | 69196 | ANIL BHOSALE | 2024-07-11 17:31 |  |  | 8
GANGA ALTUS | RMC | Ready Mix Concrete M-30 Grade FF (Pumpable) |  | 238964 | 2024-07-11 17:29 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 8 | Cu.Mtrs | ALTUS CENTRAL STORE | 37776.264 | 6799.72 | 69196 | 40.44 | 4722.033 | 0 | 0 | S/1916 | 2024-07-10 | 8 | 0 | 37776.264 | INV/24-25/00165 | 2024-07-17 | Billed | MH12WJ6715 | 8477 | 2024-07-10 16:57 | 4:57 PM | 2024-07-10 16:57 | 4:57 PM | 2024-07-10 15:26 | G E NO.8477 DT.10.07.2024 | Approved |  | 69196 | ANIL BHOSALE | 2024-07-11 17:29 |  |  | 8
GANGA ALTUS | RMC | Sand-Metal Mix M25 (Pumpable) |  | 238963 | 2024-07-11 17:19 | Purchase | SUPERMIX RMC INDIA | 7 | Cu.Mtrs | ALTUS CENTRAL STORE | 20169.492 | 3630.5 | 69217 | 35.735 | 2881.356 | 0 | 0 | 2029 | 2024-07-08 | 7 | 0 | 20169.492 | SRI/TI/089 | 2024-07-11 | Billed | MH12SX6159 | 8463 | 2024-07-08 16:57 | 4:57 PM | 2024-07-08 16:57 | 4:57 PM | 2024-07-11 15:32 | G E NO.8463 DT.08.07.2024 CEMENT CONTENT CHANGE SO GRN LATE | Approved |  | 69217 | ANIL BHOSALE | 2024-07-11 17:19 |  |  | 7
GANGA ALTUS | RMC | Sand-Metal Mix M25 (Pumpable) |  | 238962 | 2024-07-11 17:16 | Purchase | SUPERMIX RMC INDIA | 5 | Cu.Mtrs | ALTUS CENTRAL STORE | 14406.78 | 2593.22 | 69217 | 35.735 | 2881.356 | 0 | 0 | 2031 | 2024-07-08 | 5 | 0 | 14406.78 | SRI/TI/089 | 2024-07-11 | Billed | MH12SF4609 | 8466 | 2024-07-08 16:57 | 4:57 PM | 2024-07-08 16:57 | 4:57 PM | 2024-07-11 15:32 | G E NO.8466 DT.08.07.2024 CEMENT CONTENT CHANGE SO GRN LATE | Approved |  | 69217 | ANIL BHOSALE | 2024-07-11 17:16 |  |  | 5
GANGA ALTUS | RMC | Sand-Metal Mix M25 (Pumpable) |  | 238961 | 2024-07-11 17:12 | Purchase | SUPERMIX RMC INDIA | 7 | Cu.Mtrs | ALTUS CENTRAL STORE | 20169.492 | 3630.5 | 69217 | 35.735 | 2881.356 | 0 | 0 | 2030 | 2024-07-08 | 7 | 0 | 20169.492 | SRI/TI/089 | 2024-07-11 | Billed | MH12UM8788 | 8465 | 2024-07-08 16:57 | 4:57 PM | 2024-07-08 16:57 | 4:57 PM | 2024-07-11 15:32 | G E NO.8465 DT.08.07.2024 CEMENT CONTENT CHANGE SO GRN LATE | Approved |  | 69217 | ANIL BHOSALE | 2024-07-11 17:12 |  |  | 7
GANGA ALTUS | RMC | Ready Mix Concrete M-40 Grade (Pumpable) |  | 238860 | 2024-07-09 19:02 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 4.5 | Cu.Mtrs | ALTUS CENTRAL STORE | 22204.44 | 3996.8 | 69180 | 53.58 | 4934.32 | 0 | 0 | S/1861 | 2024-07-07 | 4.5 | 0 | 22204.44 | INV/24-25/00165 | 2024-07-17 | Billed | MH12NX5548 | 8462 | 2024-07-07 18:47 | 6:47 PM | 2024-07-07 18:47 | 6:47 PM | 2024-07-09 11:32 | G E NO.8462 DT.07.07.2024 | Approved |  | 69180 | ANIL BHOSALE | 2024-07-09 19:02 |  |  | 4.5
GANGA ALTUS | RMC | Ready Mix Concrete M-40 Grade (Pumpable) |  | 238859 | 2024-07-09 19:00 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 29605.92 | 5329.06 | 69180 | 53.58 | 4934.32 | 0 | 0 | S/1859 | 2024-07-07 | 6 | 0 | 29605.92 | INV/24-25/00165 | 2024-07-17 | Billed | MH12KP9215 | 8460 | 2024-07-07 18:47 | 6:47 PM | 2024-07-07 18:47 | 6:47 PM | 2024-07-09 11:32 | G E NO.8460 DT.07.07.2024 | Approved |  | 69180 | ANIL BHOSALE | 2024-07-09 19:00 |  |  | 6
GANGA ALTUS | RMC | Ready Mix Concrete M-40 Grade (Pumpable) |  | 238858 | 2024-07-09 18:59 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 29605.92 | 5329.06 | 69180 | 53.58 | 4934.32 | 0 | 0 | S/1855 | 2024-07-07 | 6 | 0 | 29605.92 | INV/24-25/00165 | 2024-07-17 | Billed | MH12KP9218 | 8459 | 2024-07-07 18:47 | 6:47 PM | 2024-07-07 18:47 | 6:47 PM | 2024-07-09 11:32 | G E NO.8459 DT.07.07.2024 | Approved |  | 69180 | ANIL BHOSALE | 2024-07-09 18:59 |  |  | 6
GANGA ALTUS | RMC | Ready Mix Concrete M-40 Grade (Pumpable) |  | 238857 | 2024-07-09 18:56 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 29605.92 | 5329.06 | 69180 | 53.58 | 4934.32 | 0 | 0 | S/1852 | 2024-07-07 | 6 | 0 | 29605.92 | INV/24-25/00165 | 2024-07-17 | Billed | MH12QG6780 | 8457 | 2024-07-07 18:47 | 6:47 PM | 2024-07-07 18:47 | 6:47 PM | 2024-07-09 11:32 | G E NO.8457 DT.07.07.2024 | Approved |  | 69180 | ANIL BHOSALE | 2024-07-09 18:56 |  |  | 6
GANGA ALTUS | RMC | Ready Mix Concrete M-40 Grade (Pumpable) |  | 238856 | 2024-07-09 18:54 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 29605.92 | 5329.06 | 69180 | 53.58 | 4934.32 | 0 | 0 | S/1851 | 2024-07-07 | 6 | 0 | 29605.92 | INV/24-25/00165 | 2024-07-17 | Billed | MH12KP9215 | 8456 | 2024-07-07 18:47 | 6:47 PM | 2024-07-07 18:47 | 6:47 PM | 2024-07-09 11:32 | G E NO.8456 DT.07.07.2024 | Approved |  | 69180 | ANIL BHOSALE | 2024-07-09 18:54 |  |  | 6
GANGA ALTUS | RMC | Ready Mix Concrete M-40 Grade (Pumpable) |  | 238855 | 2024-07-09 18:52 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 29605.92 | 5329.06 | 69180 | 53.58 | 4934.32 | 0 | 0 | S/1849 | 2024-07-07 | 6 | 0 | 29605.92 | INV/24-25/00165 | 2024-07-17 | Billed | MH12KP9216 | 8455 | 2024-07-07 18:47 | 6:47 PM | 2024-07-07 18:47 | 6:47 PM | 2024-07-09 11:32 | G E NO.8455 DT.07.07.2024 | Approved |  | 69180 | ANIL BHOSALE | 2024-07-09 18:52 |  |  | 6