## GRNRegisteritemwise638585641142
Material Wise GRN Report
From 01-04-2024 To 30-04-2024
Page 1 of 1
Total Records: 50 Records 1 to 50
Project_Name | Material_Category1 | Material_Name | Brand | GRN_No | GRN_Date | GRNType | Supplier_Issue_Store | Good_Qty | Unit_Name | Received_Store | Amount | Tax_Amount | PO_SrNo | PO_Qty | Rate | Others_Amount | Others_Tax | Challan_No | Challan_Date | Challan_Qty | Use_Challan_Qty | ChallanAmount | Bill_No | Bill_date | Billing_Status | VehicleNo | GateReg_No | GateReg date | GateReg Time | GateReg Out Date | GateReg Out Time | Po_Date | GRN_Remark | GRN_Status | Material_Category2 | GTN_SrNo | Created_By | Created_Date | Approved_By | Approved_Date | Accepted_Qty
SRA MORWADI | RMC | Sand-Metal Mix M20 (Pumpable) |  | 236912 | 2024-04-30 20:37 | Purchase | MANJULAI CONSTRUCTION COMPANY | 7 | Cu.Mtrs | MORWADI COMMON | 23491.51 | 4228.48 | 68558 | 42 | 3355.93 | 0 | 0 | MCC/24-25/0513 | 2024-04-30 | 7 | 0 | 23491.51 | MCC/24-25/0513 | 2024-04-30 | Billed | MH14LB0086 | 359 | 2024-04-30 19:00 | 7:00 PM | 2024-04-30 20:10 | 8:10 PM | 2024-04-27 19:10 | GE No.359 Date:-30.04.2024 | Approved |  | 68558 | yogesh-agarwal | 2024-04-30 20:37 |  |  | 7
SRA MORWADI | RMC | Sand-Metal Mix M20 (Pumpable) |  | 236911 | 2024-04-30 19:03 | Purchase | MANJULAI CONSTRUCTION COMPANY | 10 | Cu.Mtrs | MORWADI COMMON | 33559.3 | 6040.68 | 68558 | 42 | 3355.93 | 0 | 0 | MCC/24-25/0512 | 2024-04-30 | 10 | 0 | 33559.3 | MCC/24-25/0512 | 2024-04-30 | Billed | MH14FT1086 | 358 | 2024-04-30 17:15 | 5:15 PM | 2024-04-30 17:48 | 5:48 PM | 2024-04-27 19:10 | GE No.358 Date:-30.04.2024 | Approved |  | 68558 | yogesh-agarwal | 2024-04-30 19:03 |  |  | 10
SRA MORWADI | RMC | Sand-Metal Mix M20 (Pumpable) |  | 236910 | 2024-04-30 19:01 | Purchase | MANJULAI CONSTRUCTION COMPANY | 10 | Cu.Mtrs | MORWADI COMMON | 33559.3 | 6040.68 | 68558 | 42 | 3355.93 | 0 | 0 | MCC/24-25/0503 | 2024-04-30 | 10 | 0 | 33559.3 | MCC/24-25/0503 | 2024-04-30 | Billed | MH14FT3086 | 357 | 2024-04-30 14:40 | 2:40 PM | 2024-04-30 16:23 | 4:23 PM | 2024-04-27 19:10 | GE No.357 Date:-30.04.2024 | Approved |  | 68558 | yogesh-agarwal | 2024-04-30 19:01 |  |  | 10
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236909 | 2024-04-30 18:25 | Purchase | MANJULAI CONSTRUCTION COMPANY | 3 | Cu.Mtrs | MORWADI COMMON | 10067.79 | 1812.2 | 68469 | 3 | 3355.93 | 0 | 0 | MCC/24-25/0501 | 2024-04-30 | 3 | 0 | 10067.79 | MCC/24-25/0501 | 2024-04-30 | Billed | MH14EM9586 | 356 | 2024-04-30 12:30 | 12:30 PM | 2024-04-30 14:05 | 2:05 PM | 2024-04-17 14:50 | GE No.356 Date:-30.04.2024 | Approved |  | 68469 | yogesh-agarwal | 2024-04-30 18:25 |  |  | 3
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236833 | 2024-04-25 18:46 | Purchase | MANJULAI CONSTRUCTION COMPANY | 0.331 | Cu.Mtrs | MORWADI COMMON | 1047.6978 | 188.6 | 68544 | 0.331 | 3165.25 | 0 | 0 | MCC /24-25/ 0231 | 2024-04-15 | 0 | 0 | 1047.6978 | MCC/24-25/0231 | 2024-04-15 | Billed | MH14CP3586 |  | 2024-04-15 10:55 | 10:55 AM | 2024-04-15 15:19 | 3:19 PM | 2024-04-25 18:29 | GE No.306 Date:-15.04.2024 Balance GRN (As per Ch,No.0231) Dealy Due to Estimate/requisition and PO done Today | Approved |  | 68544 | yogesh-agarwal | 2024-04-25 18:46 |  |  | 0.331
SRA MORWADI | RMC | Sand-Metal Mix M25 (Pumpable) |  | 236561 | 2024-04-18 18:47 | Purchase | MANJULAI CONSTRUCTION COMPANY | 7.5 | Cu.Mtrs | MORWADI COMMON | 25169.475 | 4530.5 | 68470 | 39.24 | 3355.93 | 0 | 0 | MCC/24-25/0322 | 2024-04-17 | 7.5 | 0 | 25169.475 | MCC/24-25/0322 | 2024-04-17 | Billed | MH14FT2086 | 326 | 2024-04-17 23:59 | 11:59 PM | 2024-04-18 01:15 | 1:15 AM | 2024-04-17 15:53 | GE No.326 Date:-17.04.2024 | Approved |  | 68470 | yogesh-agarwal | 2024-04-18 18:47 |  |  | 7.5
SRA MORWADI | RMC | Sand-Metal Mix M25 (Pumpable) |  | 236560 | 2024-04-18 18:44 | Purchase | MANJULAI CONSTRUCTION COMPANY | 6 | Cu.Mtrs | MORWADI COMMON | 20135.58 | 3624.4 | 68470 | 39.24 | 3355.93 | 0 | 0 | MCC/24-25/0321 | 2024-04-17 | 6 | 0 | 20135.58 | MCC/24-25/0321 | 2024-04-17 | Billed | MH14EM9586 | 325 | 2024-04-17 21:49 | 9:49 PM | 2024-04-17 22:41 | 10:41 PM | 2024-04-17 15:53 | GE No.325 Date:-17.04.2024 | Approved |  | 68470 | yogesh-agarwal | 2024-04-18 18:44 |  |  | 6
SRA MORWADI | RMC | Sand-Metal Mix M25 (Pumpable) |  | 236559 | 2024-04-18 18:42 | Purchase | MANJULAI CONSTRUCTION COMPANY | 6 | Cu.Mtrs | MORWADI COMMON | 20135.58 | 3624.4 | 68470 | 39.24 | 3355.93 | 0 | 0 | MCC/24-25/0320 | 2024-04-17 | 6 | 0 | 20135.58 | MCC/24-25/0320 | 2024-04-17 | Billed | MH14EM9086 | 324 | 2024-04-17 19:47 | 7:47 PM | 2024-04-17 21:11 | 9:11 PM | 2024-04-17 15:53 | GE No.324 Date:-17.04.2024 | Approved |  | 68470 | yogesh-agarwal | 2024-04-18 18:42 |  |  | 6
SRA MORWADI | RMC | Sand-Metal Mix M25 (Pumpable) |  | 236558 | 2024-04-18 18:39 | Purchase | MANJULAI CONSTRUCTION COMPANY | 10 | Cu.Mtrs | MORWADI COMMON | 33559.3 | 6040.68 | 68470 | 39.24 | 3355.93 | 0 | 0 | MCC/24-25/0319 | 2024-04-17 | 10 | 0 | 33559.3 | MCC/24-25/0319 | 2024-04-17 | Billed | MH14FT2086 | 323 | 2024-04-17 19:35 | 7:35 PM | 2024-04-17 20:33 | 8:33 PM | 2024-04-17 15:53 | GE No.323 Date:-17.04.2024 | Approved |  | 68470 | yogesh-agarwal | 2024-04-18 18:39 |  |  | 10
SRA MORWADI | RMC | Sand-Metal Mix M25 (Pumpable) |  | 236557 | 2024-04-18 18:36 | Purchase | MANJULAI CONSTRUCTION COMPANY | 9.74 | Cu.Mtrs | MORWADI COMMON | 32686.7582 | 5883.62 | 68470 | 39.24 | 3355.93 | 0 | 0 | MCC/24-25/0318 | 2024-04-17 | 10 | 0 | 32686.7582 | MCC/24-25/0318 | 2024-04-17 | Billed | MH14FT3086 | 322 | 2024-04-17 18:40 | 6:40 PM | 2024-04-17 19:38 | 7:38 PM | 2024-04-17 15:53 | GE No.322 Date:-17.04.2024 | Approved |  | 68470 | yogesh-agarwal | 2024-04-18 18:36 |  |  | 9.74
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236513 | 2024-04-17 12:22 | Purchase | MANJULAI CONSTRUCTION COMPANY | 1.5 | Cu.Mtrs | MORWADI COMMON | 4747.881 | 854.62 | 68437 | 8.5 | 3165.254 | 0 | 0 | MCC/24-25/0285 | 2024-04-16 | 1.5 | 0 | 4747.881 | MCC/24-25/0285 | 2024-04-16 | Billed | MH14EM9286 | 317 | 2024-04-16 17:38 | 5:38 PM | 2024-04-16 19:40 | 7:40 PM | 2024-04-13 18:18 | GE No.317 Date:-16.04.2024 | Approved |  | 68437 | yogesh-agarwal | 2024-04-17 12:22 |  |  | 1.5
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236512 | 2024-04-17 12:20 | Purchase | MANJULAI CONSTRUCTION COMPANY | 3 | Cu.Mtrs | MORWADI COMMON | 9495.762 | 1709.24 | 68437 | 8.5 | 3165.254 | 0 | 0 | MCC/24-25/0286 | 2024-04-16 | 3 | 0 | 9495.762 | MCC/24-25/0286 | 2024-04-16 | Billed | MH14EM9286 | 316 | 2024-04-16 17:38 | 5:38 PM | 2024-04-16 19:40 | 7:40 PM | 2024-04-13 18:18 | GE No.316 Date:-16.04.2024 | Approved |  | 68437 | yogesh-agarwal | 2024-04-17 12:20 |  |  | 3
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236463 | 2024-04-15 21:28 | Purchase | MANJULAI CONSTRUCTION COMPANY | 4 | Cu.Mtrs | MORWADI COMMON | 12661.016 | 2278.98 | 68437 | 8.5 | 3165.254 | 0 | 0 | MCC/24-25/0249 | 2024-04-15 | 4 | 0 | 12661.016 | MCC/24-25/0249 | 2024-04-15 | Billed | MH14CP6586 | 311 | 2024-04-15 18:07 | 6:07 PM | 2024-04-15 20:37 | 8:37 PM | 2024-04-13 18:18 | GE No.311 Date:-15.04.2024 | Approved |  | 68437 | yogesh-agarwal | 2024-04-15 21:28 |  |  | 4
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236462 | 2024-04-15 18:54 | Purchase | MANJULAI CONSTRUCTION COMPANY | 1.54 | Cu.Mtrs | MORWADI COMMON | 4874.485 | 877.4 | 68398 | 4.54 | 3165.25 | 0 | 0 | MCC /24-25/0231 | 2024-04-15 | 0 | 0 | 4874.485 | MCC/24-25/0231 | 2024-04-15 | Billed | MH14CP3586 | 306 | 2024-04-15 10:55 | 10:55 AM | 2024-04-15 15:19 | 3:19 PM | 2024-04-09 16:26 | Ge No.306 Date:-15.04.2024 | Approved |  | 68398 | yogesh-agarwal | 2024-04-15 18:54 |  |  | 1.54
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236461 | 2024-04-15 18:52 | Purchase | MANJULAI CONSTRUCTION COMPANY | 1.129 | Cu.Mtrs | MORWADI COMMON | 3573.5718 | 643.24 | 68439 | 4.129 | 3165.254 | 0 | 0 | MCC/24-25/0231 | 2024-04-15 | 3 | 0 | 3573.5718 | MCC/24-25/0231 | 2024-04-15 | Billed | MH14CP3586 | 306 | 2024-04-15 10:55 | 10:55 AM | 2024-04-15 15:19 | 3:19 PM | 2024-04-13 18:46 | Ge No.306 Date:-15.04.2024 | Approved |  | 68439 | yogesh-agarwal | 2024-04-15 18:52 |  |  | 1.129
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236460 | 2024-04-15 18:45 | Purchase | MANJULAI CONSTRUCTION COMPANY | 3 | Cu.Mtrs | MORWADI COMMON | 9495.762 | 1709.24 | 68439 | 4.129 | 3165.254 | 0 | 0 | MCC/24-25/0230 | 2024-04-15 | 3 | 0 | 9495.762 | MCC/24-25/0230 | 2024-04-15 | Billed | MH14CP6586 | 305 | 2024-04-14 10:25 | 10:25 AM | 2024-04-14 12:58 | 12:58 PM | 2024-04-13 18:46 | Ge No.305 Date:-14.04.2024 | Approved |  | 68439 | yogesh-agarwal | 2024-04-15 18:45 |  |  | 3
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236450 | 2024-04-14 11:29 | Purchase | MANJULAI CONSTRUCTION COMPANY | 3 | Cu.Mtrs | MORWADI COMMON | 9495.75 | 1709.24 | 68398 | 4.54 | 3165.25 | 0 | 0 | MCC/24-25/0214 | 2024-04-13 | 3 | 0 | 9495.75 | MCC/24-25/0214 | 2024-04-13 | Billed | MH14EM9286 | 304 | 2024-04-13 17:42 | 5:42 PM | 2024-04-13 20:15 | 8:15 PM | 2024-04-09 16:26 | GE No.304 Date:-13.04.2024 | Approved |  | 68398 | yogesh-agarwal | 2024-04-14 11:29 |  |  | 3
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236449 | 2024-04-13 19:19 | Purchase | MANJULAI CONSTRUCTION COMPANY | 3 | Cu.Mtrs | MORWADI COMMON | 10067.79 | 1812.2 | 68438 | 4.93 | 3355.93 | 0 | 0 | MCC/24-25/0201 | 2024-04-13 | 3 | 0 | 10067.79 | MCC/24-25/0201 | 2024-04-13 | Billed | MH14EM9186 | 303 | 2024-04-13 03:35 | 3:35 AM | 2024-04-13 04:14 | 4:14 AM | 2024-04-13 18:31 | GE NO.303 DATE:-13.04.2024 | Approved |  | 68438 | yogesh-agarwal | 2024-04-13 19:19 |  |  | 3
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236448 | 2024-04-13 18:50 | Purchase | MANJULAI CONSTRUCTION COMPANY | 1.93 | Cu.Mtrs | MORWADI COMMON | 6476.9449 | 1165.86 | 68438 | 4.93 | 3355.93 | 0 | 0 | MCC/24-25 /0198 | 2024-04-12 | 9 | 0 | 6476.9449 | MCC/24-25/0198 | 2024-04-12 | Billed | MH14FT2086 |  | 2024-04-13 00:30 | 12:30 AM | 2024-04-13 01:37 | 1:37 AM | 2024-04-13 18:31 | GE NO.302 DATE:-13.04.2024 | Approved |  | 68438 | yogesh-agarwal | 2024-04-13 18:50 |  |  | 1.93
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236447 | 2024-04-13 18:47 | Purchase | MANJULAI CONSTRUCTION COMPANY | 6.81 | Cu.Mtrs | MORWADI COMMON | 22853.8833 | 4113.7 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0198 | 2024-04-12 | 9 | 0 | 22853.8833 | MCC/24-25/0198 | 2024-04-12 | Billed | MH14FT2086 | 302 | 2024-04-13 00:30 | 12:30 AM | 2024-04-13 01:37 | 1:37 AM | 2024-04-11 16:17 | GE NO.302 DATE:-13.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 18:47 |  |  | 6.81
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236446 | 2024-04-13 18:41 | Purchase | MANJULAI CONSTRUCTION COMPANY | 9.82 | Cu.Mtrs | MORWADI COMMON | 32955.2326 | 5931.94 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0194 | 2024-04-12 | 10 | 0 | 32955.2326 | MCC/24-25/0194 | 2024-04-12 | Billed | MH14FT2086 | 298 | 2024-04-12 21:23 | 9:23 PM | 2024-04-12 22:02 | 10:02 PM | 2024-04-11 16:17 | GE NO.298 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 18:41 |  |  | 9.82
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236440 | 2024-04-13 17:37 | Purchase | MANJULAI CONSTRUCTION COMPANY | 9.61 | Cu.Mtrs | MORWADI COMMON | 32250.4873 | 5805.08 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0189 | 2024-04-12 | 10 | 0 | 32250.4873 | MCC/24-25/0189 | 2024-04-12 | Billed | MH14KQ9486 | 295 | 2024-04-12 19:15 | 7:15 PM | 2024-04-12 20:42 | 8:42 PM | 2024-04-11 16:17 | GE NO.295 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:37 |  |  | 9.61
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236439 | 2024-04-13 17:35 | Purchase | MANJULAI CONSTRUCTION COMPANY | 8.19 | Cu.Mtrs | MORWADI COMMON | 27485.0667 | 4947.32 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0188 | 2024-04-12 | 10 | 0 | 27485.0667 | MCC/24-25/0188 | 2024-04-12 | Billed | MH14FT1086 | 294 | 2024-04-12 18:39 | 6:39 PM | 2024-04-12 19:50 | 7:50 PM | 2024-04-11 16:17 | GE NO.294 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:35 |  |  | 8.19
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236438 | 2024-04-13 17:32 | Purchase | MANJULAI CONSTRUCTION COMPANY | 9.9 | Cu.Mtrs | MORWADI COMMON | 33223.707 | 5980.26 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0186 | 2024-04-12 | 10 | 0 | 33223.707 | MCC/24-25/0186 | 2024-04-12 | Billed | MH14FT2086 | 293 | 2024-04-12 18:09 | 6:09 PM | 2024-04-12 18:40 | 6:40 PM | 2024-04-11 16:17 | GE NO.293 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:32 |  |  | 9.9
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236437 | 2024-04-13 17:31 | Purchase | MANJULAI CONSTRUCTION COMPANY | 9.78 | Cu.Mtrs | MORWADI COMMON | 32820.9954 | 5907.78 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0184 | 2024-04-12 | 10 | 0 | 32820.9954 | MCC/24-25/0184 | 2024-04-12 | Billed | MH14FT3086 | 292 | 2024-04-12 17:50 | 5:50 PM | 2024-04-12 18:07 | 6:07 PM | 2024-04-11 16:17 | GE NO.292 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:31 |  |  | 9.78
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236436 | 2024-04-13 17:29 | Purchase | MANJULAI CONSTRUCTION COMPANY | 9.88 | Cu.Mtrs | MORWADI COMMON | 33156.5884 | 5968.18 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0182 | 2024-04-12 | 10 | 0 | 33156.5884 | MCC/24-25/0182 | 2024-04-12 | Billed | MH14LB0086 | 291 | 2024-04-12 16:32 | 4:32 PM | 2024-04-12 17:27 | 5:27 PM | 2024-04-11 16:17 | GE NO.291 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:29 |  |  | 9.88
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236435 | 2024-04-13 17:26 | Purchase | MANJULAI CONSTRUCTION COMPANY | 5.85 | Cu.Mtrs | MORWADI COMMON | 19632.1905 | 3533.8 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0177 | 2024-04-12 | 6 | 0 | 19632.1905 | MCC/24-25/0177 | 2024-04-12 | Billed | MH14CP6586 | 288 | 2024-04-12 15:20 | 3:20 PM | 2024-04-12 16:05 | 4:05 PM | 2024-04-11 16:17 | GE NO.288 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:26 |  |  | 5.85
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236434 | 2024-04-13 17:23 | Purchase | MANJULAI CONSTRUCTION COMPANY | 9.76 | Cu.Mtrs | MORWADI COMMON | 32753.8768 | 5895.7 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0175 | 2024-04-12 | 10 | 0 | 32753.8768 | MCC/24-25/0175 | 2024-04-12 | Billed | MH14FT2086 | 287 | 2024-04-12 14:15 | 2:15 PM | 2024-04-12 15:13 | 3:13 PM | 2024-04-11 16:17 | GE NO.287 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:23 |  |  | 9.76
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236433 | 2024-04-13 17:21 | Purchase | MANJULAI CONSTRUCTION COMPANY | 9.35 | Cu.Mtrs | MORWADI COMMON | 31377.9455 | 5648.04 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/286 | 2024-04-12 | 10 | 0 | 31377.9455 | MCC/24-25/0174 | 2024-04-12 | Billed | MH14FT3086 | 286 | 2024-04-12 13:55 | 1:55 PM | 2024-04-12 14:38 | 2:38 PM | 2024-04-11 16:17 | GE NO.286 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:21 |  |  | 9.35
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236432 | 2024-04-13 17:18 | Purchase | MANJULAI CONSTRUCTION COMPANY | 9.83 | Cu.Mtrs | MORWADI COMMON | 32988.7919 | 5937.98 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0173 | 2024-04-12 | 10 | 0 | 32988.7919 | MCC/24-25/0173 | 2024-04-12 | Billed | MH14LB0086 | 285 | 2024-04-12 13:37 | 1:37 PM | 2024-04-12 14:12 | 2:12 PM | 2024-04-11 16:17 | GE NO.285 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:18 |  |  | 9.83
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236431 | 2024-04-13 17:16 | Purchase | MANJULAI CONSTRUCTION COMPANY | 9.82 | Cu.Mtrs | MORWADI COMMON | 32955.2326 | 5931.94 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0172 | 2024-04-12 | 10 | 0 | 32955.2326 | MCC/24-25/0172 | 2024-04-12 | Billed | MH14KQ9486 | 284 | 2024-04-12 12:50 | 12:50 PM | 2024-04-12 13:26 | 1:26 PM | 2024-04-11 16:17 | GE NO.284 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:16 |  |  | 9.82
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236430 | 2024-04-13 17:13 | Purchase | MANJULAI CONSTRUCTION COMPANY | 9.9 | Cu.Mtrs | MORWADI COMMON | 33223.707 | 5980.26 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0171 | 2024-04-12 | 10 | 0 | 33223.707 | MCC/24-25/0171 | 2024-04-12 | Billed | MH14FT1086 | 283 | 2024-04-12 11:57 | 11:57 AM | 2024-04-12 12:50 | 12:50 PM | 2024-04-11 16:17 | GE NO.283 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:13 |  |  | 9.9
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236429 | 2024-04-13 17:10 | Purchase | MANJULAI CONSTRUCTION COMPANY | 8 | Cu.Mtrs | MORWADI COMMON | 26847.44 | 4832.54 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0197 | 2024-04-12 | 8 | 0 | 26847.44 | MCC/24-25/0197 | 2024-04-12 | Billed | MH14LB0086 | 301 | 2024-04-12 22:54 | 10:54 PM | 2024-04-12 23:14 | 11:14 PM | 2024-04-11 16:17 | GE NO.301 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:10 |  |  | 8
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236428 | 2024-04-13 17:09 | Purchase | MANJULAI CONSTRUCTION COMPANY | 10 | Cu.Mtrs | MORWADI COMMON | 33559.3 | 6040.68 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0196 | 2024-04-12 | 10 | 0 | 33559.3 | MCC/24-25/0196 | 2024-04-12 | Billed | MH14FT1086 | 300 | 2024-04-12 22:26 | 10:26 PM | 2024-04-12 22:52 | 10:52 PM | 2024-04-11 16:17 | GE NO.300 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:09 |  |  | 10
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236427 | 2024-04-13 17:07 | Purchase | MANJULAI CONSTRUCTION COMPANY | 6 | Cu.Mtrs | MORWADI COMMON | 20135.58 | 3624.4 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0195 | 2024-04-12 | 6 | 0 | 20135.58 | MCC/24-25/0195 | 2024-04-12 | Billed | MH14EM9586 | 299 | 2024-04-12 21:57 | 9:57 PM | 2024-04-12 22:24 | 10:24 PM | 2024-04-11 16:17 | GE NO.299 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:07 |  |  | 6
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236426 | 2024-04-13 17:01 | Purchase | MANJULAI CONSTRUCTION COMPANY | 6 | Cu.Mtrs | MORWADI COMMON | 20135.58 | 3624.4 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0192 | 2024-04-12 | 6 | 0 | 20135.58 | MCC/24-25/0192 | 2024-04-12 | Billed | MH14EM9286 | 297 | 2024-04-12 21:05 | 9:05 PM | 2024-04-12 21:31 | 9:31 PM | 2024-04-11 16:17 | GE NO.297 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 17:01 |  |  | 6
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236425 | 2024-04-13 16:59 | Purchase | MANJULAI CONSTRUCTION COMPANY | 6 | Cu.Mtrs | MORWADI COMMON | 20135.58 | 3624.4 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0191 | 2024-04-12 | 6 | 0 | 20135.58 | MCC/24-25/0191 | 2024-04-12 | Billed | MH14EM9086 | 296 | 2024-04-12 19:50 | 7:50 PM | 2024-04-12 21:03 | 9:03 PM | 2024-04-11 16:17 | GE NO.296 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 16:59 |  |  | 6
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236422 | 2024-04-13 16:55 | Purchase | MANJULAI CONSTRUCTION COMPANY | 10 | Cu.Mtrs | MORWADI COMMON | 33559.3 | 6040.68 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24.25/0179 | 2024-04-12 | 10 | 1 | 33559.3 | MCC/24-25/0179 | 2024-04-12 | Billed | MH14FT1086 | 290 | 2024-04-12 16:04 | 4:04 PM | 2024-04-12 16:43 | 4:43 PM | 2024-04-11 16:17 | GE NO.290 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 16:55 |  |  | 10
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236419 | 2024-04-13 16:52 | Purchase | MANJULAI CONSTRUCTION COMPANY | 6 | Cu.Mtrs | MORWADI COMMON | 20135.58 | 3624.4 | 68414 | 170.5 | 3355.93 | 0 | 0 | MCC/24-25/0178 | 2024-04-12 | 6 | 0 | 20135.58 | MCC/24-25/0178 | 2024-04-12 | Billed | MH14EM9586 | 289 | 2024-04-12 15:25 | 3:25 PM | 2024-04-12 16:21 | 4:21 PM | 2024-04-11 16:17 | GE NO.289 DATE:-12.04.2024 | Approved |  | 68414 | yogesh-agarwal | 2024-04-13 16:52 |  |  | 6
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236338 | 2024-04-11 13:35 | Purchase | MANJULAI CONSTRUCTION COMPANY | 6 | Cu.Mtrs | MORWADI COMMON | 20135.58 | 3624.4 | 68400 | 16 | 3355.93 | 0 | 0 | MCC/24-25/0156 | 2024-04-10 | 6 | 0 | 20135.58 | MCC/24-25/0156 | 2024-04-10 | Billed | MH14CP3586 | 279 | 2024-04-10 20:25 | 8:25 PM | 2024-04-10 22:20 | 10:20 PM | 2024-04-09 18:02 | GE No.279 Date:-10.04.2024 | Approved |  | 68400 | yogesh-agarwal | 2024-04-11 13:35 |  |  | 6
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236337 | 2024-04-11 13:32 | Purchase | MANJULAI CONSTRUCTION COMPANY | 10 | Cu.Mtrs | MORWADI COMMON | 33559.3 | 6040.68 | 68400 | 16 | 3355.93 | 0 | 0 | MCC/24-25/0145 | 2024-04-10 | 10 | 0 | 33559.3 | MCC/24-25/0145 | 2024-04-10 | Billed | MH14FT3086 | 278 | 2024-04-10 18:00 | 6:00 PM | 2024-04-10 19:13 | 7:13 PM | 2024-04-09 18:02 | GE No.278 Date:-10.04.2024 | Approved |  | 68400 | yogesh-agarwal | 2024-04-11 13:32 |  |  | 10
SRA MORWADI | RMC | Sand-Metal Mix M20 (Pumpable) |  | 236274 | 2024-04-08 10:09 | Purchase | MANJULAI CONSTRUCTION COMPANY | 3 | Cu.Mtrs | MORWADI COMMON | 10067.79 | 1812.2 | 68386 | 13 | 3355.93 | 0 | 0 | MCC/24-25/0105 | 2024-04-07 | 3 | 0 | 10067.79 | MCC/24-25/0105 | 2024-04-07 | Billed | MH14CP3586 | 275 | 2024-04-07 16:15 | 4:15 PM | 2024-04-07 16:47 | 4:47 PM | 2024-04-06 18:52 | GE No.275 Date:-07.04.2024 | Approved |  | 68386 | yogesh-agarwal | 2024-04-08 10:09 |  |  | 3
SRA MORWADI | RMC | Sand-Metal Mix M20 (Pumpable) |  | 236273 | 2024-04-08 10:05 | Purchase | MANJULAI CONSTRUCTION COMPANY | 10 | Cu.Mtrs | MORWADI COMMON | 33559.3 | 6040.68 | 68386 | 13 | 3355.93 | 0 | 0 | MCC/24-25/0104 | 2024-04-07 | 10 | 0 | 33559.3 | MCC/24-25/0104 | 2024-04-07 | Billed | MH14LB0086 | 274 | 2024-04-07 14:43 | 2:43 PM | 2024-04-07 15:45 | 3:45 PM | 2024-04-06 18:52 | GE No.274 Date:-07.04.2024 | Approved |  | 68386 | yogesh-agarwal | 2024-04-08 10:05 |  |  | 10
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236267 | 2024-04-07 13:14 | Purchase | MANJULAI CONSTRUCTION COMPANY | 5 | Cu.Mtrs | MORWADI COMMON | 16779.65 | 3020.34 | 68380 | 15 | 3355.93 | 0 | 0 | MCC/24-25/0100 | 2024-04-06 | 5 | 0 | 16779.65 | MCC/24-25/0100 | 2024-04-06 | Billed | MH14EM9586 | 269 | 2024-04-06 20:35 | 8:35 PM | 2024-04-06 22:26 | 10:26 PM | 2024-04-06 16:15 | GE No.269 Date:-06.04.2024 | Approved |  | 68380 |  | 2024-04-07 13:14 |  |  | 5
SRA MORWADI | RMC | Sand-Metal Mix M30 (Pumpable) |  | 236266 | 2024-04-07 12:18 | Purchase | MANJULAI CONSTRUCTION COMPANY | 10 | Cu.Mtrs | MORWADI COMMON | 33559.3 | 6040.68 | 68380 | 15 | 3355.93 | 0 | 0 | MCC/24-25/0096 | 2024-04-06 | 10 | 0 | 33559.3 | MCC/24-25/0096 | 2024-04-06 | Billed | MH14LB0086 | 268 | 2024-04-06 18:10 | 6:10 PM | 2024-04-06 20:19 | 8:19 PM | 2024-04-06 16:15 | GE No.268 Date:-06.04.2024 | Approved |  | 68380 | yogesh-agarwal | 2024-04-07 12:18 |  |  | 10
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236220 | 2024-04-06 12:44 | Purchase | MANJULAI CONSTRUCTION COMPANY | 2.5 | Cu.Mtrs | MORWADI COMMON | 7913.125 | 1424.36 | 68347 | 2.5 | 3165.25 | 0 | 0 | MCC/24-25/0043 | 2024-04-04 | 2.5 | 0 | 7913.125 | MCC/24-25/0043 | 2024-04-04 | Billed | MH14EM9286 | 258 | 2024-04-04 09:24 | 9:24 AM | 2024-04-04 11:15 | 11:15 AM | 2024-04-03 15:27 | GE No.258 Date:-4.4.24 | Approved |  | 68347 | yogesh-agarwal | 2024-04-06 12:44 |  |  | 2.5
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236191 | 2024-04-05 15:26 | Purchase | MANJULAI CONSTRUCTION COMPANY | 3 | Cu.Mtrs | MORWADI COMMON | 9495.75 | 1709.24 | 68340 | 9 | 3165.25 | 0 | 0 | MCC/24-25/0064 | 2024-04-05 | 3 | 0 | 9495.75 | MCC/24-25/0064 | 2024-04-05 | Billed | MH14CP3586 | 265 | 2024-04-05 11:20 | 11:20 AM | 2024-04-05 13:35 | 1:35 PM | 2024-04-02 18:02 | GE No.265 Date:-05.04.2024 | Approved |  | 68340 | yogesh-agarwal | 2024-04-05 15:26 |  |  | 3
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236180 | 2024-04-04 16:29 | Purchase | MANJULAI CONSTRUCTION COMPANY | 3 | Cu.Mtrs | MORWADI COMMON | 9495.75 | 1709.24 | 68347 | 2.5 | 3165.25 | 0 | 0 | MCC/24.25/0043 | 2024-04-04 | 3 | 0 | 9495.75 | 0 |  | Unbilled | MH14EM9286 | 258 | 2024-04-04 09:24 | 9:24 AM | 2024-04-04 11:15 | 11:15 AM | 2024-04-03 15:27 | GE No.258 Date:-04.04.2024 | Deleted |  | 68347 | yogesh-agarwal | 2024-04-04 16:29 |  |  | 0
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236179 | 2024-04-04 16:26 | Purchase | MANJULAI CONSTRUCTION COMPANY | 3 | Cu.Mtrs | MORWADI COMMON | 9495.75 | 1709.24 | 68340 | 9 | 3165.25 | 0 | 0 | MCC/24-25/0057 | 2024-04-04 | 3 | 0 | 9495.75 | MCC/24-25/0057 | 2024-04-04 | Billed | MH14CP3586 | 259 | 2024-04-04 13:12 | 1:12 PM | 2024-04-04 15:30 | 3:30 PM | 2024-04-02 18:02 | GE No.259 Date:-04.04.2024 | Approved |  | 68340 | yogesh-agarwal | 2024-04-04 16:26 |  |  | 3
SRA MORWADI | RMC | Sand-Metal Mix M30 (Downpour) |  | 236157 | 2024-04-03 17:19 | Purchase | MANJULAI CONSTRUCTION COMPANY | 3 | Cu.Mtrs | MORWADI COMMON | 9495.75 | 1709.24 | 68340 | 9 | 3165.25 | 0 | 0 | MCC/24-25/0027 | 2024-04-03 | 3 | 0 | 9495.75 | MCC/24-25/0027 | 2024-04-03 | Billed | MH14EM9186 | 256 | 2024-04-03 12:50 | 12:50 PM | 2024-04-03 16:00 | 4:00 PM | 2024-04-02 18:02 | GE No.256 Date:-03.04.2024 | Approved |  | 68340 | yogesh-agarwal | 2024-04-03 17:19 |  |  | 3