## GRNRegisteritemwise638589744190
Material Wise GRN Report
From 01-01-2024 To 11-08-2024
Page 1 of 1
Total Records: 30 Records 1 to 30
Project_Name | Material_Category1 | Material_Name | Brand | GRN_No | GRN_Date | GRNType | Supplier_Issue_Store | Good_Qty | Unit_Name | Received_Store | Amount | Tax_Amount | PO_SrNo | PO_Qty | Rate | Others_Amount | Others_Tax | Challan_No | Challan_Date | Challan_Qty | Use_Challan_Qty | ChallanAmount | Bill_No | Bill_date | Billing_Status | VehicleNo | GateReg_No | GateReg date | GateReg Time | GateReg Out Date | GateReg Out Time | Po_Date | GRN_Remark | GRN_Status | Material_Category2 | GTN_SrNo | Created_By | Created_Date | Approved_By | Approved_Date | Accepted_Qty
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 239020 | 2024-07-12 17:23 | Purchase | SUPERMIX RMC INDIA | 6.5 | Cu.Mtrs | ALTUS CENTRAL STORE | 15947.75 | 2870.6 | 69202 | 148 | 2453.5 | 0 | 0 | 2045 | 2024-07-10 | 6.5 | 0 | 15947.75 | SRI/TI/091 | 2024-07-17 | Billed | MH12UM8788 | 8479 | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 18:09 | G E NO.8479 DT.10.07.2024 | Approved |  | 69202 | ANIL BHOSALE | 2024-07-12 17:23 |  |  | 6.5
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 239019 | 2024-07-12 17:20 | Purchase | SUPERMIX RMC INDIA | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 14721 | 2649.78 | 69202 | 148 | 2453.5 | 0 | 0 | 2046 | 2024-07-10 | 6 | 0 | 14721 | SRI/TI/091 | 2024-07-17 | Billed | MH12SF4609 | 8480 | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 18:09 | G E NO.8480 DT.10.07.2024 | Approved |  | 69202 | ANIL BHOSALE | 2024-07-12 17:20 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 239018 | 2024-07-12 17:18 | Purchase | SUPERMIX RMC INDIA | 4 | Cu.Mtrs | ALTUS CENTRAL STORE | 9814 | 1766.52 | 69202 | 148 | 2453.5 | 0 | 0 | 2047 | 2024-07-10 | 4 | 0 | 9814 | SRI/TI/091 | 2024-07-17 | Billed | MH12SX6159 | 8482 | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 17:14 | 5:14 PM | 2024-07-10 18:09 | G E NO.8482 DT.10.07.2024 | Approved |  | 69202 | ANIL BHOSALE | 2024-07-12 17:18 |  |  | 4
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 238992 | 2024-07-11 19:37 | Purchase | SUPERMIX RMC INDIA | 7.5 | Cu.Mtrs | ALTUS CENTRAL STORE | 18401.25 | 3312.22 | 69202 | 148 | 2453.5 | 0 | 0 | 2039 | 2024-07-10 | 7.5 | 0 | 18401.25 | SRI/TI/091 | 2024-07-17 | Billed | MH12SF4609 | 8474 | 2024-07-10 19:12 | 7:12 PM | 2024-07-10 19:12 | 7:12 PM | 2024-07-10 18:09 | G E NO.8474 DT.10.07.2024 | Approved |  | 69202 | ANIL BHOSALE | 2024-07-11 19:37 |  |  | 7.5
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 238991 | 2024-07-11 19:35 | Purchase | SUPERMIX RMC INDIA | 7.5 | Cu.Mtrs | ALTUS CENTRAL STORE | 18401.25 | 3312.22 | 69202 | 148 | 2453.5 | 0 | 0 | 2041 | 2024-07-10 | 7.5 | 0 | 18401.25 | SRI/TI/091 | 2024-07-17 | Billed | MH12SF4609 | 8475 | 2024-07-10 19:12 | 7:12 PM | 2024-07-10 19:12 | 7:12 PM | 2024-07-10 18:09 | G E NO.8475 DT.10.07.2024 | Approved |  | 69202 | ANIL BHOSALE | 2024-07-11 19:35 |  |  | 7.5
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 237189 | 2024-05-11 19:32 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 4 | Cu.Mtrs | ALTUS CENTRAL STORE | 22920 | 4125.6 | 68366 | 148 | 5730 | 0 | 0 | S/713 | 2024-05-09 | 4 | 0 | 22920 | INV/24-25/00061 | 2024-05-15 | Billed | MH12NX5548 | 8235 | 2024-05-09 19:22 | 7:22 PM | 2024-05-09 19:22 | 7:22 PM | 2024-04-05 18:06 | G E NO.8235 DT.09.05.2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-05-11 19:32 |  |  | 4
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 237188 | 2024-05-11 19:29 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 4 | Cu.Mtrs | ALTUS CENTRAL STORE | 22920 | 4125.6 | 68366 | 148 | 5730 | 0 | 0 | S/710 | 2024-05-09 | 4 | 0 | 22920 | INV/24-25/00061 | 2024-05-15 | Billed | MH12QW4549 | 8234 | 2024-05-09 19:22 | 7:22 PM | 2024-05-09 19:22 | 7:22 PM | 2024-04-05 18:06 | G E NO.8234 DT.09.05.2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-05-11 19:29 |  |  | 4
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 237187 | 2024-05-11 19:26 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 8 | Cu.Mtrs | ALTUS CENTRAL STORE | 45840 | 8251.2 | 68366 | 148 | 5730 | 0 | 0 | S/704 | 2024-05-09 | 8 | 0 | 45840 | INV/24-25/00061 | 2024-05-15 | Billed | MH12WJ6713 | 8233 | 2024-05-09 19:22 | 7:22 PM | 2024-05-09 19:22 | 7:22 PM | 2024-04-05 18:06 | G E NO.8233 DT.09.05.2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-05-11 19:26 |  |  | 8
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 237186 | 2024-05-11 19:21 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/703 | 2024-05-09 | 6 | 0 | 34380 | INV/24-25/00061 | 2024-05-15 | Billed | MH12KP9215 | 8232 | 2024-05-09 19:17 | 7:17 PM | 2024-05-09 19:17 | 7:17 PM | 2024-04-05 18:06 | G E NO.8232 DT.09.05.2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-05-11 19:21 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 237117 | 2024-05-09 17:27 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 8 | Cu.Mtrs | ALTUS CENTRAL STORE | 45840 | 8251.2 | 68366 | 148 | 5730 | 0 | 0 | S/676 | 2024-05-08 | 8 | 0 | 45840 | INV/24-25/00061 | 2024-05-15 | Billed | MH12WJ6712 | 8229 | 2024-05-08 17:11 | 5:11 PM | 2024-05-08 17:11 | 5:11 PM | 2024-04-05 18:06 | G E NO.8229 DT.08/05/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-05-09 17:27 |  |  | 8
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 237116 | 2024-05-09 17:26 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/664 | 2024-05-08 | 6 | 0 | 34380 | INV/24-25/00061 | 2024-05-15 | Billed | MH12KP9218 | 8226 | 2024-05-08 17:11 | 5:11 PM | 2024-05-08 17:11 | 5:11 PM | 2024-04-05 18:06 | G E NO.8226 DT.08/05/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-05-09 17:26 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 237115 | 2024-05-09 17:25 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/662 | 2024-05-08 | 6 | 0 | 34380 | INV/24-25/00061 | 2024-05-15 | Billed | MH12QW4549 | 8225 | 2024-05-08 17:11 | 5:11 PM | 2024-05-08 17:11 | 5:11 PM | 2024-04-05 18:06 | G E NO.8225 DT.09/05/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-05-09 17:25 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 237114 | 2024-05-09 17:22 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 8 | Cu.Mtrs | ALTUS CENTRAL STORE | 45840 | 8251.2 | 68366 | 148 | 5730 | 0 | 0 | S/659 | 2024-05-08 | 8 | 0 | 45840 | INV/24-25/00061 | 2024-05-15 | Billed | MH12WJ6714 | 8224 | 2024-05-08 17:11 | 5:11 PM | 2024-05-08 17:11 | 5:11 PM | 2024-04-05 18:06 | G E NO.8224 DT.08/05/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-05-09 17:22 |  |  | 8
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 237113 | 2024-05-09 17:16 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/684 | 2024-05-08 | 6 | 0 | 34380 | INV/24-25/00061 | 2024-05-15 | Billed | MH12KP9218 | 8230 | 2024-05-08 17:11 | 5:11 PM | 2024-05-08 17:11 | 5:11 PM | 2024-04-05 18:06 | G E NO.8230 DT.08/05/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-05-09 17:16 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236917 | 2024-05-02 16:46 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/464 | 2024-04-30 | 6 | 0 | 34380 | INV/24-25/00032 | 2024-05-01 | Billed | MH12KP9218 | 8190 | 2024-04-30 16:33 | 4:33 PM | 2024-04-30 16:33 | 4:33 PM | 2024-04-05 18:06 | G E NO.8190 DT.30/04/2024 GRN LATE CONCRETE TAKEN BY LATE NIGTH , NEXT DAY HOLIDAY | Approved |  | 68366 | ANIL BHOSALE | 2024-05-02 16:46 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236916 | 2024-05-02 16:45 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/462 | 2024-04-30 | 6 | 0 | 34380 | INV/24-25/00032 | 2024-05-01 | Billed | MH12NX5548 | 8189 | 2024-04-30 16:33 | 4:33 PM | 2024-04-30 16:33 | 4:33 PM | 2024-04-05 18:06 | G E NO.8189 DT.30/04/2024 GRN LATE CONCRETE TAKEN BY LATE NIGTH , NEXT DAY HOLIDAY | Approved |  | 68366 | ANIL BHOSALE | 2024-05-02 16:45 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236915 | 2024-05-02 16:42 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/455 | 2024-04-30 | 6 | 0 | 34380 | INV/24-25/00032 | 2024-05-01 | Billed | MH12FZ3490 | 8188 | 2024-04-30 16:33 | 4:33 PM | 2024-04-30 16:33 | 4:33 PM | 2024-04-05 18:06 | G E NO.8188 DT.30/04/2024 GRN LATE CONCRETE TAKEN BY LATE NIGTH , NEXT DAY HOLIDAY | Approved |  | 68366 | ANIL BHOSALE | 2024-05-02 16:42 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236901 | 2024-04-30 15:03 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/434 | 2024-04-29 | 6 | 0 | 34380 | INV/24-25/00032 | 2024-05-01 | Billed | MH12NX5548 | 8186 | 2024-04-29 15:00 | 3:00 PM | 2024-04-29 15:00 | 3:00 PM | 2024-04-05 18:06 | G E NO.8186 DT,29/04/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-30 15:03 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236866 | 2024-04-27 17:57 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 5 | Cu.Mtrs | ALTUS CENTRAL STORE | 28650 | 5157 | 68366 | 148 | 5730 | 0 | 0 | S/292 | 2024-04-23 | 5 | 0 | 28650 | INV/24-25/00032 | 2024-05-01 | Billed | MH12NX5549 | 8160 | 2024-04-23 17:47 | 5:47 PM | 2024-04-23 17:47 | 5:47 PM | 2024-04-05 18:06 | G E NO.8160 DT.23/04/2024 GRN LATE RATE ISSUE | Approved |  | 68366 | ANIL BHOSALE | 2024-04-27 17:57 |  |  | 5
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236740 | 2024-04-23 11:53 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/274 | 2024-04-22 | 6 | 0 | 34380 | INV/24-25/00032 | 2024-05-01 | Billed | MH12QG6780 | 8156 | 2024-04-22 11:45 | 11:45 AM | 2024-04-22 11:45 | 11:45 AM | 2024-04-05 18:06 | G E NO.8156 DT.22.04.2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-23 11:53 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236739 | 2024-04-23 11:51 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/273 | 2024-04-22 | 6 | 0 | 34380 | INV/24-25/00032 | 2024-05-01 | Billed | MH12KP9217 | 8155 | 2024-04-22 11:45 | 11:45 AM | 2024-04-22 11:45 | 11:45 AM | 2024-04-05 18:06 | G E NO.8155 DT.22.04.2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-23 11:51 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236738 | 2024-04-23 11:48 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/272 | 2024-04-22 | 6 | 0 | 34380 | INV/24-25/00032 | 2024-05-01 | Billed | MH12QW4549 | 8154 | 2024-04-22 11:45 | 11:45 AM | 2024-04-22 11:45 | 11:45 AM | 2024-04-05 18:06 | G E NO.8154 DT.22.04.2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-23 11:48 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236735 | 2024-04-23 11:22 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/271 | 2024-04-22 | 6 | 0 | 34380 | INV/24-25/00032 | 2024-05-01 | Billed | MH12NX5548 | 8152 | 2024-04-22 11:11 | 11:11 AM | 2024-04-22 11:11 | 11:11 AM | 2024-04-05 18:06 | G E NO.8152 DT.22.04.2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-23 11:22 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236734 | 2024-04-23 11:18 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/270 | 2024-04-22 | 6 | 0 | 34380 | INV/24-25/00032 | 2024-05-01 | Billed | MH12QG6780 | 8151 | 2024-04-22 11:11 | 11:11 AM | 2024-04-22 11:11 | 11:11 AM | 2024-04-05 18:06 | G E NO.8151 DT.22.04.2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-23 11:18 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236481 | 2024-04-16 17:12 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/177 | 2024-04-15 | 6 | 0 | 34380 | INV/24-25/00012 | 2024-04-16 | Billed | MH12KP9217 | 8088 | 2024-04-15 17:00 | 5:00 PM | 2024-04-15 17:00 | 5:00 PM | 2024-04-05 18:06 | G E NO.8088 DT.15/04/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-16 17:12 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236479 | 2024-04-16 17:10 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/176 | 2024-04-15 | 6 | 0 | 34380 | INV/24-25/00012 | 2024-04-16 | Billed | MH12KP9218 | 8087 | 2024-04-15 17:00 | 5:00 PM | 2024-04-15 17:00 | 5:00 PM | 2024-04-05 18:06 | G E NO.8087 DT.15/04/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-16 17:10 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236456 | 2024-04-15 16:33 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 3 | Cu.Mtrs | ALTUS CENTRAL STORE | 17190 | 3094.2 | 68366 | 148 | 5730 | 0 | 0 | S/167 | 2024-04-13 | 3 | 0 | 17190 | INV/24-25/00012 | 2024-04-16 | Billed | MH12QW4549 | 8085 | 2024-04-14 16:24 | 4:24 PM | 2024-04-14 16:24 | 4:24 PM | 2024-04-05 18:06 | G E NO.8085 DT.14/04/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-15 16:33 |  |  | 3
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236455 | 2024-04-15 16:31 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/166 | 2024-04-13 | 6 | 0 | 34380 | INV/24-25/00012 | 2024-04-16 | Billed | MH12KP9216 | 8084 | 2024-04-14 16:24 | 4:24 PM | 2024-04-14 16:24 | 4:24 PM | 2024-04-05 18:06 | G E NO.8084 DT.14/04/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-15 16:31 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236454 | 2024-04-15 16:29 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/165 | 2024-04-13 | 6 | 0 | 34380 | INV/24-25/00012 | 2024-04-16 | Billed | MH12NX5548 | 8083 | 2024-04-14 16:24 | 4:24 PM | 2024-04-14 16:24 | 4:24 PM | 2024-04-05 18:06 | G E NO.8083 DT.14/04/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-15 16:29 |  |  | 6
GANGA ALTUS | RMC | Pavement Quality Concrete (M40) |  | 236453 | 2024-04-15 16:28 | Purchase | INNOVEN INFRACON PVT LTD LIMITED | 6 | Cu.Mtrs | ALTUS CENTRAL STORE | 34380 | 6188.4 | 68366 | 148 | 5730 | 0 | 0 | S/164 | 2024-04-13 | 6 | 0 | 34380 | INV/24-25/00012 | 2024-04-16 | Billed | MH12QW4549 | 8082 | 2024-04-14 16:24 | 4:24 PM | 2024-04-14 16:24 | 4:24 PM | 2024-04-05 18:06 | G E NO.8082 DT.14/04/2024 | Approved |  | 68366 | ANIL BHOSALE | 2024-04-15 16:28 |  |  | 6