## GRNRegisteritemwise638591413861
Material Wise GRN Report
From 01-01-2024 To 13-08-2024
Page 1 of 1
Total Records: 18 Records 1 to 18
Project_Name | Material_Category1 | Material_Name | Brand | GRN_No | GRN_Date | GRNType | Supplier_Issue_Store | Good_Qty | Unit_Name | Received_Store | Amount | Tax_Amount | PO_SrNo | PO_Qty | Rate | Others_Amount | Others_Tax | Challan_No | Challan_Date | Challan_Qty | Use_Challan_Qty | ChallanAmount | Bill_No | Bill_date | Billing_Status | VehicleNo | GateReg_No | GateReg date | GateReg Time | GateReg Out Date | GateReg Out Time | Po_Date | GRN_Remark | GRN_Status | Material_Category2 | GTN_SrNo | Created_By | Created_Date | Approved_By | Approved_Date | Accepted_Qty
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x4"x9" |  | 239915 | 2024-08-09 15:30 | Purchase | ASH CONCEPTS | 4500 | No. | GDT/AGGE | 32400 | 3888 | 69091 | 14720.112 | 7.2 | 0 | 0 | 305 | 2024-08-09 | 4500 | 0 | 32400 | 0 |  | Unbilled | MH12RN1299 | 17610 | 2024-08-09 15:16 | 3:16 PM | 2024-08-09 15:16 | 3:16 PM | 2024-07-03 12:54 | Gate No.17610 Dt.09/08/2024 | Approved |  | 69091 | Rushikesh.Hadke | 2024-08-09 15:30 |  |  | 4500
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x4"x9" |  | 239789 | 2024-08-05 17:09 | Purchase | ASH CONCEPTS | 4500 | No. | GDT/AGGE | 32400 | 3888 | 69091 | 14720.112 | 7.2 | 0 | 0 | 285 | 2024-08-05 | 4500 | 0 | 32400 | 0 |  | Unbilled | MH12RN1299 | 17572 | 2024-08-05 17:07 | 5:07 PM | 2024-08-05 17:07 | 5:07 PM | 2024-07-03 12:54 | Gate No.17572 Dt.05/08/2024 | Approved |  | 69091 | Rushikesh.Hadke | 2024-08-05 17:09 |  |  | 4500
GANGA DHAM TOWERS | RCC MATERIAL | RCC Ch. Cov. w/fram2x3 (HD) - No. |  | 239711 | 2024-08-01 17:47 | Purchase | ASH CONCEPTS | 4 | No. | GDT/AGGE | 10953.44 | 1971.62 | 69343 | 4 | 2738.36 | 0 | 0 | 955 | 2024-07-28 | 4 | 0 | 10953.44 | 2024/25-312 | 2024-08-03 | Billed | MH05DK2184 | 17556 | 2024-08-01 17:44 | 5:44 PM | 2024-08-01 17:44 | 5:44 PM | 2024-07-27 18:39 | Gate No.17556 Dt.01/08/2024 | Approved |  | 69343 | Rushikesh.Hadke | 2024-08-01 17:47 |  |  | 4
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x6"x9" |  | 239503 | 2024-07-27 15:47 | Purchase | ASH CONCEPTS | 2599 | No. | GDT/AGGE | 22091.5 | 2650.98 | 69091 | 15732.344 | 8.5 | 0 | 0 | 245 | 2024-07-27 | 2600 | 0 | 22091.5 | 2024/25-311 | 2024-08-03 | Billed | MH12FZ4648 | 17497 | 2024-07-27 15:44 | 3:44 PM | 2024-07-27 15:44 | 3:44 PM | 2024-07-03 12:54 | Gate No.17497 Dt.27/07/2024 | Approved |  | 69091 | Rushikesh.Hadke | 2024-07-27 15:47 |  |  | 2599
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x6"x9" |  | 239478 | 2024-07-26 16:11 | Purchase | ASH CONCEPTS | 3000 | No. | GDT/AGGE | 25500 | 3060 | 69091 | 15732.344 | 8.5 | 0 | 0 | 241 | 2024-07-26 | 3000 | 0 | 25500 | 2024/25-279 | 2024-07-26 | Billed | MH12VF8594 | 17483 | 2024-07-26 16:08 | 4:08 PM | 2024-07-26 16:08 | 4:08 PM | 2024-07-03 12:54 | Gate No.17483 Dt.26/07/2024 | Approved |  | 69091 | Rushikesh.Hadke | 2024-07-26 16:11 |  |  | 3000
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x6"x9" |  | 239261 | 2024-07-18 14:58 | Purchase | ASH CONCEPTS | 1133 | No. | GDT/AGGE | 9630.5 | 1155.66 | 69091 | 15732.344 | 8.5 | 0 | 0 | 207. | 2024-07-18 | 1133 | 0 | 9630.5 | 2024/25-264 | 2024-07-20 | Billed | MH12RN1299 | 17433 | 2024-07-18 14:56 | 2:56 PM | 2024-07-18 14:56 | 2:56 PM | 2024-07-03 12:54 | Issue No.17433 Dt.18/07/2024 | Approved |  | 69091 | Rushikesh.Hadke | 2024-07-18 14:58 |  |  | 1133
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x6"x9" |  | 239260 | 2024-07-18 14:51 | Purchase | ASH CONCEPTS | 1867 | No. | GDT/AGGE | 15869.5 | 1904.34 | 69073 | 1867.056 | 8.5 | 0 | 0 | 207 | 2024-07-18 | 1867 | 0 | 15869.5 | 2024/25-264 | 2024-07-20 | Billed | MH12RN1299 | 17433 | 2024-07-18 14:46 | 2:46 PM | 2024-07-18 14:46 | 2:46 PM | 2024-07-01 13:17 | Issue No.17433 Dt.18/07/2024 | Approved |  | 69073 | Rushikesh.Hadke | 2024-07-18 14:51 |  |  | 1867
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x6"x9" |  | 239203 | 2024-07-17 12:13 | Purchase | ASH CONCEPTS | 3000 | No. | GDT/AGGE | 25500 | 3060 | 69091 | 15732.344 | 8.5 | 0 | 0 | 199 | 2024-07-17 | 3000 | 0 | 25500 | 2024/25-246 | 2024-07-17 | Billed | MH12RN1299 | 17431 | 2024-07-17 12:07 | 12:07 PM | 2024-07-17 12:07 | 12:07 PM | 2024-07-03 12:54 | Gate No.17431 Dt.17/07/2024 | Approved |  | 69091 | Rushikesh.Hadke | 2024-07-17 12:13 |  |  | 3000
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x6"x9" |  | 239082 | 2024-07-15 11:44 | Purchase | ASH CONCEPTS | 3000 | No. | GDT/AGGE | 25500 | 3060 | 69091 | 15732.344 | 8.5 | 0 | 0 | 180 | 2024-07-15 | 3000 | 0 | 25500 | 2024/25-242 | 2024-07-15 | Billed | MH12RN1299 | 17404 | 2024-07-15 11:41 | 11:41 AM | 2024-07-15 11:41 | 11:41 AM | 2024-07-03 12:54 | Gate No.17404 Dt.15/07/2024 | Approved |  | 69091 | Rushikesh.Hadke | 2024-07-15 11:44 |  |  | 3000
GANGA DHAM TOWERS | RCC MATERIAL | RCC Round Ch. Cover 24" (MD) |  | 239035 | 2024-07-12 18:57 | Purchase | ASH CONCEPTS | 8 | No. | GDT/AGGE | 12386.88 | 2229.64 | 69210 | 8 | 1548.36 | 0 | 0 | 178 | 2024-07-12 | 8 | 0 | 12386.88 | 2024/25-226 | 2024-07-12 | Billed | MH12QR1699 | 17362 | 2024-07-12 18:44 | 6:44 PM | 2024-07-12 18:44 | 6:44 PM | 2024-07-11 11:41 | Gate No.17362 Dt.12/07/2024 | Approved |  | 69210 | Rushikesh.Hadke | 2024-07-12 18:57 |  |  | 8
GANGA DHAM TOWERS | RCC MATERIAL | RCC Chamber Cover with Frame 18"x36" (MD) |  | 239034 | 2024-07-12 18:57 | Purchase | ASH CONCEPTS | 9 | No. | GDT/AGGE | 12894.84 | 2321.08 | 69210 | 9 | 1432.76 | 0 | 0 | 178 | 2024-07-12 | 9 | 0 | 12894.84 | 2024/25-226 | 2024-07-12 | Billed | MH12QR1699 | 17362 | 2024-07-12 18:44 | 6:44 PM | 2024-07-12 18:44 | 6:44 PM | 2024-07-11 11:41 | Gate No.17362 Dt.12/07/2024 | Approved |  | 69210 | Rushikesh.Hadke | 2024-07-12 18:57 |  |  | 9
GANGA DHAM TOWERS | RCC MATERIAL | RCC Chamber Cover with Frame 18"x36" (HD) |  | 239033 | 2024-07-12 18:57 | Purchase | ASH CONCEPTS | 5 | No. | GDT/AGGE | 12671.8 | 2280.92 | 69210 | 5 | 2534.36 | 0 | 0 | 178 | 2024-07-12 | 5 | 0 | 12671.8 | 2024/25-226 | 2024-07-12 | Billed | MH12QR1699 | 17362 | 2024-07-12 18:44 | 6:44 PM | 2024-07-12 18:44 | 6:44 PM | 2024-07-11 11:41 | Gate No.17362 Dt.12/07/2024 | Approved |  | 69210 | Rushikesh.Hadke | 2024-07-12 18:57 |  |  | 5
GANGA DHAM TOWERS | RCC MATERIAL | RCC Ch. Co. perfor. 1.5x3 (MD) |  | 239032 | 2024-07-12 18:57 | Purchase | ASH CONCEPTS | 7 | No. | GDT/AGGE | 10029.32 | 1805.28 | 69210 | 7 | 1432.76 | 0 | 0 | 178 | 2024-07-12 | 7 | 0 | 10029.32 | 2024/25-226 | 2024-07-12 | Billed | MH12QR1699 | 17362 | 2024-07-12 18:44 | 6:44 PM | 2024-07-12 18:44 | 6:44 PM | 2024-07-11 11:41 | Gate No.17362 Dt.12/07/2024 | Approved |  | 69210 | Rushikesh.Hadke | 2024-07-12 18:57 |  |  | 7
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x6"x9" |  | 238788 | 2024-07-09 15:24 | Purchase | ASH CONCEPTS | 3000 | No. | GDT/AGGE | 25500 | 3060 | 69091 | 15732.344 | 8.5 | 0 | 0 | 162 | 2024-07-09 | 3000 | 0 | 25500 | 2024/25-242 | 2024-07-15 | Billed | MH12RN1299 | 17326 | 2024-07-09 15:22 | 3:22 PM | 2024-07-09 15:22 | 3:22 PM | 2024-07-03 12:54 | Gate No.17326 Dt.09/07/2024 | Approved |  | 69091 | Rushikesh.Hadke | 2024-07-09 15:24 |  |  | 3000
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x4"x9" |  | 238721 | 2024-07-05 18:01 | Purchase | ASH CONCEPTS | 4000 | No. | GDT/AGGE | 28800 | 3456 | 69091 | 14720.112 | 7.2 | 0 | 0 | 152 | 2024-07-05 | 4000 | 0 | 28800 | 2024/25-210 | 2024-07-05 | Billed | MH12FZ4648 | 17312 | 2024-07-05 17:59 | 5:59 PM | 2024-07-05 17:59 | 5:59 PM | 2024-07-03 12:54 | Gate No.17312 Dt.05/07/2024 | Approved |  | 69091 | Rushikesh.Hadke | 2024-07-05 18:01 |  |  | 4000
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x4"x9" |  | 238696 | 2024-07-04 11:56 | Purchase | ASH CONCEPTS | 1705.495 | No. | GDT/AGGE | 12279.564 | 1473.54 | 69091 | 14720.112 | 7.2 | 0 | 0 | 149. | 2024-07-03 | 1705.495 | 0 | 12279.564 | 2024/25-205 | 2024-07-04 | Billed | MH12RN1299 |  | 2024-07-04 11:49 | 11:49 AM | 2024-07-04 11:49 | 11:49 AM | 2024-07-03 12:54 | Gate No.17310 Dt.04/07/2024 | Approved |  | 69091 | Rushikesh.Hadke | 2024-07-04 11:56 |  |  | 1705.495
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x4"x9" |  | 238695 | 2024-07-04 11:52 | Purchase | ASH CONCEPTS | 2794.505 | No. | GDT/AGGE | 20120.436 | 2414.46 | 69073 | 7294.505 | 7.2 | 0 | 0 | 149 | 2024-07-03 | 2794.505 | 0 | 20120.436 | 2024/25-205 | 2024-07-04 | Billed | MH12RN1299 | 17310 | 2024-07-04 11:49 | 11:49 AM | 2024-07-04 11:49 | 11:49 AM | 2024-07-01 13:17 | Gate No.17310 Dt.04/07/2024 | Approved |  | 69073 | Rushikesh.Hadke | 2024-07-04 11:52 |  |  | 2794.505
GANGA DHAM TOWERS | BRICKS/ BLOCKS | FlyAsh Bricks 3"x4"x9" |  | 238694 | 2024-07-04 11:38 | Purchase | ASH CONCEPTS | 4500 | No. | GDT/AGGE | 32400 | 3888 | 69073 | 7294.505 | 7.2 | 0 | 0 | 147 | 2024-07-04 | 4500 | 0 | 32400 | 2024/25-205 | 2024-07-04 | Billed | MH12RN1299 | 17309 | 2024-07-04 11:35 | 11:35 AM | 2024-07-04 11:35 | 11:35 AM | 2024-07-01 13:17 | Gate No.17309 Dt.04/07/2024 | Approved |  | 69073 | Rushikesh.Hadke | 2024-07-04 11:38 |  |  | 4500