## IssueRegister638573246109800820
Issue Register
From 22-07-2024 To 23-07-2024
Page 1 of 1
Total Records: 7 Records 1 to 7
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
SRA MORWADI | Sand-Metal Mix M30 (Pumpable) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 776199 | 2024-07-22 17:45 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23395 Date:-22.7.2024 Manjulai RMC | 15 | 3287.34 | 49310.1 | 8875.8 | 58185.9 | Cu.Mtrs | B Bldg Column 3rd to 4th Slab | 45.43 | yogesh-agarwal | 0
SRA MORWADI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 776200 | 2024-07-22 17:46 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23395 Date:-22.7.2024 Manjulai RMC | 3 | 5886.76 | 17660.28 | 4944.9 | 22605.18 | Metric Tonnes | B Bldg Column 3rd to 4th Slab | 41.67 | yogesh-agarwal | 0
SRA MORWADI | Binding Wire -Kgs | KRISHNA CONSTRUCTION |  | 776201 | 2024-07-22 17:47 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24505 Date:-22.7.2024 | 61 | 68.28 | 4165.08 | 741.15 | 4906.23 | Kgs | A Bldg Fourth to Fifth slab Column,lift Steel | 103.62 | yogesh-agarwal | 0
SRA MORWADI | 8 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 776202 | 2024-07-22 17:48 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24503 Date:-22.7.2024 | 2 | 102.66 | 205.32 | 0 | 205.32 | No. | A-3rd Floor Lobby Electrical Conduct | 6 | yogesh-agarwal | 0
SRA MORWADI | 12 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 776203 | 2024-07-22 17:49 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24503 Date:-22.7.2024 | 2 | 121.77 | 243.54 | 0 | 243.54 | No. | A-3rd Floor Lobby Electrical Conduct | 2 | yogesh-agarwal | 0
SRA MORWADI | 2 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 776204 | 2024-07-22 17:50 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24503 Date:-22.7.2024 | 2 | 34.71 | 69.42 | 2.2 | 71.62 | No. | A-3rd Floor Lobby Electrical Conduct | 6 | yogesh-agarwal | 0
SRA MORWADI | GI Raceway 300mmx200mm (1.2mm thk) - No. -No. | TAHA ELECTRICALS |  | 776205 | 2024-07-22 17:50 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24503 Date:-22.7.2024 | 2 | 343.72 | 687.44 | 108 | 795.44 | No. | A-3rd Floor Lobby Electrical Conduct | 2 | yogesh-agarwal | 0