## IssueRegister638573584967602351
Issue Register
From 23-07-2024 To 23-07-2024
Page 1 of 1
Total Records: 37 Records 1 to 37
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
GANGA ASMI | GP2 Waterproofing Chemical -Kgs | KRISHNA CONSTRUCTION |  | 776239 | 2024-07-23 11:29 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47985 DT: 23.07.2024 | 180 | 17.5 | 3150 | 567 | 3717 | Kgs | Wing 1-10th Slab (4th Floor) GP2 For Wall Tie & Rod Hole | 855 | Shahu Nawale | 0
GANGA ASMI | Potato Greece -Kgs | KRISHNA CONSTRUCTION |  | 776240 | 2024-07-23 11:30 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47972 DT: 23.07.2024 | 180 | 133 | 23940 | 4309.2 | 28249.2 | Kgs | Wing-1 Aluform Misc. Consumables | 20845 | Shahu Nawale | 0
GANGA ASMI | Shuttering oil-oil based -Ltrs | KRISHNA CONSTRUCTION |  | 776241 | 2024-07-23 11:31 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47972 DT: 23.07.2024 | 235 | 145 | 34075 | 6133.5 | 40208.5 | Ltrs | Wing-1 Aluform Misc. Consumables | 20065 | Shahu Nawale | 0
GANGA ASMI | Cement Loose 53 Grade -Metric Tonnes | KSHITEEJ ENTERPRISES |  | 776246 | 2024-07-23 11:57 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48782 DT: 23.07.2024 | 2.304 | 7600.97 | 17512.6349 | 0 | 17512.6349 | Metric Tonnes | Wing 2 P5 (4th Slab) to P6 (5th Slab) Column M50 | 79.8552 | Shahu Nawale | 0
GANGA ASMI | Sand-Metal Mix M50 hi-flow (Downpour) -Cu.Mtrs | KSHITEEJ ENTERPRISES |  | 776247 | 2024-07-23 11:57 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48782 DT: 23.07.2024 | 6 | 3305.68 | 19834.08 | 3570.12 | 23404.2 | Cu.Mtrs | Wing 2 P5 (4th Slab) to P6 (5th Slab) Column M50 | 222.22 | Shahu Nawale | 0
GANGA ASMI | Sand-Metal Mix M50 hi-flow (Downpour) -Cu.Mtrs | KSHITEEJ ENTERPRISES |  | 776248 | 2024-07-23 12:15 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48781 DT: 23.07.2024 | 4.72 | 1520.63 | 7177.3736 | 11234.02 | 18411.3936 | Cu.Mtrs | Wing 2 - P4 (3rd Slab) to P5 (4th Slab) Column M50 | 199.5 | Shahu Nawale | 0
GANGA ASMI | Sand-Metal Mix M50 hi-flow (Downpour) -Cu.Mtrs | KSHITEEJ ENTERPRISES |  | 776249 | 2024-07-23 12:15 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48781 DT: 23.07.2024 | 1.28 | 1520.63 | 1946.4064 | 3046.52 | 4992.9264 | Cu.Mtrs | Wing 2 P5 (4th Slab) to P6 (5th Slab) Column M50 | 226.94 | Shahu Nawale | 0
GANGA ASMI | Cement Loose 53 Grade -Metric Tonnes | KSHITEEJ ENTERPRISES |  | 776250 | 2024-07-23 12:18 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48781 DT: 23.07.2024 | 2.2342 | 5968.4 | 13334.5993 | 3696.17 | 17030.7693 | Metric Tonnes | Wing 2 - P4 (3rd Slab) to P5 (4th Slab) Column M50 | 79.925 | Shahu Nawale | 0
GANGA ASMI | Cement Loose 53 Grade -Metric Tonnes | KSHITEEJ ENTERPRISES |  | 776251 | 2024-07-23 12:18 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48781 DT: 23.07.2024 | 0.0698 | 5968.4 | 416.5943 | 115.47 | 532.0643 | Metric Tonnes | Wing 2 P5 (4th Slab) to P6 (5th Slab) Column M50 | 82.0894 | Shahu Nawale | 0
GANGA ASMI | Black Insulation Tape -No. | DEPARTMENT |  | 776252 | 2024-07-23 12:19 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45870 DT: 23.07.2024 | 5 | 9.1 | 45.5 | 8.1 | 53.6 | No. | Site Illumination | 20 | Shahu Nawale | 0
GANGA ASMI | Binding Wire -Kgs | KRISHNA CONSTRUCTION |  | 776335 | 2024-07-23 16:30 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47984 DT: 23.07.2024 | 63.14 | 67.32 | 4250.5848 | 756.42 | 5007.0048 | Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | 188.66 | Shahu Nawale | 0
GANGA ASMI | Safety Net 10mtr x 6mtr -Sq.m. | KSHITEEJ ENTERPRISES |  | 776336 | 2024-07-23 16:31 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48783 DT: 23.07.2024 | 60 | 81.05 | 4863 | 264 | 5127 | Sq.m. | Lab & Safety Equipments Site Safety Material | 5640 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 16mm -Kgs | KRISHNA CONSTRUCTION |  | 776337 | 2024-07-23 16:34 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47977 DT: 23.07.2024 | 683 | 60.51 | 41328.33 | 204.9 | 41533.23 | Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | 2192.28 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 16mm -Kgs | KRISHNA CONSTRUCTION |  | 776338 | 2024-07-23 16:41 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47979 DT: 23.07.2024 | 834 | 60.51 | 50465.34 | 250.2 | 50715.54 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 2867 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 12mm -Kgs | KRISHNA CONSTRUCTION |  | 776339 | 2024-07-23 16:43 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47979 DT: 23.07.2024 | 1280 | 60.55 | 77504 | 0 | 77504 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 1539 | Shahu Nawale | 0
GANGA ASMI | GP2 Waterproofing Chemical -Kgs | KRISHNA CONSTRUCTION |  | 776340 | 2024-07-23 16:44 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47981 DT: 23.07.2024 | 60 | 17.5 | 1050 | 189 | 1239 | Kgs | Wing 1-11th Slab (5th Floor) GP2 For Wall Tie & Rod Hole | 975 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | KRISHNA CONSTRUCTION |  | 776341 | 2024-07-23 16:46 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47981 DT: 23.07.2024 | 1 | 313.09 | 313.09 | 35.47 | 348.56 | Bags | Wing 1-11th Slab (5th Floor) Cement For Misc Work | 34 | Shahu Nawale | 0
GANGA ASMI | Diesel -Ltrs | DEPARTMENT |  | 776342 | 2024-07-23 16:47 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47982 DT: 23.07.2024 | 120 | 91.52 | 10982.4 | 0 | 10982.4 | Ltrs | Diesel for DG Set-(Ltrs) | 3430 | Shahu Nawale | 0
GANGA ASMI | Steel Bar 25mm -Kgs | KRISHNA CONSTRUCTION |  | 776375 | 2024-07-23 17:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47986 DT: 23.07.2024 | 926 | 61.06 | 56541.56 | 9.26 | 56550.82 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 2454 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 8mm -Kgs | KRISHNA CONSTRUCTION |  | 776376 | 2024-07-23 17:25 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47983 DT: 23.07.2024 | 4029 | 59.75 | 240732.75 | 10354.53 | 251087.28 | Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | 4252.07 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 20mm -Kgs | KRISHNA CONSTRUCTION |  | 776377 | 2024-07-23 17:26 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47983 DT: 23.07.2024 | 1778 | 58.62 | 104226.36 | 4569.46 | 108795.82 | Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | 2168.33 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776382 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.0075 | 313.09 | 2.3482 | 0.27 | 2.6182 | Bags | Wing-1 Flat No 201 Balcony Brickbatt+Finish Coat W/P | 2.45 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776383 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.6277 | 313.09 | 196.5266 | 22.26 | 218.7866 | Bags | Wing-1 Flat No 201 Utility Brickbatt+Finish Coat W/P | 1 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776384 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.0075 | 313.09 | 2.3482 | 0.27 | 2.6182 | Bags | Wing-1 Flat No 202 Balcony Brickbatt+Finish Coat W/P | 2.45 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776385 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.0984 | 313.09 | 30.8081 | 3.49 | 34.2981 | Bags | Wing-1 Flat No 202 Utility Brickbatt+Finish Coat W/P | 1.5 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776386 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.8167 | 313.09 | 255.7006 | 28.97 | 284.6706 | Bags | Wing-1 Flat No 203 Balcony Brickbatt+Finish Coat W/P | 1 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776387 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.5696 | 313.09 | 178.3361 | 20.2 | 198.5361 | Bags | Wing-1 Flat No 203 Utility Brickbatt+Finish Coat W/P | 1 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776388 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.8167 | 313.09 | 255.7006 | 28.97 | 284.6706 | Bags | Wing-1 Flat No 204 Balcony Brickbatt+Finish Coat W/P | 1 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776389 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.5696 | 313.09 | 178.3361 | 20.2 | 198.5361 | Bags | Wing-1 Flat No 204 Utility Brickbatt+Finish Coat W/P | 1 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776390 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.3167 | 313.09 | 99.1556 | 11.23 | 110.3856 | Bags | Wing-1 Flat No 205 Balcony Brickbatt+Finish Coat W/P | 1.5 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776391 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 1.5696 | 313.09 | 491.4261 | 55.67 | 547.0961 | Bags | Wing-1 Flat No 205 Utility Brickbatt+Finish Coat W/P | 0 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776392 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.4575 | 313.09 | 143.2387 | 16.23 | 159.4687 | Bags | Wing-1 Flat No 206 Balcony Brickbatt+Finish Coat W/P | 2 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776393 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 1.5984 | 313.09 | 500.4431 | 56.7 | 557.1431 | Bags | Wing-1 Flat No 206 Utility Brickbatt+Finish Coat W/P | 0 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776394 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.4575 | 313.09 | 143.2387 | 16.23 | 159.4687 | Bags | Wing-1 Flat No 207 Balcony Brickbatt+Finish Coat W/P | 2 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776395 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 1.5984 | 313.09 | 500.4431 | 56.7 | 557.1431 | Bags | Wing-1 Flat No 207 Utility Brickbatt+Finish Coat W/P | 0 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 776396 | 2024-07-23 18:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46352 DT: 23.07.2024 | 0.4882 | 313.09 | 152.8505 | 17.32 | 170.1705 | Bags | Wing-1 Flat No 209 Balcony Brickbatt+Finish Coat W/P | 1.3285 | Shahu Nawale | 0
GANGA ASMI | Superwhite Tile 600 X 600 (DC) (AGL) -Sq.Ft | PAPPU BAGELA |  | 776397 | 2024-07-23 18:55 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46354 DT: 23.07.2024 | 697.5 | 38.13 | 26595.675 | 4791.83 | 31387.505 | Sq.Ft | Wing 1- 201 Flat Flooring | 1.89 | Shahu Nawale | 0