## IssueRegister638578761735354284
Issue Register
From 29-07-2024 To 29-07-2024
Page 1 of 1
Total Records: 66 Records 1 to 66
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
GANGA ASMI | Steel Bars 12mm -Kgs | KRISHNA CONSTRUCTION |  | 777135 | 2024-07-29 10:03 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47997 DT: 29.07.2024 | 1280 | 60 | 76800 | 0 | 76800 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 1539 | Shahu nawale | 0
GANGA ASMI | Steel Bars 16mm -Kgs | KRISHNA CONSTRUCTION |  | 777136 | 2024-07-29 10:03 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47997 DT: 29.07.2024 | 1138 | 60.2 | 68507.6 | 0 | 68507.6 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 2563 | Shahu nawale | 0
GANGA ASMI | GP2 Waterproofing Chemical -Kgs | KRISHNA CONSTRUCTION |  | 777137 | 2024-07-29 10:04 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46366 DT: 29.07.2024 | 60 | 17.5 | 1050 | 189 | 1239 | Kgs | Wing 1-10th Slab (4th Floor) GP2 For Wall Tie & Rod Hole | 975 | Shahu nawale | 0
GANGA ASMI | Diesel -Ltrs | DEPARTMENT |  | 777138 | 2024-07-29 10:10 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48000 DT: 29.07.2024 | 100 | 91.52 | 9152 | 0 | 9152 | Ltrs | Diesel for DG Set-(Ltrs) | 4650 | Shahu nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | KSHITEEJ ENTERPRISES |  | 777139 | 2024-07-29 10:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45307 DT: 29.07.2024 | 3 | 313.1 | 939.3 | 106.41 | 1045.71 | Bags | Wing 2 . 4TH Slab (P5 ) Cement For Cover Block | 9 | Shahu nawale | 0
GANGA ASMI | Binding Wire -Kgs | KRISHNA CONSTRUCTION |  | 777140 | 2024-07-29 10:16 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47998 DT: 29.07.2024 | 57.16 | 67.32 | 3848.0112 | 684.78 | 4532.7912 | Kgs | Wing 1-4th Floor To 5th Floor Column, LW Steel | 407.528 | Shahu nawale | 0
GANGA ASMI | Binding Wire -Kgs | SAIRAJ CONSTRUCTION |  | 777141 | 2024-07-29 10:21 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45875 DT: 29.07.2024 | 26 | 67.32 | 1750.32 | 311.22 | 2061.54 | Kgs | Non Tower Area NTA 1st PT Slab (Wing 1) Steel | 116.07 | Shahu nawale | 0
GANGA ASMI | GP2 Waterproofing Chemical -Kgs | KRISHNA CONSTRUCTION |  | 777142 | 2024-07-29 10:23 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46372 DT: 29.07.2024 | 120 | 17.5 | 2100 | 378 | 2478 | Kgs | Wing 1-11th Slab (5th Floor) GP2 For Wall Tie & Rod Hole | 915 | Shahu nawale | 0
GANGA ASMI | Binding Wire -Kgs | PURVA CONSTRUCTION |  | 777150 | 2024-07-29 10:27 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45876 DT: 29.07.2024 | 10 | 67 | 670 | 120.6 | 790.6 | Kgs | UGWT RCC Top Slab & Beam Steel | 110.55 | Shahu nawale | 0
GANGA ASMI | Steel Bars 10mm -Kgs | PURVA CONSTRUCTION |  | 777151 | 2024-07-29 10:27 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45876 DT: 29.07.2024 | 244 | 60.31 | 14715.64 | 0 | 14715.64 | Kgs | UGWT RCC Top Slab & Beam Steel | 2206.13 | Shahu nawale | 0
GANGA ASMI | Steel Bars 8mm -Kgs | PURVA CONSTRUCTION |  | 777152 | 2024-07-29 10:27 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45876 DT: 29.07.2024 | 403 | 61.71 | 24869.13 | 0 | 24869.13 | Kgs | UGWT RCC Top Slab & Beam Steel | 3091.57 | Shahu nawale | 0
GANGA ASMI | Plastic (Transperent) -Kgs | SAIRAJ CONSTRUCTION |  | 777161 | 2024-07-29 10:30 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45877 DT: 29.07.2024 | 5 | 108.51 | 542.55 | 95.35 | 637.9 | Kgs | Non Tower Area Misc. Consumable Material | 25 | Shahu nawale | 0
GANGA ASMI | Artific Gris-Light Tile 300 X 600 (AGL) -Sq.Ft | PAPPU BAGELA |  | 777280 | 2024-07-29 14:45 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46375 DT: 29.07.2024 | 29.07 | 33.05 | 960.7635 | 172.97 | 1133.7335 | Sq.Ft | Wing -1 (3BHK)Flat 101 Master Toilet Dado(Light) | 120.28 | Shahu Nawale | 0
GANGA ASMI | Calleva Dark Tile 300 X 600 (AGL) -Sq.Ft | PAPPU BAGELA |  | 777296 | 2024-07-29 15:23 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46378 DT: 29.07.2024 | 7.27 | 33.05 | 240.2735 | 43.26 | 283.5335 | Sq.Ft | Wing -1 (2BHK) Flat 103 Master Toilet Dado(Dark) | 0 | Shahu nawale | 0
GANGA ASMI | Calleva Dark Tile 300 X 600 (AGL) -Sq.Ft | PAPPU BAGELA |  | 777297 | 2024-07-29 15:23 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46378 DT: 29.07.2024 | 7.26 | 33.05 | 239.943 | 43.2 | 283.143 | Sq.Ft | Wing -1 (2BHK) Flat 105 Master Toilet Dado(Dark) | 0.01 | Shahu nawale | 0
GANGA ASMI | Calleva Dark Tile 300 X 600 (AGL) -Sq.Ft | PAPPU BAGELA |  | 777298 | 2024-07-29 15:23 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46378 DT: 29.07.2024 | 7.27 | 33.05 | 240.2735 | 43.26 | 283.5335 | Sq.Ft | Wing -1 (3BHK)Flat 101 Master Toilet Dado(Dark) | 0 | Shahu nawale | 0
GANGA ASMI | Calleva Dark Tile 300 X 600 (AGL) -Sq.Ft | PAPPU BAGELA |  | 777299 | 2024-07-29 15:23 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46378 DT: 29.07.2024 | 7.27 | 33.05 | 240.2735 | 43.26 | 283.5335 | Sq.Ft | Wing -1 (3BHK)Flat 102 Master Toilet Dado(Dark) | 0 | Shahu nawale | 0
GANGA ASMI | Sunflex Sheet 6' X 4' X 2 mm Thk -No. | DEPARTMENT |  | 777302 | 2024-07-29 15:31 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46374 DT: 29.07.2024 | 3 | 89.47 | 268.41 | 21.03 | 289.44 | No. | Wing-1 Aluform Misc. Consumables | 867 | Shahu nawale | 0
GANGA ASMI | Tape Roll -No. | DEPARTMENT |  | 777303 | 2024-07-29 15:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46374 DT: 29.07.2024 | 6 | 26.84 | 161.04 | 28.08 | 189.12 | No. | Wing-1 Aluform Misc. Consumables | 864 | Shahu nawale | 0
GANGA ASMI | Plastic (Transperent) -Kgs | SAIRAJ CONSTRUCTION |  | 777305 | 2024-07-29 15:36 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45878 DT: 29.07.2024 | 3 | 108.51 | 325.53 | 57.21 | 382.74 | Kgs | Non Tower Area Misc. Consumable Material | 27 | Shahu Nawale | 0
GANGA ASMI | Binding Wire -Kgs | KRISHNA CONSTRUCTION |  | 777306 | 2024-07-29 15:40 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46371 DT: 29.07.2024 | 21.674 | 67.72 | 1467.7633 | 250.98 | 1718.7433 | Kgs | Wing 1-3rd Floor To 4th Floor Column, LW Steel | 448.522 | Shahu Nawale | 0
GANGA ASMI | Binding Wire -Kgs | KRISHNA CONSTRUCTION |  | 777307 | 2024-07-29 15:40 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46371 DT: 29.07.2024 | 1.346 | 67.72 | 91.1511 | 15.59 | 106.7411 | Kgs | Wing 1-4th Floor To 5th Floor Column, LW Steel | 463.342 | Shahu Nawale | 0
GANGA ASMI | Binding Wire -Kgs | KRISHNA CONSTRUCTION |  | 777308 | 2024-07-29 15:40 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46371 DT: 29.07.2024 | 45.86 | 67.72 | 3105.6392 | 531.06 | 3636.6992 | Kgs | Wing 1-5th Floor To 6th Floor Column, LW Steel | 309.14 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | KRISHNA CONSTRUCTION |  | 777310 | 2024-07-29 15:41 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46373 DT: 29.07.2024 | 2 | 339.34 | 678.68 | 1.74 | 680.42 | Bags | Wing 1-10th Slab (4th Floor) Cement For Misc Work | 33 | Shahu Nawale | 0
GANGA ASMI | Caron Ivory-Light Tile 300 X 600 (AGL) -Sq.Ft | PAPPU BAGELA |  | 777315 | 2024-07-29 15:44 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46363 DT: 29.07.2024 | 29.07 | 33.05 | 960.7635 | 172.97 | 1133.7335 | Sq.Ft | Wing -1 (3BHK)Flat 101 Common Toilet Dado(Light) | 116.65 | Shahu Nawale | 0
GANGA ASMI | Steel Bar 25mm -Kgs | KRISHNA CONSTRUCTION |  | 777319 | 2024-07-29 15:48 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46370 DT: 29.07.2024 | 926 | 60.49 | 56013.74 | 0 | 56013.74 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 2454 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 32mm -Kgs | KRISHNA CONSTRUCTION |  | 777322 | 2024-07-29 15:51 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46369 DT: 29.07.2024 | 152 | 60.05 | 9127.6 | 405.84 | 9533.44 | Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | 422.88 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 32mm -Kgs | KRISHNA CONSTRUCTION |  | 777323 | 2024-07-29 15:53 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46368 DT: 29.07.2024 | 607 | 60.02 | 36432.14 | 1638.9 | 38071.04 | Kgs | Wing 1-11th Slab (5th Floor) Slab,Beam,Stair. Steel | 14.91 | Shahu Nawale | 0
GANGA ASMI | MS Plank 2400x300mm -No. | KSHITEEJ ENTERPRISES |  | 777324 | 2024-07-29 15:58 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45305 DT: 29.07.2024 (FOR WING-2) | 25 | 1521.35 | 38033.75 | 6795 | 44828.75 | No. | Wing-1 Aluform Misc. Consumables | 715 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777329 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 17.325 | 4.64 | 80.388 | 14.03 | 94.418 | Sq.Ft | Wing 1- 201 Utility Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777330 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 17.83 | 4.64 | 82.7312 | 14.44 | 97.1712 | Sq.Ft | Wing 1- 203 Utility Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777331 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 76.575 | 4.64 | 355.308 | 62.03 | 417.338 | Sq.Ft | Wing 1- 204 Flat Flooring | 192 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777332 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 20.185 | 4.64 | 93.6584 | 16.35 | 110.0084 | Sq.Ft | Wing 1- 204 Balcony Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777333 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 17.44 | 4.64 | 80.9216 | 14.13 | 95.0516 | Sq.Ft | Wing 1- 204 Utility Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777334 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 268.605 | 4.64 | 1246.3272 | 217.57 | 1463.8972 | Sq.Ft | Wing 1- 205 Flat Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777335 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 20.185 | 4.64 | 93.6584 | 16.35 | 110.0084 | Sq.Ft | Wing 1- 205 Balcony Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777336 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 35.2 | 4.64 | 163.328 | 28.51 | 191.838 | Sq.Ft | Wing 1- 205 Toilet Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777337 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 55.7 | 4.64 | 258.448 | 45.12 | 303.568 | Sq.Ft | Wing 1- 206 Toilet Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777338 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 355.565 | 4.64 | 1649.8216 | 288.01 | 1937.8316 | Sq.Ft | Wing 1- 206 Flat Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777339 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 55.7 | 4.64 | 258.448 | 45.12 | 303.568 | Sq.Ft | Wing 1- 207 Toilet Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777340 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 27.305 | 4.64 | 126.6952 | 22.12 | 148.8152 | Sq.Ft | Wing 1- 207 Balcony Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777341 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 355.565 | 4.64 | 1649.8216 | 288.01 | 1937.8316 | Sq.Ft | Wing 1- 207 Flat Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777342 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 17.005 | 4.64 | 78.9032 | 13.77 | 92.6732 | Sq.Ft | Wing 1- 207 Utility Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777343 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 267.605 | 4.64 | 1241.6872 | 216.76 | 1458.4472 | Sq.Ft | Wing 1- 209 Flat Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777344 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 52.025 | 4.64 | 241.396 | 42.14 | 283.536 | Sq.Ft | Wing 1- 209 Toilet Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777345 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 17.44 | 4.64 | 80.9216 | 14.13 | 95.0516 | Sq.Ft | Wing 1- 209 Utility Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777346 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 349.695 | 4.64 | 1622.5848 | 283.25 | 1905.8348 | Sq.Ft | Wing 1- 201 Flat Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777347 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 16.415 | 4.64 | 76.1656 | 13.3 | 89.4656 | Sq.Ft | Wing 1- 201 101 Common Toilet Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777348 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 28.59 | 4.64 | 132.6576 | 23.16 | 155.8176 | Sq.Ft | Wing 1- 201 Balcony Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777349 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 17.76 | 4.64 | 82.4064 | 14.39 | 96.7964 | Sq.Ft | Wing 1- 201 Master Toilet Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777350 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 233.05 | 4.64 | 1081.352 | 188.77 | 1270.122 | Sq.Ft | Wing 1- 202 Flat Flooring | 120 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777351 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 56.88 | 4.64 | 263.9232 | 46.07 | 309.9932 | Sq.Ft | Wing 1- 202 Toilet Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777352 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 28.595 | 4.64 | 132.6808 | 23.16 | 155.8408 | Sq.Ft | Wing 1- 202 Balcony Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777353 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 17.41 | 4.63 | 80.6083 | 14.28 | 94.8883 | Sq.Ft | Wing 1- 202 Utility Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777354 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 265.915 | 4.63 | 1231.1864 | 218.05 | 1449.2365 | Sq.Ft | Wing 1- 203 Flat Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777355 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 21.26 | 4.63 | 98.4338 | 17.43 | 115.8638 | Sq.Ft | Wing 1- 203 Balcony Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777356 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 36.205 | 4.63 | 167.6292 | 29.69 | 197.3192 | Sq.Ft | Wing 1- 203 Toilet Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777357 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 51.02 | 4.63 | 236.2226 | 41.84 | 278.0626 | Sq.Ft | Wing 1- 204 Toilet Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777358 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 17.44 | 4.63 | 80.7472 | 14.3 | 95.0472 | Sq.Ft | Wing 1- 205 Utility Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777359 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 27.305 | 4.63 | 126.4222 | 22.39 | 148.8122 | Sq.Ft | Wing 1- 206 Balcony Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777360 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 17.005 | 4.63 | 78.7331 | 13.94 | 92.6732 | Sq.Ft | Wing 1- 206 Utility Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777361 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 20.185 | 4.63 | 93.4565 | 16.55 | 110.0066 | Sq.Ft | Wing 1- 208 Balcony Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Floor Guard Sheet (4ft x 6ft) -Sq.Ft | DEPARTMENT |  | 777362 | 2024-07-29 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46364 DT: 29.07.2024 | 46.015 | 4.63 | 213.0495 | 37.73 | 250.7794 | Sq.Ft | Wing 1- 208 Toilet Flooring | 5.005 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 20mm -Kgs | KRISHNA CONSTRUCTION |  | 777369 | 2024-07-29 17:31 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46377 DT: 29.07.2024 | 1778 | 58.98 | 104866.44 | 0 | 104866.44 | Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | 2168.33 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 32mm -Kgs | KRISHNA CONSTRUCTION |  | 777370 | 2024-07-29 17:31 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46377 DT: 29.07.2024 | 380 | 61.73 | 23457.4 | 0 | 23457.4 | Kgs | Wing 1-12th Slab (6th Floor) Slab,Beam,Stair. Steel | 194.88 | Shahu Nawale | 0
GANGA ASMI | Safety shoes -No. | DEPARTMENT |  | 777373 | 2024-07-29 18:22 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46741 DT: 29.07.2024 (FOR SUMIT SHARMA SIR & NIKHIL WALUNJ SIR) | 2 | 1091.94 | 2183.88 | 348.44 | 2532.32 | No. | Lab & Safety Equipments Site Safety Material | 118 | Shahu Nawale | 0