## IssueRegister638580475241589012
Issue Register
From 31-07-2024 To 31-07-2024
Page 1 of 1
Total Records: 29 Records 1 to 29
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
SRA MORWADI | Steel Bars 10mm -Kgs | KRISHNA CONSTRUCTION |  | 777658 | 2024-07-31 11:46 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | Issue slip NO.22942 Date : 31.07.2024. | 1221.66 | 61.92 | 75645.1872 | 97.73 | 75742.9172 | Kgs | UGWT padadi Steel | 7723.18 | yogesh-agarwal | 0
SRA MORWADI | Sand-Metal Mix M30 (Pumpable) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 777662 | 2024-07-31 12:25 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23397 Date:-31.07.2024 Future India | 6 | 3171.3 | 19027.8 | 3425.04 | 22452.84 | Cu.Mtrs | B Bldg Column 3rd to 4th Slab | 54.43 | yogesh-agarwal | 0
SRA MORWADI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 777671 | 2024-07-31 12:29 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23397 Date:-31.07.2024 Future India | 1.5 | 5886.76 | 8830.14 | 2472.45 | 11302.59 | Metric Tonnes | B Bldg Column 3rd to 4th Slab | 43.17 | yogesh-agarwal | 0
SRA MORWADI | Black Insulation Tape -No. | DEPARTMENT |  | 777672 | 2024-07-31 12:31 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24841 Date:-31.07.2024 | 2 | 9.04 | 18.08 | 3.24 | 21.32 | No. | Phase 2 Site Setup Electrical Work | 28 | yogesh-agarwal | 0
SRA MORWADI | Water Jar (20 lit) -No. | DEPARTMENT |  | 777673 | 2024-07-31 12:32 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24839 Date:-31.07.2024 | 122 | 35 | 4270 | 0 | 4270 | No. | Site Office Drinking Water Jar | 248 | yogesh-agarwal | 0
SRA MORWADI | PVC Hose Pipe 4" -R.Ft | DEPARTMENT |  | 777674 | 2024-07-31 12:36 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24840 Date : 30.07.2024 (Ph 2) | 200 | 119.4 | 23880 | 4032 | 27912 | R.Ft | Phase 2 Dewatering Pump | 0 | yogesh-agarwal | 0
SRA MORWADI | Hose pipe PVC Socket 4" -No. | DEPARTMENT |  | 777675 | 2024-07-31 12:39 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24840 Date : 30.07.2024 (Ph 2) | 2 | 106.61 | 213.22 | 36 | 249.22 | No. | Phase 2 Dewatering Pump | 0 | yogesh-agarwal | 0
SRA MORWADI | Hose Pipe Clamp 4" -No. | DEPARTMENT |  | 777676 | 2024-07-31 12:40 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24840 Date:-30.07.2024 | 2 | 37.32 | 74.64 | 12.6 | 87.24 | No. | Phase 2 Dewatering Pump | 0 | yogesh-agarwal | 0
SRA MORWADI | PVC Conduit Bend 1" -No. | TAHA ELECTRICALS |  | 777677 | 2024-07-31 13:54 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24512 Date:-31.07.2024 | 40 | 7.71 | 308.4 | 30.8 | 339.2 | No. | A-Flat No 305 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | PVC Conduit Bend 1" -No. | TAHA ELECTRICALS |  | 777678 | 2024-07-31 13:54 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24512 Date:-31.07.2024 | 40 | 7.71 | 308.4 | 30.8 | 339.2 | No. | A-Flat No 306 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | PVC Conduit Bend 1" -No. | TAHA ELECTRICALS |  | 777679 | 2024-07-31 13:54 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24512 Date:-31.07.2024 | 34 | 7.71 | 262.14 | 26.18 | 288.32 | No. | A-Flat No 307 Electrical Work | 6 | yogesh-agarwal | 0
SRA MORWADI | Halogen 200 Watt -No. | DEPARTMENT |  | 777680 | 2024-07-31 13:55 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23176 Date:-31.07.2024 | 1 | 2636.79 | 2636.79 | 472.95 | 3109.74 | No. | Site Illumination/ Temporary Electrical Work Material | 29 | yogesh-agarwal | 0
SRA MORWADI | Safety Jacket -No. | DEPARTMENT |  | 777681 | 2024-07-31 13:56 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23175 Date:-31.07.2024 | 2 | 145.49 | 290.98 | 182.08 | 473.06 | No. | Safety Setup Safety Material for Labours | 8 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 12mm -Kgs | KRISHNA CONSTRUCTION |  | 777724 | 2024-07-31 17:16 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23398 Date:-31.07.2024 | 170.49 | 58.31 | 9941.2719 | 163.67 | 10104.9419 | Kgs | B Parking-2nd Floor (3rd Slab) Slab,Staircase,Beam Steel | 1760.99 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 8mm -Kgs | KRISHNA CONSTRUCTION |  | 777725 | 2024-07-31 17:18 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23398 Date:-31.07.2024 | 80.58 | 62.47 | 5033.8326 | 1.61 | 5035.4426 | Kgs | B Bldg 4th Slab Column,Lift wall,S/wall Steel | 3801.29 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 12mm -Kgs | KRISHNA CONSTRUCTION |  | 777726 | 2024-07-31 17:20 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23400 Date:-31.07.2024 | 143.05 | 58.29 | 8338.3845 | 140.19 | 8478.5745 | Kgs | B Parking-2nd Floor (3rd Slab) Slab,Staircase,Beam Steel | 1788.43 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 8mm -Kgs | KRISHNA CONSTRUCTION |  | 777727 | 2024-07-31 17:26 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24514 Date:-31.07.2024 | 805.8 | 62.47 | 50338.326 | 16.12 | 50354.446 | Kgs | A Building 5th Slab Non Str. wall steel | 23.08 | yogesh-agarwal | 0
SRA MORWADI | GP2 Waterproofing Chemical -Kgs | KRISHNA CONSTRUCTION |  | 777728 | 2024-07-31 17:27 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23399 Date:-31.07.2024 | 30 | 17.5 | 525 | 94.5 | 619.5 | Kgs | B Parking-1st Floor (2nd Slab) Wall Tie Filling | 420 | yogesh-agarwal | 0
SRA MORWADI | PVC Agri Pipe 110mm x 20fts 4KG -No. | KRISHNA CONSTRUCTION |  | 777729 | 2024-07-31 17:29 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23088 Date:-31.07.2024 | 0.5 | 1056.34 | 528.17 | 0 | 528.17 | No. | B1 Bldg 2nd Slab Fire Sleeve Fixing | 0.5 | yogesh-agarwal | 0
SRA MORWADI | PVC Agri Pipe 63mm x 20fts 4KG -No. | KRISHNA CONSTRUCTION |  | 777730 | 2024-07-31 17:31 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23088 Date:-31.07.2024 | 0.5 | 370.8 | 185.4 | 0 | 185.4 | No. | B1 Bldg 2nd Slab Fire Sleeve Fixing | 0.5 | yogesh-agarwal | 0
SRA MORWADI | Aluminium Formwork (Sqm) -Sq.m. |  |  | 777739 | 2024-07-31 17:37 | Issue to IST | Non Returnable / Non Debitable | MORWADI COMMON | Transfer to Asset Store | 3175.43 | 9525 | 30245970.75 | 5444274.74 | 35690245.49 | Sq.m. | SRA MORWADI ASSETS STORE | 0 | yogesh-agarwal | 0
SRA MORWADI | Aluminium Ladder 10ft -No. |  |  | 777748 | 2024-07-31 17:40 | Issue to IST | Non Returnable / Non Debitable | MORWADI COMMON | Transfer to Asset Store | 1 | 7099.79 | 7099.79 | 1170 | 8269.79 | No. | SRA MORWADI ASSETS STORE | 0 | yogesh-agarwal | 0
SRA MORWADI | Dewatering Pump 80WQ40-18-4 3HP -No. |  |  | 777749 | 2024-07-31 17:42 | Issue to IST | Non Returnable / Non Debitable | MORWADI COMMON | Transfer to Asset Store | 1 | 44621.56 | 44621.56 | 7903.18 | 52524.74 | No. | SRA MORWADI ASSETS STORE | 0 | yogesh-agarwal | 0
SRA MORWADI | Hammer Drill Machine -No. |  |  | 777751 | 2024-07-31 17:46 | Issue to IST | Non Returnable / Non Debitable | MORWADI COMMON | Transfer to Asset Store | 1 | 4999.94 | 4999.94 | 864 | 5863.94 | No. | SRA MORWADI ASSETS STORE | 0 | yogesh-agarwal | 0
SRA MORWADI | Hilti Outdoor Rotating Laser Level (PR 30 - HVS A12) -No. |  |  | 777752 | 2024-07-31 17:47 | Issue to IST | Non Returnable / Non Debitable | MORWADI COMMON | Transfer to Asset Store | 1 | 214459 | 214459 | 38602.62 | 253061.62 | No. | SRA MORWADI ASSETS STORE | 0 | yogesh-agarwal | 0
SRA MORWADI | Mannequin -No. |  |  | 777753 | 2024-07-31 17:49 | Issue to IST | Non Returnable / Non Debitable | MORWADI COMMON | Transfer to Asset Store | 1 | 5056.58 | 5056.58 | 889.2 | 5945.78 | No. | SRA MORWADI ASSETS STORE | 0 | yogesh-agarwal | 0
SRA MORWADI | KABIL Black Revolving Chair with Chrome Finish Legs -No. |  |  | 777754 | 2024-07-31 17:56 | Issue to IST | Non Returnable / Non Debitable | MORWADI COMMON |  | 5 | 3304 | 16520 | 0 | 16520 | No. | SRA MORWADI ASSETS STORE | 0 | yogesh-agarwal | 0
SRA MORWADI | Rectangle Plain Glass 10mm (1600x900) -No. |  |  | 777755 | 2024-07-31 17:59 | Issue to IST | Non Returnable / Non Debitable | MORWADI COMMON | Transfer to Asset Store | 6 | 2137.02 | 12822.12 | 0 | 12822.12 | No. | SRA MORWADI ASSETS STORE | 0 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 8mm -Kgs | KRISHNA CONSTRUCTION |  | 777759 | 2024-07-31 18:24 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24513 Date:-31.07.2024 | 805.8 | 62.47 | 50338.326 | 16.12 | 50354.446 | Kgs | A Building 4th Slab Non Str. wall steel | 186.08 | yogesh-agarwal | 0