## IssueRegister638582208519988056
Issue Register
From 02-08-2024 To 02-08-2024
Page 1 of 1
Total Records: 8 Records 1 to 8
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
SRA MORWADI | Steel Bars 16mm -Kgs | KRISHNA CONSTRUCTION |  | 778236 | 2024-08-02 11:56 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I.slip No.23089 Date : 02.08.2024. | 606.72 | 61.31 | 37198.0032 | 0 | 37198.0032 | Kgs | B1-Column Steel 2nd To 3rd Slab | 350.76 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 12mm -Kgs | KRISHNA CONSTRUCTION |  | 778242 | 2024-08-02 11:58 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I.Slip No.23089 Date : 02.08.2024. | 170.49 | 58.28 | 9936.1572 | 168.79 | 10104.9472 | Kgs | B1-Column Steel 2nd To 3rd Slab | 26.2 | yogesh-agarwal | 0
SRA MORWADI | Binding Wire -Kgs | KRISHNA CONSTRUCTIONS |  | 778254 | 2024-08-02 12:17 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I.slip No.23090 Date : 02.08.2024. | 12 | 68.28 | 819.36 | 145.8 | 965.16 | Kgs | B1-Column Steel 2nd To 3rd Slab | 3.77 | yogesh-agarwal | 0
SRA MORWADI | Sand-Metal Mix M25 (Pumpable) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 778514 | 2024-08-02 13:29 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23092 Date:-23092 Future India | 3.9 | 2866.53 | 11179.467 | 2012.24 | 13191.707 | Cu.Mtrs | B1-2nd Slab Column Up-to 2nd Slab concrete | 3.81 | yogesh-agarwal | 0
SRA MORWADI | Sand-Metal Mix M25 (Pumpable) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 778515 | 2024-08-02 13:34 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23091 Date:-02.08.2024 Future India | 50.1 | 2866.53 | 143613.153 | 25849.6 | 169462.753 | Cu.Mtrs | B1 -2nd Slab 2nd slab concrete | 0 | yogesh-agarwal | 0
SRA MORWADI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 778516 | 2024-08-02 13:35 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23091 Date:-02.08.2024 Future India | 14.529 | 5886.76 | 85528.736 | 23948.15 | 109476.886 | Metric Tonnes | B1 -2nd Slab 2nd slab concrete | 0 | yogesh-agarwal | 0
SRA MORWADI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 778517 | 2024-08-02 14:08 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23092 Date:-02.08.2024 Future India | 1.131 | 5886.76 | 6657.9256 | 1864.23 | 8522.1556 | Metric Tonnes | B1-2nd Slab Column Up-to 2nd Slab concrete | 2.739 | yogesh-agarwal | 0
SRA MORWADI | Halogen 200 Watt -No. | DEPARTMENT |  | 778635 | 2024-08-02 18:38 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.23179 Date:-02.08.2024 | 2 | 2636.79 | 5273.58 | 945.9 | 6219.48 | No. | Site Illumination/ Temporary Electrical Work Material | 28 | yogesh-agarwal | 0