## IssueRegister638590881731789837
Issue Register
From 12-08-2024 To 12-08-2024
Page 1 of 1
Total Records: 11 Records 1 to 11
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
GANGA ASMI | Nitobond SBR (Latex) -Ltrs | KRISHNA CONSTRUCTION |  | 780058 | 2024-08-12 11:35 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47352 DT: 12.08.2024 | 20 | 190 | 3800 | 684 | 4484 | Ltrs | Wing 1-12th Slab (6th Floor) Nitobond SBR For Concrete Joint | 20 | Shahu Nawale | 0
GANGA ASMI | Hose Clip 4" -No. | DEPARTMENT |  | 780059 | 2024-08-12 12:41 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48506 DT: 12.08.2024 | 2 | 28.97 | 57.94 | 4.84 | 62.78 | No. | MTBT form One Boat Club | 9 | Shahu Nawale | 0
GANGA ASMI | PVC Connector 4" -No. | DEPARTMENT |  | 780060 | 2024-08-12 12:42 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48506 DT: 12.08.2024 | 1 | 143.44 | 143.44 | 21.6 | 165.04 | No. | Dewatering & Curing Work | 27 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 12mm -Kgs | PURVA CONSTRUCTION |  | 780078 | 2024-08-12 14:58 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48507 DT: 12.08.2024 | 85 | 57.89 | 4920.65 | 0 | 4920.65 | Kgs | UGWT RCC Wall (Paradi) Steel | 9352.35 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 16mm -Kgs | PURVA CONSTRUCTION |  | 780079 | 2024-08-12 14:58 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48507 DT: 12.08.2024 | 76 | 58.42 | 4439.92 | 0 | 4439.92 | Kgs | UGWT RCC Wall (Paradi) Steel | 41284 | Shahu Nawale | 0
GANGA ASMI | Tape Roll -No. | DEPARTMENT |  | 780080 | 2024-08-12 15:00 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47354 DT: 12.08.2024 | 10 | 28.32 | 283.2 | 32.6 | 315.8 | No. | Wing-1 Aluform Misc. Consumables | 860 | Shahu Nawale | 0
GANGA ASMI | Hard Broom -No. | DEPARTMENT |  | 780081 | 2024-08-12 15:20 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47353 DT: 12.08.2024 | 3 | 44.51 | 133.53 | 0 | 133.53 | No. | Site Expenses Site Housekeeping | 12 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 8mm -Kgs | KRISHNA CONSTRUCTION |  | 780142 | 2024-08-12 18:10 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47357 DT: 12.08.2024 | 2417 | 59.65 | 144174.05 | 5220.72 | 149394.77 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 5749 | Shahu Nawale | 0
GANGA ASMI | Diesel -Ltrs | DEPARTMENT |  | 780148 | 2024-08-12 18:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47359 DT: 12.08.2024 | 100 | 91.52 | 9152 | 0 | 9152 | Ltrs | Diesel for DG Set-(Ltrs) | 4650 | Shahu Nawale | 0
GANGA ASMI | Binding Wire -Kgs | KRISHNA CONSTRUCTION |  | 780149 | 2024-08-12 18:34 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47357 DT: 12.08.2024 | 122.35 | 66.89 | 8183.9915 | 1382.56 | 9566.5515 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 213.65 | Shahu Nawale | 0
GANGA ASMI | Foam Sheet 50mm (1.4 mtr x 2mtr) -Sq.Ft | KRISHNA CONSTRUCTION |  | 780151 | 2024-08-12 19:11 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47351 DT: 12.08.2024 | 60.26 | 23.92 | 1441.4192 | 251.28 | 1692.6992 | Sq.Ft | Wing-1 Aluform Misc. Consumables | 2527.54 | Shahu Nawale | 0