## IssueRegister638592598659659798
Issue Register
From 14-08-2024 To 14-08-2024
Page 1 of 1
Total Records: 42 Records 1 to 42
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
GANGA ASMI | Insulation Tape -No. | DEPARTMENT |  | 780268 | 2024-08-14 11:49 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48031 DT: 14.08.2024 | 5 | 9.1 | 45.5 | 8.1 | 53.6 | No. | Electrical Work for Labour Camp in Wing 01 - 1 Job | 25 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 780271 | 2024-08-14 11:53 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48030 DT: 14.08.2024 | 0.6437 | 339.96 | 218.8323 | 0.04 | 218.8723 | Bags | Wing-1 Flat No 205 Int Flat Chemical Grouting Work | 0.2159 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | POONAM WATERPROOFING |  | 780272 | 2024-08-14 11:53 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48030 DT: 14.08.2024 | 1.3563 | 339.96 | 461.0877 | 0.08 | 461.1677 | Bags | Wing-1 Flat No 205 M.Toilet IPS W/P | 0 | Shahu Nawale | 0
GANGA ASMI | Coton Hand gloves -Pair | DEPARTMENT |  | 780273 | 2024-08-14 11:54 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45324 DT: 14.08.2024 | 4 | 14.16 | 56.64 | 2.8 | 59.44 | Pair | Lab & Safety Equipments Site Safety Material | 246 | Shahu Nawale | 0
GANGA ASMI | Diesel -Ltrs | DEPARTMENT |  | 780274 | 2024-08-14 11:58 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47363 DT: 14.08.2024 | 200 | 91.52 | 18304 | 0 | 18304 | Ltrs | Diesel for DG Set of Tower Crane | 13250 | Shahu Nawale | 0
GANGA ASMI | Cement Loose 53 Grade -Metric Tonnes | KSHITEEJ ENTERPRISES |  | 780278 | 2024-08-14 12:07 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45325 DT: 14.08.2024 | 2.304 | 5703.13 | 13140.0115 | 2365.19 | 15505.2015 | Metric Tonnes | Wing 2 P5 (4th Slab) to P6 (5th Slab) Column M50 | 79.8552 | Shahu Nawale | 0
GANGA ASMI | Sand-Metal Mix M50 hi-flow (Downpour) -Cu.Mtrs | KSHITEEJ ENTERPRISES |  | 780279 | 2024-08-14 12:07 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45325 DT: 14.08.2024 | 6 | 3305.68 | 19834.08 | 3570.12 | 23404.2 | Cu.Mtrs | Wing 2 P5 (4th Slab) to P6 (5th Slab) Column M50 | 222.22 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 10mm -Kgs | SAIRAJ CONSTRUCTION |  | 780294 | 2024-08-14 12:30 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48511 DT: 14.08.2024 | 1222 | 59.55 | 72770.1 | 1417.52 | 74187.62 | Kgs | Non Tower Area NTA 1st PT Slab (Wing 1) Steel | 2292.98 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 8mm -Kgs | SAIRAJ CONSTRUCTION |  | 780295 | 2024-08-14 12:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48509 DT: 14.08.2024 | 1450 | 59.54 | 86333 | 3306 | 89639 | Kgs | Non Tower Area Column Upto Plinth | 4345.05 | Shahu Nawale | 0
GANGA ASMI | Mcon NSA Grey (Gold) 50kg -Bags | PAPPU BAGELA |  | 780322 | 2024-08-14 14:34 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48032 DT: 14.08.2024 | 0.7388 | 769.08 | 568.1963 | 101.87 | 670.0663 | Bags | Wing .1 (3BHK) 201 Master Toilet Dado(Light) | 2.9053 | Shahu Nawale | 0
GANGA ASMI | Mcon NSA Grey (Gold) 50kg -Bags | PAPPU BAGELA |  | 780323 | 2024-08-14 14:34 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48032 DT: 14.08.2024 | 2.6001 | 769.08 | 1999.6849 | 358.5 | 2358.1849 | Bags | Wing .1 (3BHK)202 Utility .Dado (M) | 0 | Shahu Nawale | 0
GANGA ASMI | Mcon NSA Grey (Gold) 50kg -Bags | PAPPU BAGELA |  | 780324 | 2024-08-14 14:34 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48032 DT: 14.08.2024 | 2.6828 | 769.07 | 2063.261 | 369.93 | 2433.191 | Bags | Wing.1 (2BHK) Flat 208 Utility Dado (M) | 0 | Shahu Nawale | 0
GANGA ASMI | Mcon NSA Grey (Gold) 50kg -Bags | PAPPU BAGELA |  | 780325 | 2024-08-14 14:34 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48032 DT: 14.08.2024 | 2.9783 | 769.07 | 2290.5212 | 410.68 | 2701.2012 | Bags | Wing.1 (2BHK) Flat 209 Utility Dado (M) | 0 | Shahu Nawale | 0
GANGA ASMI | Binding Wire -Kgs | PURVA CONSTRUCTION |  | 780326 | 2024-08-14 14:41 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48512 DT: 14.08.2024 | 10 | 66.89 | 668.9 | 113 | 781.9 | Kgs | UGWT RCC Top Slab & Beam Steel | 110.55 | Shahu Nawale | 0
GANGA ASMI | Superwhite Tile 600 X 600 (DC) (AGL) -Sq.Ft | PAPPU BAGELA |  | 780329 | 2024-08-14 14:48 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48025 DT: 14.08.2024 | 697.5 | 38.13 | 26595.675 | 4791.83 | 31387.505 | Sq.Ft | Wing 1- 207 Flat Flooring | 13.63 | Shahu Nawale | 0
GANGA ASMI | Superwhite Tile 600 X 600 (DC) (AGL) -Sq.Ft | PAPPU BAGELA |  | 780330 | 2024-08-14 14:48 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48025 DT: 14.08.2024 | 527 | 38.13 | 20094.51 | 3620.49 | 23715 | Sq.Ft | Wing 1- 203 Flat Flooring | 4.83 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 12mm -Kgs | KSHITEEJ ENTERPRISES |  | 780331 | 2024-08-14 14:50 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45327 DT: 14.08.2024 | 1280 | 59.7 | 76416 | 0 | 76416 | Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | 2137.32 | Shahu Nawale | 0
GANGA ASMI | MS Sq. Pipe 40mmx40mmx16G- 20ft kg -Kgs | DEPARTMENT |  | 780333 | 2024-08-14 15:11 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45326 DT: 14.08.2024 (FOR WING-2) | 275 | 65.21 | 17932.75 | 3093.75 | 21026.5 | Kgs | Wing 1 - Window hard barrication work (Typical - 10 Floor) | 2120.4 | Shahu Nawale | 0
GANGA ASMI | Binding Wire -Kgs | SAIRAJ CONSTRUCTION |  | 780344 | 2024-08-14 16:04 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSSUE NO. 48513 DT: 14.08.2024 | 61.78 | 66.89 | 4132.4642 | 698.11 | 4830.5742 | Kgs | Non Tower Area Column 1st Slab P1 To 2nd Slab P2 Steel | 51.455 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | PAPPU BAGELA |  | 780345 | 2024-08-14 16:07 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSSUE NO. 48026 DT: 14.08.2024 | 0.122 | 339.96 | 41.4751 | 0.01 | 41.4851 | Bags | Wing 1- 202 Flat Flooring | 14 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | PAPPU BAGELA |  | 780346 | 2024-08-14 16:07 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSSUE NO. 48026 DT: 14.08.2024 | 10.6366 | 339.96 | 3616.0185 | 0.64 | 3616.6585 | Bags | Wing 1- 203 Flat Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | PAPPU BAGELA |  | 780347 | 2024-08-14 16:07 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSSUE NO. 48026 DT: 14.08.2024 | 0.8504 | 339.96 | 289.102 | 0.05 | 289.152 | Bags | Wing 1- 203 Balcony Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | PAPPU BAGELA |  | 780348 | 2024-08-14 16:07 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSSUE NO. 48026 DT: 14.08.2024 | 0.391 | 339.96 | 132.9244 | 0.02 | 132.9444 | Bags | Wing 1- 204 Toilet Flooring | 1.017 | Shahu Nawale | 0
GANGA ASMI | MS Sq. Pipe 40mmx40mmx16G- 20ft kg -Kgs | KRISHNA CONSTRUCTION |  | 780349 | 2024-08-14 16:08 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSSUE NO. 47362 DT: 14.08.2024 | 165 | 65.21 | 10759.65 | 1856.25 | 12615.9 | Kgs | Wing 1 - Window hard barrication work (Typical - 10 Floor) | 2230.4 | Shahu Nawale | 0
GANGA ASMI | Sunflex Sheet 6' X 4' X 2 mm Thk -No. | DEPARTMENT |  | 780350 | 2024-08-14 16:10 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSSUE NO. 47360 DT: 14.08.2024 | 2 | 89.47 | 178.94 | 14.02 | 192.96 | No. | Wing-1 Aluform Misc. Consumables | 868 | Shahu Nawale | 0
GANGA ASMI | Tape Roll -No. | DEPARTMENT |  | 780351 | 2024-08-14 16:11 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSSUE NO. 47360 DT: 14.08.2024 | 4 | 28.32 | 113.28 | 13.04 | 126.32 | No. | Wing-1 Aluform Misc. Consumables | 866 | Shahu Nawale | 0
GANGA ASMI | Safety Net 10mtr x 6mtr -Sq.m. | KRISHNA CONSTRUCTION |  | 780352 | 2024-08-14 16:23 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47361 DT: 14.08.2024 (FOR WING-1) | 600 | 81.05 | 48630 | 2640 | 51270 | Sq.m. | Lab & Safety Equipments Site Safety Material | 5100 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | DEPARTMENT |  | 780353 | 2024-08-14 16:30 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45323 DT: 14.08.2024 | 1 | 339.96 | 339.96 | 0.06 | 340.02 | Bags | Wing 2 . 4th Slab (P5 Lvl) Cement Slurry & Ponding | 19 | Shahu Nawale | 0
GANGA ASMI | PVC Tee 4" -No. | DEPARTMENT |  | 780377 | 2024-08-14 16:58 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48514 DT: 14.08.2024 | 1 | 88.33 | 88.33 | 15.73 | 104.06 | No. | New Labour Camp Plumbing work | 16 | Shahu Nawale | 0
GANGA ASMI | PVC Cone -No. | KRISHNA CONSTRUCTION |  | 780384 | 2024-08-14 17:10 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48029 DT: 14.08.2024 | 300 | 1.84 | 552 | 42 | 594 | No. | Wing-1 Aluform Misc. Consumables | 33300 | Shahu Nawale | 0
GANGA ASMI | Foam Sheet 3mm thk. (6.5x4) -Sq.Ft | KRISHNA CONSTRUCTION |  | 780387 | 2024-08-14 17:11 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48029 DT: 14.08.2024 | 172 | 1.34 | 230.48 | 0 | 230.48 | Sq.Ft | Wing-1 Aluform Misc. Consumables | 37138 | Shahu Nawale | 0
GANGA ASMI | Steel Bar 25mm -Kgs | KRISHNA CONSTRUCTION |  | 780388 | 2024-08-14 18:22 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48028 DT: 14.08.2024 | 463 | 59.88 | 27724.44 | 0 | 27724.44 | Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | 2840.13 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 12mm -Kgs | KRISHNA CONSTRUCTION |  | 780389 | 2024-08-14 18:22 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48028 DT: 14.08.2024 | 853 | 57.89 | 49380.17 | 0 | 49380.17 | Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | 2021.67 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 16mm -Kgs | KRISHNA CONSTRUCTION |  | 780390 | 2024-08-14 18:22 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48028 DT: 14.08.2024 | 758 | 58.42 | 44282.36 | 0 | 44282.36 | Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | 2117.28 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 10mm -Kgs | KRISHNA CONSTRUCTION |  | 780393 | 2024-08-14 18:28 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48027 DT: 14.08.2024 | 1629 | 59.06 | 96208.74 | 0 | 96208.74 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 1591 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 20mm -Kgs | KRISHNA CONSTRUCTION |  | 780394 | 2024-08-14 18:28 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48027 DT: 14.08.2024 | 3997 | 58.98 | 235743.06 | 0 | 235743.06 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 4178 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 32mm -Kgs | KRISHNA CONSTRUCTION |  | 780395 | 2024-08-14 18:28 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48027 DT: 14.08.2024 | 683 | 61.73 | 42161.59 | 0 | 42161.59 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 3413 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 8mm -Kgs | KRISHNA CONSTRUCTION |  | 780396 | 2024-08-14 18:28 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48027 DT: 14.08.2024 | 3223 | 59.89 | 193025.47 | 0 | 193025.47 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 4943 | Shahu Nawale | 0
GANGA ASMI | Cast Nylon Rod OD100MM x L200MM -No. | DEPARTMENT |  | 780398 | 2024-08-14 18:35 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47365 DT: 14.08.2024 | 5 | 598.5 | 2992.5 | 538.65 | 3531.15 | No. | Wing-1 Aluform Misc. Consumables Plumbing Sleeves | 31 | Shahu Nawale | 0
GANGA ASMI | Cast Nylon Rod OD110MM x L300MM -No. | DEPARTMENT |  | 780406 | 2024-08-14 18:39 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47365 DT: 14.08.2024 | 4 | 999 | 3996 | 719.28 | 4715.28 | No. | Wing-1 Aluform Misc. Consumables AC Sleeves | 19 | Shahu Nawale | 0
GANGA ASMI | Cast Nylon Rod OD50MM x L200MM -No. | DEPARTMENT |  | 780407 | 2024-08-14 18:39 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47365 DT: 14.08.2024 | 15 | 157.5 | 2362.5 | 425.25 | 2787.75 | No. | Wing-1 Aluform Misc. Consumables AC Sleeves | 21 | Shahu Nawale | 0
GANGA ASMI | Cast Nylon Rod OD50mm x L300mm -No. | DEPARTMENT |  | 780408 | 2024-08-14 18:39 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47365 DT: 14.08.2024 | 2 | 242.25 | 484.5 | 87.22 | 571.72 | No. | Wing-1 Aluform Misc. Consumables AC Sleeves | 8 | Shahu Nawale | 0