## IssueRegister638595155756357733
Issue Register
From 17-08-2024 To 17-08-2024
Page 1 of 1
Total Records: 40 Records 1 to 40
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
GANGA ASMI | Cement 43 Grade -Bags | PAPPU BAGELA |  | 780648 | 2024-08-17 10:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48036 DT: 17.08.2024 | 0.582 | 339.95 | 197.8509 | 0.04 | 197.8909 | Bags | Wing 1- 202 Toilet Flooring | 1 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | PAPPU BAGELA |  | 780649 | 2024-08-17 10:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48036 DT: 17.08.2024 | 0.6964 | 339.95 | 236.7412 | 0.05 | 236.7912 | Bags | Wing 1- 202 Utility Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | PAPPU BAGELA |  | 780650 | 2024-08-17 10:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48036 DT: 17.08.2024 | 0.624 | 339.95 | 212.1288 | 0.04 | 212.1688 | Bags | Wing 1- 204 Toilet Flooring | 0.784 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | PAPPU BAGELA |  | 780651 | 2024-08-17 10:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48036 DT: 17.08.2024 | 0.6802 | 339.95 | 231.234 | 0.05 | 231.284 | Bags | Wing 1- 206 Utility Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | PAPPU BAGELA |  | 780652 | 2024-08-17 10:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48036 DT: 17.08.2024 | 10.7442 | 339.95 | 3652.4908 | 0.75 | 3653.2408 | Bags | Wing 1- 208 Flat Flooring | 0 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | PAPPU BAGELA |  | 780653 | 2024-08-17 10:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48036 DT: 17.08.2024 | 0.8 | 339.95 | 271.96 | 0.06 | 272.02 | Bags | Wing 1- 208 Balcony Flooring | 0.0074 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | PAPPU BAGELA |  | 780654 | 2024-08-17 10:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48036 DT: 17.08.2024 | 0.8732 | 339.95 | 296.8443 | 0.06 | 296.9043 | Bags | Wing 1- 208 Toilet Flooring | 0.5348 | Shahu Nawale | 0
GANGA ASMI | Steel Bar 25mm -Kgs | KSHITEEJ ENTERPRISES |  | 780671 | 2024-08-17 11:45 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45328 DT: 17.08.2024 | 1389 | 59.88 | 83173.32 | 0 | 83173.32 | Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | 31.3 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 10mm -Kgs | KSHITEEJ ENTERPRISES |  | 780672 | 2024-08-17 11:45 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45328 DT: 17.08.2024 | 3665 | 59.06 | 216454.9 | 0 | 216454.9 | Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | 27.92 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 12mm -Kgs | KSHITEEJ ENTERPRISES |  | 780673 | 2024-08-17 11:45 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45328 DT: 17.08.2024 | 2134 | 57.89 | 123537.26 | 0 | 123537.26 | Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | 1283.32 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 16mm -Kgs | KSHITEEJ ENTERPRISES |  | 780674 | 2024-08-17 11:45 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45328 DT: 17.08.2024 | 3261 | 58.42 | 190507.62 | 0 | 190507.62 | Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | 35.98 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 20mm -Kgs | KSHITEEJ ENTERPRISES |  | 780675 | 2024-08-17 11:45 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45328 DT: 17.08.2024 | 2133 | 58.98 | 125804.34 | 0 | 125804.34 | Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | 1.36 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 8mm -Kgs | KSHITEEJ ENTERPRISES |  | 780676 | 2024-08-17 11:45 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45328 DT: 17.08.2024 | 7413 | 59.89 | 443964.57 | 0 | 443964.57 | Kgs | Wing 2 . 5th Slab (Staircase, Beam,Slab) Steel | 63 | Shahu Nawale | 0
GANGA ASMI | Diesel -Ltrs | DEPARTMENT |  | 780677 | 2024-08-17 11:53 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48035 DT: 17.08.2024 | 100 | 91.52 | 9152 | 0 | 9152 | Ltrs | Diesel for DG Set-(Ltrs) | 4650 | Shahu Nawale | 0
GANGA ASMI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 780683 | 2024-08-17 14:23 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47375 DT: 17.08.2024 | 3.52 | 5703.13 | 20075.0176 | 3613.49 | 23688.5076 | Metric Tonnes | Wing 1-11th Slab (5th Floor) Beam, Slab Stair. Concrete M-30 | 57.791 | Shahu Nawale | 0
GANGA ASMI | Sand-Metal Mix M30 hi-flow (Downpour) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 780684 | 2024-08-17 14:23 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47375 DT: 17.08.2024 | 16 | 3591.53 | 57464.48 | 10343.52 | 67808 | Cu.Mtrs | Wing 1-11th Slab (5th Floor) Beam, Slab Stair. Concrete M-30 | 20 | Shahu Nawale | 0
GANGA ASMI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 780685 | 2024-08-17 14:27 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47374 DT: 17.08.2024 | 11 | 5703.13 | 62734.43 | 11292.16 | 74026.59 | Metric Tonnes | Wing 1.12th Slab (6th Flr) Slab,Beam,Stair Con M30 | 38.049 | Shahu Nawale | 0
GANGA ASMI | Sand-Metal Mix M30 hi-flow (Pumpable) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 780686 | 2024-08-17 14:27 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47374 DT: 17.08.2024 | 50 | 3782.2 | 189110 | 34040 | 223150 | Cu.Mtrs | Wing 1.12th Slab (6th Flr) Slab,Beam,Stair Con M30 | 172.95 | Shahu Nawale | 0
GANGA ASMI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 780687 | 2024-08-17 14:29 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47373 DT: 17.08.2024 | 4.68 | 5703.13 | 26690.6484 | 4804.3 | 31494.9484 | Metric Tonnes | Wing 1.12th Slab (6th Floor) Column,LW,SW M.40 | 68.655 | Shahu Nawale | 0
GANGA ASMI | Sand-Metal Mix M40 hi-flow (Pumpable) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 780688 | 2024-08-17 14:29 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47373 DT: 17.08.2024 | 18 | 3782.2 | 68079.6 | 12254.4 | 80334 | Cu.Mtrs | Wing 1.12th Slab (6th Floor) Column,LW,SW M.40 | 264.06 | Shahu Nawale | 0
GANGA ASMI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 780689 | 2024-08-17 14:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47372 DT: 17.08.2024 | 17.16 | 5703.13 | 97865.7108 | 17615.77 | 115481.4808 | Metric Tonnes | Wing 1.12th Slab (6th Floor) Column,LW,SW M.40 | 56.175 | Shahu Nawale | 0
GANGA ASMI | Sand-Metal Mix M40 hi-flow (Pumpable) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 780690 | 2024-08-17 14:32 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47372 DT: 17.08.2024 | 66 | 3782.2 | 249625.2 | 44932.8 | 294558 | Cu.Mtrs | Wing 1.12th Slab (6th Floor) Column,LW,SW M.40 | 216.06 | Shahu Nawale | 0
GANGA ASMI | Helmet Yellow for Labours -No. | DEPARTMENT |  | 780692 | 2024-08-17 14:38 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47371 DT: 17.08.2024 (FOR RAMRAJ MAJI) | 1 | 139.22 | 139.22 | 24.3 | 163.52 | No. | Lab & Safety Equipments Site Safety Material | 64 | Shahu Nawale | 0
GANGA ASMI | Reflecting Jackets Red for Labours -No. | DEPARTMENT |  | 780693 | 2024-08-17 14:39 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47371 DT: 17.08.2024 (FOR RAMRAJ MAJI) | 1 | 50.62 | 50.62 | 3.54 | 54.16 | No. | Lab & Safety Equipments Site Safety Material | 44 | Shahu Nawale | 0
GANGA ASMI | Sunflex Sheet 6' X 4' X 2 mm Thk -No. | KRISHNA CONSTRUCTION |  | 780698 | 2024-08-17 16:40 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48038 DT: 17.08.2024 | 15 | 89.47 | 1342.05 | 105.15 | 1447.2 | No. | Wing-1 Aluform Misc. Consumables | 855 | Shahu Nawale | 0
GANGA ASMI | Safety Net 10mtr x 6mtr -Sq.m. | KRISHNA CONSTRUCTION |  | 780700 | 2024-08-17 16:41 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48038 DT: 17.08.2024 | 60 | 81.05 | 4863 | 264 | 5127 | Sq.m. | Lab & Safety Equipments Site Safety Material | 5640 | Shahu Nawale | 0
GANGA ASMI | PVC 4 way Deep junction Bx. 1" -No. | LAXMI ELECTRICALS |  | 780701 | 2024-08-17 16:48 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48521 DT: 17.08.2024 | 30 | 28.6 | 858 | 154.5 | 1012.5 | No. | NTA 1st Slab Electrical Work | 10 | Shahu Nawale | 0
GANGA ASMI | PVC Conduit Pipe 1" mtrs -Mtrs | LAXMI ELECTRICALS |  | 780702 | 2024-08-17 16:48 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48521 DT: 17.08.2024 | 267 | 18.56 | 4955.52 | 891.78 | 5847.3 | Mtrs | NTA 1st Slab Electrical Work | 33 | Shahu Nawale | 0
GANGA ASMI | PVC Conduit Socket 1" -No. | LAXMI ELECTRICALS |  | 780703 | 2024-08-17 16:48 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48521 DT: 17.08.2024 | 20 | 2.65 | 53 | 9.6 | 62.6 | No. | NTA 1st Slab Electrical Work | 80 | Shahu Nawale | 0
GANGA ASMI | PVC Solvent (250 ml.) Elect. - -No. | LAXMI ELECTRICALS |  | 780704 | 2024-08-17 16:48 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48521 DT: 17.08.2024 | 2 | 53 | 106 | 19.08 | 125.08 | No. | NTA 1st Slab Electrical Work | 0 | Shahu Nawale | 0
GANGA ASMI | Binding Wire -Kgs | PURVA CONSTRUCTION |  | 780705 | 2024-08-17 16:56 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48520 DT: 17.08.2024 | 11.62 | 66.89 | 777.2618 | 131.31 | 908.5718 | Kgs | UGWT RCC Top Slab & Beam Steel | 108.93 | Shahu Nawale | 0
GANGA ASMI | Binding Wire -Kgs | KRISHNA CONSTRUCTION |  | 780724 | 2024-08-17 17:03 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48799 DT: 17.08.2024 | 118.34 | 66.89 | 7915.7626 | 1337.24 | 9253.0026 | Kgs | Wing 1-6th Floor To 7th Floor Column, LW Steel | 217.66 | Shahu Nawale | 0
GANGA ASMI | MS Plank 2400x300mm -No. | KRISHNA CONSTRUCTION |  | 780725 | 2024-08-17 17:17 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47377 DT: 17.08.2024 | 18 | 1521.35 | 27384.3 | 4892.4 | 32276.7 | No. | Wing-1 Aluform Misc. Consumables | 722 | Shahu Nawale | 0
GANGA ASMI | Cement Loose 53 Grade -Metric Tonnes | KSHITEEJ ENTERPRISES |  | 780726 | 2024-08-17 17:20 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45329 DT: 17.08.2024 | 2.1 | 5703.13 | 11976.573 | 2155.78 | 14132.353 | Metric Tonnes | Wing 2 P5 (4th Slab) to P6 (5th Slab) Column M50 | 80.0592 | Shahu Nawale | 0
GANGA ASMI | Sand-Metal Mix M50 hi-flow (Downpour) -Cu.Mtrs | KSHITEEJ ENTERPRISES |  | 780727 | 2024-08-17 17:20 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45329 DT: 17.08.2024 | 6 | 3591.53 | 21549.18 | 3878.82 | 25428 | Cu.Mtrs | Wing 2 P5 (4th Slab) to P6 (5th Slab) Column M50 | 222.22 | Shahu Nawale | 0
GANGA ASMI | Safari (9' x 4') -set | DEPARTMENT |  | 780728 | 2024-08-17 18:05 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46747 DT: 17.08.2024 | 6 | 1350 | 8100 | 405 | 8505 | set | Uniform Material | 2 | Shahu Nawale | 0
GANGA ASMI | Room Freshner -No. | DEPARTMENT |  | 780733 | 2024-08-17 18:16 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46748 DT: 17.08.2024 | 10 | 50 | 500 | 90 | 590 | No. | Material required for GH | 36 | Shahu Nawale | 0
GANGA ASMI | Ultra Soft & smooth Foam Soap 1000ml -No. | DEPARTMENT |  | 780734 | 2024-08-17 18:16 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46748 DT: 17.08.2024 | 12 | 270 | 3240 | 583.2 | 3823.2 | No. | Material required for GH | 72 | Shahu Nawale | 0
GANGA ASMI | Toilet Paper Roll -ROLL | DEPARTMENT |  | 780735 | 2024-08-17 18:18 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46748 DT: 17.08.2024 | 24 | 16 | 384 | 69.12 | 453.12 | ROLL | Material required for GH | 72 | Shahu Nawale | 0
GANGA ASMI | Keep Kleen Aerosol 100ml Refills -No. | DEPARTMENT |  | 780736 | 2024-08-17 18:18 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 46748 DT: 17.08.2024 | 12 | 300 | 3600 | 648 | 4248 | No. | Material required for GH | 54 | Shahu Nawale | 0