## IssueRegister638597782254960676
Issue Register
From 20-08-2024 To 20-08-2024
Page 1 of 1
Total Records: 28 Records 1 to 28
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
GANGA ASMI | Tape Roll -No. | HIGHRISE CONSTRUCTION COMPANY |  | 780958 | 2024-08-20 11:10 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47381 DT: 20.08.2024 | 1 | 28.32 | 28.32 | 3.26 | 31.58 | No. | Wing-1 Aluform Misc. Consumables | 869 | Shahu Nawale | 0
GANGA ASMI | Sunflex Sheet 6' X 4' X 2 mm Thk -No. | KRISHNA CONSTRUCTION |  | 780959 | 2024-08-20 11:11 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47381 DT: 20.08.2024 | 10 | 89.47 | 894.7 | 70.1 | 964.8 | No. | Wing-1 Aluform Misc. Consumables | 860 | Shahu Nawale | 0
GANGA ASMI | PVC Conduit Pipe 1" mtrs -Mtrs | DEPARTMENT |  | 780969 | 2024-08-20 11:21 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45332 DT: 20.08.2024 | 30 | 22.34 | 670.2 | 0 | 670.2 | Mtrs | New Labour Camp Electrical Mat. (Wing 2) | 270 | Shahu Nawale | 0
GANGA ASMI | PVC 4 way junction Box. 1" -No. | DEPARTMENT |  | 780971 | 2024-08-20 11:23 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 45332 DT: 20.08.2024 | 10 | 11.38 | 113.8 | 19.6 | 133.4 | No. | Labour Camp Electrical Work | 26 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | KRISHNA CONSTRUCTION |  | 780972 | 2024-08-20 12:06 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47385 DT: 20.08.2024 | 3 | 339.95 | 1019.85 | 0.21 | 1020.06 | Bags | Wing 1-12th Slab (6th Floor) Cement For Misc Work | 32 | Shahu Nawale | 0
GANGA ASMI | Cement 43 Grade -Bags | KSHITEEJ ENTERPRISES |  | 780973 | 2024-08-20 12:37 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48800 DT: 20.08.2024 | 2 | 339.95 | 679.9 | 0.14 | 680.04 | Bags | Wing 2 . 2nd Slab (P3 Lvl) Cement Slurry & Ponding | 18 | Shahu Nawale | 0
GANGA ASMI | Steel Bar 25mm -Kgs | KRISHNA CONSTRUCTION |  | 780981 | 2024-08-20 15:05 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47387 DT: 20.08.2024 | 2315 | 59.88 | 138622.2 | 0 | 138622.2 | Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | 1666 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 10mm -Kgs | KRISHNA CONSTRUCTION |  | 780982 | 2024-08-20 15:05 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47387 DT: 20.08.2024 | 733 | 59.06 | 43290.98 | 0 | 43290.98 | Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | 2549 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 12mm -Kgs | KRISHNA CONSTRUCTION |  | 780983 | 2024-08-20 15:05 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47387 DT: 20.08.2024 | 2134 | 57.89 | 123537.26 | 0 | 123537.26 | Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | 734 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 16mm -Kgs | KRISHNA CONSTRUCTION |  | 780984 | 2024-08-20 15:05 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47387 DT: 20.08.2024 | 2275 | 58.42 | 132905.5 | 0 | 132905.5 | Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | 1347 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 20mm -Kgs | KRISHNA CONSTRUCTION |  | 780985 | 2024-08-20 15:05 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47387 DT: 20.08.2024 | 2222 | 58.98 | 131053.56 | 0 | 131053.56 | Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | 5328 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 32mm -Kgs | KRISHNA CONSTRUCTION |  | 780986 | 2024-08-20 15:05 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47387 DT: 20.08.2024 | 1213 | 61.73 | 74878.49 | 0 | 74878.49 | Kgs | Wing 1-7th Floor To 8th Floor Column, LW Steel | 1821 | Shahu Nawale | 0
GANGA ASMI | PPR-C Brass MTA 20mm -No. | PRASNA PLUMBING SERVICE |  | 780987 | 2024-08-20 15:07 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48048 DT: 20.08.2024 | 8 | 45.02 | 360.16 | 64.8 | 424.96 | No. | Flat -201 Wing-1- PPRC -Internal Plumbing Work (M) | 0 | Shahu Nawale | 0
GANGA ASMI | CP Flush Valve FLV-CHR-1085N -No. | PRASNA PLUMBING SERVICE |  | 780988 | 2024-08-20 15:09 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48049 DT: 20.08.2024 | 1 | 2683.23 | 2683.23 | 0 | 2683.23 | No. | CP Material | 1 | Shahu Nawale | 0
GANGA ASMI | CP Flush Valve FLV-CHR-1085N -No. | PRASNA PLUMBING SERVICE |  | 780989 | 2024-08-20 15:09 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48049 DT: 20.08.2024 | 1 | 2683.23 | 2683.23 | 0 | 2683.23 | No. | CP Material | 1 | Shahu Nawale | 0
GANGA ASMI | Concealed body for single lever diverter ALD-CHR-065M -No. | PRASNA PLUMBING SERVICE |  | 780990 | 2024-08-20 15:11 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48049 DT: 20.08.2024 | 1 | 1871.99 | 1871.99 | 0 | 1871.99 | No. | CP Material | 1 | Shahu Nawale | 0
GANGA ASMI | Concealed body for single lever diverter ALD-CHR-065M -No. | PRASNA PLUMBING SERVICE |  | 780991 | 2024-08-20 15:11 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 48049 DT: 20.08.2024 | 1 | 1871.99 | 1871.99 | 0 | 1871.99 | No. | CP Material | 1 | Shahu Nawale | 0
GANGA ASMI | Binding Wire -Kgs | KRISHNA CONSTRUCTION |  | 780992 | 2024-08-20 15:56 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47386 DT: 20.08.2024 | 51 | 64 | 3264 | 587.52 | 3851.52 | Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | 200.8 | Shahu Nawale | 0
GANGA ASMI | Steel Bar 25mm -Kgs | KRISHNA CONSTRUCTION |  | 780993 | 2024-08-20 15:56 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47386 DT: 20.08.2024 | 47 | 59.88 | 2814.36 | 0 | 2814.36 | Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | 3256.13 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 10mm -Kgs | KRISHNA CONSTRUCTION |  | 780994 | 2024-08-20 15:56 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47386 DT: 20.08.2024 | 1710 | 59.06 | 100992.6 | 0 | 100992.6 | Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | 1653.91 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 12mm -Kgs | KRISHNA CONSTRUCTION |  | 780995 | 2024-08-20 15:56 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47386 DT: 20.08.2024 | 256 | 57.89 | 14819.84 | 0 | 14819.84 | Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | 2618.67 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 16mm -Kgs | KRISHNA CONSTRUCTION |  | 780996 | 2024-08-20 15:56 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47386 DT: 20.08.2024 | 531 | 58.42 | 31021.02 | 0 | 31021.02 | Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | 2344.28 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 20mm -Kgs | KRISHNA CONSTRUCTION |  | 780997 | 2024-08-20 15:56 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47386 DT: 20.08.2024 | 800 | 58.98 | 47184 | 0 | 47184 | Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | 3146.33 | Shahu Nawale | 0
GANGA ASMI | Steel Bars 8mm -Kgs | KRISHNA CONSTRUCTION |  | 780998 | 2024-08-20 15:56 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47386 DT: 20.08.2024 | 3223 | 59.89 | 193025.47 | 0 | 193025.47 | Kgs | Wing 1-13th Slab (7th Floor) Slab,Beam,Stair. Steel | 5043.88 | Shahu Nawale | 0
GANGA ASMI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 780999 | 2024-08-20 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47384 DT: 20.08.2024 | 5.28 | 5703.13 | 30112.5264 | 8431.47 | 38543.9964 | Metric Tonnes | Wing 1.12th Slab (6th Flr) Slab,Beam,Stair Con M30 | 43.769 | Shahu Nawale | 0
GANGA ASMI | Sand-Metal Mix M30 hi-flow (Pumpable) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 781000 | 2024-08-20 16:14 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47384 DT: 20.08.2024 | 24 | 3782.2 | 90772.8 | 16339.2 | 107112 | Cu.Mtrs | Wing 1.12th Slab (6th Flr) Slab,Beam,Stair Con M30 | 198.95 | Shahu Nawale | 0
GANGA ASMI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 781001 | 2024-08-20 16:50 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47383 DT: 20.08.2024 | 12.48 | 5703.13 | 71175.0624 | 19928.94 | 91104.0024 | Metric Tonnes | Wing 1.12th Slab (6th Floor) Column,LW,SW M.40 | 60.855 | Shahu Nawale | 0
GANGA ASMI | Sand-Metal Mix M40 hi-flow (Pumpable) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 781002 | 2024-08-20 16:50 | Issue to Task | Non Returnable / Non Debitable | WAKAD COMMON STORE | ISSUE NO. 47383 DT: 20.08.2024 | 48 | 3782.2 | 181545.6 | 32678.4 | 214224 | Cu.Mtrs | Wing 1.12th Slab (6th Floor) Column,LW,SW M.40 | 234.06 | Shahu Nawale | 0