## IssueRegister638600885951130565
Issue Register
From 23-08-2024 To 24-08-2024
Page 1 of 1
Total Records: 11 Records 1 to 11
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
SRA MORWADI | PVC Conduit Pipe 1" mtrs -Mtrs | TAHA ELECTRICALS |  | 781440 | 2024-08-23 15:11 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | Issue slip No.24714 Dated 23.08.2024. | 450 | 19.07 | 8581.5 | 1543.5 | 10125 | Mtrs | Slab 4 Internal Electrical Work (M) | 636 | yogesh-agarwal | 0
SRA MORWADI | Binding Wire -Kgs | KRISHNA CONSTRUCTION |  | 781548 | 2024-08-23 18:10 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24713 Date:-23.08.2024 | 55 | 65.9 | 3624.5 | 645.15 | 4269.65 | Kgs | B Bldg 4th Slab Column,Lift wall,S/wall Steel | 187.76 | yogesh-agarwal | 0
SRA MORWADI | Potato Greece -Kgs | KRISHNA CONSTRUCTION |  | 781549 | 2024-08-23 18:16 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25626 Date:-23.08.2024 | 15 | 133 | 1995 | 359.1 | 2354.1 | Kgs | A Bldg Aluform Misc. Consumable | 804 | yogesh-agarwal | 0
SRA MORWADI | Shuttering oil-oil based -Ltrs | KRISHNA CONSTRUCTION |  | 781550 | 2024-08-23 18:17 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25626 Date:-23.08.2024 | 15 | 145 | 2175 | 391.5 | 2566.5 | Ltrs | A Bldg Aluform Misc. Consumable | 690 | yogesh-agarwal | 0
SRA MORWADI | PVC 2 way Deep junction Bx. 1" -No. | TAHA ELECTRICALS |  | 781551 | 2024-08-23 18:28 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24714 Date:-23.08.2024 | 26 | 12.61 | 327.86 | 47.06 | 374.92 | No. | B BUILDING 3RD Floor | 6 | yogesh-agarwal | 0
SRA MORWADI | PVC 4 way Deep junction Bx. 1" -No. | TAHA ELECTRICALS |  | 781552 | 2024-08-23 18:29 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24714 Date:-23.08.2024 | 10 | 16.23 | 162.3 | 27.2 | 189.5 | No. | B BUILDING 3RD Floor | 1 | yogesh-agarwal | 0
SRA MORWADI | PVC 3 way Deep junction Bx. 1" -No. | TAHA ELECTRICALS |  | 781553 | 2024-08-23 18:33 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24714 Date:-23.08.2024 | 20 | 19.71 | 394.2 | 8 | 402.2 | No. | B BUILDING 3RD Floor | 38 | yogesh-agarwal | 0
SRA MORWADI | PVC Solvent (250 ml.) Elect. - -No. | TAHA ELECTRICALS |  | 781554 | 2024-08-23 18:34 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24714 Date:-23.08.2024 | 4 | 55.07 | 220.28 | 36.32 | 256.6 | No. | B BUILDING 3RD Floor | 1 | yogesh-agarwal | 0
SRA MORWADI | Tape Roll -No. | TAHA ELECTRICALS |  | 781557 | 2024-08-23 18:36 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24714 Date:-23.08.2024 | 5 | 26.28 | 131.4 | 23.4 | 154.8 | No. | B BUILDING 3RD Floor | 0 | yogesh-agarwal | 0
SRA MORWADI | Tape Roll -No. | TAHA ELECTRICALS |  | 781558 | 2024-08-23 18:36 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24714 Date:-23.08.2024 | 3 | 26.28 | 78.84 | 14.04 | 92.88 | No. | B1 Bldg 2nd Slab | 2 | yogesh-agarwal | 0
SRA MORWADI | Water Jar (20 lit) -No. | TAHA ELECTRICALS |  | 781559 | 2024-08-23 18:46 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24868 Date:-23.08.2024 | 1 | 35 | 35 | 0 | 35 | No. | Site Office Drinking Water Jar | 369 | yogesh-agarwal | 0