## IssueRegister638602623416422515
Issue Register
From 24-08-2024 To 26-08-2024
Page 1 of 1
Total Records: 68 Records 1 to 68
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
SRA MORWADI | Steel Bars 8mm -Kgs | KRISHNA CONSTRUCTION |  | 781656 | 2024-08-24 17:07 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24542 Date:-24.08.2024 | 805.8 | 62.48 | 50346.384 | 8.06 | 50354.444 | Kgs | A Bldg 5th Slab,Beam &amp; Staircase Steel Work | 6675.87 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 16mm -Kgs | KRISHNA CONSTRUCTION |  | 781657 | 2024-08-24 17:07 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24542 Date:-24.08.2024 | 1516.8 | 61.31 | 92995.008 | 0 | 92995.008 | Kgs | A Bldg 5th Slab,Beam &amp; Staircase Steel Work | 1583.2 | yogesh-agarwal | 0
SRA MORWADI | 12 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781658 | 2024-08-24 17:09 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 108.86 | 217.72 | 24.3 | 242.02 | No. | A-Flat No 402 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 12 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781659 | 2024-08-24 17:09 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 108.86 | 217.72 | 24.3 | 242.02 | No. | A-Flat No 403 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 12 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781660 | 2024-08-24 17:09 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 108.86 | 217.72 | 24.3 | 242.02 | No. | A-Flat No 404 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 12 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781661 | 2024-08-24 17:09 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 108.86 | 217.72 | 24.3 | 242.02 | No. | A-Flat No 411 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 12 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781662 | 2024-08-24 17:09 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 108.86 | 217.72 | 24.3 | 242.02 | No. | A-Flat No 412 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 12 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781663 | 2024-08-24 17:09 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 108.86 | 217.72 | 24.3 | 242.02 | No. | A-Flat No 413 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 8 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781664 | 2024-08-24 17:16 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 91.69 | 183.38 | 20.64 | 204.02 | No. | A-Flat No 402 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 8 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781665 | 2024-08-24 17:16 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 91.69 | 183.38 | 20.64 | 204.02 | No. | A-Flat No 403 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 8 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781666 | 2024-08-24 17:16 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 91.69 | 183.38 | 20.64 | 204.02 | No. | A-Flat No 404 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 8 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781667 | 2024-08-24 17:16 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 91.69 | 183.38 | 20.64 | 204.02 | No. | A-Flat No 411 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 8 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781668 | 2024-08-24 17:16 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 91.69 | 183.38 | 20.64 | 204.02 | No. | A-Flat No 412 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 8 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781669 | 2024-08-24 17:16 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 91.69 | 183.38 | 20.64 | 204.02 | No. | A-Flat No 413 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 6 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781670 | 2024-08-24 17:18 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 69.26 | 138.52 | 13.48 | 152 | No. | A-Flat No 402 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 6 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781671 | 2024-08-24 17:18 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 69.26 | 138.52 | 13.48 | 152 | No. | A-Flat No 403 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 6 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781672 | 2024-08-24 17:18 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 69.26 | 138.52 | 13.48 | 152 | No. | A-Flat No 404 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 6 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781673 | 2024-08-24 17:18 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 69.26 | 138.52 | 13.48 | 152 | No. | A-Flat No 411 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 6 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781674 | 2024-08-24 17:18 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 69.26 | 138.52 | 13.48 | 152 | No. | A-Flat No 412 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 6 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781675 | 2024-08-24 17:18 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 69.26 | 138.52 | 13.48 | 152 | No. | A-Flat No 413 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 4 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781676 | 2024-08-24 17:21 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 1 | 55.14 | 55.14 | 6.55 | 61.69 | No. | A-Flat No 402 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 4 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781677 | 2024-08-24 17:21 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 1 | 55.14 | 55.14 | 6.55 | 61.69 | No. | A-Flat No 403 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 4 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781678 | 2024-08-24 17:21 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 1 | 55.14 | 55.14 | 6.55 | 61.69 | No. | A-Flat No 404 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 4 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781679 | 2024-08-24 17:21 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 1 | 55.14 | 55.14 | 6.55 | 61.69 | No. | A-Flat No 411 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 4 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781680 | 2024-08-24 17:21 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 1 | 55.14 | 55.14 | 6.55 | 61.69 | No. | A-Flat No 412 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 4 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781681 | 2024-08-24 17:21 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 1 | 55.14 | 55.14 | 6.55 | 61.69 | No. | A-Flat No 413 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 3 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781682 | 2024-08-24 17:22 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 43.68 | 87.36 | 12.62 | 99.98 | No. | A-Flat No 402 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 3 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781683 | 2024-08-24 17:22 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 43.68 | 87.36 | 12.62 | 99.98 | No. | A-Flat No 403 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 3 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781684 | 2024-08-24 17:22 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 43.68 | 87.36 | 12.62 | 99.98 | No. | A-Flat No 404 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 3 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781685 | 2024-08-24 17:22 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 43.68 | 87.36 | 12.62 | 99.98 | No. | A-Flat No 411 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 3 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781686 | 2024-08-24 17:22 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 43.68 | 87.36 | 12.62 | 99.98 | No. | A-Flat No 412 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 3 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781687 | 2024-08-24 17:22 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 2 | 43.68 | 87.36 | 12.62 | 99.98 | No. | A-Flat No 413 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 2 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781688 | 2024-08-24 17:24 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 31.72 | 95.16 | 11.64 | 106.8 | No. | A-Flat No 402 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 2 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781689 | 2024-08-24 17:24 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 31.72 | 95.16 | 11.64 | 106.8 | No. | A-Flat No 403 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 2 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781690 | 2024-08-24 17:24 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 31.72 | 95.16 | 11.64 | 106.8 | No. | A-Flat No 404 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 2 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781691 | 2024-08-24 17:24 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 31.72 | 95.16 | 11.64 | 106.8 | No. | A-Flat No 411 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 2 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781692 | 2024-08-24 17:24 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 31.72 | 95.16 | 11.64 | 106.8 | No. | A-Flat No 412 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 2 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781693 | 2024-08-24 17:24 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 31.72 | 95.16 | 11.64 | 106.8 | No. | A-Flat No 413 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | Tape Roll -No. | TAHA ELECTRICALS |  | 781694 | 2024-08-24 17:26 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 26.28 | 78.84 | 14.04 | 92.88 | No. | A-Flat No 402 Electrical Work | 5 | yogesh-agarwal | 0
SRA MORWADI | Tape Roll -No. | TAHA ELECTRICALS |  | 781695 | 2024-08-24 17:26 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 26.28 | 78.84 | 14.04 | 92.88 | No. | A-Flat No 403 Electrical Work | 5 | yogesh-agarwal | 0
SRA MORWADI | Tape Roll -No. | TAHA ELECTRICALS |  | 781696 | 2024-08-24 17:26 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 26.28 | 78.84 | 14.04 | 92.88 | No. | A-Flat No 404 Electrical Work | 5 | yogesh-agarwal | 0
SRA MORWADI | Tape Roll -No. | TAHA ELECTRICALS |  | 781697 | 2024-08-24 17:26 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 26.28 | 78.84 | 14.04 | 92.88 | No. | A-Flat No 411 Electrical Work | 5 | yogesh-agarwal | 0
SRA MORWADI | Tape Roll -No. | TAHA ELECTRICALS |  | 781698 | 2024-08-24 17:26 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 26.28 | 78.84 | 14.04 | 92.88 | No. | A-Flat No 412 Electrical Work | 5 | yogesh-agarwal | 0
SRA MORWADI | Tape Roll -No. | TAHA ELECTRICALS |  | 781699 | 2024-08-24 17:26 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25632 Date:-24.08.2024 | 3 | 26.28 | 78.84 | 14.04 | 92.88 | No. | A-Flat No 413 Electrical Work | 5 | yogesh-agarwal | 0
SRA MORWADI | Tape Roll -No. | TAHA ELECTRICALS |  | 781700 | 2024-08-24 17:27 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 2 | 26.28 | 52.56 | 9.36 | 61.92 | No. | A-Flat No 401 Electrical Work | 6 | yogesh-agarwal | 0
SRA MORWADI | Tape Roll -No. | TAHA ELECTRICALS |  | 781701 | 2024-08-24 17:27 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 2 | 26.28 | 52.56 | 9.36 | 61.92 | No. | A-Flat No 414 Electrical Work | 6 | yogesh-agarwal | 0
SRA MORWADI | 12 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781702 | 2024-08-24 17:29 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 2 | 108.86 | 217.72 | 24.3 | 242.02 | No. | A-Flat No 401 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 12 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781703 | 2024-08-24 17:29 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 2 | 108.86 | 217.72 | 24.3 | 242.02 | No. | A-Flat No 414 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 8 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781704 | 2024-08-24 17:30 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 2 | 91.69 | 183.38 | 20.64 | 204.02 | No. | A-Flat No 401 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 8 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781705 | 2024-08-24 17:30 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 2 | 91.69 | 183.38 | 20.64 | 204.02 | No. | A-Flat No 414 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 6 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781706 | 2024-08-24 17:31 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 2 | 69.26 | 138.52 | 13.48 | 152 | No. | A-Flat No 401 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 6 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781707 | 2024-08-24 17:31 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 2 | 69.26 | 138.52 | 13.48 | 152 | No. | A-Flat No 414 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 4 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781708 | 2024-08-24 17:32 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 1 | 55.14 | 55.14 | 6.55 | 61.69 | No. | A-Flat No 401 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 4 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781709 | 2024-08-24 17:32 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 1 | 55.14 | 55.14 | 6.55 | 61.69 | No. | A-Flat No 414 Electrical Work | 0 | yogesh-agarwal | 0
SRA MORWADI | 3 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781710 | 2024-08-24 17:33 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 2 | 43.68 | 87.36 | 12.62 | 99.98 | No. | A-Flat No 401 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 3 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781711 | 2024-08-24 17:33 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 2 | 43.68 | 87.36 | 12.62 | 99.98 | No. | A-Flat No 414 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 2 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781712 | 2024-08-24 17:34 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 3 | 31.72 | 95.16 | 11.64 | 106.8 | No. | A-Flat No 401 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | 2 Module GI Concealed Box -No. | TAHA ELECTRICALS |  | 781713 | 2024-08-24 17:34 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25631 Date:-24.08.2024 | 3 | 31.72 | 95.16 | 11.64 | 106.8 | No. | A-Flat No 414 Electrical Work | 1 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 16mm -Kgs | KRISHNA CONSTRUCTION |  | 781714 | 2024-08-24 17:43 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24716 Date:-24.08.2024 | 530.88 | 61.31 | 32548.2528 | 0 | 32548.2528 | Kgs | B Bldg 4th Slab,Beam & Staircase Steel | 2354.36 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 8mm -Kgs | KRISHNA CONSTRUCTION |  | 781715 | 2024-08-24 17:46 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24716 Date:-24.08.2024 | 402.9 | 62.48 | 25173.192 | 4.03 | 25177.222 | Kgs | B Bldg 4th Slab Column,Lift wall,S/wall Steel | 3478.97 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 20mm -Kgs | KRISHNA CONSTRUCTION |  | 781716 | 2024-08-24 17:49 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24716 Date:-24.08.2024 | 37.72 | 60.76 | 2291.8672 | 4.9 | 2296.7672 | Kgs | B Bldg 4th Slab Column,Lift wall,S/wall Steel | 6029.84 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 20mm -Kgs | KRISHNA CONSTRUCTION |  | 781717 | 2024-08-24 17:49 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24716 Date:-24.08.2024 | 406.68 | 60.76 | 24709.8768 | 52.87 | 24762.7468 | Kgs | B Bldg 4th Slab,Beam & Staircase Steel | 888.8 | yogesh-agarwal | 0
SRA MORWADI | Steel Bar 25mm -Kgs | KRISHNA CONSTRUCTION |  | 781718 | 2024-08-24 17:52 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24716 Date:-24.08.2024 | 255.48 | 41.61 | 10630.5228 | 4866.89 | 15497.4128 | Kgs | B - Bldg H/2 Column 2nd to 3rd Slab | 270.37 | yogesh-agarwal | 0
SRA MORWADI | Steel Bar 25mm -Kgs | KRISHNA CONSTRUCTION |  | 781719 | 2024-08-24 17:52 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24716 Date:-24.08.2024 | 114.82 | 40.98 | 4705.3236 | 2259.66 | 6964.9836 | Kgs | B Bldg 4th Slab Column,Lift wall,S/wall Steel | 694.44 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 12mm -Kgs | KRISHNA CONSTRUCTION |  | 781720 | 2024-08-24 17:54 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24717 Date:-24.08.2024 | 170.496 | 58.41 | 9958.6714 | 146.63 | 10105.3014 | Kgs | B Bldg 4th Slab,Beam & Staircase Steel | 1834.334 | yogesh-agarwal | 0
SRA MORWADI | Safety Net 10mtr x 6mtr -Sq.m. | KRISHNA CONSTRUCTION |  | 781721 | 2024-08-24 17:55 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25628 Date:-24.08.2024 | 240 | 78.49 | 18837.6 | 936 | 19773.6 | Sq.m. | Safety Setup -Safety PPE & Equipments | 1380 | yogesh-agarwal | 0
SRA MORWADI | MS Square Pipe 40mmx40mmx1.6mm -Mtrs | KRISHNA CONSTRUCTION |  | 781724 | 2024-08-24 18:04 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25628 Date:-24.08.2024 | 195 | 128.24 | 25006.8 | 4387.5 | 29394.3 | Mtrs | Material For Store,Office & Labour camp | 591 | yogesh-agarwal | 0
SRA MORWADI | PP Rope 4mm Dia. -Kgs | KRISHNA CONSTRUCTION |  | 781725 | 2024-08-24 18:06 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25628 Date:-24.08.2024 | 6 | 160.26 | 961.56 | 112.86 | 1074.42 | Kgs | Safety Setup Safety Material for Labours | 24 | yogesh-agarwal | 0