## IssueRegister638603545090617244
Issue Register
From 20-08-2024 To 27-08-2024
Page 1 of 1
Total Records: 6 Records 1 to 6
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
GANGA ALTUS | Steel Bars 16mm -Kgs | UPRISEN CONSTRUCTION |  | 780951 | 2024-08-20 11:01 | Issue to Task | Non Returnable / Non Debitable | ALTUS CENTRAL STORE | ISSUE NO.33396 DT.20/08/2024 | 431.974 | 60.9776 | 26340.7378 | 0.39 | 26341.1278 | Kgs | E-Bldg Steel Process Wastage -Upto 31st Slab | 9017.026 | ANIL BHOSALE | 0
GANGA ALTUS | Binding Wire -Kgs | UPRISEN CONSTRUCTION |  | 781351 | 2024-08-22 16:19 | Issue to Task | Non Returnable / Non Debitable | ALTUS CENTRAL STORE | ISSUE NO.37263 DT.22.08.2024 | 11 | 66.29 | 729.19 | 129.03 | 858.22 | Kgs | Club House-Tie Beam Steel Work | 12 | ANIL BHOSALE | 0
GANGA ALTUS | Binding Wire -Kgs | UPRISEN CONSTRUCTION |  | 781352 | 2024-08-22 16:23 | Issue to Task | Non Returnable / Non Debitable | ALTUS CENTRAL STORE | ISSUE NO.37263 DT.22.08.2024 | 11 | 66.29 | 729.19 | 129.03 | 858.22 | Kgs | RCC Work Tie Beam Steel | 0.35 | ANIL BHOSALE | 0
GANGA ALTUS | Binding Wire -Kgs | UPRISEN CONSTRUCTION |  | 781353 | 2024-08-22 16:23 | Issue to Task | Non Returnable / Non Debitable | ALTUS CENTRAL STORE | ISSUE NO.37263 DT.22.08.2024 | 3 | 66.29 | 198.87 | 35.19 | 234.06 | Kgs | Well RCC Pardi Steel | 26.46 | ANIL BHOSALE | 0
GANGA ALTUS | Steel Bars 10mm -Kgs | RITU ENTERPRISES |  | 781417 | 2024-08-23 11:50 | Issue to Task | Non Returnable / Non Debitable | ALTUS CENTRAL STORE | ISSUE NO-271125 DT23.08.2024 | 33.04 | 60.51 | 1999.2504 | 1.32 | 2000.5704 | Kgs | 1st PT Slab,Beam Steel | 3141.96 | Anand Jadhav | 0
GANGA ALTUS | Steel Bars 10mm -Kgs | RITU ENTERPRISES |  | 781418 | 2024-08-23 11:50 | Issue to Task | Non Returnable / Non Debitable | ALTUS CENTRAL STORE | ISSUE NO-271125 DT23.08.2024 | -33.04 | 60.51 | -1999.2504 | -1.32 | -2000.5704 | Kgs | Club House-Tie Beam Steel Work | 38 | Anand Jadhav | 0