## IssueRegister638605228842186499
Issue Register
From 27-08-2024 To 29-08-2024
Page 1 of 1
Total Records: 28 Records 1 to 28
Project_Name | Material_Name | Contractor Name | Wo No | Issue_No | Issue_Date | Issue_Type | Issue_As | Issuing_Store | Remark | Good_Qty | Rate | Amount | GST | Net_Amount | Unit_Name | Task_Store_Supplier_Name | Bal_Task_Qty | UserName | IssueReqSlip_No
SRA MORWADI | Binding Wire -Kgs | KRISHNA CONSTRUCTION |  | 781973 | 2024-08-27 10:13 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24546 Date:-27.08.2024 | 60 | 65.9 | 3954 | 703.8 | 4657.8 | Kgs | A Bldg 5th Slab,Beam &amp; Staircase Steel Work | 102.44 | yogesh-agarwal | 0
SRA MORWADI | Cement Loose 53 Grade -Metric Tonnes | MAHALAXMI BUILDCON |  | 782030 | 2024-08-27 13:11 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24871 Sate:-27.08.2024 Future India | 4.68 | 5844.07 | 27350.2476 | 7658.07 | 35008.3176 | Metric Tonnes | G-PCC & Plump Concrete | 56.35 | yogesh-agarwal | 0
SRA MORWADI | Cement Loose 53 Grade -Metric Tonnes | MAHALAXMI BUILDCON |  | 782032 | 2024-08-27 13:12 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24870 Sate:-27.08.2024 Manjulai RMC | 56.35 | 5844.07 | 329313.3445 | 92207.76 | 421521.1045 | Metric Tonnes | G-PCC & Plump Concrete | 4.68 | yogesh-agarwal | 0
SRA MORWADI | Brown Tape 2" -No. | DEPARTMENT |  | 782033 | 2024-08-27 13:24 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24725 Sate:-27.08.2024 | 1 | 26.87 | 26.87 | 1.9 | 28.77 | No. | B Bldg Ground Floor | 9 | yogesh-agarwal | 0
SRA MORWADI | PVC Conduit Bend 1" -No. | TAHA ELECTRICALS |  | 782034 | 2024-08-27 13:27 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24726 Sate:-27.08.2024 | 60 | 6.81 | 408.6 | 67.8 | 476.4 | No. | B BUILDING 3RD Floor | 0 | yogesh-agarwal | 0
SRA MORWADI | Issue Slip Book -No. | TAHA ELECTRICALS |  | 782035 | 2024-08-27 13:28 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24727 Sate:-27.08.2024 | 1 | 44.85 | 44.85 | 0 | 44.85 | No. | Office & Store Setup | 49 | yogesh-agarwal | 0
SRA MORWADI | MS Aldrop 10" -No. | DEPARTMENT |  | 782036 | 2024-08-27 13:29 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.22615 Sate:-27.08.2024 | 1 | 94.08 | 94.08 | 15.3 | 109.38 | No. | Material For Store,Office & Labour camp | 5 | yogesh-agarwal | 0
SRA MORWADI | GP2 Waterproofing Chemical -Kgs | KRISHNA CONSTRUCTION |  | 782037 | 2024-08-27 14:09 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip no.23191 Date:-27.08.2024 | 30 | 17.5 | 525 | 94.5 | 619.5 | Kgs | B BLDG Material On Debit Basis | 0 | yogesh-agarwal | 0
SRA MORWADI | Sand-Metal Mix M15 (Downpour) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 782065 | 2024-08-27 16:58 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip no.22616 Date:-27.08.2024 | 3 | 3066.1 | 9198.3 | 1655.7 | 10854 | Cu.Mtrs | Phase 1 DG Foundation Concrete Work | 0 | yogesh-agarwal | 0
SRA MORWADI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 782066 | 2024-08-27 16:59 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip no.22616 Date:-27.08.2024 | 0.42 | 5844.07 | 2454.5094 | 687.26 | 3141.7694 | Metric Tonnes | Phase 1 DG Foundation Concrete Work | 0 | yogesh-agarwal | 0
SRA MORWADI | Halogen 200 Watt -No. | DEPARTMENT |  | 782067 | 2024-08-27 17:00 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip no.24872 Date:-27.08.2024 | 6 | 2636.79 | 15820.74 | 2837.7 | 18658.44 | No. | Phase 2 Site Setup Electrical Work | 34 | yogesh-agarwal | 0
SRA MORWADI | Black Insulation Tape -No. | DEPARTMENT |  | 782068 | 2024-08-27 17:02 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip no.24872 Date:-27.08.2024 | 1 | 9.04 | 9.04 | 1.62 | 10.66 | No. | Phase 2 Site Setup Electrical Work | 89 | yogesh-agarwal | 0
SRA MORWADI | Potato Greece -Kgs | KRISHNA CONSTRUCTION |  | 782259 | 2024-08-28 16:28 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25634 Date:-28.08.2024 | 20 | 133 | 2660 | 478.8 | 3138.8 | Kgs | A Bldg Aluform Misc. Consumable | 799 | yogesh-agarwal | 0
SRA MORWADI | Kiltan ( Hessian Cloth ) -Mtrs | DEPARTMENT |  | 782260 | 2024-08-28 16:29 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24728 Date:-28.08.2024 | 100 | 25.09 | 2509 | 126 | 2635 | Mtrs | B Parking-2nd Floor (3rd Slab) Misc.Work (M) | 6400 | yogesh-agarwal | 0
SRA MORWADI | MS Aldrop 10" -No. | CHINTAMANI ENTERPRISES (Prop.Sonawane) |  | 782261 | 2024-08-28 16:30 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.22617 Date:-28.08.2024 | 1 | 94.08 | 94.08 | 15.3 | 109.38 | No. | Labour Camp Fabrication For Labour Camp Room | 11 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 20mm -Kgs | KRISHNA CONSTRUCTION |  | 782262 | 2024-08-28 16:32 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24548 Date:-28.08.2024 | 266.65 | 60.76 | 16201.654 | 34.66 | 16236.314 | Kgs | A-5th To 6th Slab Column,lift Steel | 3015.72 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 8mm -Kgs | KRISHNA CONSTRUCTION |  | 782263 | 2024-08-28 16:33 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24547 Date:-28.08.2024 | 2417.4 | 62.48 | 151039.152 | 24.17 | 151063.322 | Kgs | A Bldg 5th Slab,Beam &amp; Staircase Steel Work | 5064.27 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 12mm -Kgs | KRISHNA CONSTRUCTION |  | 782264 | 2024-08-28 16:34 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24547 Date:-28.08.2024 | 1704.96 | 58.41 | 99586.7136 | 1466.27 | 101052.9836 | Kgs | A Bldg 5th Slab,Beam &amp; Staircase Steel Work | 1200.51 | yogesh-agarwal | 0
SRA MORWADI | Steel Bars 16mm -Kgs | KRISHNA CONSTRUCTION |  | 782265 | 2024-08-28 16:35 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24547 Date:-28.08.2024 | 1516.8 | 61.31 | 92995.008 | 0 | 92995.008 | Kgs | A Bldg 5th Slab,Beam &amp; Staircase Steel Work | 1583.2 | yogesh-agarwal | 0
SRA MORWADI | GP2 Waterproofing Chemical -Kgs | KRISHNA CONSTRUCTION |  | 782266 | 2024-08-28 16:37 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24549 Date:-28.08.2024 | 30 | 17.5 | 525 | 94.5 | 619.5 | Kgs | A Bldg 4th Slab Curing & Other Material | 95 | yogesh-agarwal | 0
SRA MORWADI | Anchor Fastner 10mmx75mm -No. | PROTECT ENTERPRISES |  | 782267 | 2024-08-28 16:38 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.25630 Date:-28.08.2024 | 100 | 14 | 1400 | 252 | 1652 | No. | B Bldg Safety Net 1st Floor | 10 | yogesh-agarwal | 0
SRA MORWADI | Sand-Metal Mix M30 (Pumpable) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 782363 | 2024-08-28 18:52 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON |  | 130.29 | 3327.12 | 433490.4648 | 78028.08 | 511518.5448 | Cu.Mtrs | B Bldg 4th Slab Beam,Slab,Staircase Concrete | 1.86 | yogesh-agarwal | 0
SRA MORWADI | Sand-Metal Mix M30 (Pumpable) -Cu.Mtrs | KRISHNA CONSTRUCTION |  | 782364 | 2024-08-28 18:52 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON |  | 6.93 | 3327.1 | 23056.803 | 4150.38 | 27207.183 | Cu.Mtrs | B Bldg Column 3rd to 4th & Non str. Wall Slab | 53.5 | yogesh-agarwal | 0
SRA MORWADI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 782369 | 2024-08-28 18:59 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24729 Date:-28.08.2024 Manjulai RMC | 23.43 | 5844.07 | 136926.5601 | 38339.45 | 175266.0101 | Metric Tonnes | B Bldg 4th Slab Beam,Slab,Staircase Concrete | 0 | yogesh-agarwal | 0
SRA MORWADI | Cement Loose 53 Grade -Metric Tonnes | KRISHNA CONSTRUCTION |  | 782370 | 2024-08-28 18:59 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.24729 Date:-28.08.2024 Manjulai RMC | 4.014 | 5844.07 | 23458.097 | 6568.27 | 30026.367 | Metric Tonnes | B Bldg Column 3rd to 4th & Non str. Wall Slab | 40.656 | yogesh-agarwal | 0
SRA MORWADI | MS Aldrop 10" -No. | CHINTAMANI ENTERPRISES (Prop.Sonawane) |  | 782371 | 2024-08-28 19:00 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.22620 Date:-28.08.2024 | 1 | 94.08 | 94.08 | 15.3 | 109.38 | No. | Labour Camp Fabrication For Labour Camp Room | 11 | yogesh-agarwal | 0
SRA MORWADI | ASTM Pipe 1" x 10fts -No. | DEPARTMENT |  | 782372 | 2024-08-28 19:01 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.22619 Date:-28.08.2024 | 1 | 262.64 | 262.64 | 30.56 | 293.2 | No. | Plumbing Setup Temporary Curing Line | 19 | yogesh-agarwal | 0
SRA MORWADI | ASTM Socket 1" -No. | DEPARTMENT |  | 782373 | 2024-08-28 19:01 | Issue to Task | Non Returnable / Non Debitable | MORWADI COMMON | I Slip No.22619 Date:-28.08.2024 | 3 | 8.7 | 26.1 | 4.29 | 30.39 | No. | Plumbing Setup Temporary Curing Line | 27 | yogesh-agarwal | 0