## Requisition_Tracking-Summary638
Requistion Tracking - Summary
From Date : 19/07/2024 To date: 19/08/2024
Material Category : RMC
Page 1 of 1
Total Records: 29 Records 1 to 29
Project | Material_Name | Unit_Name | ReqSr_No | Requisition_Date | Requirement_Date | Qty | APP_Qty | PO_Qty | User_Name | Status | Remark
GANGA ALTUS | Ready Mix Concrete M-35 Grade (Downpour) | Cu.Mtrs | 711602 | 2024-08-03 17:57 | 2024-08-03 12:00 | 4.87 | 4.87 | 4.87 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M-35 Grade (Downpour) | Cu.Mtrs | 711603 | 2024-08-03 17:57 | 2024-08-03 12:00 | 7.86 | 7.86 | 7.86 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M-40 Grade (Pumpable) | Cu.Mtrs | 712622 | 2024-08-13 15:26 | 2024-08-13 12:00 | 10.155 | 10.155 | 10.155 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M-40 Grade (Pumpable) | Cu.Mtrs | 712623 | 2024-08-13 15:26 | 2024-08-13 12:00 | 15.26 | 15.26 | 15.26 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M-40 Grade (Pumpable) | Cu.Mtrs | 712624 | 2024-08-13 15:26 | 2024-08-13 12:00 | 4.28 | 4.28 | 4.28 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M-40 Grade (Pumpable) | Cu.Mtrs | 712625 | 2024-08-13 15:26 | 2024-08-13 12:00 | 29.957 | 29.957 | 29.957 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M-40 Grade (Pumpable) | Cu.Mtrs | 712626 | 2024-08-13 15:26 | 2024-08-13 12:00 | 2.235 | 2.235 | 2.235 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M-40 Grade (Pumpable) | Cu.Mtrs | 712627 | 2024-08-13 15:26 | 2024-08-13 12:00 | 17.36 | 17.36 | 17.36 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M-40 Grade (Pumpable) | Cu.Mtrs | 712628 | 2024-08-13 15:26 | 2024-08-13 12:00 | 14.6 | 14.6 | 14.6 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M-40 Grade (Pumpable) | Cu.Mtrs | 712629 | 2024-08-13 15:26 | 2024-08-13 12:00 | 6.95 | 6.95 | 6.95 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M-40 Grade (Pumpable) | Cu.Mtrs | 712630 | 2024-08-13 15:26 | 2024-08-13 12:00 | 6.95 | 6.95 | 6.95 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M-40 Grade (Pumpable) | Cu.Mtrs | 712631 | 2024-08-13 15:26 | 2024-08-13 12:00 | 6.95 | 6.95 | 6.95 | Deepak Kumbhar | Completed
GANGA ALTUS | Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 712675 | 2024-08-13 20:36 | 2024-08-13 12:00 | 1.78 | 1.78 | 0 | sandip kute | Completed
GANGA ALTUS | Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 712676 | 2024-08-13 20:36 | 2024-08-13 12:00 | 0.002 | 0.002 | 0 | sandip kute | Completed
GANGA ALTUS | Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 712677 | 2024-08-13 20:36 | 2024-08-13 12:00 | 1.48 | 1.48 | 0 | sandip kute | Completed
GANGA ALTUS | Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 712678 | 2024-08-13 20:37 | 2024-08-13 12:00 | 0.18 | 0.18 | 0 | sandip kute | Completed
GANGA ALTUS | Ready Mix Concrete M25 Regular Downpour | Cu.Mtrs | 712679 | 2024-08-13 20:37 | 2024-08-13 12:00 | 7 | 7 | 0 | sandip kute | Completed
GANGA ALTUS | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 712680 | 2024-08-13 20:47 | 2024-08-13 12:00 | 2 | 2 | 0 | sandip kute | Completed
GANGA ALTUS | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 712681 | 2024-08-13 20:47 | 2024-08-13 12:00 | 7.24 | 7.24 | 0 | sandip kute | Completed
GANGA ALTUS | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 712682 | 2024-08-13 20:47 | 2024-08-13 12:00 | 3.62 | 3.62 | 0 | sandip kute | Completed
GANGA ALTUS | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 712683 | 2024-08-13 20:51 | 2024-08-13 12:00 | 0.85 | 0.85 | 0 | sandip kute | Completed
GANGA ALTUS | Dry Lean Concrete (M10) | Cu.Mtrs | 712687 | 2024-08-14 11:44 | 2024-08-14 12:00 | 0 | 0 | 0 | sandip kute | Deleted
GANGA ALTUS | Dry Lean Concrete M15- | Cu.Mtrs | 712763 | 2024-08-15 11:58 | 2024-08-15 12:00 | 60 | 60 | 0 | sandip kute | Completed
GANGA ALTUS | Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 713258 | 2024-08-19 12:45 | 2024-08-19 12:00 | 10.005 | 0 | 0 | Deepak Kumbhar | Unapproved
GANGA ALTUS | Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs | 713259 | 2024-08-19 12:45 | 2024-08-19 12:00 | 2.73 | 0 | 0 | Deepak Kumbhar | Unapproved
GANGA ALTUS | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 713260 | 2024-08-19 12:49 | 2024-08-19 12:00 | 2.54 | 0 | 0 | sandip kute | Unapproved
GANGA ALTUS | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | 713261 | 2024-08-19 12:49 | 2024-08-19 12:00 | 2.9227 | 0 | 0 | sandip kute | Unapproved
GANGA ALTUS | Ready Mix Concrete M25 Regular Pumpable | Cu.Mtrs | 713262 | 2024-08-19 12:53 | 2024-08-19 12:00 | 0 | 0 | 0 | sandip kute | Deleted
GANGA ALTUS | Ready Mix Concrete M25 Regular Pumpable | Cu.Mtrs | 713263 | 2024-08-19 12:53 | 2024-08-19 12:00 | 0 | 0 | 0 | sandip kute | Deleted