## Requisition_Tracking-Summary638
Requistion Tracking - Summary
From Date : 01/01/2016 To date: 27/08/2024
Material Category : STEEL
Page 1 of 1
Total Records: 37 Records 1 to 37
Project | Material_Name | Unit_Name | ReqSr_No | Requisition_Date | Requirement_Date | Qty | APP_Qty | PO_Qty | User_Name | Status | Remark
GANGA DHAM TOWERS | Binding Wire | Kgs | 409795 | 2016-06-01 09:24 | 2016-06-10 | 798 | 789.4 | 798 | collidium | Approved
GANGA DHAM TOWERS | Steel Bar 25mm | Kgs | 409796 | 2016-06-01 09:26 | 2016-06-10 | 31941 | 31563 | 31941 | collidium | Approved
GANGA DHAM TOWERS | Steel Bars 10mm | Kgs | 409803 | 2016-06-01 09:34 | 2016-06-10 | 564 | 350 | 564 | collidium | Approved
GANGA DHAM TOWERS | Steel Bars 12mm | Kgs | 409804 | 2016-06-01 09:35 | 2016-06-10 | 1918 | 1841 | 1918 | collidium | Approved
GANGA DHAM TOWERS | Steel Bars 16mm | Kgs | 409805 | 2016-06-01 09:36 | 2016-06-10 | 1067 | 1000 | 1067 | collidium | Approved
GANGA DHAM TOWERS | Steel Bars 10mm | Kgs | 431499 | 2016-12-10 16:17 | 2016-12-12 | 2766 | 2610 | 2766 | MAHAJAN | Approved
GANGA DHAM TOWERS | Steel Bars 16mm | Kgs | 436225 | 2017-01-16 10:23 | 2017-01-25 | 68 | 67.14 | 67.14 | MAHAJAN | Approved
GANGA DHAM TOWERS | Steel Bars 12mm | Kgs | 447296 | 2017-03-09 13:23 | 2017-03-24 | 1940 | 1912 | 1968 | MAHAJAN | Approved | Drg recd for study purpose 1/3/2017,estimate done today
GANGA DHAM TOWERS | Steel Bars 32mm | Kgs | 447299 | 2017-03-09 13:24 | 2017-03-24 | 449 | 408 | 436 | MAHAJAN | Approved | Drg recd for study purpose 1/3/2017,estimate done today
GANGA DHAM TOWERS | Steel Bars 12mm | Kgs | 448112 | 2017-03-22 18:01 | 2017-04-06 | 6383 | 6297 | 6383 | MAHAJAN | Approved | MMD,Estimate done today
GANGA DHAM TOWERS | Steel Bars 16mm | Kgs | 448113 | 2017-03-22 18:01 | 2017-04-06 | 3592 | 3591 | 3592 | MAHAJAN | Approved | MMD,Estimate done today
GANGA DHAM TOWERS | Steel Bars 20mm | Kgs | 448114 | 2017-03-22 18:02 | 2017-04-06 | 5664 | 5647 | 5664 | MAHAJAN | Approved | MMD,Estimate done today
GANGA DHAM TOWERS | Steel Bars 20mm | Kgs | 448269 | 2017-03-24 11:43 | 2017-03-31 | 2947 | 2884.12 | 2947 | MAHAJAN | Approved | MMD,drg recd 23/3/2017, estimate done today
GANGA DHAM TOWERS | Steel Bars 8mm | Kgs | 448270 | 2017-03-24 11:44 | 2017-03-31 | 1182 | 1126.33 | 1182 | MAHAJAN | Approved | MMD,drg recd 23/3/2017, estimate done today
GANGA DHAM TOWERS | Steel Bars 10mm | Kgs | 448272 | 2017-03-24 11:47 | 2017-03-31 | 900 | 807.69 | 900 | MAHAJAN | Approved | MMD,drg recd 23/3/2017, estimate done today
GANGA DHAM TOWERS | Steel Bars 16mm | Kgs | 448275 | 2017-03-24 11:50 | 2017-03-31 | 254 | 219 | 254 | MAHAJAN | Approved | MMD,drg recd 23/3/2017, estimate done today
GANGA DHAM TOWERS | Steel Bars 20mm | Kgs | 449991 | 2017-04-17 10:52 | 2017-04-30 | 4264 | 4260 | 4264 | MAHAJAN | Approved | MMD
GANGA DHAM TOWERS | Steel Bars 12mm | Kgs | 449998 | 2017-04-17 11:07 | 2017-04-30 | 152 | 151 | 152 | MAHAJAN | Approved | MMD
GANGA DHAM TOWERS | Steel Bars 12mm | Kgs | 450194 | 2017-04-18 17:18 | 2017-04-30 | 1938 | 1845 | 1938 | MAHAJAN | Approved | MMD
GANGA DHAM TOWERS | Steel Bars 32mm | Kgs | 450196 | 2017-04-18 17:20 | 2017-04-30 | 1620 | 1490 | 1620 | MAHAJAN | Approved | MMD
GANGA DHAM TOWERS | Steel Bar 25mm | Kgs | 450569 | 2017-04-20 15:51 | 2017-04-25 | 24035 | 23345 | 24035 | MAHAJAN | Approved
GANGA DHAM TOWERS | Steel Bars 12mm | Kgs | 450573 | 2017-04-20 15:54 | 2017-04-25 | 4309 | 4180 | 4309 | MAHAJAN | Approved
GANGA DHAM TOWERS | Steel Bars 16mm | Kgs | 450574 | 2017-04-20 15:55 | 2017-04-25 | 10573 | 10365 | 10573 | MAHAJAN | Approved
GANGA DHAM TOWERS | Steel Bars 20mm | Kgs | 450575 | 2017-04-20 15:55 | 2017-04-25 | 22678 | 21840 | 22678 | MAHAJAN | Approved
GANGA DHAM TOWERS | Steel Bars 32mm | Kgs | 450576 | 2017-04-20 15:56 | 2017-04-25 | 585 | 470 | 585 | MAHAJAN | Approved
GANGA DHAM TOWERS | Binding Wire | Kgs | 451555 | 2017-04-26 10:26 | 2017-05-02 | 1358 | 1356 | 1358 | MAHAJAN | Approved | MMD
GANGA DHAM TOWERS | Steel Bars 8mm | Kgs | 456156 | 2017-07-17 12:33 | 2017-07-27 | 2123 | 2078 | 2091 | MAHAJAN | Approved
GANGA DHAM TOWERS | Steel Bars 10mm | Kgs | 464660 | 2017-11-28 09:53 | 2017-12-04 | 6054 | 6019 | 6019 | MAHAJAN | Approved
GANGA DHAM TOWERS | Steel Bars 32mm | Kgs | 467405 | 2017-12-23 12:21 | 2017-12-30 | 1548 | 1536 | 2182 | MAHAJAN | Approved
GANGA DHAM TOWERS | Steel Bars 20mm | Kgs | 468282 | 2018-01-09 16:48 | 2018-01-20 | 6969 | 6965 | 7148 | MAHAJAN | Approved
GANGA DHAM TOWERS | Binding Wire | Kgs | 471049 | 2018-02-16 12:06 | 2018-02-25 | 315 | 312 | 315 | sandip rupanawar | Approved
GANGA DHAM TOWERS | Steel Bars 8mm | Kgs | 491971 | 2018-06-09 16:38 | 2018-06-25 | 8989 | 8789 | 9434 | VINIT | Approved
GANGA DHAM TOWERS | Binding Wire | Kgs | 518752 | 2018-12-03 10:50 | 2018-12-10 | 324 | 211 | 324 | vinit | Approved
GANGA DHAM TOWERS | Steel Bars 20mm | Kgs | 553207 | 2020-03-14 17:34 | 2020-03-25 | 3717 | 3171 | 3171 | savita takale.r | Approved
GANGA DHAM TOWERS | Steel Bars 8mm | Kgs | 578132 | 2020-11-23 12:00 | 2020-12-05 12:00 | 8945.25 | 8195.25 | 8195.25 | savita.takle | Approved
GANGA DHAM TOWERS | Steel Bars 16mm | Kgs | 578143 | 2020-11-23 13:01 | 2020-12-05 | 2007 | 1515 | 1515 | savita.takle | Approved
GANGA DHAM TOWERS | Steel Bars 20mm | Kgs | 578146 | 2020-11-23 13:06 | 2020-12-05 | 1954 | 1755 | 1755 | savita.takle | Approved