## Requisition_Tracking63857862311
Requisition Tracking
From 01-06-2014 To 30-07-2024
Page 1 of 1
Total Records: 139 Records 1 to 139
Project | Req SrNo | Req Date | Task Name | Material Name | Unit | Specifications | Qty | App Qty | Approve Details | PO No. | PO Status | Rate
GANGA DHAM TOWERS | 423569 | 30 Sep 2016 | Ent Gate - Footing RCC M-25 | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 10.56 | 10.56 | rajeshn | 39394 | Raised | 2250
GANGA DHAM TOWERS | 423721 | 01 Oct 2016 | Ent Gate - Footing RCC M-25 | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 0.44 | 0.44 | rajeshn | 39394 | Raised | 2250
GANGA DHAM TOWERS | 463874 | 15 Nov 2017 | Sewage Treatment Plant RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 50 | 36.12 | rajeshn | 46052 | Raised | 2665
GANGA DHAM TOWERS | 463874 | 15 Nov 2017 | Sewage Treatment Plant RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 13.88 | 13.88 | rajeshn | 47639 | Raised | 2850
GANGA DHAM TOWERS | 463874 | 15 Nov 2017 | Sewage Treatment Plant RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 15 | 15 | rajeshn | 46052 | Raised | 2665
GANGA DHAM TOWERS | 463874 | 15 Nov 2017 | Sewage Treatment Plant RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 70 | 5 | rajeshn | 45802 | Raised | 2270
GANGA DHAM TOWERS | 463875 | 15 Nov 2017 | Sewage Treatment Plant RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 74.38 | 74.38 | rajeshn | 45613 | Raised | 2665
GANGA DHAM TOWERS | 471655 | 21 Feb 2018 | EWS Bldg RCC Footings RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 100 | 100 | rajeshn | 47639 | Raised | 2850
GANGA DHAM TOWERS | 511735 | 03 Oct 2018 | Pump room Pardi M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 42.46 | 24 | kantilalJ | 51627 | Raised | 2400
GANGA DHAM TOWERS | 518286 | 28 Nov 2018 | EWS Bldg RCC 5th Slab RMC M25 (S-M Mix) Downpour | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 70.33 | 70.33 | kantilalj | 50876 | Raised | 2850
GANGA DHAM TOWERS | 518288 | 28 Nov 2018 | EWS Bldg 4th To 5th Slab RCC Columns RMC M25 (S-M Mix) Downp | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 27.03 | 27.03 | kantilalj | 50876 | Raised | 2850
GANGA DHAM TOWERS | 518290 | 28 Nov 2018 | EWS Bldg RCC 6th Slab RMC M25 (S-M Mix) Downpour | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 70.33 | 70.23 | kantilalj | 50876 | Raised | 2850
GANGA DHAM TOWERS | 518290 | 28 Nov 2018 | EWS Bldg RCC 6th Slab RMC M25 (S-M Mix) Downpour | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 0.1 | 0.1 | raviraj | 53218 | Raised | 3050
GANGA DHAM TOWERS | 518292 | 28 Nov 2018 | EWS Bldg 5th To 6th Slab RCC Columns RMC M25 (S-M Mix) Downp | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 27.03 | 27.03 | kantilalj | 50876 | Raised | 2850
GANGA DHAM TOWERS | 523781 | 23 Jan 2019 | UGWT Raft M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier ACC | 17.25 | 16.5 | raviraj | 51751 | Raised | 2850
GANGA DHAM TOWERS | 523781 | 23 Jan 2019 | UGWT Raft M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier ACC | 0.75 | 0.75 | raviraj | 51898 | Raised | 2850
GANGA DHAM TOWERS | 524529 | 05 Feb 2019 | EWS Bldg 5th To 6th Slab RCC Columns RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | ACC LTD | 25.71 | 16.42 | kantilalj | 51898 | Raised | 2850
GANGA DHAM TOWERS | 524529 | 05 Feb 2019 | EWS Bldg 5th To 6th Slab RCC Columns RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | ACC LTD | 9.29 | 9.29 | kantilalJ | 52590 | Raised | 2250
GANGA DHAM TOWERS | 524531 | 05 Feb 2019 | EWS Bldg RCC 7th Slab RMC M25 (S-M Mix) Downpour | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | ACC LTD | 70.33 | 70.33 | kantilalj | 51898 | Raised | 2850
GANGA DHAM TOWERS | 524533 | 05 Feb 2019 | EWS Bldg 7th To 8th Slab RCC Columns RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | ACC LTD | 25.71 | 25.71 | kantilalJ | 52590 | Raised | 2250
GANGA DHAM TOWERS | 524535 | 05 Feb 2019 | EWS Bldg RCC 8th Slab RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | ACC LTD | 70.33 | 70.32 | kantilalJ | 52590 | Raised | 2250
GANGA DHAM TOWERS | 526612 | 05 Mar 2019 | UGWT Raft M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier ACC | 1.87 | 1.87 | raviraj | 56466 | Raised | 3213
GANGA DHAM TOWERS | 526612 | 05 Mar 2019 | UGWT Raft M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier ACC | 40 | 3 | raviraj | 55217 | Raised | 2250
GANGA DHAM TOWERS | 526612 | 05 Mar 2019 | UGWT Raft M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier ACC | 11 | 11 | raviraj | 55297 | Raised | 2250
GANGA DHAM TOWERS | 526612 | 05 Mar 2019 | UGWT Raft M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier ACC | 65 | 25 | kantilalJ | 52258 | Raised | 2400
GANGA DHAM TOWERS | 526612 | 05 Mar 2019 | UGWT Raft M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier ACC | 37 | 18.13 | raviraj | 55483 | Raised | 2250
GANGA DHAM TOWERS | 526612 | 05 Mar 2019 | UGWT Raft M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier ACC | 37 | 6 | raviraj | 55237 | Raised | 2275
GANGA DHAM TOWERS | 526613 | 05 Mar 2019 | UGWT Pardi M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier ACC | 23 | 23 | kantilalJ | 52258 | Raised | 2400
GANGA DHAM TOWERS | 529614 | 02 Apr 2019 | EWS Bldg 8th To 9th Slab RCC Columns RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | given to ACC | 25.71 | 25.71 | raviraj | 53218 | Raised | 3050
GANGA DHAM TOWERS | 529616 | 02 Apr 2019 | EWS Bldg RCC 9th Slab RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | given to ACC | 70.33 | 70.33 | raviraj | 53218 | Raised | 3050
GANGA DHAM TOWERS | 533687 | 17 Jun 2019 | Pump room Corner Retaining Wall M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 12.44 | 12.44 | kantilalJ | 53441 | Raised | 3050
GANGA DHAM TOWERS | 533690 | 17 Jun 2019 | Pump Room Corner Ret.wall Raft M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 4 | 4 | kantilalJ | 53441 | Raised | 3050
GANGA DHAM TOWERS | 533696 | 17 Jun 2019 | UGWT Column M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 18 | 18 | kantilalJ | 53441 | Raised | 3050
GANGA DHAM TOWERS | 533701 | 17 Jun 2019 | Club House Footing M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 26 | 26 | kantilalJ | 53441 | Raised | 3050
GANGA DHAM TOWERS | 533703 | 17 Jun 2019 | Club House Plinth Beam M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 20.31 | 20.31 | kantilalJ | 53441 | Raised | 3050
GANGA DHAM TOWERS | 533704 | 17 Jun 2019 | UGWT Pardi Rework extra work M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 21.56 | 21.36 | kantilalJ | 53441 | Raised | 3050
GANGA DHAM TOWERS | 534348 | 01 Jul 2019 | A Type Retaining Wall Raft RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : ACC Ltd. | 14.2 | 14.2 | kantilalJ | 53664 | Raised | 3050
GANGA DHAM TOWERS | 534349 | 01 Jul 2019 | A Type Retaining Wall RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 20.7 | 20.7 | kantilalJ | 53664 | Raised | 3050
GANGA DHAM TOWERS | 534351 | 01 Jul 2019 | B Type Retaining Wall Raft RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 10.75 | 10.75 | kantilalJ | 53664 | Raised | 3050
GANGA DHAM TOWERS | 534352 | 01 Jul 2019 | B Type Retaining Wall RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 7.03 | 7.03 | kantilalJ | 53664 | Raised | 3050
GANGA DHAM TOWERS | 534354 | 01 Jul 2019 | C Type Retaining Wall Raft RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 8.8 | 8.8 | kantilalJ | 53664 | Raised | 3050
GANGA DHAM TOWERS | 534355 | 01 Jul 2019 | C Type Retaining Wall RMC M25 (S-M Mix) Downpour | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 13.27 | 13.27 | kantilalJ | 53664 | Raised | 3050
GANGA DHAM TOWERS | 541482 | 25 Sep 2019 | Club House 1st Slab RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC ltd. | 52.05 | 52.05 | raviraj | 55455 | Raised | 2250
GANGA DHAM TOWERS | 549810 | 30 Jan 2020 | A Type Retaining Wall RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : Amix n=Infra | 5.96 | 5.96 | raviraj | 55806 | Raised | 2275
GANGA DHAM TOWERS | 549811 | 30 Jan 2020 | B Type Retaining Wall RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : Amix Infra | 6.06 | 6.06 | raviraj | 55806 | Raised | 2275
GANGA DHAM TOWERS | 549812 | 30 Jan 2020 | C Type Retaining Wall RMC M25 (S-M Mix) Downpour | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : Amix Infra | 7.45 | 7.45 | raviraj | 55806 | Raised | 2275
GANGA DHAM TOWERS | 550871 | 25 Feb 2020 | EWS Bldg 9th To 10th Slab RCC Columns RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : Amix Infra | 25.71 | 6.03 | raviraj | 55987 | Raised | 2275
GANGA DHAM TOWERS | 550871 | 25 Feb 2020 | EWS Bldg 9th To 10th Slab RCC Columns RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : Amix Infra | 19.68 | 19.68 | raviraj | 56466 | Raised | 3213
GANGA DHAM TOWERS | 570099 | 20 Jul 2020 | EWS Bldg RCC 6th Slab RMC M25 (S-M Mix) Downpour | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 0.67 | 0.67 | kantilalJ | 57999 | Raised | 2375
GANGA DHAM TOWERS | 570100 | 20 Jul 2020 | EWS Bldg RCC 5th Slab RMC M25 (S-M Mix) Downpour | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 0.67 | 0.67 | kantilalJ | 57999 | Raised | 2375
GANGA DHAM TOWERS | 570101 | 20 Jul 2020 | EWS Bldg RCC 7th Slab RMC M25 (S-M Mix) Downpour | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | ACC LTD | 0.67 | 0.67 | kantilalJ | 59860 | Raised | 3694
GANGA DHAM TOWERS | 570102 | 20 Jul 2020 | EWS Bldg RCC 8th Slab RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | ACC LTD | 0.68 | 0.68 | kantilalJ | 59860 | Raised | 3694
GANGA DHAM TOWERS | 571827 | 06 Aug 2020 | EWS Bldg 10th To 11th Slab RCC Columns RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Prism Johnsons | 24.45 | 24.45 | kantilalJ | 56886 | Raised | 3213
GANGA DHAM TOWERS | 576246 | 01 Oct 2020 | Trimix Road Ramp outside RCC Pardi | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Prism Johnsons | 31.61 | 14 | SANKET PATIL | 57393 | Raised | 3213
GANGA DHAM TOWERS | 576246 | 01 Oct 2020 | Trimix Road Ramp outside RCC Pardi | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Prism Johnsons | 17.61 | 14.66 | ACCOUNT | 57600 | Raised | 2375
GANGA DHAM TOWERS | 583166 | 20 Jan 2021 | EWS RCC Slab,Beam,Column,RMC M25 (S-M Mix) - | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Amix Infra | 15 | 5 | SANKET PATIL | 60283 | Raised | 3525
GANGA DHAM TOWERS | 583166 | 20 Jan 2021 | EWS RCC Slab,Beam,Column,RMC M25 (S-M Mix) - | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Amix Infra | 26 | 11 | SANKET PATIL | 60256 | Raised | 3525
GANGA DHAM TOWERS | 583166 | 20 Jan 2021 | EWS RCC Slab,Beam,Column,RMC M25 (S-M Mix) - | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Amix Infra | 52 | 26 | SANKET PATIL | 59255 | Raised | 2183
GANGA DHAM TOWERS | 583166 | 20 Jan 2021 | EWS RCC Slab,Beam,Column,RMC M25 (S-M Mix) - | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Amix Infra | 15 | 10 | SANKET PATIL | 60284 | Raised | 3009
GANGA DHAM TOWERS | 588034 | 14 May 2021 | A Parking Floor 2 Trimix ( M)- | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji RMC | 110 | 110 | SANKET PATIL | 59267 | Raised | 2183
GANGA DHAM TOWERS | 588990 | 05 Jun 2021 | B Parking Floor 2 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji RMC | 30 | 30 | Meghna Gunge | 59450 | Raised | 2183
GANGA DHAM TOWERS | 589277 | 14 Jun 2021 | B Parking Floor 2 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji RMC | 5.95 | 5.95 | SANKET PATIL | 60284 | Raised | 3009
GANGA DHAM TOWERS | 589277 | 14 Jun 2021 | B Parking Floor 2 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji RMC | 130 | 43.05 | Meghna Gunge | 59847 | Raised | 3200
GANGA DHAM TOWERS | 589277 | 14 Jun 2021 | B Parking Floor 2 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji RMC | 188 | 58 | Meghna Gunge | 59577 | Raised | 2183
GANGA DHAM TOWERS | 589277 | 14 Jun 2021 | B Parking Floor 2 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji RMC | 130 | 81 | NIKHIL ATRE | 59860 | Raised | 3694
GANGA DHAM TOWERS | 590072 | 30 Jun 2021 | Trimix Road Ramp outside RCC Pardi | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 2.95 | 2.95 | kantilal.jagtap | 59621 | Raised | 3200
GANGA DHAM TOWERS | 590073 | 30 Jun 2021 | EWS Bldg RCC 9th Slab RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 0.67 | 0.67 | kantilal.jagtap | 59621 | Raised | 3200
GANGA DHAM TOWERS | 590074 | 30 Jun 2021 | UGWT Pardi Rework extra work M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 0.2 | 0.2 | kantilal.jagtap | 59621 | Raised | 3200
GANGA DHAM TOWERS | 590075 | 30 Jun 2021 | B Type Retaining Wall RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 0.27 | 0.27 | kantilal.jagtap | 59621 | Raised | 3200
GANGA DHAM TOWERS | 590076 | 30 Jun 2021 | EWS Bldg 11th to 12th Slab RCC Column RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 24.45 | 24.45 | kantilal.jagtap | 59621 | Raised | 3200
GANGA DHAM TOWERS | 590077 | 30 Jun 2021 | EWS RCC Slab,Beam,Column,RMC M25 (S-M Mix) - | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 0.31 | 0.31 | kantilal.jagtap | 59621 | Raised | 3200
GANGA DHAM TOWERS | 590078 | 30 Jun 2021 | A Bldg RCC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 21.6 | 21.6 | kantilal.jagtap | 59621 | Raised | 3200
GANGA DHAM TOWERS | 592644 | 09 Aug 2021 | A Parking Floor 2 Trimix ( M)- | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji RMC | 110 | 39 | sanket patil | 60002 | Raised | 3009
GANGA DHAM TOWERS | 592644 | 09 Aug 2021 | A Parking Floor 2 Trimix ( M)- | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji RMC | 17 | 17 | SANKET PATIL | 60442 | Raised | 3735
GANGA DHAM TOWERS | 592644 | 09 Aug 2021 | A Parking Floor 2 Trimix ( M)- | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji RMC | 110 | 30 | Meghna Gunge | 60001 | Raised | 3750
GANGA DHAM TOWERS | 592644 | 09 Aug 2021 | A Parking Floor 2 Trimix ( M)- | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji RMC | 16 | 16 | SANKET PATIL | 60284 | Raised | 3009
GANGA DHAM TOWERS | 592644 | 09 Aug 2021 | A Parking Floor 2 Trimix ( M)- | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji RMC | 25 | 8 | SANKET PATIL | 60283 | Raised | 3525
GANGA DHAM TOWERS | 594096 | 23 Aug 2021 | A Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 30.35 | 5 | SANKET PATIL | 60498 | Raised | 3229
GANGA DHAM TOWERS | 594096 | 23 Aug 2021 | A Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 110.35 | 30 | SANKET PATIL | 60308 | Raised | 3694
GANGA DHAM TOWERS | 594096 | 23 Aug 2021 | A Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 16.3 | 6 | SANKET PATIL | 61208 | Raised | 3735
GANGA DHAM TOWERS | 594096 | 23 Aug 2021 | A Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 18 | 18 | SANKET PATIL | 60669 | Raised | 3735
GANGA DHAM TOWERS | 594096 | 23 Aug 2021 | A Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 10.3 | 10.3 | Ranjit Deore | 61378 | Raised | 3229
GANGA DHAM TOWERS | 594096 | 23 Aug 2021 | A Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 110.35 | 7.05 | SANKET PATIL | 60307 | Raised | 3009
GANGA DHAM TOWERS | 594096 | 23 Aug 2021 | A Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 30.35 | 7.35 | SANKET PATIL | 60605 | Raised | 3229
GANGA DHAM TOWERS | 594096 | 23 Aug 2021 | A Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 42.95 | 25 | SANKET PATIL | 60553 | Raised | 3735
GANGA DHAM TOWERS | 594096 | 23 Aug 2021 | A Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 42.95 | 1.65 | SANKET PATIL | 60605 | Raised | 3229
GANGA DHAM TOWERS | 594096 | 23 Aug 2021 | A Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 220 | 109.65 | sanket patil | 60147 | Raised | 3694
GANGA DHAM TOWERS | 600144 | 11 Oct 2021 | B Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : balalji Infra. | 98 | 60 | SANKET PATIL | 60995 | Raised | 3735
GANGA DHAM TOWERS | 600144 | 11 Oct 2021 | B Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : balalji Infra. | 34 | 34 | SANKET PATIL | 61140 | Raised | 3229
GANGA DHAM TOWERS | 600144 | 11 Oct 2021 | B Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : balalji Infra. | 98 | 4 | Sanket Patil | 60996 | Raised | 3229
GANGA DHAM TOWERS | 600144 | 11 Oct 2021 | B Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : balalji Infra. | 110 | 12 | KantilalJ | 60910 | Raised | 3229
GANGA DHAM TOWERS | 600145 | 11 Oct 2021 | A Bldg RCC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : Balaji Infra. | 45 | 28 | SANKET PATIL | 60802 | Raised | 3735
GANGA DHAM TOWERS | 600145 | 11 Oct 2021 | A Bldg RCC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : Balaji Infra. | 12 | 6 | SANKET PATIL | 60991 | Raised | 3735
GANGA DHAM TOWERS | 600145 | 11 Oct 2021 | A Bldg RCC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : Balaji Infra. | 6 | 6 | SANKET PATIL | 61140 | Raised | 3229
GANGA DHAM TOWERS | 600145 | 11 Oct 2021 | A Bldg RCC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : Balaji Infra. | 0.1 | 0.1 | Ranjit Deore | 62597 | Raised | 3229
GANGA DHAM TOWERS | 600145 | 11 Oct 2021 | A Bldg RCC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : Balaji Infra. | 5 | 4.9 | Ranjit Deore | 61378 | Raised | 3229
GANGA DHAM TOWERS | 601079 | 02 Nov 2021 | EWS Bldg RCC 13th Slab RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : Hella | 0.01 | 0.01 | Ranjit Deore | 62597 | Raised | 3229
GANGA DHAM TOWERS | 601079 | 02 Nov 2021 | EWS Bldg RCC 13th Slab RMC M25 (S-M Mix) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : Hella | 71.81 | 71.8 | SANKET PATIL | 60996 | Raised | 3229
GANGA DHAM TOWERS | 606105 | 14 Jan 2022 | A Parking Floor 1 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 75 | 50 | Sanket Patil | 61488 | Raised | 3229
GANGA DHAM TOWERS | 606105 | 14 Jan 2022 | A Parking Floor 1 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 75 | 25 | Sanket Patil | 62597 | Raised | 3229
GANGA DHAM TOWERS | 613476 | 11 May 2022 | EWS RCC Slab,Beam,Column,RMC M25 (S-M Mix) - | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier Balaji infra | 3.16 | 3.16 | kantilal.jagtap | 62926 | Raised | 3229
GANGA DHAM TOWERS | 613619 | 18 May 2022 | B Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : Balaji Infra. | 50 | 50 | SANKET PATIL | 62657 | Raised | 3229
GANGA DHAM TOWERS | 613794 | 21 May 2022 | B Parking Floor 1 Trimix ( M) - 200 | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 50 | 4 | Sanket Patil | 62718 | Raised | 3735
GANGA DHAM TOWERS | 613794 | 21 May 2022 | B Parking Floor 1 Trimix ( M) - 200 | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 3.67 | 3.67 | vinay mittal | 65324 | Raised | 3735
GANGA DHAM TOWERS | 613794 | 21 May 2022 | B Parking Floor 1 Trimix ( M) - 200 | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 10.67 | 7 | SANKET PATIL | 63527 | Raised | 3925
GANGA DHAM TOWERS | 613794 | 21 May 2022 | B Parking Floor 1 Trimix ( M) - 200 | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 46 | 35.33 | SANKET PATIL | 63461 | Raised | 3229
GANGA DHAM TOWERS | 614730 | 04 Jun 2022 | A Parking Floor 1 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : Balaji Infra. | 100 | 30.39 | Sanket Patil | 62851 | Raised | 3229
GANGA DHAM TOWERS | 614730 | 04 Jun 2022 | A Parking Floor 1 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : Balaji Infra. | 69.61 | 51.5 | SANKET PATIL | 64076 | Raised | 3853
GANGA DHAM TOWERS | 614730 | 04 Jun 2022 | A Parking Floor 1 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : Balaji Infra. | 18.11 | 18.11 | vinay mittal | 64499 | Raised | 3735
GANGA DHAM TOWERS | 615175 | 11 Jun 2022 | Ews STP concrete | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 45.51 | 34.84 | Parshuram kore | 62926 | Raised | 3229
GANGA DHAM TOWERS | 615175 | 11 Jun 2022 | Ews STP concrete | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 10.67 | 10.67 | KantilalJ | 63056 | Raised | 3229
GANGA DHAM TOWERS | 617069 | 29 Jun 2022 | EWS RCC Slab,Beam,Column,RMC M25 (S-M Mix) - | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier Balaji infra | 20 | 20 | Sanket Patil | 63070 | Raised | 3229
GANGA DHAM TOWERS | 619492 | 24 Aug 2022 | EWS RCC Slab,Beam,Column,RMC M25 (S-M Mix) - | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji infra. | 15 | 6 | vinay mittal | 63984 | Raised | 3853
GANGA DHAM TOWERS | 619492 | 24 Aug 2022 | EWS RCC Slab,Beam,Column,RMC M25 (S-M Mix) - | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Balaji infra. | 9 | 9 | SANKET PATIL | 64095 | Raised | 3735
GANGA DHAM TOWERS | 626520 | 30 Nov 2022 | A Ground Floor Parking Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : ACC Ltd. | 50 | 50 | vinay mittal | 65324 | Raised | 3735
GANGA DHAM TOWERS | 626521 | 30 Nov 2022 | A Ground Floor Parking Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : Hella Infra. | 10.35 | 10.35 | SANKET PATIL | 65374 | Raised | 3693
GANGA DHAM TOWERS | 626521 | 30 Nov 2022 | A Ground Floor Parking Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Supplier : Hella Infra. | 50 | 39.65 | Sanket Patil | 64615 | Raised | 3735
GANGA DHAM TOWERS | 627453 | 09 Dec 2022 | EWS RCC Slab,Beam,Column,RMC M25 (S-M Mix) - | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Hella Infra. | 30.236 | 30.236 | Sanket Patil | 64222 | Raised | 3735
GANGA DHAM TOWERS | 627454 | 09 Dec 2022 | A Parking Floor 1 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Hella Infra. | 42 | 42 | Sanket Patil | 64222 | Raised | 3735
GANGA DHAM TOWERS | 627455 | 09 Dec 2022 | A Ground Floor Parking Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | supplier : ACC Ltd. | 30 | 30 | vinay mittal | 64499 | Raised | 3735
GANGA DHAM TOWERS | 632147 | 27 Jan 2023 | A Ground Floor Parking Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Hella Infra. | 87 | 9.63 | Vinay Mittal | 66714 | Raised | 3735
GANGA DHAM TOWERS | 632147 | 27 Jan 2023 | A Ground Floor Parking Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Hella Infra. | 27 | 27 | vinay mittal | 65324 | Raised | 3735
GANGA DHAM TOWERS | 632147 | 27 Jan 2023 | A Ground Floor Parking Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs | Hella Infra. | 87 | 23 | VINAY MITTAL | 65111 | Raised | 3693
GANGA DHAM TOWERS | 643891 | 29 Apr 2023 | UGWT Extension RCC Work for Wall concrete | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 24.098 | 18.15 | SANKET PATIL | 65522 | Raised | 3693
GANGA DHAM TOWERS | 644007 | 04 May 2023 | D Building UGWT Concrete Work | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 25 | 25 | Sanket Patil | 65408 | Raised | 3693
GANGA DHAM TOWERS | 648405 | 13 Jun 2023 | Meditation Hall Plinth Beam Concrete | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 8.699 | 8.699 | RAKESH WAGHMARE | 65718 | Raised | 3735
GANGA DHAM TOWERS | 656092 | 19 Jul 2023 | D Building UGWT Concrete Work | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 15 | 15 | AKSHADA MAHAJAN | 66039 | Raised | 3735
GANGA DHAM TOWERS | 656154 | 20 Jul 2023 | STP-A.B.C Deck Slab steel & concrete | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 8 | 8 | AKSHADA MAHAJAN | 66081 | Raised | 3735
GANGA DHAM TOWERS | 656240 | 26 Jul 2023 | B Parking Floor 3 Trimix ( M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 58 | 58 | AKSHADA MAHAJAN | 66087 | Raised | 3735
GANGA DHAM TOWERS | 696937 | 22 May 2024 | Meditation Hall 1st slab Concrete M25 | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 5.42 | 5.42 | Sajid khan | 68714 | Raised | 3824
GANGA DHAM TOWERS | 706703 | 15 Jul 2024 | Meditation Hall Column upto plinth (M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 4.5 | 4.5 | kantilal.jagtap | 69267 | Raised | 4023
GANGA DHAM TOWERS | 706704 | 15 Jul 2024 | Meditation Hall Footing Concrete- M25 | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 1.55 | 1.55 | kantilal.jagtap | 69267 | Raised | 4023
GANGA DHAM TOWERS | 706705 | 15 Jul 2024 | Meditation Hall GF to 1st Column Concrete | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 6.75 | 6.75 | kantilal.jagtap | 69267 | Raised | 4023
GANGA DHAM TOWERS | 706706 | 15 Jul 2024 | Meditation Hall 1st Slab Beam Concrete | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 9.195 | 9.195 | kantilal.jagtap | 69267 | Raised | 4023
GANGA DHAM TOWERS | 706707 | 15 Jul 2024 | 150 Numbers Flag Foundation | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 10 | 10 | kantilal.jagtap | 69267 | Raised | 4023
GANGA DHAM TOWERS | 707314 | 22 Jul 2024 | Meditation Hall Footing (M) | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 9.11 | 9.11 | SANKET PATIL | 69317 | Raised | 4023
GANGA DHAM TOWERS | 707315 | 22 Jul 2024 | UGWT Extension RCC Work for Wall concrete | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 5.948 | 5.948 | SANKET PATIL | 69317 | Raised | 4023
GANGA DHAM TOWERS | 707323 | 23 Jul 2024 | EWS STP Pump Room RCC Work | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 9.03 | 9.03 | kantilal.jagtap | 69326 | Raised | 4023
GANGA DHAM TOWERS | 707324 | 23 Jul 2024 | D Building UGWT Concrete Work | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 45.67 | 45.67 | kantilal.jagtap | 69326 | Raised | 4023