## Requisition_Tracking63857951602
Requisition Tracking
From 01-08-2023 To 31-07-2024
Page 1 of 1
Total Records: 9 Records 1 to 9
Project | Req SrNo | Req Date | Task Name | Material Name | Unit | Specifications | Qty | App Qty | Approve Details | PO No. | PO Status | Rate
GANGA ALTUS | 674388 | 02 Dec 2023 | In F-Building Storm Water Line-In F-Bldg | RCC NP2 Class Pipe 12" | Mtrs |  | 31.83 | 31 | Sajid khan | 67426 | Raised | 407
GANGA ALTUS | 674388 | 02 Dec 2023 | In F-Building Storm Water Line-In F-Bldg | RCC NP2 Class Pipe 12" | Mtrs |  | 0.83 | 0.83 | Sajid khan | 0 | Pending | 0
GANGA ALTUS | 674389 | 02 Dec 2023 | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | RCC NP2 Class Pipe 12" | Mtrs |  | 130 | 130 | Sajid khan | 67426 | Raised | 407
GANGA ALTUS | 674564 | 03 Dec 2023 | Ele.Line -Transf. R to FBldg.-As per Sit | RCC NP2 Class Pipe 12" | Mtrs |  | 65 | 65 | SANKET PATIL | 69292 | Raised | 481
GANGA ALTUS | 674565 | 03 Dec 2023 | Ele.Line -Transformer R to F Bldg. | RCC NP2 Class Pipe 12" | Mtrs |  | 156 | 156 | SANKET PATIL | 69292 | Raised | 481
GANGA ALTUS | 674567 | 03 Dec 2023 | Ele.Line-D Bldg.to F Bldg. | RCC NP2 Class Pipe 12" | Mtrs |  | 216 | 216 | SANKET PATIL | 69292 | Raised | 481
GANGA ALTUS | 674568 | 03 Dec 2023 | Ele.Line-F Bldg. to Club House | RCC NP2 Class Pipe 12" | Mtrs |  | 100 | 100 | SANKET PATIL | 69292 | Raised | 481
GANGA ALTUS | 674570 | 03 Dec 2023 | Ele.Line-Common Electrical Meter Line | RCC NP2 Class Pipe 12" | Mtrs |  | 239 | 239 | SANKET PATIL | 69292 | Raised | 481
GANGA ALTUS | 674570 | 03 Dec 2023 | Ele.Line-Common Electrical Meter Line | RCC NP2 Class Pipe 12" | Mtrs |  | 360 | 121 | Sajid khan | 67426 | Raised | 407