## Requisition_Tracking63859748116
Requisition Tracking
From 16-07-2024 To 21-08-2024
Page 1 of 1
Total Records: 446 Records 1 to 446
Project | Req SrNo | Req Date | Task Name | Material Name | Unit | Specifications | Qty | App Qty | Approve Details | PO No. | PO Status | Rate
SRA MORWADI | 707362 | 29 Jul 2024 | A.Grid Slab 150mm Thk. (Raft GRN Done here) | Cement Loose 53 Grade | Metric Tonnes |  | 0.25 | 0.25 | GULSHAN GANGWANI | 0 | Pending | 0
SRA MORWADI | 707709 | 01 Aug 2024 | B Building 4th Slab Non Str. wall steel | GFRP Bars 8mm | Kgs |  | 331.59 | 331.59 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 707710 | 01 Aug 2024 | B Building 5th Slab Non Str. wall steel | GFRP Bars 8mm | Kgs |  | 331.59 | 331.59 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 707711 | 01 Aug 2024 | A Building 7th Slab Non Str. wall steel | GFRP Bars 8mm | Kgs |  | 147.86 | 147.86 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 707712 | 01 Aug 2024 | A Building 8th Slab Non Str. wall steel | GFRP Bars 8mm | Kgs |  | 358.21 | 358.21 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 707713 | 01 Aug 2024 | B Building 6th Slab Non Str. wall steel | GFRP Bars 8mm | Kgs |  | 331.59 | 331.59 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 707714 | 01 Aug 2024 | B Building 7th Slab Non Str. wall steel | GFRP Bars 8mm | Kgs |  | 331.59 | 331.59 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 707715 | 01 Aug 2024 | B Building 8th Slab Non Str. wall steel | GFRP Bars 8mm | Kgs |  | 331.59 | 331.59 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 710807 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710808 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710809 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710810 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710811 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710812 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710813 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710814 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710815 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710816 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710817 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710818 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710819 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710820 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI Angle Valve With Flange 1/2" | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710821 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710822 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710823 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710824 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710825 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710826 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710827 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710828 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710829 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710830 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710831 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710832 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710833 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710834 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI Basin Piller Cock | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710835 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710836 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710837 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710838 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710839 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710840 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710841 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710842 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710843 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710844 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710845 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710846 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710847 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710848 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI Connector Pipe 1/2" x 2' | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710849 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710850 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710851 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710852 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710853 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710854 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710855 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710856 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710857 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710858 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710859 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710860 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710861 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710862 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI CP Bib Cock With Nozzle | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710863 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710864 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710865 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710866 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710867 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710868 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710869 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710870 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710871 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710872 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710873 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710874 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710875 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710876 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI Flush Tank | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710877 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710878 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710879 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710880 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710881 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710882 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710883 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710884 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710885 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710886 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710887 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710888 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710889 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710890 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI PVC Jali 6" With Cover | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710891 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710892 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710893 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710894 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710895 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710896 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710897 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710898 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710899 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710900 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710901 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710902 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710903 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710904 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI PVC Jali With Cover& Hole (6"x6") | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710905 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710906 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710907 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710908 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710909 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710910 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710911 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710912 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710913 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710914 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710915 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710916 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710917 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710918 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI Shower Arm With Flange | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710919 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710920 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710921 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710922 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710923 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710924 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710925 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710926 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710927 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710928 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710929 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710930 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710931 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710932 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI Shower Head | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710933 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710934 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710935 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710936 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710937 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710938 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710939 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710940 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710941 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710942 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710943 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710944 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710945 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710946 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI Sink Tap With Flange | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710947 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710948 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710949 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710950 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710951 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710952 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710953 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710954 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710955 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710956 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710957 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710958 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710959 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710960 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI Wall Mixer With Provision | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710961 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710962 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710963 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710964 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710965 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710966 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710967 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710968 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710969 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710970 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710971 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710972 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710973 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710974 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI Waste Coupling 32MM Half Threaded | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710975 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710976 | 01 Aug 2024 | A-Flat No 301 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710977 | 01 Aug 2024 | A-Flat No 303 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710978 | 01 Aug 2024 | A-Flat No 304 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710979 | 01 Aug 2024 | A-Flat No 305 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710980 | 01 Aug 2024 | A-Flat No 306 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710981 | 01 Aug 2024 | A-Flat No 307 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710982 | 01 Aug 2024 | A-Flat No 308 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710983 | 01 Aug 2024 | A-Flat No 309 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710984 | 01 Aug 2024 | A-Flat No 310 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710985 | 01 Aug 2024 | A-Flat No 311 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710986 | 01 Aug 2024 | A-Flat No 312 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710987 | 01 Aug 2024 | A-Flat No 313 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710988 | 01 Aug 2024 | A-Flat No 314 CP Fittings | ISI Waste Pipe | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710989 | 01 Aug 2024 | A-Flat No 301 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710990 | 01 Aug 2024 | A-Flat No 302 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710991 | 01 Aug 2024 | A-Flat No 303 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710992 | 01 Aug 2024 | A-Flat No 304 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710993 | 01 Aug 2024 | A-Flat No 305 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710994 | 01 Aug 2024 | A-Flat No 306 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710995 | 01 Aug 2024 | A-Flat No 307 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710996 | 01 Aug 2024 | A-Flat No 308 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710997 | 01 Aug 2024 | A-Flat No 309 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710998 | 01 Aug 2024 | A-Flat No 310 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 710999 | 01 Aug 2024 | A-Flat No 311 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711000 | 01 Aug 2024 | A-Flat No 312 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711001 | 01 Aug 2024 | A-Flat No 313 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711002 | 01 Aug 2024 | A-Flat No 314 Sanitary Fittings | ISI Corner Wash Basin With Ragbolts | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711003 | 01 Aug 2024 | A-Flat No 301 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711004 | 01 Aug 2024 | A-Flat No 302 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711005 | 01 Aug 2024 | A-Flat No 303 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711006 | 01 Aug 2024 | A-Flat No 304 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711007 | 01 Aug 2024 | A-Flat No 305 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711008 | 01 Aug 2024 | A-Flat No 306 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711009 | 01 Aug 2024 | A-Flat No 307 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711010 | 01 Aug 2024 | A-Flat No 308 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711011 | 01 Aug 2024 | A-Flat No 309 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711012 | 01 Aug 2024 | A-Flat No 310 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711013 | 01 Aug 2024 | A-Flat No 311 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711014 | 01 Aug 2024 | A-Flat No 312 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711015 | 01 Aug 2024 | A-Flat No 313 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711016 | 01 Aug 2024 | A-Flat No 314 Sanitary Fittings | ISI Kitchen Sink | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711017 | 01 Aug 2024 | A-Flat No 301 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711018 | 01 Aug 2024 | A-Flat No 302 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711019 | 01 Aug 2024 | A-Flat No 303 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711020 | 01 Aug 2024 | A-Flat No 304 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711021 | 01 Aug 2024 | A-Flat No 305 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711022 | 01 Aug 2024 | A-Flat No 306 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711023 | 01 Aug 2024 | A-Flat No 307 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711024 | 01 Aug 2024 | A-Flat No 308 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711025 | 01 Aug 2024 | A-Flat No 309 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711026 | 01 Aug 2024 | A-Flat No 310 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711027 | 01 Aug 2024 | A-Flat No 311 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711028 | 01 Aug 2024 | A-Flat No 312 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711029 | 01 Aug 2024 | A-Flat No 313 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711030 | 01 Aug 2024 | A-Flat No 314 Sanitary Fittings | ISI Orisa Pan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711031 | 01 Aug 2024 | A-301 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 87.932 | 87.932 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711032 | 01 Aug 2024 | A-301 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 103.056 | 103.056 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711033 | 01 Aug 2024 | A-302 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 87.932 | 87.932 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711034 | 01 Aug 2024 | A-302 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711035 | 01 Aug 2024 | A-303 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.05 | 94.05 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711036 | 01 Aug 2024 | A-303 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711037 | 01 Aug 2024 | A-304 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.468 | 94.468 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711038 | 01 Aug 2024 | A-304 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711039 | 01 Aug 2024 | A-305 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.05 | 94.05 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711040 | 01 Aug 2024 | A-305 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711041 | 01 Aug 2024 | A-306 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.886 | 94.886 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711042 | 01 Aug 2024 | A-306 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711043 | 01 Aug 2024 | A-307 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.468 | 94.468 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711044 | 01 Aug 2024 | A-307 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711045 | 01 Aug 2024 | A-308 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.468 | 94.468 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711046 | 01 Aug 2024 | A-308 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711047 | 01 Aug 2024 | A-309 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 90.782 | 90.782 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711048 | 01 Aug 2024 | A-309 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711049 | 01 Aug 2024 | A-310 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 90.782 | 90.782 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711050 | 01 Aug 2024 | A-310 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.526 | 105.526 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711051 | 01 Aug 2024 | A-311 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 90.782 | 90.782 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711052 | 01 Aug 2024 | A-311 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711053 | 01 Aug 2024 | A-312 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 90.782 | 90.782 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711054 | 01 Aug 2024 | A-312 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711055 | 01 Aug 2024 | A-313 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 95.95 | 95.95 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711056 | 01 Aug 2024 | A-313 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711057 | 01 Aug 2024 | A-314 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 87.932 | 87.932 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711058 | 01 Aug 2024 | A-314 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 103.056 | 103.056 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711419 | 03 Aug 2024 | A-401 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 87.932 | 87.932 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711420 | 03 Aug 2024 | A-401 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 103.056 | 103.056 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711421 | 03 Aug 2024 | A-402 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 87.932 | 87.932 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711422 | 03 Aug 2024 | A-402 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711423 | 03 Aug 2024 | A-403 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.05 | 94.05 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711424 | 03 Aug 2024 | A-403 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711425 | 03 Aug 2024 | A-404 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.468 | 94.468 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711426 | 03 Aug 2024 | A-404 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711427 | 03 Aug 2024 | A-405 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.05 | 94.05 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711428 | 03 Aug 2024 | A-405 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711429 | 03 Aug 2024 | A-406 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.886 | 94.886 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711430 | 03 Aug 2024 | A-406 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711431 | 03 Aug 2024 | A-407 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.468 | 94.468 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711432 | 03 Aug 2024 | A-407 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711433 | 03 Aug 2024 | A-408 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 94.468 | 94.468 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711434 | 03 Aug 2024 | A-408 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711435 | 03 Aug 2024 | A-409 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 90.782 | 90.782 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711436 | 03 Aug 2024 | A-409 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711437 | 03 Aug 2024 | A-410 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 90.782 | 90.782 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711438 | 03 Aug 2024 | A-410 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.526 | 105.526 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711439 | 03 Aug 2024 | A-411 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 90.782 | 90.782 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711440 | 03 Aug 2024 | A-411 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711441 | 03 Aug 2024 | A-412 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 90.782 | 90.782 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711442 | 03 Aug 2024 | A-412 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711443 | 03 Aug 2024 | A-413 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 95.95 | 95.95 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711444 | 03 Aug 2024 | A-413 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 105.108 | 105.108 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711445 | 03 Aug 2024 | A-414 Balcony Waterproofing Work | Red Bricks 4" | No. |  | 87.932 | 87.932 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711446 | 03 Aug 2024 | A-414 WC & Bath Brickbat Work | Red Bricks 4" | No. |  | 103.056 | 103.056 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711447 | 03 Aug 2024 | A-301 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.3304 | 8.3304 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711448 | 03 Aug 2024 | A-301 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.136 | 8.136 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711449 | 03 Aug 2024 | A-302 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.3304 | 8.3304 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711450 | 03 Aug 2024 | A-302 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711451 | 03 Aug 2024 | A-303 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.91 | 8.91 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711452 | 03 Aug 2024 | A-303 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711453 | 03 Aug 2024 | A-304 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9496 | 8.9496 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711454 | 03 Aug 2024 | A-304 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711455 | 03 Aug 2024 | A-305 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.91 | 8.91 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711456 | 03 Aug 2024 | A-305 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711457 | 03 Aug 2024 | A-306 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9892 | 8.9892 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711458 | 03 Aug 2024 | A-306 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711459 | 03 Aug 2024 | A-307 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9496 | 8.9496 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711460 | 03 Aug 2024 | A-307 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711461 | 03 Aug 2024 | A-308 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9496 | 8.9496 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711462 | 03 Aug 2024 | A-308 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711463 | 03 Aug 2024 | A-309 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711464 | 03 Aug 2024 | A-309 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711465 | 03 Aug 2024 | A-310 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711466 | 03 Aug 2024 | A-310 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.331 | 8.331 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711467 | 03 Aug 2024 | A-311 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711468 | 03 Aug 2024 | A-311 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711469 | 03 Aug 2024 | A-312 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711470 | 03 Aug 2024 | A-312 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711471 | 03 Aug 2024 | A-313 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 9.09 | 9.09 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711472 | 03 Aug 2024 | A-313 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711473 | 03 Aug 2024 | A-314 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.3304 | 8.3304 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711474 | 03 Aug 2024 | A-314 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.136 | 8.136 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711475 | 03 Aug 2024 | A-401 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.3304 | 8.3304 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711476 | 03 Aug 2024 | A-401 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.136 | 8.136 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711477 | 03 Aug 2024 | A-402 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.3304 | 8.3304 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711478 | 03 Aug 2024 | A-402 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711479 | 03 Aug 2024 | A-403 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.91 | 8.91 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711480 | 03 Aug 2024 | A-403 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711481 | 03 Aug 2024 | A-404 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9496 | 8.9496 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711482 | 03 Aug 2024 | A-404 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711483 | 03 Aug 2024 | A-405 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.91 | 8.91 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711484 | 03 Aug 2024 | A-405 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711485 | 03 Aug 2024 | A-406 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9892 | 8.9892 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711486 | 03 Aug 2024 | A-406 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711487 | 03 Aug 2024 | A-407 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9496 | 8.9496 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711488 | 03 Aug 2024 | A-407 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711489 | 03 Aug 2024 | A-408 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9496 | 8.9496 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711490 | 03 Aug 2024 | A-408 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711491 | 03 Aug 2024 | A-409 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711492 | 03 Aug 2024 | A-409 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711493 | 03 Aug 2024 | A-410 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711494 | 03 Aug 2024 | A-410 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.331 | 8.331 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711495 | 03 Aug 2024 | A-411 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711496 | 03 Aug 2024 | A-411 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711497 | 03 Aug 2024 | A-412 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711498 | 03 Aug 2024 | A-412 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711499 | 03 Aug 2024 | A-413 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 9.09 | 9.09 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711500 | 03 Aug 2024 | A-413 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711501 | 03 Aug 2024 | A-414 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.3304 | 8.3304 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711502 | 03 Aug 2024 | A-414 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.136 | 8.136 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711503 | 03 Aug 2024 | A-501 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.3304 | 8.3304 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711504 | 03 Aug 2024 | A-501 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.136 | 8.136 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711505 | 03 Aug 2024 | A-502 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.3304 | 8.3304 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711506 | 03 Aug 2024 | A-502 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711507 | 03 Aug 2024 | A-503 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.91 | 8.91 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711508 | 03 Aug 2024 | A-503 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711509 | 03 Aug 2024 | A-504 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9496 | 8.9496 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711510 | 03 Aug 2024 | A-504 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711511 | 03 Aug 2024 | A-505 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.91 | 8.91 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711512 | 03 Aug 2024 | A-505 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711513 | 03 Aug 2024 | A-506 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9892 | 8.9892 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711514 | 03 Aug 2024 | A-506 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711515 | 03 Aug 2024 | A-507 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9496 | 8.9496 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711516 | 03 Aug 2024 | A-507 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711517 | 03 Aug 2024 | A-508 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.9496 | 8.9496 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711518 | 03 Aug 2024 | A-508 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711519 | 03 Aug 2024 | A-509 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711520 | 03 Aug 2024 | A-509 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711521 | 03 Aug 2024 | A-510 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711522 | 03 Aug 2024 | A-510 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.331 | 8.331 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711523 | 03 Aug 2024 | A-511 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711524 | 03 Aug 2024 | A-511 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711525 | 03 Aug 2024 | A-512 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.6004 | 8.6004 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711526 | 03 Aug 2024 | A-512 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711527 | 03 Aug 2024 | A-513 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 9.09 | 9.09 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711528 | 03 Aug 2024 | A-513 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.298 | 8.298 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711529 | 03 Aug 2024 | A-514 Balcony Waterproofing Work | M Sand | Cu.Ft |  | 8.3304 | 8.3304 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711530 | 03 Aug 2024 | A-514 WC & Bath Brickbat Work | M Sand | Cu.Ft |  | 8.136 | 8.136 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711531 | 03 Aug 2024 | A Bldg 4th Slab Curing & Other Material | Crush Sand | Cu.Ft |  | 100 | 100 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711532 | 03 Aug 2024 | A Bldg 5th Slab Curing & Other material | Crush Sand | Cu.Ft |  | 100 | 100 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711533 | 03 Aug 2024 | B Bldg 4th Slab Curing & Other Material | Crush Sand | Cu.Ft |  | 100 | 100 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711534 | 03 Aug 2024 | A Bldg 6th Slab Curing &amp; Other material | Crush Sand | Cu.Ft |  | 100 | 100 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711535 | 03 Aug 2024 | A Bldg 7th Slab Curing &amp; Other material | Crush Sand | Cu.Ft |  | 100 | 100 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711536 | 03 Aug 2024 | B Bldg 5th Slab Curing &amp; Other Material | Crush Sand | Cu.Ft |  | 100 | 100 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711537 | 03 Aug 2024 | B Bldg 6th Slab Curing &amp; Other Material | Crush Sand | Cu.Ft |  | 100 | 100 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711654 | 03 Aug 2024 | A-Bldg Aluform Mis. Consumables For Shuttering | Kicker Nut 16mm | No. |  | 6303 | 6303 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711655 | 03 Aug 2024 | A-Bldg Aluform Mis. Consumables For Shuttering | Kicker Washer | No. |  | 6303 | 6303 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711656 | 03 Aug 2024 | A-Bldg Aluform Mis. Consumables For Shuttering | Kicker Bolt 16mm x 75mm | No. |  | 6303 | 6303 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711657 | 03 Aug 2024 | A-Bldg Aluform Mis. Consumables For Shuttering | PVC Cone | No. |  | 3828 | 3828 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711668 | 03 Aug 2024 | Phase 1 New Office Electrical Material | Ceiling Fan | No. |  | 4 | 4 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711671 | 03 Aug 2024 | Phase 1 New Office Electrical Material | Exhaust Fan | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711674 | 03 Aug 2024 | Phase 1 New Office Electrical Material | Anchor Fastner 10mmx100mm | No. |  | 10 | 10 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711682 | 03 Aug 2024 | Phase 1 New Office Electrical Material | 12 module surface box | No. |  | 5 | 5 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711683 | 03 Aug 2024 | Phase 1 New Office Electrical Material | 8 Module Surface Box | No. |  | 5 | 5 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 711684 | 03 Aug 2024 | Phase 1 New Office Electrical Material | 8 Module Surface plate | No. |  | 5 | 5 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712258 | 07 Aug 2024 | A Bldg 3rd To 4th Slab column & non str. wall concrete | Sand-Metal Mix M30 hi-flow (Pumpable) | Cu.Mtrs |  | 0.85 | 0.85 | GULSHAN GANGWANI | 0 | Pending | 0
SRA MORWADI | 712415 | 09 Aug 2024 | New Office Capital BBM & Plaster Work | M Sand | Cu.Ft |  | 200 | 200 | KANTILAL.JAGTAP | 0 | Pending | 0
SRA MORWADI | 712465 | 10 Aug 2024 | B1-3rd Slab,Beam Concrete | Sand-Metal Mix M25 (Pumpable) | Cu.Mtrs |  | 1.3 | 1.3 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712471 | 10 Aug 2024 | UGWT Padadi Concrete | Sand-Metal Mix M25 (Downpour) | Cu.Mtrs |  | 10 | 2 | AKSHADA MAHAJAN | 0 | Pending | 0
SRA MORWADI | 712481 | 12 Aug 2024 | New HO 2nd Floor PPRC Material | PPR-C End Cap 20mm | No. |  | 4 | 4 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712518 | 12 Aug 2024 | New HO 2nd Floor CP & Sanitary Fittings | Flush Tank (Full Frame) JCS-WHT-2400FP | No. |  | 2 | 2 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 712519 | 12 Aug 2024 | New HO 2nd Floor CP & Sanitary Fittings | Flush Plate JCT-CHR-152415 | No. |  | 2 | 2 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 712520 | 12 Aug 2024 | New HO 2nd Floor CP & Sanitary Fittings | Urinal URS-WHT-13253N | No. |  | 1 | 1 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 712521 | 12 Aug 2024 | New HO 2nd Floor CP & Sanitary Fittings | Urinal Sensor -SNR-STL-51087 | No. |  | 1 | 1 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 712522 | 12 Aug 2024 | New HO 2nd Floor CP & Sanitary Fittings | Wash Basin (Corner) with coupling JDS-WHT-25841 | No. |  | 1 | 1 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 712523 | 12 Aug 2024 | New HO 2nd Floor CP & Sanitary Fittings | Wash Basin (Regular) with coupling CMS-WHT-813 | No. |  | 1 | 1 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 712524 | 12 Aug 2024 | New HO 2nd Floor CP & Sanitary Fittings | Bottle Trap ALD-769L250X190 | No. |  | 3 | 3 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 712525 | 12 Aug 2024 | New HO 2nd Floor CP & Sanitary Fittings | Two-way Bib Cock FUS-29041 | No. |  | 2 | 2 | SANKET PATIL | 0 | Pending | 0
SRA MORWADI | 712532 | 13 Aug 2024 | Safety Setup -Safety PPE & Equipments | Helmet Green for Safety | No. |  | 5 | 5 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712533 | 13 Aug 2024 | Safety Setup -Safety PPE & Equipments | Safety Jacket | No. |  | 10 | 10 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712719 | 14 Aug 2024 | A Bldg Aluform Misc. Consumable | Plumbing Nails 2.5" | Kgs |  | 100 | 100 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712722 | 14 Aug 2024 | Phase 1 Curing Materail | ASTM Pipe 1/2" x 10 fts | No. |  | 10 | 10 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712723 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Pipe 1/2" x 10 fts | No. |  | 4 | 4 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712724 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Elbow 1/2" | No. |  | 10 | 10 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712725 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Brass Elbow 1/2" | No. |  | 3 | 3 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712726 | 14 Aug 2024 | Phase 1 Curing Materail | ASTM Tee 1-1/2" | No. |  | 10 | 10 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712727 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Tee 1-1/2" | No. |  | 3 | 3 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712728 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Pipe 3/4" x 10 fts | No. |  | 3 | 3 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712729 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Socket 1/2" | No. |  | 6 | 6 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712730 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Elbow 4" | No. |  | 6 | 6 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712731 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Elbow 1-1/2" | No. |  | 4 | 4 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712732 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Pipe 1-1/2" x 10fts | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712733 | 14 Aug 2024 | Phase 1 Site office Plumbing material | PVC Solvent (500 ml.) - | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712734 | 14 Aug 2024 | Phase 1 Site office Plumbing material | PVC Multifloor Trap 4" | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712735 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Pipe 11/4" x 10 fts | No. |  | 2 | 2 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712736 | 14 Aug 2024 | Phase 1 Site office Plumbing material | PVC Door Bend 4" | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712737 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Reducer Bushing 4" x 1.5" | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712738 | 14 Aug 2024 | Phase 1 Site office Plumbing material | PVC Double Y 4" | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712739 | 14 Aug 2024 | Phase 1 Site office Plumbing material | PVC Door Bend 2.5" | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712740 | 14 Aug 2024 | Phase 1 Site office Plumbing material | ASTM Tee 3/4" | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712742 | 14 Aug 2024 | Phase 1 Curing Materail | Plumbing Nails 11/2" | Kgs |  | 5 | 5 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712743 | 14 Aug 2024 | Office & Store Setup | Self tapping screw 5.5 x 25mm | Pack |  | 10 | 10 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712744 | 14 Aug 2024 | Phase 1 Curing Materail | Curing Pipe 1/2" | Bundle |  | 3 | 3 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712745 | 14 Aug 2024 | Phase 1 Curing Materail | GI Clamps - 1-1/2" | No. |  | 60 | 60 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712746 | 14 Aug 2024 | Phase 1 Curing Materail | GI Clamps - 2" | No. |  | 60 | 60 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712747 | 14 Aug 2024 | A&B Building Safety Fastner | Anchor Fastner 10mmx75mm | No. |  | 260 | 260 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712748 | 14 Aug 2024 | A-Drill Bits | Drill Bit 8mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712749 | 14 Aug 2024 | B-Drill Bits | Drill Bit 8mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712750 | 14 Aug 2024 | A-Drill Bits | Drill Bit 10mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712751 | 14 Aug 2024 | B-Drill Bits | Drill Bit 10mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712752 | 14 Aug 2024 | A-Drill Bits | Drill Bit 12mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712753 | 14 Aug 2024 | B-Drill Bits | Drill Bit 12mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712754 | 14 Aug 2024 | A-Drill Bits | Drill Bit 16mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712755 | 14 Aug 2024 | B-Drill Bits | Drill Bit 16mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712756 | 14 Aug 2024 | A-Drill Bits | Drill Bit 20mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712757 | 14 Aug 2024 | B-Drill Bits | Drill Bit 20mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712758 | 14 Aug 2024 | A-Drill Bits | Drill Bit 5mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712759 | 14 Aug 2024 | B-Drill Bits | Drill Bit 5mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712760 | 14 Aug 2024 | A-Drill Bits | Drill Bit 6mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712761 | 14 Aug 2024 | B-Drill Bits | Drill Bit 6mm | No. |  | 1 | 1 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712762 | 14 Aug 2024 | Phase 2 Curing work | Curing Pipe 1" | Bundle |  | 4 | 4 | Sajid khan | 0 | Pending | 0
SRA MORWADI | 712769 | 16 Aug 2024 | Phase 1 Site office material | Cupboard | No. |  | 3 | 3 | Sajid khan | 0 | Pending | 0