## StockRegister_Ledger63860270361
Material Transaction Report
From 26-07-2024 To 26-08-2024
Page 1 of 1
Total Records: 139 Records 1 to 139
Project_Name | Store_Name | Material_Group_Name | Material_Name | Unit_Name | DocumentNo | Document_Date | GRN_IssueType | Supplier_Task_Store_name | GRN_Qty | GRN_Rate | GRN_Basic | GRN_Tax | GRN_Value | Issue_Qty | Issue_Rate | Issue_Value | Issue_Type_As | Bal_Qty | Bal_Rate | Bal_Value | Invoice_No | Invoice_Date | Challan_No | Bill_No
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 776934 | Jul 26 2024 3:47PM | Issue-THEORETICAL | 8th Slab (3rd Floor) Slab Steel | 0 | 77.84 | 0 | 0 | 0 | 65 | 77.84 | 5059.6 | Non Returnable / Non Debitable | -65 | 77.84 | -5059.6 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 777261 | Jul 29 2024 12:35PM | Issue-THEORETICAL | Pour 5 108.00 to 111.00 lvl Slab Steel | 0 | 77.84 | 0 | 0 | 0 | 65 | 77.84 | 5059.6 | Non Returnable / Non Debitable | -130 | 77.84 | -10119.2 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 777424 | Jul 30 2024 10:59AM | Issue-THEORETICAL | 8th to 9th Column & SW Steel | 0 | 77.84 | 0 | 0 | 0 | 57.5 | 77.84 | 4475.8 | Non Returnable / Non Debitable | -187.5 | 77.84 | -14595 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 777448 | Jul 30 2024 11:43AM | Issue-THEORETICAL | Pour 3A 108.00 to 111.00 lvl Drop panel Steel | 0 | 77.84 | 0 | 0 | 0 | 58 | 77.84 | 4514.72 | Non Returnable / Non Debitable | -245.5 | 77.84 | -19109.72 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 777760 | Jul 31 2024 6:44PM | Issue-THEORETICAL | 8th to 9th Column & SW Steel | 0 | 77.84 | 0 | 0 | 0 | 67 | 77.84 | 5215.28 | Non Returnable / Non Debitable | -312.5 | 77.84 | -24325 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 778587 | Aug 2 2024 4:07PM | Issue-THEORETICAL | New HO 2nd Floor PPRC Material | 0 | 77.84 | 0 | 0 | 0 | 1 | 77.84 | 77.84 | Non Returnable / Non Debitable | -313.5 | 77.84 | -24402.84 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 778762 | Aug 3 2024 5:27PM | Issue-THEORETICAL | 8th to 9th Column & SW Steel | 0 | 77.84 | 0 | 0 | 0 | 69 | 77.84 | 5370.96 | Non Returnable / Non Debitable | -382.5 | 77.84 | -29773.8 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 778946 | Aug 5 2024 5:54PM | Issue-THEORETICAL | Pour 5 102.00 to 105.00 lvl Slab Steel | 0 | 77.84 | 0 | 0 | 0 | 70 | 77.84 | 5448.8 | Non Returnable / Non Debitable | -452.5 | 77.84 | -35222.6 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 779056 | Aug 6 2024 4:59PM | Issue-THEORETICAL | Pour 5 108.00 to 111.00 lvl Drop panel Steel | 0 | 77.84 | 0 | 0 | 0 | 65 | 77.84 | 5059.6 | Non Returnable / Non Debitable | -517.5 | 77.84 | -40282.2 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 779092 | Aug 6 2024 6:45PM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Beam Steel | 0 | 77.84 | 0 | 0 | 0 | 68 | 77.84 | 5293.12 | Non Returnable / Non Debitable | -585.5 | 77.84 | -45575.32 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 779752 | Aug 10 2024 3:34PM | Issue-THEORETICAL | 8th to 9th Column & SW Steel | 0 | 77.84 | 0 | 0 | 0 | 43 | 77.84 | 3347.12 | Non Returnable / Non Debitable | -628.5 | 77.84 | -48922.44 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 779753 | Aug 10 2024 3:34PM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Beam Steel | 0 | 77.84 | 0 | 0 | 0 | 22 | 77.84 | 1712.48 | Non Returnable / Non Debitable | -650.5 | 77.84 | -50634.92 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 779779 | Aug 10 2024 3:51PM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 77.84 | 0 | 0 | 0 | 65 | 77.84 | 5059.6 | Non Returnable / Non Debitable | -715.5 | 77.84 | -55694.52 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 780217 | Aug 13 2024 2:37PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 77.83 | 0 | 0 | 0 | 61 | 77.83 | 4747.63 | Non Returnable / Non Debitable | -776.5 | 77.8392 | -60442.15 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 780293 | Aug 14 2024 12:23PM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 77.84 | 0 | 0 | 0 | 64 | 77.84 | 4981.76 | Non Returnable / Non Debitable | -840.5 | 77.8393 | -65423.91 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 780493 | Aug 16 2024 3:28PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 77.83 | 0 | 0 | 0 | 68 | 77.83 | 5292.44 | Non Returnable / Non Debitable | -908.5 | 77.8386 | -70716.35 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 780496 | Aug 16 2024 3:31PM | Issue-THEORETICAL | Pour 3 99.00 to 102.00 lvl Column Steel | 0 | 77.8401 | 0 | 0 | 0 | 23.83 | 77.8401 | 1854.93 | Non Returnable / Non Debitable | -932.33 | 77.8386 | -72571.28 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 780497 | Aug 16 2024 3:31PM | Issue-THEORETICAL | Pour 3 99.00 to 102.00 lvl Drop panel Steel | 0 | 77.8396 | 0 | 0 | 0 | 10.04 | 77.8396 | 781.51 | Non Returnable / Non Debitable | -942.37 | 77.8386 | -73352.79 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 780498 | Aug 16 2024 3:31PM | Issue-THEORETICAL | Pour 3 99.00 to 102.00 lvl Slab Steel | 0 | 77.8401 | 0 | 0 | 0 | 12.38 | 77.8401 | 963.66 | Non Returnable / Non Debitable | -954.75 | 77.8386 | -74316.45 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 780499 | Aug 16 2024 3:31PM | Issue-THEORETICAL | Pour 3A 102.00 to 105.00 lvl Drop panel Steel | 0 | 77.84 | 0 | 0 | 0 | 17.75 | 77.84 | 1381.66 | Non Returnable / Non Debitable | -972.5 | 77.8387 | -75698.11 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 780748 | Aug 17 2024 6:46PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 77.83 | 0 | 0 | 0 | 53 | 77.83 | 4124.99 | Non Returnable / Non Debitable | -1025.5 | 77.8382 | -79823.1 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 780870 | Aug 19 2024 6:40PM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Beam Steel | 0 | 77.84 | 0 | 0 | 0 | 37.57 | 77.84 | 2924.45 | Non Returnable / Non Debitable | -1063.07 | 77.8383 | -82747.55 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 780871 | Aug 19 2024 6:40PM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Steel | 0 | 77.84 | 0 | 0 | 0 | 20.69 | 77.84 | 1610.51 | Non Returnable / Non Debitable | -1083.76 | 77.8383 | -84358.06 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 781066 | Aug 20 2024 6:39PM | Issue-THEORETICAL | Pour 3 108.00 to 111.00 lvl Column Steel | 0 | 77.83 | 0 | 0 | 0 | 23.83 | 77.83 | 1854.69 | Non Returnable / Non Debitable | -1107.59 | 77.8381 | -86212.75 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 781067 | Aug 20 2024 6:39PM | Issue-THEORETICAL | Pour 3 108.00 to 111.00 lvl Drop panel Steel | 0 | 77.83 | 0 | 0 | 0 | 48.17 | 77.83 | 3749.07 | Non Returnable / Non Debitable | -1155.76 | 77.8378 | -89961.82 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 781192 | Aug 21 2024 2:25PM | Issue-THEORETICAL | Pour 6 105.00 to 108.00 lvl Drop panel Steel | 0 | 77.84 | 0 | 0 | 0 | 65 | 77.84 | 5059.6 | Non Returnable / Non Debitable | -1220.76 | 77.8379 | -95021.42 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Binding Wire | Kgs | Issue No : 781224 | Aug 21 2024 3:50PM | Issue-THEORETICAL | Pour 5 108.00 to 111.00 lvl Slab Steel | 0 | 77.83 | 0 | 0 | 0 | 73 | 77.83 | 5681.59 | Non Returnable / Non Debitable | -1293.76 | 77.8375 | -100703.01 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | GFRP Bars 8mm | Kgs | Issue No : 780933 | Aug 20 2024 10:37AM | Issue-THEORETICAL | C 8th Slab (4th Floor) Non structural GFRP bars | 0 | 174.64 | 0 | 0 | 0 | 278 | 174.64 | 48549.92 | Non Returnable / Non Debitable | -278 | 174.64 | -48549.92 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bar 25mm | Kgs | Issue No : 780289 | Aug 14 2024 12:17PM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 59.88 | 0 | 0 | 0 | 324 | 59.88 | 19401.12 | Non Returnable / Non Debitable | -10555 | 62.0805 | -655259.56 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bar 25mm | Kgs | Issue No : 780746 | Aug 17 2024 6:44PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 59.88 | 0 | 0 | 0 | 3056 | 59.88 | 182993.28 | Non Returnable / Non Debitable | -13611 | 61.5864 | -838252.84 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bar 25mm | Kgs | Issue No : 781313 | Aug 22 2024 1:11PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 59.88 | 0 | 0 | 0 | 1852 | 59.88 | 110897.76 | Non Returnable / Non Debitable | -15463 | 61.382 | -949150.6 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bar 25mm | Kgs | Issue No : 777062 | Jul 27 2024 4:25PM | Issue-IST | WAKAD COMMON STORE | 0 | 59.88 | 0 | 0 | 0 | 11690 | 59.88 | 699997.2 | Non Returnable / Non Debitable | 0 | -23226.16 | -23226.16 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bar 25mm | Kgs | Issue No : 777450 | Jul 30 2024 11:51AM | Issue-THEORETICAL | 8th to 9th Column & SW Steel | 0 | 59.88 | 0 | 0 | 0 | 4630 | 59.88 | 277244.4 | Non Returnable / Non Debitable | -4630 | 64.8964 | -300470.56 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bar 25mm | Kgs | Issue No : 778763 | Aug 3 2024 5:30PM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Beam Steel | 0 | 59.88 | 0 | 0 | 0 | 2563 | 59.88 | 153472.44 | Non Returnable / Non Debitable | -7193 | 63.109 | -453943 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bar 25mm | Kgs | Issue No : 778764 | Aug 3 2024 5:30PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 59.88 | 0 | 0 | 0 | 1881 | 59.88 | 112634.28 | Non Returnable / Non Debitable | -9074 | 62.4396 | -566577.28 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bar 25mm | Kgs | Issue No : 778769 | Aug 3 2024 5:37PM | Issue-THEORETICAL | Pour 5 108.00 to 111.00 lvl Drop panel Steel | 0 | 59.88 | 0 | 0 | 0 | 1157 | 59.88 | 69281.16 | Non Returnable / Non Debitable | -10231 | 62.1502 | -635858.44 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bar 25mm | Kgs | GRN No : 239510 | Jul 27 2024 4:03PM | GRN-Purchase | RUDDRAH VENTURES LLP | 11690 | 57.8932 | 573534.78 | 103236.26 | 676771.04 | 0 | 676771.04 | 0 | - | 11690 | 57.8932 | 676771.04 | 94548 | 2024-07-22 | 112 | 112
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | GRN No : 239511 | Jul 27 2024 4:03PM | GRN-Purchase | RUDDRAH VENTURES LLP | 7640 | 57.8932 | 374833.68 | 67470.06 | 442303.74 | 0 | 442303.74 | 0 | - | 7640 | 57.8932 | 442303.74 | 94548 | 2024-07-22 | 112 | 112
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 777063 | Jul 27 2024 4:25PM | Issue-IST | WAKAD COMMON STORE | 0 | 59.06 | 0 | 0 | 0 | 7640 | 59.06 | 451218.4 | Non Returnable / Non Debitable | 0 | -8914.66 | -8914.66 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 777195 | Jul 29 2024 11:27AM | Issue-THEORETICAL | Pour 3A 108.00 to 111.00 lvl Slab Steel | 0 | 59.06 | 0 | 0 | 0 | 3260 | 59.06 | 192535.6 | Non Returnable / Non Debitable | -3260 | 61.7946 | -201450.26 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 777574 | Jul 30 2024 4:50PM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Beam Steel | 0 | 59.06 | 0 | 0 | 0 | 48 | 59.06 | 2834.88 | Non Returnable / Non Debitable | -3308 | 61.7549 | -204285.14 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 777575 | Jul 30 2024 4:50PM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Steel | 0 | 59.06 | 0 | 0 | 0 | 1582 | 59.06 | 93432.92 | Non Returnable / Non Debitable | -4890 | 60.883 | -297718.06 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 777722 | Jul 31 2024 4:52PM | Issue-THEORETICAL | Fire Ramp (99 to 105 Level) RCC Retaining wall | 0 | 59.06 | 0 | 0 | 0 | 815 | 59.06 | 48133.9 | Non Returnable / Non Debitable | -5705 | 60.6226 | -345851.96 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 779722 | Aug 10 2024 11:42AM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Steel | 0 | 59.06 | 0 | 0 | 0 | 49 | 59.06 | 2893.94 | Non Returnable / Non Debitable | -5754 | 60.6093 | -348745.9 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 779723 | Aug 10 2024 11:42AM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 59.06 | 0 | 0 | 0 | 2395 | 59.06 | 141448.7 | Non Returnable / Non Debitable | -8149 | 60.154 | -490194.6 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 779763 | Aug 10 2024 3:47PM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 59.06 | 0 | 0 | 0 | 815 | 59.06 | 48133.9 | Non Returnable / Non Debitable | -8964 | 60.0545 | -538328.5 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 780284 | Aug 14 2024 12:12PM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 59.05 | 0 | 0 | 0 | 407 | 59.05 | 24033.35 | Non Returnable / Non Debitable | -9371 | 60.0109 | -562361.85 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 780747 | Aug 17 2024 6:46PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 59.05 | 0 | 0 | 0 | 2689 | 59.05 | 158785.45 | Non Returnable / Non Debitable | -12060 | 59.7966 | -721147.3 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 781116 | Aug 20 2024 7:02PM | Issue-THEORETICAL | Pour 6 105.00 to 108.00 lvl Slab Steel | 0 | 59.06 | 0 | 0 | 0 | 244 | 59.06 | 14410.64 | Non Returnable / Non Debitable | -12304 | 59.782 | -735557.94 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 781309 | Aug 22 2024 1:02PM | Issue-THEORETICAL | Fire Ramp (99 to 105 Level) RCC Retaining wall | 0 | 59.06 | 0 | 0 | 0 | 1222 | 59.06 | 72171.32 | Non Returnable / Non Debitable | -13526 | 59.7168 | -807729.26 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 781314 | Aug 22 2024 1:12PM | Issue-THEORETICAL | 10th Slab (6th Floor) Slab Beam Steel | 0 | 59.06 | 0 | 0 | 0 | 2444 | 59.06 | 144342.64 | Non Returnable / Non Debitable | -15970 | 59.6163 | -952071.9 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 781545 | Aug 23 2024 5:29PM | Issue-THEORETICAL | Pour 6 105.00 to 108.00 lvl Drop panel Steel | 0 | 59.05 | 0 | 0 | 0 | 113 | 59.05 | 6672.65 | Non Returnable / Non Debitable | -16083 | 59.6123 | -958744.55 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 10mm | Kgs | Issue No : 781546 | Aug 23 2024 5:29PM | Issue-THEORETICAL | Pour 6 105.00 to 108.00 lvl Slab Steel | 0 | 59.05 | 0 | 0 | 0 | 131 | 59.05 | 7735.55 | Non Returnable / Non Debitable | -16214 | 59.6078 | -966480.1 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 776810 | Jul 26 2024 10:58AM | Issue-THEORETICAL | Fire Ramp (99 to 105 Level) RCC Retaining wall | 0 | 57.89 | 0 | 0 | 0 | 1707 | 57.89 | 98818.23 | Non Returnable / Non Debitable | -1707 | 57.89 | -98818.23 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 780745 | Aug 17 2024 6:42PM | Issue-THEORETICAL | Pour 6 105.00 to 108.00 lvl Slab Steel | 0 | 57.89 | 0 | 0 | 0 | 427 | 57.89 | 24719.03 | Non Returnable / Non Debitable | -19029 | 57.8916 | -1101619.83 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 781264 | Aug 21 2024 6:54PM | Issue-THEORETICAL | 10th Slab (6th Floor) Slab Beam Steel | 0 | 57.9 | 0 | 0 | 0 | 1674 | 57.9 | 96924.6 | Non Returnable / Non Debitable | -20703 | 57.8923 | -1198544.43 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 781265 | Aug 21 2024 6:54PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 57.9 | 0 | 0 | 0 | 33 | 57.9 | 1910.7 | Non Returnable / Non Debitable | -20736 | 57.8923 | -1200455.13 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 781310 | Aug 22 2024 1:04PM | Issue-THEORETICAL | Fire Ramp (99 to 105 Level) RCC Retaining wall | 0 | 57.89 | 0 | 0 | 0 | 688 | 57.89 | 39828.32 | Non Returnable / Non Debitable | -21424 | 57.8922 | -1240283.45 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 781311 | Aug 22 2024 1:04PM | Issue-THEORETICAL | Fire Ramp (99 to 105 Level) Retaining wall Raft | 0 | 57.89 | 0 | 0 | 0 | 592 | 57.89 | 34270.88 | Non Returnable / Non Debitable | -22016 | 57.8922 | -1274554.33 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 781315 | Aug 22 2024 1:12PM | Issue-THEORETICAL | 10th Slab (6th Floor) Slab Beam Steel | 0 | 57.89 | 0 | 0 | 0 | 3413 | 57.89 | 197578.57 | Non Returnable / Non Debitable | -25429 | 57.8919 | -1472132.9 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 777058 | Jul 27 2024 4:17PM | Issue-IST | MORWADI COMMON | 0 | 57.89 | 0 | 0 | 0 | 5000 | 57.89 | 289450 | Non Returnable / Non Debitable | 5613 | 57.8969 | 324975.51 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 777064 | Jul 27 2024 4:25PM | Issue-IST | WAKAD COMMON STORE | 0 | 57.89 | 0 | 0 | 0 | 7320 | 57.89 | 423754.8 | Non Returnable / Non Debitable | -1707 | 57.8672 | -98779.29 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 777198 | Jul 29 2024 11:29AM | Issue-THEORETICAL | Pour 3A 108.00 to 111.00 lvl Slab Steel | 0 | 57.89 | 0 | 0 | 0 | 2560 | 57.89 | 148198.4 | Non Returnable / Non Debitable | -4267 | 57.8809 | -246977.69 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 777449 | Jul 30 2024 11:49AM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Steel | 0 | 57.89 | 0 | 0 | 0 | 2560 | 57.89 | 148198.4 | Non Returnable / Non Debitable | -6827 | 57.8843 | -395176.09 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 777723 | Jul 31 2024 4:52PM | Issue-THEORETICAL | Fire Ramp (99 to 105 Level) RCC Retaining wall | 0 | 57.9 | 0 | 0 | 0 | 853 | 57.9 | 49388.7 | Non Returnable / Non Debitable | -7680 | 57.886 | -444564.79 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 779540 | Aug 9 2024 10:25AM | Issue-THEORETICAL | Pour 3 108.00 to 111.00 lvl Slab Steel | 0 | 57.9 | 0 | 0 | 0 | 1280 | 57.9 | 74112 | Non Returnable / Non Debitable | -8960 | 57.888 | -518676.79 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 779541 | Aug 9 2024 10:41AM | Issue-THEORETICAL | Pour 3 108.00 to 111.00 lvl Slab Steel | 0 | 57.9 | 0 | 0 | 0 | 1745 | 57.9 | 101035.5 | Non Returnable / Non Debitable | -10705 | 57.89 | -619712.29 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 779542 | Aug 9 2024 10:41AM | Issue-THEORETICAL | Pour 6 105.00 to 108.00 lvl Drop panel Steel | 0 | 57.9 | 0 | 0 | 0 | 388 | 57.9 | 22465.2 | Non Returnable / Non Debitable | -11093 | 57.8903 | -642177.49 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 779720 | Aug 10 2024 11:41AM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Steel | 0 | 57.89 | 0 | 0 | 0 | 3246 | 57.89 | 187910.94 | Non Returnable / Non Debitable | -14339 | 57.8903 | -830088.43 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 779721 | Aug 10 2024 11:41AM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 57.89 | 0 | 0 | 0 | 253 | 57.89 | 14646.17 | Non Returnable / Non Debitable | -14592 | 57.8903 | -844734.6 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 779741 | Aug 10 2024 2:57PM | Issue-THEORETICAL | Pour 6 105.00 to 108.00 lvl Slab Steel | 0 | 57.9 | 0 | 0 | 0 | 597 | 57.9 | 34566.3 | Non Returnable / Non Debitable | -15189 | 57.8906 | -879300.9 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 779761 | Aug 10 2024 3:46PM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 57.9 | 0 | 0 | 0 | 853 | 57.9 | 49388.7 | Non Returnable / Non Debitable | -16042 | 57.8911 | -928689.6 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 780285 | Aug 14 2024 12:13PM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 57.89 | 0 | 0 | 0 | 1280 | 57.89 | 74099.2 | Non Returnable / Non Debitable | -17322 | 57.8911 | -1002788.8 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | Issue No : 780660 | Aug 17 2024 10:40AM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 57.9 | 0 | 0 | 0 | 1280 | 57.9 | 74112 | Non Returnable / Non Debitable | -18602 | 57.8917 | -1076900.8 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | GRN No : 239505 | Jul 27 2024 3:57PM | GRN-Purchase | RUDDRAH VENTURES LLP | 5000 | 57.8932 | 245310 | 44155.8 | 289465.8 | 0 | 289465.8 | 0 | - | 3293 | 57.8948 | 190647.57 | 94565 | 2024-07-22 | 111 | 111
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 12mm | Kgs | GRN No : 239512 | Jul 27 2024 4:03PM | GRN-Purchase | RUDDRAH VENTURES LLP | 7320 | 57.8932 | 359133.84 | 64644.1 | 423777.94 | 0 | 423777.94 | 0 | - | 10613 | 57.8937 | 614425.51 | 94548 | 2024-07-22 | 112 | 112
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | GRN No : 239506 | Jul 27 2024 3:57PM | GRN-Purchase | RUDDRAH VENTURES LLP | 11370 | 57.8932 | 557834.94 | 100410.28 | 658245.22 | 0 | 658245.22 | 0 | - | 10232 | 57.7867 | 591273.92 | 94565 | 2024-07-22 | 111 | 111
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | GRN No : 239513 | Jul 27 2024 4:03PM | GRN-Purchase | RUDDRAH VENTURES LLP | 8460 | 57.8932 | 415064.52 | 74711.6 | 489776.12 | 0 | 489776.12 | 0 | - | 18692 | 57.8349 | 1081050.04 | 94548 | 2024-07-22 | 112 | 112
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 779548 | Aug 9 2024 10:44AM | Issue-THEORETICAL | Pour 6 102.00 to 105.00 lvl Drop panel Steel | 0 | 58.42 | 0 | 0 | 0 | 30 | 58.42 | 1752.6 | Non Returnable / Non Debitable | -6806 | 60.0269 | -408543.12 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 779549 | Aug 9 2024 10:44AM | Issue-THEORETICAL | Pour 6 102.00 to 105.00 lvl P1 Column Steel | 0 | 58.42 | 0 | 0 | 0 | 369 | 58.42 | 21556.98 | Non Returnable / Non Debitable | -7175 | 59.9443 | -430100.1 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 779713 | Aug 10 2024 11:25AM | Issue-THEORETICAL | 10th Slab (6th Floor) Slab Beam Steel | 0 | 58.42 | 0 | 0 | 0 | 1937 | 58.42 | 113159.54 | Non Returnable / Non Debitable | -9112 | 59.6202 | -543259.64 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 779714 | Aug 10 2024 11:25AM | Issue-THEORETICAL | 10th Slab (6th Floor) Slab Steel | 0 | 58.42 | 0 | 0 | 0 | 1552 | 58.42 | 90667.84 | Non Returnable / Non Debitable | -10664 | 59.4456 | -633927.48 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 779715 | Aug 10 2024 11:36AM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 58.42 | 0 | 0 | 0 | 531 | 58.42 | 31021.02 | Non Returnable / Non Debitable | -11195 | 59.3969 | -664948.5 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 779742 | Aug 10 2024 2:59PM | Issue-THEORETICAL | Pour 3 105.00 to 108.00 lvl Drop panel Steel | 0 | 58.42 | 0 | 0 | 0 | 228 | 58.42 | 13319.76 | Non Returnable / Non Debitable | -11423 | 59.3774 | -678268.26 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 780286 | Aug 14 2024 12:15PM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 58.42 | 0 | 0 | 0 | 1138 | 58.42 | 66481.96 | Non Returnable / Non Debitable | -12561 | 59.2907 | -744750.22 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 778771 | Aug 3 2024 5:40PM | Issue-THEORETICAL | Pour 5 105.00 to 108.00 lvl Drop panel Steel | 0 | 58.42 | 0 | 0 | 0 | 329 | 58.42 | 19220.18 | Non Returnable / Non Debitable | -5607 | 60.3705 | -338497.54 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 778772 | Aug 3 2024 5:40PM | Issue-THEORETICAL | Pour 5 108.00 to 111.00 lvl Drop panel Steel | 0 | 58.42 | 0 | 0 | 0 | 430 | 58.42 | 25120.6 | Non Returnable / Non Debitable | -6037 | 60.2316 | -363618.14 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 779543 | Aug 9 2024 10:44AM | Issue-THEORETICAL | Pour 3 108.00 to 111.00 lvl Dowel Bars | 0 | 58.42 | 0 | 0 | 0 | 13 | 58.42 | 759.46 | Non Returnable / Non Debitable | -6050 | 60.2277 | -364377.6 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 779544 | Aug 9 2024 10:44AM | Issue-THEORETICAL | Pour 3A 99.00 to 102.00 lvl Drop panel Steel | 0 | 58.42 | 0 | 0 | 0 | 254 | 58.42 | 14838.68 | Non Returnable / Non Debitable | -6304 | 60.1549 | -379216.28 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 779545 | Aug 9 2024 10:44AM | Issue-THEORETICAL | Pour 5 102.00 to 105.00 lvl Column Steel | 0 | 58.42 | 0 | 0 | 0 | 74 | 58.42 | 4323.08 | Non Returnable / Non Debitable | -6378 | 60.1347 | -383539.36 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 779546 | Aug 9 2024 10:44AM | Issue-THEORETICAL | Pour 5 102.00 to 105.00 lvl Drop panel Steel | 0 | 58.42 | 0 | 0 | 0 | 272 | 58.42 | 15890.24 | Non Returnable / Non Debitable | -6650 | 60.0646 | -399429.6 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 779547 | Aug 9 2024 10:44AM | Issue-THEORETICAL | Pour 5 108.00 to 111.00 lvl Drop panel Steel | 0 | 58.42 | 0 | 0 | 0 | 126 | 58.42 | 7360.92 | Non Returnable / Non Debitable | -6776 | 60.034 | -406790.52 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 776811 | Jul 26 2024 11:03AM | Issue-THEORETICAL | Fire Ramp (99 to 105 Level) RCC Footings | 0 | 58.85 | 0 | 0 | 0 | 1138 | 58.85 | 66971.3 | Non Returnable / Non Debitable | -1138 | 58.85 | -66971.3 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 781312 | Aug 22 2024 1:05PM | Issue-THEORETICAL | Fire Ramp (99 to 105 Level) RCC Columns | 0 | 58.42 | 0 | 0 | 0 | 1138 | 58.42 | 66481.96 | Non Returnable / Non Debitable | -13699 | 59.2184 | -811232.18 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 781540 | Aug 23 2024 5:19PM | Issue-THEORETICAL | Pour 3A 108.00 to 111.00 lvl Drop panel Steel | 0 | 58.41 | 0 | 0 | 0 | 1593 | 58.41 | 93047.13 | Non Returnable / Non Debitable | -15292 | 59.1341 | -904279.31 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 781541 | Aug 23 2024 5:21PM | Issue-THEORETICAL | Podium P4 RCC Slab Dowel Bar | 0 | 58.42 | 0 | 0 | 0 | 1046 | 58.42 | 61107.32 | Non Returnable / Non Debitable | -16338 | 59.0884 | -965386.63 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 781542 | Aug 23 2024 5:21PM | Issue-THEORETICAL | Podium Pour (3&3A) Column Footing Steel | 0 | 58.42 | 0 | 0 | 0 | 16 | 58.42 | 934.72 | Non Returnable / Non Debitable | -16354 | 59.0878 | -966321.35 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 777059 | Jul 27 2024 4:17PM | Issue-IST | MORWADI COMMON | 0 | 58.42 | 0 | 0 | 0 | 11370 | 58.42 | 664235.4 | Non Returnable / Non Debitable | 7322 | 56.9263 | 416814.64 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 777065 | Jul 27 2024 4:25PM | Issue-IST | WAKAD COMMON STORE | 0 | 58.42 | 0 | 0 | 0 | 8460 | 58.42 | 494233.2 | Non Returnable / Non Debitable | -1138 | 68.0304 | -77418.56 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 777570 | Jul 30 2024 4:47PM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Beam Steel | 0 | 58.42 | 0 | 0 | 0 | 4 | 58.42 | 233.68 | Non Returnable / Non Debitable | -1142 | 67.9967 | -77652.24 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 777571 | Jul 30 2024 4:47PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 58.42 | 0 | 0 | 0 | 1513 | 58.42 | 88389.46 | Non Returnable / Non Debitable | -2655 | 62.5392 | -166041.7 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 778148 | Aug 1 2024 3:59PM | Issue-THEORETICAL | Pour 3A 108.00 to 111.00 lvl Column Steel | 0 | 58.42 | 0 | 0 | 0 | 79 | 58.42 | 4615.18 | Non Returnable / Non Debitable | -2734 | 62.4202 | -170656.88 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 778149 | Aug 1 2024 3:59PM | Issue-THEORETICAL | Pour 3A 108.00 to 111.00 lvl Drop panel Steel | 0 | 58.42 | 0 | 0 | 0 | 680 | 58.42 | 39725.6 | Non Returnable / Non Debitable | -3414 | 61.6235 | -210382.48 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 16mm | Kgs | Issue No : 778765 | Aug 3 2024 5:31PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 58.42 | 0 | 0 | 0 | 1864 | 58.42 | 108894.88 | Non Returnable / Non Debitable | -5278 | 60.4921 | -319277.36 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 777573 | Jul 30 2024 4:48PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 58.98 | 0 | 0 | 0 | 2661 | 58.98 | 156945.78 | Non Returnable / Non Debitable | -2667 | 67.8271 | -180894.96 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 778770 | Aug 3 2024 5:38PM | Issue-THEORETICAL | Pour 5 108.00 to 111.00 lvl Drop panel Steel | 0 | 58.98 | 0 | 0 | 0 | 889 | 58.98 | 52433.22 | Non Returnable / Non Debitable | -3556 | 65.6153 | -233328.18 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 779718 | Aug 10 2024 11:39AM | Issue-THEORETICAL | 8th to 9th Column & SW Steel | 0 | 58.98 | 0 | 0 | 0 | 57 | 58.98 | 3361.86 | Non Returnable / Non Debitable | -3613 | 65.5107 | -236690.04 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 779719 | Aug 10 2024 11:39AM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 58.98 | 0 | 0 | 0 | 4387 | 58.98 | 258745.26 | Non Returnable / Non Debitable | -8000 | 61.9294 | -495435.3 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 779758 | Aug 10 2024 3:44PM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 58.98 | 0 | 0 | 0 | 1333 | 58.98 | 78620.34 | Non Returnable / Non Debitable | -9333 | 61.5082 | -574055.64 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 780288 | Aug 14 2024 12:16PM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 58.98 | 0 | 0 | 0 | 178 | 58.98 | 10498.44 | Non Returnable / Non Debitable | -9511 | 61.4608 | -584554.08 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 781266 | Aug 21 2024 6:55PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 58.98 | 0 | 0 | 0 | 1778 | 58.98 | 104866.44 | Non Returnable / Non Debitable | -11289 | 61.0701 | -689420.52 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 777060 | Jul 27 2024 4:17PM | Issue-IST | MORWADI COMMON | 0 | 58.98 | 0 | 0 | 0 | 8520 | 58.98 | 502509.6 | Non Returnable / Non Debitable | 13190 | 57.1911 | 754350.9 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 777066 | Jul 27 2024 4:25PM | Issue-IST | WAKAD COMMON STORE | 0 | 58.98 | 0 | 0 | 0 | 13190 | 58.98 | 777946.2 | Non Returnable / Non Debitable | 0 | -23595.3 | -23595.3 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 777572 | Jul 30 2024 4:48PM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Beam Steel | 0 | 58.98 | 0 | 0 | 0 | 6 | 58.98 | 353.88 | Non Returnable / Non Debitable | -6 | 3991.53 | -23949.18 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | GRN No : 239514 | Jul 27 2024 4:03PM | GRN-Purchase | RUDDRAH VENTURES LLP | 13190 | 57.8932 | 647127.78 | 116483 | 763610.78 | 0 | 763610.78 | 0 | - | 21710 | 57.8932 | 1256860.5 | 94548 | 2024-07-22 | 112 | 112
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 781316 | Aug 22 2024 1:16PM | Issue-THEORETICAL | 10th Slab (6th Floor) Slab Beam Steel | 0 | 58.98 | 0 | 0 | 0 | 43 | 58.98 | 2536.14 | Non Returnable / Non Debitable | -11332 | 61.0622 | -691956.66 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | Issue No : 781317 | Aug 22 2024 1:16PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 58.98 | 0 | 0 | 0 | 6713 | 58.98 | 395932.74 | Non Returnable / Non Debitable | -18045 | 60.2876 | -1087889.4 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | GRN No : 239507 | Jul 27 2024 3:57PM | GRN-Purchase | RUDDRAH VENTURES LLP | 8500 | 57.8932 | 417027 | 75064.86 | 492091.86 | 0 | 492091.86 | 0 | - | 8500 | 57.8932 | 492091.86 | 94565 | 2024-07-22 | 111 | 111
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 20mm | Kgs | GRN No : 239509 | Jul 27 2024 3:58PM | GRN-Purchase | RUDDRAH VENTURES LLP | 20 | 57.893 | 981.24 | 176.62 | 1157.86 | 0 | 1157.86 | 0 | - | 8520 | 57.8932 | 493249.72 | 94565 | 2024-07-22 | 111. | 111
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 32mm | Kgs | GRN No : 239515 | Jul 27 2024 4:03PM | GRN-Purchase | RUDDRAH VENTURES LLP | 1940 | 59.6986 | 98148.48 | 17666.72 | 115815.2 | 0 | 115815.2 | 0 | - | 1940 | 59.6986 | 115815.2 | 94548 | 2024-07-22 | 112 | 112
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 32mm | Kgs | Issue No : 777067 | Jul 27 2024 4:25PM | Issue-IST | WAKAD COMMON STORE | 0 | 61.73 | 0 | 0 | 0 | 1940 | 61.73 | 119756.2 | Non Returnable / Non Debitable | -1940 | 61.73 | -119756.2 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 32mm | Kgs | Issue No : 777452 | Jul 30 2024 11:55AM | Issue-THEORETICAL | 8th to 9th Column & SW Steel | 0 | 61.73 | 0 | 0 | 0 | 329 | 61.73 | 20309.17 | Non Returnable / Non Debitable | -2269 | 61.73 | -140065.37 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 32mm | Kgs | Issue No : 779716 | Aug 10 2024 11:37AM | Issue-THEORETICAL | 8th to 9th Column & SW Steel | 0 | 61.74 | 0 | 0 | 0 | 1267 | 61.74 | 78224.58 | Non Returnable / Non Debitable | -3536 | 61.7336 | -218289.95 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 32mm | Kgs | Issue No : 779717 | Aug 10 2024 11:37AM | Issue-THEORETICAL | 9th Slab (5th Floor) Slab Beam Steel | 0 | 61.74 | 0 | 0 | 0 | 250 | 61.74 | 15435 | Non Returnable / Non Debitable | -3786 | 61.734 | -233724.95 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/COMM | STEEL | Steel Bars 32mm | Kgs | Issue No : 777451 | Jul 30 2024 11:54AM | Issue-THEORETICAL | 8th to 9th Column & SW Steel | 0 | 69.96 | 0 | 0 | 0 | 430 | 69.96 | 30082.8 | Non Returnable / Non Debitable | -430 | 69.96 | -30082.8 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | GRN No : 239508 | Jul 27 2024 3:57PM | GRN-Purchase | RUDDRAH VENTURES LLP | 15000 | 59.6986 | 758880 | 136598.4 | 895478.4 | 0 | 895478.4 | 0 | - | 15000 | 59.6986 | 895478.4 | 94565 | 2024-07-22 | 111 | 111
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | GRN No : 239516 | Jul 27 2024 4:03PM | GRN-Purchase | RUDDRAH VENTURES LLP | 19690 | 59.6986 | 996156.48 | 179308.18 | 1175464.66 | 0 | 1175464.66 | 0 | - | 34690 | 59.6986 | 2070943.06 | 94548 | 2024-07-22 | 112 | 112
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 777061 | Jul 27 2024 4:17PM | Issue-IST | MORWADI COMMON | 0 | 59.89 | 0 | 0 | 0 | 15000 | 59.89 | 898350 | Non Returnable / Non Debitable | 19690 | 59.5527 | 1172593.06 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 777068 | Jul 27 2024 4:25PM | Issue-IST | WAKAD COMMON STORE | 0 | 59.89 | 0 | 0 | 0 | 19690 | 59.89 | 1179234.1 | Non Returnable / Non Debitable | 0 | -6641.04 | -6641.04 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 777576 | Jul 30 2024 4:52PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 59.88 | 0 | 0 | 0 | 2418 | 59.88 | 144789.84 | Non Returnable / Non Debitable | -2418 | 62.6265 | -151430.88 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 777721 | Jul 31 2024 4:51PM | Issue-THEORETICAL | Fire Ramp (99 to 105 Level) RCC Columns | 0 | 59.88 | 0 | 0 | 0 | 806 | 59.88 | 48263.28 | Non Returnable / Non Debitable | -3224 | 61.9399 | -199694.16 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 778767 | Aug 3 2024 5:33PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 59.88 | 0 | 0 | 0 | 2015 | 59.88 | 120658.2 | Non Returnable / Non Debitable | -5239 | 61.1476 | -320352.36 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 778773 | Aug 3 2024 5:41PM | Issue-THEORETICAL | Pour 5 105.00 to 108.00 lvl Drop panel Steel | 0 | 59.88 | 0 | 0 | 0 | 1612 | 59.88 | 96526.56 | Non Returnable / Non Debitable | -6851 | 60.8494 | -416878.92 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 779724 | Aug 10 2024 11:44AM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 59.88 | 0 | 0 | 0 | 3063 | 59.88 | 183412.44 | Non Returnable / Non Debitable | -9914 | 60.5499 | -600291.36 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 779764 | Aug 10 2024 3:49PM | Issue-THEORETICAL | Pour 6 108.00 to 111.00 lvl Drop panel Steel | 0 | 59.88 | 0 | 0 | 0 | 1209 | 59.88 | 72394.92 | Non Returnable / Non Debitable | -11123 | 60.4771 | -672686.28 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 781263 | Aug 21 2024 6:52PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 59.88 | 0 | 0 | 0 | 1612 | 59.88 | 96526.56 | Non Returnable / Non Debitable | -12735 | 60.4015 | -769212.84 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 781308 | Aug 22 2024 12:59PM | Issue-THEORETICAL | Fire Ramp (99 to 105 Level) RCC Columns | 0 | 59.88 | 0 | 0 | 0 | 1209 | 59.88 | 72394.92 | Non Returnable / Non Debitable | -13944 | 60.3563 | -841607.76 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 781318 | Aug 22 2024 1:18PM | Issue-THEORETICAL | 10th Slab (6th Floor) Slab Beam Steel | 0 | 59.88 | 0 | 0 | 0 | 3427 | 59.88 | 205208.76 | Non Returnable / Non Debitable | -17371 | 60.2623 | -1046816.52 | 0 | 1900-01-01
GANGA DHAM TOWERS | GDT/AGGE | STEEL | Steel Bars 8mm | Kgs | Issue No : 781319 | Aug 22 2024 1:18PM | Issue-THEORETICAL | 9th to 10th Column & SW Steel | 0 | 59.88 | 0 | 0 | 0 | 38 | 59.88 | 2275.44 | Non Returnable / Non Debitable | -17409 | 60.2615 | -1049091.96 | 0 | 1900-01-01