## Work_Completion_Browse638575956
Work Completion Browse
Project : GANGA ALTUS
From Date : 26/07/2024 To date: 26/07/2024
Page 1 of 1
Total Records: 10 Records 1 to 10
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2306 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2307 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2308 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2401 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2403 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2404 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY H SHARMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2405 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | S. K ENTERPRISES (LAXMI SHINDE)
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2406 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2407 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2408 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA