## Work_Completion_Browse638576036
Work Completion Browse
Project : GANGA ASMI
Labour : RCC Superstructure (B-up area)
Contractor : SAIRAJ CONSTRUCTION
From Date : 02/06/2021 To date: 02/06/2021
Page 1 of 1
Total Records: 46 Records 1 to 46
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 1563.9 | 260 | 0 | 406614 | 73190.52 | 2022-07-30 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 95690 | 2022-07-30 | 406614 | 2022-07-30 15:27 | 0 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 1042.6 | 260 | 0 | 271076 | 48793.68 | 2022-08-06 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 95831 | 2022-08-08 | 677690 | 2022-08-30 12:36 | -406614 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 1042.6 | 260 | 0 | 271076 | 48793.68 | 2022-10-21 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 96844 | 2022-10-22 | 609921 | 2022-11-16 11:24 | -338845 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 706.2833 | 260 | 0 | 183633.658 | 33054.06 | 2023-02-24 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 98327 | 2023-02-25 | 183633.66 | 2023-03-14 18:56 | -0.002 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 96.1538 | 260 | 0 | 24999.988 | 0 | 2023-03-13 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 98637 | 2023-03-13 | 24999.99 | 2023-03-29 11:09 | -0.002 | VIKAS GARADE
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 761.4629 | 260 | 0 | 197980.354 | 35636.46 | 2023-03-14 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 98653 | 2023-03-15 | 604594.35 | 2023-03-30 12:37 | -406613.996 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1563.9 | 155 | 0 | 242404.5 | 43632.82 | 2022-08-19 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 | Wing-1 2nd slab column complete 30% | 95934 | 2022-08-20 | 242404.5 | 2022-08-30 12:44 | 0 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1824.55 | 155 | 0 | 282805.25 | 50904.94 | 2022-11-30 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 97168 | 2022-12-01 | 565610.5 | 2022-12-23 11:01 | -282805.25 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1824.55 | 155 | 0 | 282805.25 | 50904.94 | 2023-04-10 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 99103 | 2023-04-11 | 565610.5 | 2023-04-24 10:35 | -282805.25 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 1563.9 | 260 | 0 | 406614 | 73190.52 | 2022-08-06 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 95831 | 2022-08-08 | 677690 | 2022-08-30 12:36 | -271076 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 781.95 | 260 | 0 | 203307 | 36595.26 | 2022-10-04 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 96549 | 2022-10-05 | 445711.5 | 2022-10-12 11:14 | -242404.5 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 1303.25 | 260 | 0 | 338845 | 60992.1 | 2022-10-21 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 96844 | 2022-10-22 | 609921 | 2022-11-16 11:24 | -271076 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 1563.9 | 260 | 0 | 406614 | 73190.52 | 2023-03-14 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 98653 | 2023-03-15 | 604594.35 | 2023-03-30 12:37 | -197980.35 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1563.9 | 155 | 0 | 242404.5 | 43632.82 | 2022-10-04 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 96549 | 2022-10-05 | 445711.5 | 2022-10-12 11:14 | -203307 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1824.55 | 155 | 0 | 282805.25 | 50904.94 | 2022-11-30 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 97168 | 2022-12-01 | 565610.5 | 2022-12-23 11:01 | -282805.25 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1824.55 | 155 | 0 | 282805.25 | 50904.94 | 2023-04-10 | Labor Charges for- Slab Shuttering, Reinforcement & Concreting work for Slab, Beam, Staircase & All Shear Walls. | 100 |  | 99103 | 2023-04-11 | 565610.5 | 2023-04-24 10:35 | -282805.25 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | 2226.2116 | 160 | 0 | 356193.856 | 64114.9 | 2022-12-28 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 97545 | 2022-12-29 | 356193.86 | 2023-01-02 11:56 | -0.004 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | 2112.3337 | 160 | 0 | 337973.392 | 60835.22 | 2023-01-04 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 97627 | 2023-01-05 | 337973.39 | 2023-01-17 11:47 | 0.002 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | 874.2201 | 160 | 0 | 139875.216 | 25177.54 | 2023-05-13 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 99651 | 2023-05-16 | 666930.37 | 2023-05-30 16:14 | -527055.154 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | 2971.41 | 165 | 0 | 490282.65 | 88250.88 | 2023-01-24 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 97930 | 2023-01-25 | 797257.45 | 2023-02-20 15:43 | -306974.8 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | 2241.59 | 165 | 0 | 369862.35 | 66575.22 | 2023-05-29 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 99834 | 2023-05-30 | 1230007.35 | 2023-05-30 16:14 | -860145 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | 2225.951 | 175 | 0 | 389541.425 | 70117.46 | 2023-04-03 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 98950 | 2023-04-04 | 389541.43 | 2023-04-11 17:42 | -0.005 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | 2986 | 175 | 0 | 522550 | 94059 | 2023-06-22 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 100236 | 2023-06-22 | 1434825 | 2023-06-28 17:47 | -912275 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | 5213 | 265.1 | 0 | 1381966.3 | 248753.94 | 2023-08-21 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 101367 | 2023-08-22 | 1381966.3 | 2023-09-20 12:03 | 0 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1918.5925 | 160 | 0 | 306974.8 | 55255.46 | 2023-01-24 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 97930 | 2023-01-25 | 797257.45 | 2023-02-20 15:43 | -490282.65 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | 3294.0947 | 160 | 0 | 527055.152 | 94869.92 | 2023-05-13 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 99651 | 2023-05-16 | 666930.37 | 2023-05-30 16:14 | -139875.218 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | 5213 | 175 | 0 | 912275 | 164209.5 | 2023-06-21 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 100236 | 2023-06-22 | 1434825 | 2023-06-28 17:47 | -522550 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | 5213 | 265.1 | 0 | 1381966.3 | 248753.94 | 2023-08-23 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 101405 | 2023-08-24 | 1381966.3 | 2023-09-20 12:03 | 0 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | 5213 | 165 | 0 | 860145 | 154826.1 | 2023-05-29 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for slab,Beam,Staircase & All shear walls. | 100 |  | 99834 | 2023-05-30 | 1230007.35 | 2023-05-30 16:14 | -369862.35 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Qty Diff Elevational Chajja RCC | 201.4276 | 400 | 0 | 80571.04 | 14502.78 | 2023-03-17 | Labour charges for Shuttering, Reinforcement and RCC Work for Wing-1 Flower Bed Elevational Chajja. | 100 |  | 98776 | 2023-03-17 | 80571.04 | 2023-03-30 12:37 | 0 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 2nd Slab (P3 Lvl)Qty Diff Elevational Chajja RCC | 201.42 | 200 | 0 | 40284 | 7251.12 | 2023-09-15 | Labour charges for Shuttering, Reinforcement and RCC Work for Wing-1 Flower Bed Elevational Chajja. | 100 |  | 101901 | 2023-09-16 | 80568 | 2023-10-17 13:06 | -40284 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 3rd Slab (P4 Lvl) Qty Diff Elevational Chajja RCC | 201.42 | 200 | 0 | 40284 | 7251.12 | 2023-09-15 | Labour charges for Shuttering, Reinforcement and RCC Work for Wing-1 Flower Bed Elevational Chajja. | 100 |  | 101901 | 2023-09-16 | 80568 | 2023-10-17 13:06 | -40284 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 3rd Slab (P4 Lvl) Qty Diff Elevational Chajja RCC | 232.42 | 200 | 0 | 46484 | 8367.12 | 2024-07-20 | Labour charges for Shuttering, Reinforcement and RCC Work for Wing-1 Flower Bed Elevational Chajja. | 100 |  | 109219 | 2024-07-22 | 674797 | 1900-01-01 | -628313 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 400 | 400 | 0 | 160000 | 28800 | 2024-07-26 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1000 | 200 | 0 | 200000 | 36000 | 2024-07-26 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1000 | 200 | 0 | 200000 | 36000 | 2024-07-20 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 109219 | 2024-07-22 | 674797 | 1900-01-01 | -474797 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1000 | 200 | 0 | 200000 | 36000 | 2024-07-20 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 109219 | 2024-07-22 | 674797 | 1900-01-01 | -474797 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1000 | 200 | 0 | 200000 | 36000 | 2024-07-20 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 109219 | 2024-07-22 | 674797 | 1900-01-01 | -474797 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | 1000 | 200 | 0 | 200000 | 36000 | 2024-07-26 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 243 | 2022-02-16 | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | 1041.352 | 155 | 0 | 161409.56 | 29053.72 | 2022-11-03 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab, Beam, Column & Staircase.(Podium Area) | 100 |  | 96918 | 2022-11-04 | 322819.12 | 2022-11-16 11:23 | -161409.56 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 243 | 2022-02-16 | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | 1041.352 | 155 | 0 | 161409.56 | 29053.72 | 2022-11-03 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab, Beam, Column & Staircase.(Podium Area) | 100 |  | 96918 | 2022-11-04 | 322819.12 | 2022-11-16 11:23 | -161409.56 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 243 | 2022-02-16 | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | 1041.5581 | 170 | 0 | 177064.877 | 31871.68 | 2022-12-28 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab, Beam, Column & Staircase.(Podium Area) | 100 |  | 97546 | 2022-12-29 | 177064.88 | 2023-01-14 10:54 | -0.003 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 243 | 2022-02-16 | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | 1041.5581 | 170 | 0 | 177064.877 | 31871.68 | 2023-01-24 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab, Beam, Column & Staircase.(Podium Area) | 100 |  | 97929 | 2023-01-25 | 177064.88 | 2023-02-20 15:42 | -0.003 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 243 | 2022-02-16 | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | 1041.5581 | 180 | 0 | 187480.458 | 33746.48 | 2023-04-03 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab, Beam, Column & Staircase.(Podium Area) | 100 |  | 98952 | 2023-04-04 | 187480.46 | 2023-04-11 17:43 | -0.002 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 243 | 2022-02-16 | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | 1041 | 180 | 0 | 187380 | 33728.4 | 2023-08-21 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab, Beam, Column & Staircase.(Podium Area) | 100 |  | 101366 | 2023-08-22 | 187380 | 2023-09-20 12:03 | 0 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 243 | 2022-02-16 | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | 434.51 | 155 | 0 | 67349.05 | 12122.82 | 2024-04-22 | Labour Charges for-Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and Column. | 100 |  | 107091 | 2024-04-23 | 67349.05 | 2024-05-29 10:16 | 0 | AVCON TECHNICS PVT LTD