## Work_Completion_Browse638579273
Work Completion Browse
Project : GANGA ALTUS
From Date : 07/06/2019 To date: 07/06/2019
Page 1 of 1
Total Records: 13 Records 1 to 13
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
10" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 132 | 28 | 0 | 3696 | 665.28 | 2024-04-07 16:33 | Labour Charges for 10 inch RCC Hume pipe fixing and Laying work for Storm water line work. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -47764.73 | SAI PLUMBING WORKS
10" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | STP Overflow line-265KLD to Nala Line-(L) | 61.992 | 28 | 0 | 1735.776 | 312.44 | 2024-04-07 16:33 | Charges for 10 inch RCC NP2 Hume Pipe laying & Fixing work for STP Overflow line (From 265 KLD to Nala) | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -49724.954 | SAI PLUMBING WORKS
10" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | STP Overflow line-265KLD to Nala Line-(L) | 121.6806 | 28 | 0 | 3407.0568 | 613.28 | 2024-07-28 18:47 | Charges for 10 inch RCC NP2 Hume Pipe laying & Fixing work for STP Overflow line (From 265 KLD to Nala) | 100 |  | 109410 | 2024-07-29 | 12541.76 | 1900-01-01 | -9134.7032 | SAI PLUMBING WORKS
10" RCC Hume Pipe laying & fixing -UST - | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Drainage Line.-Side of F Bldg.-As per Site Condition | 76.916 | 28 | 0 | 2153.648 | 387.66 | 2024-04-07 16:33 | Charges for 10 inch RCC NP2 Hume Pipe laying & Fixing work for Drainage line work. | 100 | D bldg Side Drainage line Qty Released as W.O. is not available | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -49307.082 | SAI PLUMBING WORKS
Round Chamber- UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Drainage Line (L) | 3 | 4000 | 0 | 12000 | 2160 | 2024-04-07 16:33 | Labour charges for construction of Round Chamber upto 1 Mtr Depth for D & E-Bldg External Services. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -39460.73 | SAI PLUMBING WORKS
Round Chamber- UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Overflow Line (From 265KLD to Na | 2 | 4000 | 0 | 8000 | 1440 | 2024-04-07 16:33 | Labour charges for construction of Round Chamber for overflow line (from 265 KLD to Nala) upto 1 Mtr Depth for D & E-Bldg External Services. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -43460.73 | SAI PLUMBING WORKS
Chamber 24" x 36" (4ft Ht) - UTI | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Storm water line (L) | 2 | 2600 | 0 | 5200 | 936 | 2024-05-17 11:17 | Labour charges for construction of Chamber for strom water line size- 2ft x 3ft upto 4ft Depth for D & E-Bldg External Services. | 100 |  | 107688 | 2024-05-20 | 7400 | 2024-07-05 11:52 | -2200 | SAI PLUMBING WORKS
Chamber 36" x 18" (4ft Ht) - UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Storm water line (L) | 1 | 2200 | 0 | 2200 | 396 | 2024-05-17 11:30 | Labour charges for construction of Chamber for strom water line size- 1.5ft x 3ft upto 4ft Depth for D & E-Bldg External Services. | 100 |  | 107688 | 2024-05-20 | 7400 | 2024-07-05 11:52 | -5200 | SAI PLUMBING WORKS
Chamber 24" x 24" (4ft Ht) - USL | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Storm water line (L) | 2 | 2100 | 0 | 4200 | 756 | 2024-04-07 16:33 | Labour charges for construction of Chamber for strom water line size- 2ft x 2ft upto 4ft Depth for D & E-Bldg External Services. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -47260.73 | SAI PLUMBING WORKS
Round Chamber- UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Storm water line (L) | 4 | 4000 | 0 | 16000 | 2880 | 2024-04-07 16:33 | Labour charges for construction of Round Chamber for Storm Water line upto 1 Mtr depth for D & E-Bldg External Services. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -35460.73 | SAI PLUMBING WORKS
12" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 122.51 | 30 | 0 | 3675.3 | 661.56 | 2024-04-07 16:33 | Labour Charges for 12 inch RCC Hume pipe fixing and laying work for storm water line work. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -47785.43 | SAI PLUMBING WORKS
12" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 304.49 | 30 | 0 | 9134.7 | 1644.24 | 2024-07-29 10:14 | Labour Charges for 12 inch RCC Hume pipe fixing and laying work for storm water line work. | 100 |  | 109410 | 2024-07-29 | 12541.76 | 1900-01-01 | -3407.06 | SAI PLUMBING WORKS
Chamber Making -USL | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Blockwork & Plaster Work for Rainwater Harvesting Chamber | 2 | 10000 | 0 | 20000 | 3600 | 2024-07-12 19:19 | Charges for Construction of (7ft 6inch x 5ft x 6 inch x 6ft) Rainwater Harvesting Chamber including PCC, Ghotai, Brickwork9", Internal Ghotai Plaster, Outer Chat Plaster, Chamber cover fixing, etc . | 100 |  | 109121 | 2024-07-15 | 20000 | 1900-01-01 | 0 | SAI PLUMBING WORKS