## Work_Completion_Browse638579283
Work Completion Browse
Project : GANGA ALTUS
From Date : 07/06/2019 To date: 07/06/2019
Page 1 of 1
Total Records: 4 Records 1 to 4
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
12" RCC Pipe Laying-USL | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 391.9696 | 30 | 0 | 11759.088 | 2116.64 | 2024-07-28 18:38 | Labour charges for 12" RCC Pipe laying for HT & LT Line laying & for Construction of Chamber from Transformer Room to UGWT. | 100 |  | 109409 | 2024-07-29 | 11759.09 | 1900-01-01 | -0.002 | SAI PLUMBING WORKS
Chamber 48" x 48" (5ft Ht) - UTI | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 3 | 4000 | 0 | 12000 | 2160 | 2024-07-16 12:17 | Charges for 4ft x 4ft x 1.5m Construction of Chamber near UGWT, near Pride Transformer Room, near F-Bldg. | 100 |  | 109230 | 2024-07-22 | 22700 | 1900-01-01 | -10700 | SAI PLUMBING WORKS
Chamber 24" x 24" (3ft Ht) USL | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 3 | 2100 | 0 | 6300 | 1134 | 2024-07-16 12:20 | Charges for 2ft x 2ft x 1m Construction of Chamber for LT Line | 100 |  | 109230 | 2024-07-22 | 22700 | 1900-01-01 | -16400 | SAI PLUMBING WORKS
Chamber 36" x 18" (3ft Ht) - UDR | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 2 | 2200 | 0 | 4400 | 792 | 2024-07-16 12:23 | Charges for 1ft 6 inch x 3ft x 1m Construction of Chamber for LT Line. | 100 |  | 109230 | 2024-07-22 | 22700 | 1900-01-01 | -18300 | SAI PLUMBING WORKS