## Work_Completion_Browse638579375
Work Completion Browse
Project : GANGA DHAM TOWERS
Contractor : B & B ENTERPRISES
From Date : 01/06/2018 To date: 01/06/2018
Page 1 of 1
Total Records: 10 Records 1 to 10
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 6th Slab (2nd Floor) Slab Built-up Area (L) | 4066.096 | 150 | 0 | 609914.4 | 109784.6 | 2024-01-20 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 | Flat no 104 & 101 casting completed | 104727 | 2024-01-23 | 609914.4 | 2024-03-18 12:39 | 0 | B & B ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 7th Slab (3rd Floor) Slab Built-up Area (L) | 5103.26 | 150 | 0 | 765489 | 137788.02 | 2024-04-08 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 | Flat no 201 & Flat no 202 with Core Area | 106717 | 2024-04-08 | 765489 | 2024-04-20 11:32 | 0 | B & B ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 8th Slab (4th Floor) Slab Built-up Area (L) | 5082.62 | 150 | 0 | 762393 | 137230.74 | 2024-06-15 12:39 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 | 3rd floor flat no.1 & 2 | 108449 | 2024-06-18 | 762393 | 2024-07-11 10:32 | 0 | B & B ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 9th Slab (5th Floor) Slab Built-up Area (L) | 5103.26 | 150 | 0 | 765489 | 137788.02 | 2024-07-30 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 | flat no 404 & 401 | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | B & B ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 6th Slab (2nd Floor) Slab Built-up Area (L) | 4269.4008 | 150 | 0 | 640410.12 | 115273.82 | 2024-03-13 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 | flat no. 102 & 103 with core area | 106058 | 2024-03-15 | 640410.12 | 2024-03-18 12:25 | 0 | B & B ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 7th Slab (3rd Floor) Slab Built-up Area (L) | 3061.956 | 150 | 0 | 459293.4 | 82672.82 | 2024-07-30 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | B & B ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 8th Slab (4th Floor) Slab Built-up Area (L) | 3049.572 | 150 | 0 | 457435.8 | 82338.44 | 2024-07-30 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | B & B ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 9th Slab (5th Floor) Slab Built-up Area (L) | 3061.956 | 150 | 0 | 459293.4 | 82672.82 | 2024-07-30 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 | Flat no 402 | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | B & B ENTERPRISES
Sorting & Shifting Work | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg Sorting & Shifting, Mock-up, Checking & Rework (1st F | 5082.625 | 100 | 0 | 508262.5 | 91487.26 | 2024-02-28 | Labour charges for Sorting & Shifting, Mockup, Checking & Rework at 1st floor. | 100 | Tower A&B Podium lvl 111 sorting, shifting & mockup to Tower C 6th slab. | 105771 | 2024-03-04 | 508262.5 | 2024-03-18 12:29 | 0 | B & B ENTERPRISES
Sorting & Shifting Work | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg Sorting & Shifting, Mock-up, Checking & Rework (1st F | 5082.625 | 100 | 0 | 508262.5 | 91487.26 | 2024-03-20 | Labour charges for Sorting & Shifting, Mockup, Checking & Rework at 1st floor. | 100 |  | 106302 | 2024-03-20 | 508262.5 | 2024-03-30 11:46 | 0 | B & B ENTERPRISES