## Work_Completion_Browse638579380
Work Completion Browse
Project : GANGA ALTUS
Executed By : RADHEYSHYAM YADAV
From Date : 01/06/2014 To date: 01/06/2014
Page 1 of 1
Total Records: 22 Records 1 to 22
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg LG Floor Toilet False Ceiling Work | 30 | 15 | 0 | 450 | 0 | 2024-01-15 16:12 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 104672 | 2024-01-22 | 21191.94 | 2024-02-02 14:24 | -20741.94 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg LG Floor Toilet False Ceiling Work | 7 | 15 | 0 | 105 | 0 | 2024-04-07 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 106645 | 2024-04-08 | 2385 | 2024-04-30 15:26 | -2280 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 1st Floor Toilet False Ceiling Work | 195 | 15 | 0 | 2925 | 0 | 2024-01-15 16:12 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 104672 | 2024-01-22 | 21191.94 | 2024-02-02 14:24 | -18266.94 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 1st Floor Toilet False Ceiling Work | 88 | 15 | 0 | 1320 | 0 | 2024-04-07 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 106645 | 2024-04-08 | 2385 | 2024-04-30 15:26 | -1065 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 2nd Floor Toilet False Ceiling Work | 30 | 15 | 0 | 450 | 0 | 2024-01-15 16:12 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 104672 | 2024-01-22 | 21191.94 | 2024-02-02 14:24 | -20741.94 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 2nd Floor Toilet False Ceiling Work | 64 | 15 | 0 | 960 | 0 | 2024-04-07 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 106645 | 2024-04-08 | 2385 | 2024-04-30 15:26 | -1425 | RADHEYSHYAM YADAV
False Ceiling (l) -BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1157.796 | 15 | 0 | 17366.94 | 0 | 2023-12-21 16:03 | Labour Charges for- Internal False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 104097 | 2023-12-25 | 17366.94 | 2024-01-02 11:46 | 0 | RADHEYSHYAM YADAV
False Ceiling (l) -BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1157.796 | 15 | 0 | 17366.94 | 0 | 2024-01-15 16:08 | Labour Charges for- Internal False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 104672 | 2024-01-22 | 21191.94 | 2024-02-02 14:24 | -3825 | RADHEYSHYAM YADAV
False Ceiling (l) -BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1543.7 | 15 | 0 | 23155.5 | 0 | 2024-04-15 | Labour Charges for- Internal False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 106827 | 2024-04-15 | 23155.5 | 2024-04-30 15:26 | 0 | RADHEYSHYAM YADAV
False Ceiling (L)- SOS | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | Altus-Shop-29-Grid Ceiling &Partition Work | 105.0667 | 15 | 0 | 1576.0005 | 0 | 2024-01-30 | Labour Charges for Shop No.29 False Ceiling work | 100 |  | 105007 | 2024-02-05 | 2180.65 | 2024-03-02 12:03 | -604.6495 | RADHEYSHYAM YADAV
Gypsum Board Partition (L) | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | Altus-Shop-29-Grid Ceiling &Partition Work | 40.31 | 15 | 0 | 604.65 | 0 | 2024-01-30 | Labour Charges for Shop No.29 Gypsum board partition | 100 |  | 105007 | 2024-02-05 | 2180.65 | 2024-03-02 12:03 | -1576 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg LG Floor Toilet False Ceiling Work | 30 | 60 | 0 | 1800 | 0 | 2024-01-15 16:21 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -82967.76 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg LG Floor Toilet False Ceiling Work | 7 | 60 | 0 | 420 | 0 | 2024-04-07 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106647 | 2024-04-08 | 9540 | 2024-04-30 15:26 | -9120 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Toilet False Ceiling Work | 195 | 60 | 0 | 11700 | 0 | 2024-01-15 16:21 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -73067.76 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Toilet False Ceiling Work | 88 | 60 | 0 | 5280 | 0 | 2024-04-07 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106647 | 2024-04-08 | 9540 | 2024-04-30 15:26 | -4260 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 2nd Floor Toilet False Ceiling Work | 30 | 60 | 0 | 1800 | 0 | 2024-01-15 16:21 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -82967.76 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 2nd Floor Toilet False Ceiling Work | 64 | 60 | 0 | 3840 | 0 | 2024-04-07 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106647 | 2024-04-08 | 9540 | 2024-04-30 15:26 | -5700 | RADHEYSHYAM YADAV
False Ceiling (m) -BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1157.796 | 60 | 0 | 69467.76 | 0 | 2023-12-21 16:07 | Material Supply Charges for- Internal Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104098 | 2023-12-25 | 69467.76 | 2024-01-08 16:12 | 0 | RADHEYSHYAM YADAV
False Ceiling (m) -BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1157.796 | 60 | 0 | 69467.76 | 0 | 2024-01-15 16:04 | Material Supply Charges for- Internal Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -15300 | RADHEYSHYAM YADAV
False Ceiling (m) -BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1543 | 60 | 0 | 92580 | 0 | 2024-04-15 | Material Supply Charges for- Internal Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106828 | 2024-04-15 | 92580 | 2024-04-30 15:26 | 0 | RADHEYSHYAM YADAV
False Ceiling (M)- SOS | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | Altus-Shop-29-Grid Ceiling &Partition Work | 105.05 | 60 | 0 | 6303 | 0 | 2024-01-30 | Material Charges for Shop No.29 False ceiling work. | 100 |  | 105006 | 2024-02-05 | 8721.6 | 2024-03-02 11:57 | -2418.6 | RADHEYSHYAM YADAV
Gypsum Board Partition (M) | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | Altus-Shop-29-Grid Ceiling &Partition Work | 40.31 | 60 | 0 | 2418.6 | 0 | 2024-01-30 | Material Charges for Shop No.29 Gypsum Board Partition Work. | 100 |  | 105006 | 2024-02-05 | 8721.6 | 2024-03-02 11:57 | -6303 | RADHEYSHYAM YADAV