## Work_Completion_Browse638579483
Work Completion Browse
Project : GANGA ALTUS
From Date : 03/06/2020 To date: 03/06/2020
Page 1 of 1
Total Records: 5 Records 1 to 5
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 1036 | 2024-07-01 | D&E-Entrance Gate-External Texture Work | 1546.857 | 8 | 0 | 12374.856 | 2227.48 | 2024-07-27 16:36 | Material supply charges for Applying Texture work for D & E-Bldg Entrance Gate External Texture work. | 100 | 90% Bill | 109407 | 2024-07-29 | 33644.15 | 1900-01-01 | -21269.294 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 1036 | 2024-07-01 | F-Entrance Gate-External Texture Work | 1546.857 | 8 | 0 | 12374.856 | 2227.48 | 2024-07-27 16:57 | Material supply charges for Applying Texture Paint work for F-Bldg Entrance Gate External Texture work. | 100 | 90% Bill | 109407 | 2024-07-29 | 33644.15 | 1900-01-01 | -21269.294 | VEER BHADRA ENTERPRISES (MATERIAL)
1 Coat Primer (Water Base) (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 1036 | 2024-07-01 | F-Entrance Gate-External Texture Work | 1546.857 | 1 | 0 | 1546.857 | 278.44 | 2024-07-27 16:57 | Material supply charges for Applying 1 Coat water Base Primer work for F-Bldg Entrance Gate External Texture work. | 100 | 90% Bill | 109407 | 2024-07-29 | 33644.15 | 1900-01-01 | -32097.293 | VEER BHADRA ENTERPRISES (MATERIAL)
1st Coat Acrylic Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 1036 | 2024-07-01 | F-Entrance Gate-External Texture Work | 1546.857 | 2.25 | 0 | 3480.4282 | 626.48 | 2024-07-27 16:57 | Material supply charges for Applying 1st Coat Acrylic Paint work for F-Bldg Entrance Gate External Texture work. | 100 | 90% Bill | 109407 | 2024-07-29 | 33644.15 | 1900-01-01 | -30163.7218 | VEER BHADRA ENTERPRISES (MATERIAL)
2nd Coat Acrylic Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 1036 | 2024-07-01 | F-Entrance Gate-External Texture Work | 1546.857 | 2.5 | 0 | 3867.1425 | 696.08 | 2024-07-27 16:57 | Material supply charges for Applying 2nd Coat Acrylic Paint work for F-Bldg Entrance Gate External Texture work. | 100 | 90% Bill | 109407 | 2024-07-29 | 33644.15 | 1900-01-01 | -29777.0075 | VEER BHADRA ENTERPRISES (MATERIAL)