## Work_Completion_Browse638580190
Work Completion Browse
Project : GANGA ALTUS
From Date : 01/01/2016 To date: 01/01/2016
Page 1 of 1
Total Records: 143 Records 1 to 143
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-101-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26402.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-103-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26602.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-104-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26602.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-105-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26402.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-106-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26402.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-107-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26602.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-108-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26602.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-201-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -30936 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-202-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -30936 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-203-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -31135.8 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-204-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -31135.8 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-205-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -30936 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-206-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -30936 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-207-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -31135.8 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-208-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -31135.8 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-301-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -21868.8 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-302-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-303-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -22068.6 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-304-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -22068.6 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-305-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -21868.8 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-306-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-307-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -22068.6 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-308-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -22068.6 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-401-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-401-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-402-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-403-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-404-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-405-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-406-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-407-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-408-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-408-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-501-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-501-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-502-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-503-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-504-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-505-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-505-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-506-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-506-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-507-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-507-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-508-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-601-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-602-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-603-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-604-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-605-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-605-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-606-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-606-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-607-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-608-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-701-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-702-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-703-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-704-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-704-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-705-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-706-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-707-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-708-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-708-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-801-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-801-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-802-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-803-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-804-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-804-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-805-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-805-3BHK Toilet False ceiling work | 22.6 | 60 | 0 | 1356 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182064 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-806-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-807-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-807-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-808-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-901-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-902-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-903-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-903-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-904-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-905-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-905-3BHK Toilet False ceiling work | 22.6 | 60 | 0 | 1356 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182064 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-906-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-907-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-908-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-908-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1001-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1001-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1002-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1003-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1004-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1004-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1005-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1006-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1008-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1102-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1102-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1104-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1104-2BHK Toilet False ceiling work | 21.6 | 60 | 0 | 1296 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182124 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1204-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1204-2BHK Toilet False ceiling work | 21.669 | 60 | 0 | 1300.14 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -88300.56 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1302-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1302-3BHK Toilet False ceiling work | 22.668 | 60 | 0 | 1360.08 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -88240.62 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1304-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1304-2BHK Toilet False ceiling work | 21.669 | 60 | 0 | 1300.14 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -88300.56 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1306-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1401-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1407-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1501-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1502-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1503-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1504-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1505-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1506-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1507-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1508-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1508-2BHK Toilet False ceiling work | 21.669 | 60 | 0 | 1300.14 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -88300.56 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1601-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1602-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1603-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1604-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1605-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1606-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1607-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1608-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1703-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1802-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1804-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1904-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2003-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg LG Floor Toilet False Ceiling Work | 30 | 60 | 0 | 1800 | 0 | 2024-01-15 16:21 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -82967.76 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg LG Floor Toilet False Ceiling Work | 7 | 60 | 0 | 420 | 0 | 2024-04-07 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106647 | 2024-04-08 | 9540 | 2024-04-30 15:26 | -9120 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Toilet False Ceiling Work | 195 | 60 | 0 | 11700 | 0 | 2024-01-15 16:21 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -73067.76 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Toilet False Ceiling Work | 88 | 60 | 0 | 5280 | 0 | 2024-04-07 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106647 | 2024-04-08 | 9540 | 2024-04-30 15:26 | -4260 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 2nd Floor Toilet False Ceiling Work | 30 | 60 | 0 | 1800 | 0 | 2024-01-15 16:21 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -82967.76 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 2nd Floor Toilet False Ceiling Work | 64 | 60 | 0 | 3840 | 0 | 2024-04-07 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106647 | 2024-04-08 | 9540 | 2024-04-30 15:26 | -5700 | RADHEYSHYAM YADAV
False Ceiling (m) -BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1157.796 | 60 | 0 | 69467.76 | 0 | 2023-12-21 16:07 | Material Supply Charges for- Internal Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104098 | 2023-12-25 | 69467.76 | 2024-01-08 16:12 | 0 | RADHEYSHYAM YADAV
False Ceiling (m) -BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1157.796 | 60 | 0 | 69467.76 | 0 | 2024-01-15 16:04 | Material Supply Charges for- Internal Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -15300 | RADHEYSHYAM YADAV
False Ceiling (m) -BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1543 | 60 | 0 | 92580 | 0 | 2024-04-15 | Material Supply Charges for- Internal Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106828 | 2024-04-15 | 92580 | 2024-04-30 15:26 | 0 | RADHEYSHYAM YADAV
False Ceiling (M)- SOS | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | Altus-Shop-29-Grid Ceiling &Partition Work | 105.05 | 60 | 0 | 6303 | 0 | 2024-01-30 | Material Charges for Shop No.29 False ceiling work. | 100 |  | 105006 | 2024-02-05 | 8721.6 | 2024-03-02 11:57 | -2418.6 | RADHEYSHYAM YADAV
Gypsum Board Partition (M) | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | Altus-Shop-29-Grid Ceiling &Partition Work | 40.31 | 60 | 0 | 2418.6 | 0 | 2024-01-30 | Material Charges for Shop No.29 Gypsum Board Partition Work. | 100 |  | 105006 | 2024-02-05 | 8721.6 | 2024-03-02 11:57 | -6303 | RADHEYSHYAM YADAV