## Work_Completion_Browse638580201
Work Completion Browse
Project : GANGA DHAM TOWERS
Executed By : JAISAN
From Date : 01/01/2024 To date: 01/01/2024
Page 1 of 1
Total Records: 204 Records 1 to 204
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Soling & PCC | N/C | N/C | UNIQUE ENTERPRISES | 1120 | 2021-07-08 | C Podium Area Soling & PCC Work | 430.818 | 25 | 0 | 10770.45 | 0 | 2024-04-08 16:49 | Charges for Solling & PCC Work. | 100 |  | 106704 | 2024-04-08 | 10770.45 | 2024-04-20 11:36 | 0 | JAISAN
Italian marble Skirting - BCo | N/C | N/C | AVCON TECHNICS PVT LTD | 1234 | 2021-12-15 | A 2304 NOC | 50 | 55 | 0 | 2750 | 0 | 2024-04-08 | Italian Marble Skirting in Kitchen. | 100 |  | 106580 | 2024-04-08 | 2750 | 2024-04-20 11:27 | 0 | JAISAN
Scaffolding work - BC | N/C | N/C | J K INTERIOR | 1505 | 2023-02-06 | B 17th-18th fl. double ht. scaffolding for Staircase Plaster | 1 | 3000 | 0 | 3000 | 0 | 2024-06-11 13:26 | Scaffolding fixing & removing charges for B-Bldg 17th to 18th Floor Double Height Floor for Staircase-2 Gypsum Tikki Dhada work. | 100 |  | 108291 | 2024-06-11 | 3000 | 2024-06-24 11:40 | 0 | JAISAN
Tractor Trips (external) DLT | N/C | N/C | JAISAN | 1620 | 2023-05-06 | Tractor trip debris shifting | 52 | 1200 | 0 | 62400 | 0 | 2024-01-29 | Charges for Debris & Material Shifting work outside the site premises by tractor for A, B, C & D Building & Development. | 100 |  | 104842 | 2024-01-29 | 66000 | 2024-02-02 14:09 | -3600 | JAISAN
Tractor Trip - DCW | N/C | N/C | JAISAN | 1620 | 2023-05-06 | Tractor trip debris shifting | 9 | 400 | 0 | 3600 | 0 | 2024-01-29 | Charges for Debris & Material Shifting work outside the premises by tractor trips for A, B, C & D Building and Development. | 100 |  | 104842 | 2024-01-29 | 66000 | 2024-02-02 14:09 | -62400 | JAISAN
Soling & PCC | N/C | N/C | VIMAL CONSTRUCTION | 1634 | 2023-05-24 | C Podium Area Soling & PCC Work | 110.223 | 25 | 0 | 2755.575 | 0 | 2024-04-05 15:30 | Charges for Solling & PCC Work. | 100 |  | 106534 | 2024-04-08 | 2755.58 | 2024-04-20 11:28 | -0.005 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1709 | 2023-08-18 | Mandir area MS sheet removing, material shifting & PCC | 1 | 18000 | 0 | 18000 | 0 | 2024-07-06 | Charges for Labour used for Material Shifting, PCC work & MS Sheet Removing work Including Breaking material removing in storm waterline, 102 stock water removing work for Mandir area. | 100 |  | 108857 | 2024-07-08 | 18000 | 1900-01-01 | 0 | JAISAN
Breaker-BC | N/C | N/C | JAISAN | 1751 | 2023-09-11 | Parking, Podium Breaking, Chipping Plumbing Ducts & Chambers | 8 | 1300 | 0 | 10400 | 0 | 2024-07-31 | Breaker charges including Helper for Breaking & Chipping work for plumbing duct / Chamber for Services. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 1751 | 2023-09-11 | Parking, Podium Breaking, Chipping Plumbing Ducts & Chambers | 5 | 600 | 0 | 3000 | 0 | 2024-07-31 | Male Coolie Charges for Breaking & Chipping work for plumbing duct / Chamber for Services. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1765 | 2023-09-23 | Shifting material near D bldg. to C 99 lvl. | 1 | 40000 | 0 | 40000 | 0 | 2024-02-12 | Charges for Material Shifting near D-Building to Tower C 99 Level. | 100 |  | 105275 | 2024-02-12 | 40000 | 2024-02-27 10:38 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1765 | 2023-09-23 | 111 lvl. Material shifting from B Tower To C Tower | 1 | 22000 | 0 | 22000 | 0 | 2024-07-09 | Charges for Material shifting from B-Tower to C-Tower at 111 level. | 100 | 111 lvl B TOWER to C TOWER Aluform material shifting work & rabit ,scrap aslo shiftinf work | 109015 | 2024-07-15 | 22000 | 2024-07-26 12:30 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1766 | 2023-09-23 | Main gate roadside area Housekeeping work | 1 | 4000 | 0 | 4000 | 0 | 2024-04-12 | Charges for Project Road Side Housekeeping work near main Entrance Gate side footh path cleaning due to PMC Complaint. | 100 |  | 106846 | 2024-04-15 | 4000 | 2024-04-25 11:50 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1766 | 2023-09-23 | Main Gate, Mandir, Club House material shifting, housekeepin | 1 | 10200 | 0 | 10200 | 0 | 2024-05-06 | Labour Charges for Entrance gate to club house cleaning work,internal and external gate housekeeping work,mandir boulder shifting work,A Tower 108 level Balance PCC Work,Siprox Block Shifting and Old Concrete debris removing behind club house. | 100 |  | 107355 | 2024-05-06 | 10200 | 2024-05-15 14:34 | 0 | JAISAN
Material Shifting | N/C | N/C | JAISAN | 1766 | 2023-09-23 | H frame, channel & Steel material shifting from 99 to 102 le | 1 | 35000 | 0 | 35000 | 0 | 2024-05-17 | Material Shifting charges of H-Frame, Flex Frame, MS Sheet, Round Pipe, Steel Bar,etc from 99 level to 102 level at C-Bldg. | 100 |  | 107647 | 2024-05-20 | 101000 | 2024-06-06 12:28 | -66000 | JAISAN
Material Shifting | N/C | N/C | JAISAN | 1766 | 2023-09-23 | H frame, channel & Steel material shifting from 99 to 102 le | 1 | 66000 | 0 | 66000 | 0 | 2024-05-17 | Material Shifting charges of H-Frame, Flex Frame, MS Sheet, Round Pipe, Steel Bar, Wooden material, Channel, etc from 99 level to 102 level at C-Bldg. | 100 |  | 107647 | 2024-05-20 | 101000 | 2024-06-06 12:28 | -35000 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1767 | 2023-09-23 | C Building area Labour camp & Store Material shifting | 1 | 11800 | 0 | 11800 | 0 | 2024-05-06 | Labour Charges for material Shifting from labour camp,store,Murum levelling at parking area and housekeeping work at C Building 99 level lobby. | 100 |  | 107356 | 2024-05-06 | 11800 | 2024-05-15 14:34 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1767 | 2023-09-23 | Material shifting & Stacking from C 99 to 102 Level | 1 | 28000 | 0 | 28000 | 0 | 2024-06-17 | Charges for Material shifting & stacking from C-Bldg 99 level to 102 level. | 100 |  | 108409 | 2024-06-17 | 60000 | 2024-06-24 11:57 | -32000 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1767 | 2023-09-23 | Material shifting & Stacking from C 99 to 102 Level | 1 | 32000 | 0 | 32000 | 0 | 2024-06-17 | Charges for Material shifting & stacking from C Building 99 level to 102 level.. | 100 |  | 108409 | 2024-06-17 | 60000 | 2024-06-24 11:57 | -28000 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1785 | 2023-10-07 | Podium Level Lobby & Amenity (Indoor) area Brickwork, plaste | 1 | 7700 | 0 | 7700 | 0 | 2024-04-18 | Labour Charges for Podium 111 level A- Tower Lobby Area Brickwork & Plasterwork | 100 |  | 107033 | 2024-04-22 | 7700 | 2024-05-06 12:53 | 0 | JAISAN
Breaking & Chipping work | N/C | N/C | JAISAN | 1785 | 2023-10-07 | A & B 99, 102, 105, 108 Parking & Podium Breaking & Chippin | 1 | 40450 | 0 | 40450 | 0 | 2024-05-06 12:01 | Labour Charges for Podium A2,A3 Part Grinding and Chipping work,Expansion joint opening work,Plumbing duct breaking work for down take line,A3 Part bore hole opening work,Chamber and duct rectification work,B 99,102,105 Level plumbing duct opening work. | 100 |  | 107348 | 2024-05-06 | 40450 | 2024-05-15 14:35 | 0 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 1785 | 2023-10-07 | A,B,C D & Development Housekeeping | 57 | 650 | 0 | 37050 | 0 | 2024-07-31 | Department labour (M/C ) charges for Housekeeping,Garbage & Material shifting for A,B,C,D Building and Development for JULY-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 1785 | 2023-10-07 | A,B,C D & Development Housekeeping | 33 | 450 | 0 | 14850 | 0 | 2024-07-31 | Department labour (F/C ) charges for Housekeeping,Garbage & Material shifting for A,B,C,D Building and Development for JULY-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1786 | 2023-10-09 | Shifting material near B lobby at Podium level | 0.9 | 9000 | 0 | 8100 | 0 | 2024-02-12 13:13 | Charges for Material Shifting Near 111 Level Podium of B-Tower Lobby . | 100 |  | 105267 | 2024-02-12 | 8100 | 2024-02-27 10:38 | 0 | JAISAN
Material Shifting | N/C | N/C | JAISAN | 1786 | 2023-10-09 | 108, 111 lvl. H frame, Jacks, Supports, Square pipe shifting | 1 | 60000 | 0 | 60000 | 0 | 2024-06-25 | Charges for Material Shifting (Safety net,Square pipe,H Frame,Supporting Jacks etc) from A and B Building Podium 111 level to 102 level C Tower,108 level to 102 level C Tower,Cleaning of all podium A2,A3 & Amenities area . | 100 |  | 108604 | 2024-06-26 | 60000 | 2024-07-05 11:58 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1800 | 2023-10-26 | A Bldg 1st to 31st floor Cleaning & Ponding | 1 | 30000 | 0 | 30000 | 0 | 2024-02-12 | Labour charges for Debris Removing & Floor Cleaning work for A-Bldg Common Lobby from 1st Floor to 31st Floor. | 100 |  | 105266 | 2024-02-12 | 30000 | 2024-02-27 10:39 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1800 | 2023-10-26 | B Service platform plumbing work | 1 | 14000 | 0 | 14000 | 0 | 2024-02-21 13:13 | Charges for Scaffolding, Erection & Dismentling work in B Building at 105 level Ramp. | 100 |  | 105480 | 2024-02-26 | 14000 | 2024-03-01 11:27 | 0 | JAISAN
Scaffolding & Removing | N/C | N/C | JAISAN | 1800 | 2023-10-26 | H frame scaffolding for Refuge area Plumbing work | 2080 | 5 | 0 | 10400 | 0 | 2024-07-11 | Charges for H- Frame Scaffolding Fixing & removing for Refuge Area Plumbing work for A-Tower. | 100 |  | 109050 | 2024-07-15 | 10400 | 2024-07-26 12:30 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1801 | 2023-10-26 | B 15th, 16th, 23rd to 31st floor Cleaning & Ponding | 1 | 15000 | 0 | 15000 | 0 | 2024-02-12 11:15 | Labour charges for Debris Removing & Floor Cleaning work for B-Bldg Common Lobby and Staircase area for 15th,16th Floor & 23rd to 31st Floor. | 100 |  | 105276 | 2024-02-12 | 15000 | 2024-02-27 10:39 | 0 | JAISAN
PCC | N/C | N/C | JAISAN | 1801 | 2023-10-26 | B 99 Level Staircases & Meter room area PCC work | 480.02 | 5 | 0 | 2400.1 | 0 | 2024-07-01 | Charges for PCC work with RMC at B-Bldg 99 level | 100 |  | 108772 | 2024-07-03 | 2400.1 | 2024-07-15 11:24 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1815 | 2023-11-06 | ABC & Development Misc Work | 1 | 27160 | 0 | 27160 | 0 | 2024-01-29 | Labour charges for Pump room Material shifting, Plum Wall top Breaking,cleaning work at club house,murum for club house extended area,Scrap material Shifting,Club House pipe Shifting work,etc | 100 |  | 104879 | 2024-01-29 | 27160 | 2024-02-02 14:16 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1815 | 2023-11-06 | Club House area development & C bldg. services misc. work | 1 | 80160 | 0 | 80160 | 0 | 2024-02-23 | Labour charges for Bricks Shifting stacking at club house, scrap collecting & Shifting to scrap yard,trimix curing at club house,preparation of PCC for seater,Nala cleaning at club house,SB murum shiting,Diesel room Fabrication material shifting,etc | 100 |  | 105499 | 2024-02-26 | 80160 | 2024-03-12 14:38 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1815 | 2023-11-06 | Debris removing from B parking 102, 105 & 108 level | 1 | 4000 | 0 | 4000 | 0 | 2024-03-18 | Lumpsum Charges for Debris removing and Shiting work from B Building 102,105,108 level to 102 level. | 100 |  | 106916 | 2024-04-16 | 4000 | 2024-04-20 11:30 | 0 | JAISAN
Tractor Breaker - DER | N/C | N/C | JAISAN | 1815 | 2023-11-06 | Club House area development & C bldg. services misc. work | 18 | 6000 | 0 | 108000 | 0 | 2024-04-12 | Charges for Tractor Breaker for Hard Murum breaking work at C-Bldg. | 100 |  | 106972 | 2024-04-20 | 108000 | 2024-04-23 11:06 | 0 | JAISAN
Tractor Breaker - DER | N/C | N/C | JAISAN | 1815 | 2023-11-06 | Club House area development & C bldg. services misc. work | 2 | 6000 | 0 | 12000 | 0 | 2024-05-20 | Charges for Tractor Breaker for Hard Murum breaking work at C-Bldg. | 100 |  | 107693 | 2024-05-20 | 12000 | 2024-06-27 18:33 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1815 | 2023-11-06 | 99 level MS sheet, Square pipes shifting & Housekeeping wor | 1 | 10000 | 0 | 10000 | 0 | 2024-07-06 | Charges for Material Shifting (MS Sheets, Square Pipe, etc) and Housekeeping work at 99 Level Entrance Lobby at C-Building. | 100 |  | 108860 | 2024-07-08 | 10000 | 2024-07-15 11:24 | 0 | JAISAN
Tractor - BRE | N/C | N/C | JAISAN | 1815 | 2023-11-06 | Tractor Trips For Garbage Shifting | 6 | 3500 | 0 | 21000 | 0 | 2024-07-31 | Tractor Charges for Garbage shifting of A,B,C,D Building & development & Tile Godown shifting from 102 level to 99 level. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1817 | 2023-11-16 | A Parking Cleaning, shifting, chipping, Misc. work | 1 | 24750 | 0 | 24750 | 0 | 2024-01-29 | Labour charges for Lobby Breaker work,Chipping work at 111 Level, Lobby area material shifting 108 lvl to podium,111 lvl. BBM & Plaster work,Ghadai work at Lobby area, A2 parking cleaning work, 99 lvl. Staircase Rabit shifting. | 100 |  | 104880 | 2024-01-29 | 36050 | 2024-02-02 14:16 | -11300 | JAISAN
Labour lumpsum | N/C | N/C | JAISAN | 1817 | 2023-11-16 | C Parking Cleaning, Shifting, Chipping Misc. work | 1 | 11300 | 0 | 11300 | 0 | 2024-01-29 | Labour charges for Scrap collection for C-Bldg to club house, Chamber making work, Murum shifting from club house to C-Bldg,Material shifting PT Fabrication at C-Bldg. | 100 |  | 104880 | 2024-01-29 | 36050 | 2024-02-02 14:16 | -24750 | JAISAN
PCC | N/C | N/C | JAISAN | 1817 | 2023-11-16 | A 99 Level Staircases & Meter room area PCC work | 617.85 | 7 | 0 | 4324.95 | 0 | 2024-07-01 | Charges for PCC work, without RMC (Manually Concrete) at A-Bldg 99 level | 100 |  | 108771 | 2024-07-03 | 4324.95 | 1900-01-01 | 0 | JAISAN
Int Flat CP & Sanitory Rate Diff. | N/C | N/C | SAROJ KUMAR PRADHAN | 1837 | 2023-11-27 | B Bldg 2501 Internal Plumbing CP & Sanitary (L) | 1.631 | 2053.57 | 0 | 3349.3727 | 0 | 2024-04-06 18:05 | Labour Charges for Internal Flat Plumbing work (7 Toilet +Kitchen+ Ledge wall) CP and Sanitory Fittings | 100 | debris removal, duct cleaning, unwanted material removal work. | 106567 | 2024-04-08 | 3349.37 | 2024-04-29 11:55 | 0.00267 | JAISAN
Panel Shifting - UTI | N/C | N/C | JAISAN | 1848 | 2023-12-05 | A, B & C bldg. ACCL panel Shifting to 99 lvl. Meter room | 1 | 4000 | 0 | 4000 | 0 | 2024-02-17 | Labour Charges for 5 No Panel Shifting Work from B building to Meter Room | 100 |  | 105366 | 2024-02-19 | 4000 | 2024-03-02 11:53 | 0 | JAISAN
Brickwork 4" (L) - LC | N/C | N/C | JAISAN | 1848 | 2023-12-05 | Pump room foundation work | 165.16 | 20 | 0 | 3303.2 | 0 | 2024-06-08 | Labour charges for Construction of 4" brickwork with in sirtu 1:6 cement mortar with Red/ Fly ash Brick, cement, sand & water , etc with plumb & right angle cornerwith proper joint filling & strikingjoints on unexposed faces, raking out joints, etc | 100 |  | 108236 | 2024-06-10 | 5347.7 | 2024-06-24 11:40 | -2044.5 | JAISAN
Concrete - M25 | N/C | N/C | JAISAN | 1848 | 2023-12-05 | Pump room foundation work | 5.15 | 300 | 0 | 1545 | 0 | 2024-06-08 | Material supply charges for Concrete (M25) for Pumproom Foundation work | 100 |  | 108236 | 2024-06-10 | 5347.7 | 2024-06-24 11:40 | -3802.7 | JAISAN
Material Shifting | N/C | N/C | JAISAN | 1848 | 2023-12-05 | Pump room foundation work | 0.333 | 1500 | 0 | 499.5 | 0 | 2024-06-08 | Charges for Material Shifting from 99 level to UGWT Manually. | 100 |  | 108236 | 2024-06-10 | 5347.7 | 2024-06-24 11:40 | -4848.2 | JAISAN
Departmental Labour | N/C | N/C | JAISAN | 1848 | 2023-12-05 | Hard rock broken material removing from Strom water trench | 17 | 650 | 0 | 11050 | 0 | 2024-07-06 | Male coolie Charges for Hard Rock Breaking work, Material removing in storm water trench for C-Bldg. | 100 |  | 108858 | 2024-07-08 | 11950 | 1900-01-01 | -900 | JAISAN
Departmental Labour | N/C | N/C | JAISAN | 1848 | 2023-12-05 | Hard rock broken material removing from Strom water trench | 2 | 450 | 0 | 900 | 0 | 2024-07-06 | Female coolie Charges for Hard Rock Breaking work, Material removing in storm water trench for C-Bldg. | 100 |  | 108858 | 2024-07-08 | 11950 | 1900-01-01 | -11050 | JAISAN
Poclain Charges - BC - | N/C | N/C | JAISAN | 1850 | 2023-12-06 | Mini poclain for C bldg. services excavation work | 72 | 1100 | 0 | 79200 | 0 | 2024-07-06 | Charges for hiring Mini Poclain for C-Bldg Services Excavation work. | 100 |  | 108861 | 2024-07-08 | 79200 | 1900-01-01 | 0 | JAISAN
Trimix Work | N/C | N/C | HOLE ENTERPRISES | 1853 | 2023-12-22 | Club House extended area hardscape Raft slab & Trimix | 600 | 10 | 0 | 6000 | 0 | 2024-03-20 11:13 | Labour Charges for Trimix with Plastic sheet opposite to Club House extended Hard Scape Area . | 100 |  | 106509 | 2024-04-08 | 6000 | 2024-04-20 11:33 | 0 | JAISAN
Tractor Breaker - DER | N/C | N/C | JAISAN | 2035 | 2024-06-27 | Tractor breaker for C building services | 21 | 6000 | 0 | 126000 | 0 | 2024-07-13 | Charges for Tractor Breaker for Breaking of Hard rock for C-Building Storm Water Line work. | 100 |  | 109051 | 2024-07-15 | 126000 | 1900-01-01 | 0 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 2071 | 2024-07-17 | A,B,C D & Development Housekeeping | 92 | 450 | 0 | 41400 | 0 | 2024-07-31 | Department labour (F/C ) charges for Housekeeping,Garbage & Material shifting for A,B,C,D Building and Development for MAY-2024 & JUNE-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 2071 | 2024-07-17 | A,B,C D & Development Housekeeping | 103.5 | 650 | 0 | 67275 | 0 | 2024-07-31 | Department labour (M/C ) charges for Housekeeping,Garbage & Material shifting for A,B,C,D Building,godown shifting and Development for MAY-2024 & JUNE-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 372 | 2018-04-30 | B Bldg Terrace Slab Built-up Area (L) | 20.55 | 175.174 | 0 | 3599.8257 | 0 | 2024-03-11 11:25 | Aluform Shuttering/Reinforcement/Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 105960 | 2024-03-11 | 3599.83 | 2024-03-18 12:42 | -0.0043 | JAISAN
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 372 | 2018-04-30 | B Bldg Terrace Parapet Work Built-up Area (L) - 7072.99 S | 83.75 | 80 | 0 | 6700 | 0 | 2024-04-06 17:19 | Aluform Shuttering/Reinforcement/Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 | unwanted material debris, steel, & toi. duct cleaning work. | 106557 | 2024-04-08 | 6700 | 2024-04-29 11:55 | 0 | JAISAN
Chemical W/P (L+M) | N/C | N/C | SHWETA SURESH GOVALKAR | 498 | 2019-01-09 | B 1101 Chemical & IPS Waterproofing | 176.31 | 19 | 0 | 3349.89 | 0 | 2024-04-06 17:49 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet,Guest Toilet & Attached Terrace) M+L | 100 | debris & unwanted material removal & toi. duct cleaning work. | 106564 | 2024-04-08 | 3349.89 | 2024-04-29 11:55 | 0 | JAISAN
Italian marble Skirting - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 601 Guest Bed Marble Flooring | 28.422 | 45 | 0 | 1278.99 | 0 | 2024-04-08 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 107699 | 2024-05-20 | 4190.63 | 2024-05-20 13:34 | -2911.64 | JAISAN
Italian marble Skirting - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 602 Parents Bed Marble Flooring | 44.703 | 45 | 0 | 2011.635 | 0 | 2024-04-08 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 107699 | 2024-05-20 | 4190.63 | 2024-05-20 13:34 | -2178.995 | JAISAN
Italian marble Skirting - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 701 Living,Dining,Passa. Marble Flooring | 12 | 50 | 0 | 600 | 0 | 2024-04-14 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -8251.25 | JAISAN
Italian marble Skirting - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 701 Master Bed Marble Flooring | 10 | 50 | 0 | 500 | 0 | 2024-04-14 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -8351.25 | JAISAN
Italian marble Skirting - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Master Bed Marble Flooring | 15 | 60 | 0 | 900 | 0 | 2024-04-07 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 107699 | 2024-05-20 | 4190.63 | 2024-05-20 13:34 | -3290.63 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1102 Kitchen Vitrified Flooring | 14 | 20 | 0 | 280 | 0 | 2024-03-20 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107700 | 2024-05-20 | 8100.29 | 2024-05-20 13:34 | -7820.29 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1102 Terrace Vitrified Flooring | 14 | 20 | 0 | 280 | 0 | 2024-03-20 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107700 | 2024-05-20 | 8100.29 | 2024-05-20 13:34 | -7820.29 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1402 Kitchen Vitrified Flooring | 38 | 24 | 0 | 912 | 0 | 2024-02-11 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13394.36 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2001 Kitchen Vitrified Flooring | 16 | 28 | 0 | 448 | 0 | 2024-04-14 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -8403.25 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2101 Terrace Vitrified Flooring | 16 | 28 | 0 | 448 | 0 | 2024-04-21 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5597.96 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Terrace Vitrified Flooring | 15 | 28 | 0 | 420 | 0 | 2024-04-21 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5625.96 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 201 Kitchen Vitrified Flooring | 4 | 15 | 0 | 60 | 0 | 2024-04-21 | 1200 x 800 Vitrified Skirting | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5985.96 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 202 Kitchen Vitrified Flooring | 42 | 15 | 0 | 630 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13676.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1001 Kitchen Vitrified Flooring | 18 | 20 | 0 | 360 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13946.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1002 Kitchen Vitrified Flooring | 16 | 20 | 0 | 320 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13986.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1101 Terrace Vitrified Flooring | 10 | 20 | 0 | 200 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -14106.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1302 Kitchen Vitrified Flooring | 42 | 24 | 0 | 1008 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13298.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1501 Kitchen Vitrified Flooring | 22 | 24 | 0 | 528 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13778.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1501 Terrace Vitrified Flooring | 23 | 24 | 0 | 552 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13754.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1502 Kitchen Vitrified Flooring | 22 | 24 | 0 | 528 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13778.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1502 Terrace Vitrified Flooring | 0.15 | 24 | 0 | 3.6 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -14302.76 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1901 Kitchen Vitrified Flooring | 25 | 28 | 0 | 700 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13606.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Kitchen Vitrified Flooring | 0.42 | 28 | 0 | 11.76 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -14294.6 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2201 Kitchen Vitrified Flooring | 44 | 28 | 0 | 1232 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13074.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2301 Kitchen Vitrified Flooring | 40.446 | 28 | 0 | 1132.488 | 0 | 2024-04-21 | 1200 x 800 Vitrified Skirting | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -4913.472 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2302 Kitchen Vitrified Flooring | 42 | 28 | 0 | 1176 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13130.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2401 Kitchen Vitrified Flooring | 44 | 28 | 0 | 1232 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13074.36 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 202 Powder Toilet Vitrified Flooring | 8 | 13 | 0 | 104 | 0 | 2024-04-21 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5941.96 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 202 Staff Room Vitrified Flooring | 13 | 13 | 0 | 169 | 0 | 2024-04-21 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5876.96 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1002 Staff Room Vitrified Flooring | 40.617 | 17 | 0 | 690.489 | 0 | 2024-03-20 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107700 | 2024-05-20 | 8100.29 | 2024-05-20 13:34 | -7409.801 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1601 Parents Toilet Vitrified Flooring | 5 | 21 | 0 | 105 | 0 | 2024-02-11 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -14201.36 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1901 Dry Balcony Vitrified Flooring | 18 | 24 | 0 | 432 | 0 | 2024-04-21 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5613.96 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1901 Staff Room Vitrified Flooring | 4 | 24 | 0 | 96 | 0 | 2024-04-14 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -8755.25 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2001 Master Toilet Vitrified Flooring | 5 | 24 | 0 | 120 | 0 | 2024-04-14 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -8731.25 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2001 Parents Toilet Vitrified Flooring | 5 | 24 | 0 | 120 | 0 | 2024-04-21 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5925.96 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2001 Children Toilet Flooring | 4 | 24 | 0 | 96 | 0 | 2024-04-14 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -8755.25 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Dry Balcony Vitrified Flooring | 4 | 24 | 0 | 96 | 0 | 2024-04-21 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5949.96 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Children Toilet Vitrified Flooring | 5 | 24 | 0 | 120 | 0 | 2024-04-21 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5925.96 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2301 Staff Room Vitrified Flooring | 39.645 | 24 | 0 | 951.48 | 0 | 2024-04-22 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5094.48 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 201 Staff Room Vitrified Flooring | 17 | 13 | 0 | 221 | 0 | 2024-02-11 | 600 x 600 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -14085.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 202 Staff Room Vitrified Flooring | 17 | 13 | 0 | 221 | 0 | 2024-02-11 | 600 x 600 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -14085.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 502 Staff Room Vitrified Flooring | 15.642 | 13 | 0 | 203.346 | 0 | 2024-04-21 | 600 x 600 Vitrified Skirting | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5842.614 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 602 Staff Room Vitrified Flooring | 15.642 | 13 | 0 | 203.346 | 0 | 2024-04-21 | 600 x 600 Vitrified Skirting | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5842.614 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1501 Staff Room Vitrified Flooring | 7 | 21 | 0 | 147 | 0 | 2024-02-11 | 600 x 600 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -14159.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2001 Staff Room Vitrified Flooring | 3 | 24 | 0 | 72 | 0 | 2024-04-21 | 600 x 600 Vitrified Skirting | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5973.96 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2002 Staff Room Vitrified Flooring | 17 | 24 | 0 | 408 | 0 | 2024-02-11 | 600 x 600 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13898.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Staff Room Vitrified Flooring | 17 | 24 | 0 | 408 | 0 | 2024-04-21 | 600 x 600 Vitrified Skirting | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5637.96 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2201 Staff Room Vitrified Flooring | 17 | 24 | 0 | 408 | 0 | 2024-02-11 | 600 x 600 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13898.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2301 Staff Room Vitrified Flooring | 17 | 24 | 0 | 408 | 0 | 2024-02-11 | 600 x 600 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13898.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2302 Staff Room Vitrified Flooring | 17 | 24 | 0 | 408 | 0 | 2024-02-11 | 600 x 600 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13898.36 | JAISAN
I Marble Patti - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 401 Toilet & Dry Balcony Devider Patti | 7 | 45 | 0 | 315 | 0 | 2024-04-14 | Italian Marble Divider Patti Cutting & Fixing | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -8536.25 | JAISAN
I Marble Patti - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 402 Toilet & Dry Balcony Devider Patti | 9 | 45 | 0 | 405 | 0 | 2024-04-14 | Italian Marble Divider Patti Cutting & Fixing | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -8446.25 | JAISAN
I Marble Patti - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 701 Toilet & Dry Balcony Devider Patti | 28.665 | 50 | 0 | 1433.25 | 0 | 2024-04-15 | Italian Marble Divider Patti Cutting & Fixing | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -7418 | JAISAN
I Marble Patti - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 802 Toilet & Dry Balcony Devider Patti | 29.98 | 50 | 0 | 1499 | 0 | 2024-04-15 | Italian Marble Divider Patti Cutting & Fixing | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -7352.25 | JAISAN
I Marble Patti - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 902 Toilet & Dry Balcony Devider Patti | 29.98 | 50 | 0 | 1499 | 0 | 2024-04-15 | Italian Marble Divider Patti Cutting & Fixing | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -7352.25 | JAISAN
I Marble Patti - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1502 Toilet & Dry Balcony Devider Patti | 4 | 55 | 0 | 220 | 0 | 2024-04-14 | Italian Marble Divider Patti Cutting & Fixing | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -8631.25 | JAISAN
I Marble Patti - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2401 Toilet & Dry Balcony Devider Patti | 7 | 60 | 0 | 420 | 0 | 2024-04-14 | Italian Marble Divider Patti Cutting & Fixing | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -8431.25 | JAISAN
I Marble Patti - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2402 Toilet & Dry Balcony Devider Patti | 20 | 60 | 0 | 1200 | 0 | 2024-04-14 | Italian Marble Divider Patti Cutting & Fixing | 100 |  | 107701 | 2024-05-20 | 8851.25 | 2024-05-20 13:35 | -7651.25 | JAISAN
Granite Sill-BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 202 Terrace Parapet Top Granite | 23.62 | 40 | 0 | 944.8 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing | 100 |  | 107700 | 2024-05-20 | 8100.29 | 2024-05-20 13:34 | -7155.49 | JAISAN
Granite Sill-BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1302 Terrace Parapet Top Granite | 23.62 | 50 | 0 | 1181 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing | 100 |  | 107700 | 2024-05-20 | 8100.29 | 2024-05-20 13:34 | -6919.29 | JAISAN
Granite Sill-BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1702 Terrace Parapet Top Granite | 23.62 | 50 | 0 | 1181 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing | 100 |  | 107700 | 2024-05-20 | 8100.29 | 2024-05-20 13:34 | -6919.29 | JAISAN
Granite Sill-BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2601 Terrace Parapet Top Granite | 23.62 | 75 | 0 | 1771.5 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing | 100 |  | 107700 | 2024-05-20 | 8100.29 | 2024-05-20 13:34 | -6328.79 | JAISAN
Granite Sill-BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2602 Terrace Parapet Top Granite | 23.62 | 75 | 0 | 1771.5 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing | 100 |  | 107700 | 2024-05-20 | 8100.29 | 2024-05-20 13:34 | -6328.79 | JAISAN
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2201 Terrace Vitrified Flooring | 15 | 28 | 0 | 420 | 0 | 2024-04-21 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5625.96 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 201 Terrace Vitrified Flooring | 17 | 15 | 0 | 255 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -14051.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 202 Terrace Vitrified Flooring | 8 | 15 | 0 | 120 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -14186.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 602 Terrace Vitrified Flooring | 38.286 | 15 | 0 | 574.29 | 0 | 2024-04-21 | 1200 x 800 Vitrified Skirting | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5471.67 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1402 Terrace Vitrified Flooring | 42 | 24 | 0 | 1008 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13298.36 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2001 Terrace Vitrified Flooring | 4 | 28 | 0 | 112 | 0 | 2024-04-21 | 1200 x 800 Vitrified Skirting | 100 |  | 107070 | 2024-04-23 | 6045.96 | 2024-05-03 13:37 | -5933.96 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2401 Terrace Vitrified Flooring | 43 | 28 | 0 | 1204 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105247 | 2024-02-12 | 14306.36 | 2024-03-16 12:44 | -13102.36 | JAISAN
Italian marble Skirting - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 604 Guest Bed Marble Flooring - | 28.422 | 45 | 0 | 1278.99 | 0 | 2024-04-08 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 106619 | 2024-04-08 | 2838.99 | 1900-01-01 | -1560 | JAISAN
Italian marble Skirting - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2103 Living,Dining,Passa. Marble Flooring | 19 | 60 | 0 | 1140 | 0 | 2024-04-07 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 106619 | 2024-04-08 | 2838.99 | 1900-01-01 | -1698.99 | JAISAN
Italian marble Skirting - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2103 Guest Bed Marble Flooring | 7 | 60 | 0 | 420 | 0 | 2024-04-07 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 106619 | 2024-04-08 | 2838.99 | 1900-01-01 | -2418.99 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 103 Terrace Vitrified Flooring | 13 | 15 | 0 | 195 | 0 | 2024-03-20 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -15275.87 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 104 Kitchen Vitrified Flooring | 15 | 15 | 0 | 225 | 0 | 2024-03-20 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -15245.87 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 203 Terrace Vitrified Flooring | 20 | 15 | 0 | 300 | 0 | 2024-04-21 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -8138.84 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 1303 Kitchen Vitrified Flooring | 11 | 24 | 0 | 264 | 0 | 2024-02-11 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -12412.25 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 1904 Terrace Vitrified Flooring | 110 | 28 | 0 | 3080 | 0 | 2024-04-14 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 106869 | 2024-04-15 | 8279.89 | 2024-04-30 15:28 | -5199.89 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2003 Kitchen Vitrified Flooring | 11 | 28 | 0 | 308 | 0 | 2024-04-21 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -8130.84 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 203 Kitchen Vitrified Flooring | 37 | 15 | 0 | 555 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -12121.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 203 Terrace Vitrified Flooring | 4 | 15 | 0 | 60 | 0 | 2024-04-21 | 1200 x 800 Vitrified Skirting | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -8378.84 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 204 Kitchen Vitrified Flooring | 22 | 15 | 0 | 330 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -12346.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 204 Terrace Vitrified Flooring | 20 | 15 | 0 | 300 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -12376.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 503 Terrace Vitrified Flooring | 36.513 | 15 | 0 | 547.695 | 0 | 2024-04-21 | 1200 x 800 Vitrified Skirting | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -7891.145 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 603 Kitchen Vitrified Flooring | 33.354 | 15 | 0 | 500.31 | 0 | 2024-04-21 | 1200 x 800 Vitrified Skirting | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -7938.53 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 1204 Terrace Vitrified Flooring | 16 | 20 | 0 | 320 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -12356.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 1403 Terrace Vitrified Flooring | 27 | 24 | 0 | 648 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -12028.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 1604 Kitchen Vitrified Flooring | 44 | 24 | 0 | 1056 | 0 | 2024-04-21 | 1200 x 800 Vitrified Skirting | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -7382.84 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2003 Kitchen Vitrified Flooring | 37 | 28 | 0 | 1036 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -11640.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2003 Terrace Vitrified Flooring | 40 | 28 | 0 | 1120 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -11556.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2004 Kitchen Vitrified Flooring | 44 | 28 | 0 | 1232 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -11444.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2103 Kitchen Vitrified Flooring | 33.354 | 28 | 0 | 933.912 | 0 | 2024-04-21 | 1200 x 800 Vitrified Skirting | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -7504.928 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2103 Terrace Vitrified Flooring | 36.513 | 28 | 0 | 1022.364 | 0 | 2024-04-21 | 1200 x 800 Vitrified Skirting | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -7416.476 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2104 Kitchen Vitrified Flooring | 44 | 28 | 0 | 1232 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -11444.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2104 Terrace Vitrified Flooring | 35 | 28 | 0 | 980 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -11696.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2203 Kitchen Vitrified Flooring | 37 | 28 | 0 | 1036 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -11640.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2204 Kitchen Vitrified Flooring | 44 | 28 | 0 | 1232 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -11444.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2204 Terrace Vitrified Flooring | 4 | 28 | 0 | 112 | 0 | 2024-02-11 | 1200 x 800 Vitrified Skirting | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -12564.25 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 103 Staff Room Vitrified Flooring | 71.69 | 13 | 0 | 931.97 | 0 | 2024-03-20 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -14538.9 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 104 Dry Balcony Vitrified Flooring | 8 | 13 | 0 | 104 | 0 | 2024-03-20 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -15366.87 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 104 Staff Room Vitrified Flooring | 5 | 13 | 0 | 65 | 0 | 2024-03-20 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -15405.87 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 203 Staff Room Vitrified Flooring | 6 | 13 | 0 | 78 | 0 | 2024-04-21 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -8360.84 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 1403 Dry Balcony Vitrified Flooring | 34.488 | 21 | 0 | 724.248 | 0 | 2024-02-11 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -11952.002 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2103 Staff Room Vitrified Flooring | 64.521 | 24 | 0 | 1548.504 | 0 | 2024-04-21 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -6890.336 | JAISAN
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2203 Dry Balcony Vitrified Flooring | 34.488 | 24 | 0 | 827.712 | 0 | 2024-04-22 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -7611.128 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 203 Staff Room Vitrified Flooring | 31 | 13 | 0 | 403 | 0 | 2024-02-11 | 600 x 600 Vitrified Skirting (L) | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -12273.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 404 Staff Room Vitrified Flooring | 16.8245 | 13 | 0 | 218.7185 | 0 | 2024-04-21 | 600 x 600 Vitrified Skirting (L) | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -8220.1215 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 603 Staff Room Vitrified Flooring | 28.044 | 13 | 0 | 364.572 | 0 | 2024-04-21 | 600 x 600 Vitrified Skirting (L) | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -8074.268 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2103 Staff Room Vitrified Flooring | 28.044 | 24 | 0 | 673.056 | 0 | 2024-04-21 | 600 x 600 Vitrified Skirting (L) | 100 |  | 107073 | 2024-04-23 | 8438.84 | 2024-05-15 14:34 | -7765.784 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2104 Staff Room Vitrified Flooring | 17 | 24 | 0 | 408 | 0 | 2024-02-11 | 600 x 600 Vitrified Skirting (L) | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -12268.25 | JAISAN
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2203 Staff Room Vitrified Flooring | 31 | 24 | 0 | 744 | 0 | 2024-02-11 | 600 x 600 Vitrified Skirting (L) | 100 |  | 105237 | 2024-02-12 | 12676.25 | 2024-03-16 12:44 | -11932.25 | JAISAN
I Marble Patti - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 403 Toilet & Dry Balcony Devider Patti | 4 | 45 | 0 | 180 | 0 | 2024-04-14 | Italian Marble Divider Patti Cutting & Fixing (L) | 100 |  | 106869 | 2024-04-15 | 8279.89 | 2024-04-30 15:28 | -8099.89 | JAISAN
I Marble Patti - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 404 Toilet & Dry Balcony Devider Patti | 20 | 45 | 0 | 900 | 0 | 2024-04-14 | Italian Marble Divider Patti Cutting & Fixing (L) | 100 |  | 106869 | 2024-04-15 | 8279.89 | 2024-04-30 15:28 | -7379.89 | JAISAN
I Marble Patti - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 503 Toilet & Dry Balcony Devider Patti | 20.01 | 45 | 0 | 900.45 | 0 | 2024-04-15 | Italian Marble Divider Patti Cutting & Fixing (L) | 100 |  | 106869 | 2024-04-15 | 8279.89 | 2024-04-30 15:28 | -7379.44 | JAISAN
I Marble Patti - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 504 Toilet & Dry Balcony Devider Patti | 51.543 | 45 | 0 | 2319.435 | 0 | 2024-04-14 | Italian Marble Divider Patti Cutting & Fixing (L) | 100 |  | 106869 | 2024-04-15 | 8279.89 | 2024-04-30 15:28 | -5960.455 | JAISAN
I Marble Patti - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 603 Toilet & Dry Balcony Devider Patti | 10 | 45 | 0 | 450 | 0 | 2024-04-15 | Italian Marble Divider Patti Cutting & Fixing (L) | 100 |  | 106869 | 2024-04-15 | 8279.89 | 2024-04-30 15:28 | -7829.89 | JAISAN
I Marble Patti - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 604 Toilet & Dry Balcony Devider Patti | 10 | 45 | 0 | 450 | 0 | 2024-04-15 | Italian Marble Divider Patti Cutting & Fixing (L) | 100 |  | 106869 | 2024-04-15 | 8279.89 | 2024-04-30 15:28 | -7829.89 | JAISAN
Granite Sill-BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 104 Terrace Parapet Top Granite | 23.62 | 40 | 0 | 944.8 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -14526.07 | JAISAN
Granite Sill-BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 1404 Terrace Parapet Top Granite | 23.62 | 50 | 0 | 1181 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -14289.87 | JAISAN
Granite Sill-BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 1503 Terrace Parapet Top Granite | 27.29 | 50 | 0 | 1364.5 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -14106.37 | JAISAN
Granite Sill-BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 1703 Terrace Parapet Top Granite | 27.29 | 50 | 0 | 1364.5 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -14106.37 | JAISAN
Granite Sill-BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 1704 Terrace Parapet Top Granite | 23.62 | 50 | 0 | 1181 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -14289.87 | JAISAN
Granite Sill-BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 1803 Terrace Parapet Top Granite | 27.29 | 50 | 0 | 1364.5 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -14106.37 | JAISAN
Granite Sill-BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2003 Terrace Parapet Top Granite | 27.29 | 55 | 0 | 1500.95 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -13969.92 | JAISAN
Granite Sill-BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2103 Terrace Parapet Top Granite | 27.29 | 55 | 0 | 1500.95 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -13969.92 | JAISAN
Granite Sill-BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2403 Terrace Parapet Top Granite | 27.29 | 55 | 0 | 1500.95 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -13969.92 | JAISAN
Granite Sill-BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2503 Terrace Parapet Top Granite | 27.29 | 75 | 0 | 2046.75 | 0 | 2024-03-20 | Sadarhalli Granite Sill Cutting & Fixing (L) | 100 |  | 107697 | 2024-05-20 | 15470.87 | 2024-05-20 13:35 | -13424.12 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 502 Parents Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 502 Children Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 503 Guest Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 503 Children Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 504 Parents Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 504 Children Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 601 Parents Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 601 Children Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 602 Parents Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 602 Children Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 603 Guest Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 603 Children Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 604 Parents Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 604 Children Toilet Counter wash Basin | 5.5 | 45 | 0 | 247.5 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4317.5 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 701 Parents Toilet Counter wash Basin | 5.5 | 50 | 0 | 275 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4290 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 701 Children Toilet Counter wash Basin | 5.5 | 50 | 0 | 275 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4290 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Parents Toilet Counter wash Basin | 5.5 | 50 | 0 | 275 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4290 | JAISAN
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Children Toilet Counter wash Basin | 5.5 | 50 | 0 | 275 | 0 | 2024-04-21 | Wash Basin Counter Champher & Polish (L) | 100 |  | 107078 | 2024-04-23 | 4565 | 2024-05-21 18:47 | -4290 | JAISAN
Italian Marble Flooring - BCo | N/C | N/C | RAHUL ENTERPRISES (Prop Laburi) | 758 | 2020-02-13 | B 2001 Master Bed,Dreeser Marble Flooring | 30 | 60 | 0 | 1800 | 0 | 2024-03-11 11:19 | Italian Marble Flooring with Proper Cutting,Shifting,Fixing,Line Level,Joint Filling,Right Angle etc & POP Sheet or Floor Guard Laying & Removing,with all Necessary Tools | 100 | debris shifting work | 106004 | 2024-03-11 | 6823.56 | 2024-03-23 11:58 | -5023.56 | JAISAN
Italian Marble Flooring - BCo | N/C | N/C | RAHUL ENTERPRISES (Prop Laburi) | 758 | 2020-02-13 | B 2001 Parents Bed Marble Flooring | 30 | 60 | 0 | 1800 | 0 | 2024-03-11 11:19 | Italian Marble Flooring with Proper Cutting,Shifting,Fixing,Line Level,Joint Filling,Right Angle etc & POP Sheet or Floor Guard Laying & Removing,with all Necessary Tools | 100 | debris shifting work | 106004 | 2024-03-11 | 6823.56 | 2024-03-23 11:58 | -5023.56 | JAISAN
Dado BC | N/C | N/C | RAHUL ENTERPRISES (Prop Laburi) | 758 | 2020-02-13 | B 1101 Dry Balcony Dado | 90.42 | 18 | 0 | 1627.56 | 0 | 2024-03-11 13:00 | 600 x 600 Dado Fixing with Proper Line Level,Readymade Adhesive Mortar of Approved Quality on Plaster of 1:2 Cement Mortar Including Joint Filling with White/ Colour Cement Slurry etc | 100 | refuge terrace acid wash done by JAISAN | 106004 | 2024-03-11 | 6823.56 | 2024-03-23 11:58 | -5196 | JAISAN
Dado BC | N/C | N/C | RAHUL ENTERPRISES (Prop Laburi) | 758 | 2020-02-13 | B 1601 StaffToilet Dado - 1 No. | 76 | 21 | 0 | 1596 | 0 | 2024-03-11 13:11 | 600 x 300 Dado Fixing with Proper Line Level,Readymade Adhesive Mortar of Approved Quality on Plaster of 1:2 Cement Mortar Including Joint Filling with White/ Colour Cement Slurry etc | 100 | refuge terrace acid wash done by JAISAN | 106004 | 2024-03-11 | 6823.56 | 2024-03-23 11:58 | -5227.56 | JAISAN
Italian marble Skirting - BCo | N/C | N/C | RAHUL ENTERPRISES (Prop Laburi) | 772 | 2020-03-05 | A 1904 NOC | 42.021 | 60 | 0 | 2521.26 | 0 | 2024-04-07 | Labour charges for fixing of Italian Marble Skirting for A-Bldg 1904 Children Room. | 100 |  | 106614 | 2024-04-08 | 2521.26 | 1900-01-01 | 0 | JAISAN