## Work_Completion_Browse638580240
Work Completion Browse
Project : GANGA DHAM TOWERS
From Date : 30/07/2024 To date: 30/07/2024
Page 1 of 1
Total Records: 36 Records 1 to 36
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Garden work - Mkt | N/C | N/C | GREEN GARDEN DEVLOPERS AND MENTENANCE | 1360 | 2022-04-11 | Road Divider Garden Maintenance | 1 | 15000 | 0 | 15000 | 0 | 2024-07-31 | Charges for Road divider Maintenance work for the month of JUL-2024 Including watering and tanker is in Contractors scope | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | GREEN GARDEN DEVLOPERS AND MENTENANCE
9" Brick Work | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 139.446 | 28 | 0 | 3904.488 | 0 | 2024-07-30 18:12 | Labour charges for Construction of 9 inch Brickwork for Club House Back side Feature wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
9" Brick Work | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 15.494 | 28 | 0 | 433.832 | 0 | 2024-07-30 18:19 | Labour charges for Construction of 9 inch Brickwork for Club House Back side Feature wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Patli (Band)- BC | GLAZING SERVICES | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 21.258 | 12 | 0 | 255.096 | 0 | 2024-07-30 18:12 | Labour charges for Construction of Patli (Band) for Club House Back side Feature wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Patli (Band)- BC | GLAZING SERVICES | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 2.362 | 12 | 0 | 28.344 | 0 | 2024-07-30 18:19 | Labour charges for Construction of Patli (Band) for Club House Back side Feature wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Dhar Making - Mkt | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 33.066 | 25 | 0 | 826.65 | 0 | 2024-07-30 18:12 | Labour charges for Dhar Making work for Club House Back side Feature wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Dhar Making - Mkt | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 3.674 | 25 | 0 | 91.85 | 0 | 2024-07-30 18:19 | Labour charges for Dhar Making work for Club House Back side Feature wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
9" Brick Work | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 121.725 | 28 | 0 | 3408.3 | 0 | 2024-07-30 18:12 | Labour charges for Construction of 9 inch Brickwork for 105 level South-west side. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
9" Brick Work | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 13.525 | 28 | 0 | 378.7 | 0 | 2024-07-30 18:19 | Labour charges for Construction of 9 inch Brickwork for 105 level South-west side. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Dhar Making - Mkt | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 65.151 | 25 | 0 | 1628.775 | 0 | 2024-07-30 18:12 | Labour charges for Dhar Making work for 105 level South-west side BBM Plaster work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Dhar Making - Mkt | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 7.239 | 25 | 0 | 180.975 | 0 | 2024-07-30 18:19 | Labour charges for Dhar Making work for 105 level South-west side BBM Plaster work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Patli Mkt - R.Ft | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 65.151 | 12 | 0 | 781.812 | 0 | 2024-07-30 18:12 | Labour charges for Patli making work for 105 level South-west side BBM Plaster work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Patli Mkt - R.Ft | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 7.239 | 12 | 0 | 86.868 | 0 | 2024-07-30 18:19 | Labour charges for Patli making work for 105 level South-west side BBM Plaster work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Double Coat Plaster work (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 139.5 | 35 | 0 | 4882.5 | 0 | 2024-07-30 18:12 | Labour charges for Applying Double coat Tar Plaster Work for Club house Back side Feature wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Double Coat Plaster work (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 15.5 | 35 | 0 | 542.5 | 0 | 2024-07-30 18:19 | Labour charges for Applying Double coat Tar Plaster Work for Club house Back side Feature wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Double Coat Plaster work (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 139.5 | 35 | 0 | 4882.5 | 0 | 2024-07-30 18:12 | Labour charges for Applying Double coat Sponge Finish Plaster Work for Club house Back side Feature wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Double Coat Plaster work (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 15.5 | 35 | 0 | 542.5 | 0 | 2024-07-30 18:19 | Labour charges for Applying Double coat Sponge Finish Plaster Work for Club house Back side Feature wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Single Coat Plaster (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 243.828 | 25 | 0 | 6095.7 | 0 | 2024-07-30 18:12 | Labour charges for Applying Single coat Sand face Plaster Work for 105 lvl. Southwest side area. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Single Coat Plaster (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 27.092 | 25 | 0 | 677.3 | 0 | 2024-07-30 18:19 | Labour charges for Applying Single coat Sand face Plaster Work for 105 lvl. Southwest side area. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Garbage Collection & Shifting | N/C | N/C | HANUMANT DADA MANE | 1539 | 2023-03-16 | Garbage Collection& Shifting (Sales Office, Site office, Lab | 1 | 7500 | 0 | 7500 | 0 | 2024-07-31 | Charges for Garbage Collection & shifting from site to outside & staff toilet, labour camp toilet cleaning for month JULY-2024. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HANUMANT DADA MANE
AAC Block Filling BC | N/C | N/C | SURESH KUMAR MURALIDHAR | 1579 | 2023-04-17 | A Podium 111 Level Blockfilling | 1802.32 | 7.5 | 0 | 13517.4 | 0 | 2024-07-30 16:13 | Labour Charges for AAC Block filling work at podium 111 level A Building Core area for height increase by 300mm as per drawing specifications. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Breaker-BC | N/C | N/C | JAISAN | 1751 | 2023-09-11 | Parking, Podium Breaking, Chipping Plumbing Ducts & Chambers | 8 | 1300 | 0 | 10400 | 0 | 2024-07-31 | Breaker charges including Helper for Breaking & Chipping work for plumbing duct / Chamber for Services. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 1751 | 2023-09-11 | Parking, Podium Breaking, Chipping Plumbing Ducts & Chambers | 5 | 600 | 0 | 3000 | 0 | 2024-07-31 | Male Coolie Charges for Breaking & Chipping work for plumbing duct / Chamber for Services. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 1785 | 2023-10-07 | A,B,C D & Development Housekeeping | 57 | 650 | 0 | 37050 | 0 | 2024-07-31 | Department labour (M/C ) charges for Housekeeping,Garbage & Material shifting for A,B,C,D Building and Development for JULY-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 1785 | 2023-10-07 | A,B,C D & Development Housekeeping | 33 | 450 | 0 | 14850 | 0 | 2024-07-31 | Department labour (F/C ) charges for Housekeeping,Garbage & Material shifting for A,B,C,D Building and Development for JULY-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 9th Slab (5th Floor) Slab Built-up Area (L) | 5103.26 | 150 | 0 | 765489 | 137788.02 | 2024-07-30 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 | flat no 404 & 401 | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | B & B ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 7th Slab (3rd Floor) Slab Built-up Area (L) | 3061.956 | 150 | 0 | 459293.4 | 82672.82 | 2024-07-30 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | B & B ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 8th Slab (4th Floor) Slab Built-up Area (L) | 3049.572 | 150 | 0 | 457435.8 | 82338.44 | 2024-07-30 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | B & B ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | B & B ENTERPRISES | 1807 | 2023-10-30 | C Bldg 9th Slab (5th Floor) Slab Built-up Area (L) | 3061.956 | 150 | 0 | 459293.4 | 82672.82 | 2024-07-30 | Labour charges for Aluform Shuttering, Reinforcement & Concreting for slab, beam, staircase and all shear walls. | 100 | Flat no 402 | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | B & B ENTERPRISES
Tractor - BRE | N/C | N/C | JAISAN | 1815 | 2023-11-06 | Tractor Trips For Garbage Shifting | 6 | 3500 | 0 | 21000 | 0 | 2024-07-31 | Tractor Charges for Garbage shifting of A,B,C,D Building & development & Tile Godown shifting from 102 level to 99 level. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 1852 | 2023-12-09 | GDT Electricity expenses | 0.0719 | 550000 | -25 | 39545 | 0 | 2024-07-30 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 109444 | 2024-07-30 | 39520 | 2024-07-30 15:54 | 25 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 1852 | 2023-12-09 | GDT Electricity expenses | 0.4875 | 550000 | 25 | 268125 | 0 | 2024-07-30 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 109445 | 2024-07-30 | 268150 | 2024-07-30 15:55 | -25 | MSEDCL
Event Sponsorship | N/C | N/C | OMS AC TIMES INTERNET LTD., | 2032 | 2024-06-24 | MEDIA Branding | 0.95 | 150000 | 1 | 142500 | 25650.18 | 2024-07-30 | TIMES POWER BRANDS JUNE 2024- COST RS. 150000/- + TAX 100% FULL ADVANCE PAYMENT ( PROFILING SUPPLIMENT PUNE DITION - 200 SQ CM. QTY 1 & POST EVENT COVERAGE IN PUNE TIMES+ MAHARASHTRA TIMES - PUNE PLUS QTY 1 | 100 | TIMES POWER BRANDS JUNE 2024- COST RS. 150000/- + TAX 100% FULL ADVANCE PAYMENT ( PROFILING SUPPLIMENT PUNE DITION - 200 SQ CM. QTY 1 & POST EVENT COVERAGE IN PUNE TIMES+ MAHARASHTRA TIMES - PUNE PLUS QTY 1 | 109440 | 2024-07-30 | 142501 | 1900-01-01 | -1 | OMS AC TIMES INTERNET LTD.,
Department Labour - DEn | N/C | N/C | JAISAN | 2071 | 2024-07-17 | A,B,C D & Development Housekeeping | 92 | 450 | 0 | 41400 | 0 | 2024-07-31 | Department labour (F/C ) charges for Housekeeping,Garbage & Material shifting for A,B,C,D Building and Development for MAY-2024 & JUNE-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 2071 | 2024-07-17 | A,B,C D & Development Housekeeping | 103.5 | 650 | 0 | 67275 | 0 | 2024-07-31 | Department labour (M/C ) charges for Housekeeping,Garbage & Material shifting for A,B,C,D Building,godown shifting and Development for MAY-2024 & JUNE-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JAISAN
Garden work - Mkt | N/C | N/C | RESHMA JALINDAR CHANDGUDE | 940 | 2020-12-28 | Road Divider Garden Maintenance | 1 | 22000 | 0 | 22000 | 0 | 2024-07-31 | Charges for Road Divider Maintenance work for the month of JUL-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | GREEN GARDEN DEVLOPERS AND MENTENANCE