## Work_Completion_Browse638580488
Work Completion Browse
Project : GANGA ALTUS
Contractor : PAPPU BAGELA
Executed By : PAPPU BAGELA
From Date : 01/07/2024 To date: 01/07/2024
Page 1 of 1
Total Records: 1 Records 1 to 1
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Granite Flooring (M)- BCE | N/C | N/C | PAPPU BAGELA | 1052 | 2024-07-12 | F-Entrance Gate(Security Cabin)-Tiling Work | 247.52 | 110.7 | 0 | 27400.464 | 0 | 2024-07-24 10:42 | Material Supply charges for Orissa Blue Granite for Entrace gate Granite work includig loading,unloading & transportation of material. | 100 |  | 109398 | 2024-07-29 | 27400.46 | 1900-01-01 | 0.004 | PAPPU BAGELA