## Work_Completion_Browse638580499
Work Completion Browse
Project : GANGA ALTUS
Contractor : PAPPU BAGELA
Executed By : PAPPU BAGELA
From Date : 01/07/2024 To date: 01/07/2024
Page 1 of 1
Total Records: 5 Records 1 to 5
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Granite Flooring (L)- BCE | N/C | N/C | PAPPU BAGELA | 1051 | 2024-07-12 | F-Entrance Gate(Security Cabin)-Tiling Work | 169.1 | 45 | 0 | 7609.5 | 0 | 2024-07-24 11:31 | Labour Charges for Orissa Granite flooring work for Entrance gate with line,level,right angle & proper joint filling etc complete. | 100 |  | 109399 | 2024-07-29 | 11746.35 | 1900-01-01 | -4136.85 | PAPPU BAGELA
Vertical Patta (L) | N/C | N/C | PAPPU BAGELA | 1051 | 2024-07-12 | F-Entrance Gate(Security Cabin)-Tiling Work | 21.67 | 45 | 0 | 975.15 | 0 | 2024-07-24 11:31 | Labour Charges for Orissa Granite Vertical patta work for Entrance gate with line,level,right angle & proper joint filling etc complete. | 100 |  | 109399 | 2024-07-29 | 11746.35 | 1900-01-01 | -10771.2 | PAPPU BAGELA
Granite Riser (L)- BCE | N/C | N/C | PAPPU BAGELA | 1051 | 2024-07-12 | F-Entrance Gate(Security Cabin)-Tiling Work | 46.33 | 40 | 0 | 1853.2 | 0 | 2024-07-24 11:31 | Labour Charges for Orissa Granite riser fixing work for Entrance gate with line,level,right angle & proper joint filling etc complete. | 100 |  | 109399 | 2024-07-29 | 11746.35 | 1900-01-01 | -9893.15 | PAPPU BAGELA
Granite Tread | N/C | N/C | PAPPU BAGELA | 1051 | 2024-07-12 | F-Entrance Gate(Security Cabin)-Tiling Work | 22.92 | 40 | 0 | 916.8 | 0 | 2024-07-24 11:31 | Labour Charges for Orissa Granite tread fixing work for Entrance gate with line,level,right angle & proper joint filling etc complete. | 100 |  | 109399 | 2024-07-29 | 11746.35 | 1900-01-01 | -10829.55 | PAPPU BAGELA
Granite Edge Polish (L) | N/C | N/C | PAPPU BAGELA | 1051 | 2024-07-12 | F-Entrance Gate(Security Cabin)-Tiling Work | 39.17 | 10 | 0 | 391.7 | 0 | 2024-07-24 11:31 | Labour Charges for Orissa Blue Granite Edge polish work for Entrance gate. | 100 |  | 109399 | 2024-07-29 | 11746.35 | 1900-01-01 | -11354.65 | PAPPU BAGELA