## Work_Completion_Browse638581122
Work Completion Browse
Project : GANGA ALTUS
From Date : 01/07/2024 To date: 01/07/2024
Page 1 of 1
Total Records: 1127 Records 1 to 1127
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 19th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 20th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 21st Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 22nd Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 23rd Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 24th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg LG Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg Ground Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg P1 Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg P2 Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg P3 Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg P5 Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg Stilt Fl Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 1st Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 2nd Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 3rd Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 4th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 6th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 5th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 7th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 8th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 9th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 10th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 11th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 12th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 13th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 14th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 15th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 16th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 17th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 18th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 1900-01-01 | -196370.699 | PAPPU BAGELA
Concreting Work | N/C | N/C | UPRISEN CONSTRUCTION | 1026 | 2024-06-25 | Making of Foundation for D.G Set Near F Bldg. | 23.1 | 300 | 0 | 6930 | 1247.4 | 2024-07-11 19:40 | Charges for Concreting work (M25) for making of Foundation for DG to F-Bldg | 100 |  | 109088 | 2024-07-15 | 16307.5 | 1900-01-01 | -9377.5 | UPRISEN CONSTRUCTION
Shuttering Work-Dev | N/C | N/C | UPRISEN CONSTRUCTION | 1026 | 2024-06-25 | Making of Foundation for D.G Set Near F Bldg. | 17.05 | 550 | 0 | 9377.5 | 1687.96 | 2024-07-11 19:40 | Charges for Shuttering work for making of Foundation for DG to F-Bldg | 100 |  | 109088 | 2024-07-15 | 16307.5 | 1900-01-01 | -6930 | UPRISEN CONSTRUCTION
Labour lumpsum | N/C | N/C | VEER BHADRA ENTERPRISES | 1035 | 2024-07-01 | D&E-Entrance Gate-External Texture Work | 0.6 | 48000 | 0 | 28800 | 5184 | 2024-07-27 16:31 | Labour charges for Applying Texture Paint for D & E-Bldg Entrance Gate including scaffolding fixing & removing, 1 coat water base Primer, 2 coat Acrylic Paint work. | 100 |  | 109406 | 2024-07-29 | 72000 | 1900-01-01 | -43200 | VEER BHADRA ENTERPRISES
Labour lumpsum | N/C | N/C | VEER BHADRA ENTERPRISES | 1035 | 2024-07-01 | F-Entrance Gate-External Texture Work | 0.9 | 48000 | 0 | 43200 | 7776 | 2024-07-27 16:55 | Labour charges for Applying Texture Paint for F-Bldg Entrance Gate including scaffolding fixing & removing, 1 coat water base Primer, 2 coat Acrylic Paint work. | 100 | 90% Bill | 109406 | 2024-07-29 | 72000 | 1900-01-01 | -28800 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 1036 | 2024-07-01 | D&E-Entrance Gate-External Texture Work | 1546.857 | 8 | 0 | 12374.856 | 2227.48 | 2024-07-27 16:36 | Material supply charges for Applying Texture work for D & E-Bldg Entrance Gate External Texture work. | 100 | 90% Bill | 109407 | 2024-07-29 | 33644.15 | 1900-01-01 | -21269.294 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 1036 | 2024-07-01 | F-Entrance Gate-External Texture Work | 1546.857 | 8 | 0 | 12374.856 | 2227.48 | 2024-07-27 16:57 | Material supply charges for Applying Texture Paint work for F-Bldg Entrance Gate External Texture work. | 100 | 90% Bill | 109407 | 2024-07-29 | 33644.15 | 1900-01-01 | -21269.294 | VEER BHADRA ENTERPRISES (MATERIAL)
1 Coat Primer (Water Base) (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 1036 | 2024-07-01 | F-Entrance Gate-External Texture Work | 1546.857 | 1 | 0 | 1546.857 | 278.44 | 2024-07-27 16:57 | Material supply charges for Applying 1 Coat water Base Primer work for F-Bldg Entrance Gate External Texture work. | 100 | 90% Bill | 109407 | 2024-07-29 | 33644.15 | 1900-01-01 | -32097.293 | VEER BHADRA ENTERPRISES (MATERIAL)
1st Coat Acrylic Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 1036 | 2024-07-01 | F-Entrance Gate-External Texture Work | 1546.857 | 2.25 | 0 | 3480.4282 | 626.48 | 2024-07-27 16:57 | Material supply charges for Applying 1st Coat Acrylic Paint work for F-Bldg Entrance Gate External Texture work. | 100 | 90% Bill | 109407 | 2024-07-29 | 33644.15 | 1900-01-01 | -30163.7218 | VEER BHADRA ENTERPRISES (MATERIAL)
2nd Coat Acrylic Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 1036 | 2024-07-01 | F-Entrance Gate-External Texture Work | 1546.857 | 2.5 | 0 | 3867.1425 | 696.08 | 2024-07-27 16:57 | Material supply charges for Applying 2nd Coat Acrylic Paint work for F-Bldg Entrance Gate External Texture work. | 100 | 90% Bill | 109407 | 2024-07-29 | 33644.15 | 1900-01-01 | -29777.0075 | VEER BHADRA ENTERPRISES (MATERIAL)
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1001-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1002-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1003-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1004-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1101-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1102-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1103-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1104-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1201-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1202-2BHK(Near Refuse Area) Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1203-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1204-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1301-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1302-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1303-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1304-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1401-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1402-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1403-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1404-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1501-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1502-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1503-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1504-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1601-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1602-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1603-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1604-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1701-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1702-2BHK(Near Refuse Area) Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1703-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1704-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1801-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1802-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1803-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1804-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Fabrication work Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 1043 | 2024-07-05 | Fabrication Work at Front Side Compound Wall | 71.91 | 6 | 0 | 431.46 | 0 | 2024-07-15 16:03 | Labour charges for GI Sheet Frame Removing work for D & E-Bldg Front side compound wall. | 100 |  | 109120 | 2024-07-15 | 3851.28 | 1900-01-01 | -3419.82 | SURESH RANGNATH SHITOLE
Fabrication work Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 1043 | 2024-07-05 | Fabrication Work at Front Side Compound Wall | 123.07 | 6 | 0 | 738.42 | 0 | 2024-07-15 16:03 | Labour charges for Fabrication Removing work (MS Angle- 50x50x5mm) for D & E-Bldg Front side compound wall. | 100 |  | 109120 | 2024-07-15 | 3851.28 | 1900-01-01 | -3112.86 | SURESH RANGNATH SHITOLE
Fabrication work Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 1043 | 2024-07-05 | Fabrication Work at Front Side Compound Wall | 154.8 | 6 | 0 | 928.8 | 0 | 2024-07-15 16:03 | Labour charges for Fabrication Removing work (ISMC 125) for D & E-Bldg Front side compound wall. | 100 |  | 109120 | 2024-07-15 | 3851.28 | 1900-01-01 | -2922.48 | SURESH RANGNATH SHITOLE
Fabrication work Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 1043 | 2024-07-05 | Fabrication Work at Front Side Compound Wall | 78.4 | 6 | 0 | 470.4 | 0 | 2024-07-15 16:03 | Labour charges for Fabrication Removing work (ISMC 100) for D & E-Bldg Front side compound wall. | 100 |  | 109120 | 2024-07-15 | 3851.28 | 1900-01-01 | -3380.88 | SURESH RANGNATH SHITOLE
Fabrication work Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 1043 | 2024-07-05 | Fabrication Work at Front Side Compound Wall | 155.58 | 6 | 0 | 933.48 | 0 | 2024-07-15 16:03 | Labour charges for Fabrication Removing work (MS Square pipe- 50x50mm) for D & E-Bldg Front side compound wall. | 100 |  | 109120 | 2024-07-15 | 3851.28 | 1900-01-01 | -2917.8 | SURESH RANGNATH SHITOLE
Fabrication work Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 1043 | 2024-07-05 | Fabrication Work at Front Side Compound Wall | 58.12 | 6 | 0 | 348.72 | 0 | 2024-07-15 16:03 | Labour charges for Fabrication Removing work (MS Square pipe- 40x40mm & 25x25mm ) for D & E-Bldg Front side compound wall. | 100 |  | 109120 | 2024-07-15 | 3851.28 | 1900-01-01 | -3502.56 | SURESH RANGNATH SHITOLE
Fabrication Work (L) - DEn | N/C | N/C | SURESH RANGNATH SHITOLE | 1045 | 2024-07-06 | Board Frame Fabrication Work | 1278.5 | 10 | 0 | 12785 | 0 | 2024-07-14 14:12 | Charges for Fabrication work for Frame making & fixing for fixing flex to Compound Wall at F-Building. | 100 |  | 109098 | 2024-07-15 | 12785 | 1900-01-01 | 0 | SURESH RANGNATH SHITOLE
12" RCC Pipe Laying-USL | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 391.9696 | 30 | 0 | 11759.088 | 2116.64 | 2024-07-28 18:38 | Labour charges for 12" RCC Pipe laying for HT & LT Line laying & for Construction of Chamber from Transformer Room to UGWT. | 100 |  | 109409 | 2024-07-29 | 11759.09 | 1900-01-01 | -0.002 | SAI PLUMBING WORKS
Chamber 48" x 48" (5ft Ht) - UTI | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 3 | 4000 | 0 | 12000 | 2160 | 2024-07-16 12:17 | Charges for 4ft x 4ft x 1.5m Construction of Chamber near UGWT, near Pride Transformer Room, near F-Bldg. | 100 |  | 109230 | 2024-07-22 | 22700 | 1900-01-01 | -10700 | SAI PLUMBING WORKS
Chamber 24" x 24" (3ft Ht) USL | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 3 | 2100 | 0 | 6300 | 1134 | 2024-07-16 12:20 | Charges for 2ft x 2ft x 1m Construction of Chamber for LT Line | 100 |  | 109230 | 2024-07-22 | 22700 | 1900-01-01 | -16400 | SAI PLUMBING WORKS
Chamber 36" x 18" (3ft Ht) - UDR | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 2 | 2200 | 0 | 4400 | 792 | 2024-07-16 12:23 | Charges for 1ft 6 inch x 3ft x 1m Construction of Chamber for LT Line. | 100 |  | 109230 | 2024-07-22 | 22700 | 1900-01-01 | -18300 | SAI PLUMBING WORKS
Brickwork 9" DCW | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1049 | 2024-07-09 | Front Side Compound Wall Brickwork | 189.4203 | 24 | 0 | 4546.0872 | 818.3 | 2024-07-14 14:12 | Construction of 9" Brick Work with in-situ 1:6 Cement mortar with Fly ash Brick, Cement, Sand & water etc. with Plumb & Right angle at corner, with proper joint filling & striking joints on unexposed faces, raking out joints on exposed faces etc. | 100 |  | 109099 | 2024-07-15 | 5266.09 | 1900-01-01 | -720.0028 | SHUBHAM SURENDRA BAHADUR SINGH
Brickwork Pillar | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1049 | 2024-07-09 | Front Side Compound Wall Brickwork | 12 | 60 | 0 | 720 | 129.6 | 2024-07-14 14:19 | Charges for Construction of 15" thick Brick Pillar for front Side Compound wall | 100 |  | 109099 | 2024-07-15 | 5266.09 | 1900-01-01 | -4546.09 | SHUBHAM SURENDRA BAHADUR SINGH
Subcription Fees | N/C | N/C | BHUGOL ANALYTICS PRIVATE LIMITED | 1056 | 2024-07-19 | ONLINE / DIGITAL Social / Digital Activity | 1 | 29750 | 0 | 29750 | 5355 | 2024-07-19 | CRE MATRIX - ONLINE MARKETING INTELLIGENCE REPORTR ON RENTAL BENCHMARKING : COMMERICAL OFFICE LEASES REPORT CHARGES | 100 | CRE MATRIX - ONLINE MARKETING INTELLIGENCE REPORTR ON RENTAL BENCHMARKING : COMMERICAL OFFICE LEASES REPORT CHARGES | 109169 | 2024-07-19 | 29750 | 2024-07-19 11:48 | 0 | BHUGOL ANALYTICS PRIVATE LIMITED
LEAD GENERATION - LIVE CHATS | N/C | N/C | KENYT TECHONOLOGIES PRIVATE LIMITED | 1059 | 2024-07-22 | ONLINE / DIGITAL Social / Digital Activity | 1 | 210000 | 0 | 168000 | 30240 | 2024-07-24 | CHAT SERVICES | 80 | LEAD GENERATION CHAT (UNLIMITED ) PERIOD AS ON 04TH MAY 2024 TO 03RD MAY 2025 FOR 1 YEAR | 109307 | 2024-07-24 | 210000 | 2024-07-25 13:28 | -42000 | KENYT TECHONOLOGIES PRIVATE LIMITED
LEAD GENERATION - LIVE CHATS | N/C | N/C | KENYT TECHONOLOGIES PRIVATE LIMITED | 1059 | 2024-07-22 | ONLINE / DIGITAL Social / Digital Activity | 1 | 210000 | 0 | 42000 | 7560 | 2024-07-24 | NURTURING SERVICES | 20 | LEAD GENERATION CHAT (UNLIMITED ) PERIOD AS ON 04TH MAY 2024 TO 03RD MAY 2025 FOR 1 YEAR | 109307 | 2024-07-24 | 210000 | 2024-07-25 13:28 | -168000 | KENYT TECHONOLOGIES PRIVATE LIMITED
Murum Filling-DLD | N/C | N/C | SS ENTERPRISES | 141 | 2021-02-17 | Substructure Road Murum filling work | 2083.33 | 60 | 0 | 124999.8 | 0 | 2024-07-17 | D & E Bldg Surrouding area Murrum Filling Work | 100 |  | 109231 | 2024-07-22 | 124999.8 | 1900-01-01 | 0 | SHIVAM ENTERPRISES
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2024-07-09 | Charges for Legal Consultancy for the month of JUNE-2024 | 100 |  | 108952 | 2024-07-09 | 66666 | 2024-07-09 14:35 | 0 | BHASKAR VITTAL SONPARATE
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49998 | 0 | 2024-07-09 | JUNE 2024 | 8.333 |  | 108960 | 2024-07-09 | 49998 | 2024-07-09 14:38 | 0 | MADHAVI ANJAN GHOSH
Site Expenses -SO | N/C | N/C | SACHIN ANKUSH CHAUDHARI | 189 | 2021-04-30 | Site Expenses | 12 | 15000 | 0 | 14999.4 | 0 | 2024-07-09 | JUNE 2024 | 8.333 |  | 108961 | 2024-07-09 | 14999.4 | 2024-07-09 14:38 | 0 | SACHIN ANKUSH CHAUDHARI
Int Plumbing CP & Sanitary Fittings. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 238 | 2021-06-30 | E-Bldg Internal & External Plumbing Work Shop No-17 | 1 | 1800 | 0 | 1800 | 324 | 2024-07-15 | Internal Plumbing CP & Sanitary Fitting (Wash basin Fixing & Commode Fixing) | 100 |  | 109118 | 2024-07-15 | 1800 | 1900-01-01 | 0 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rabit Shifting Work | N/C | N/C | BASSAPPA CHAVAN | 308 | 2021-12-09 | D-Bldg Rabit Shifting Work - 1 No. | 32 | 400 | 0 | 12800 | 0 | 2024-07-01 | Charges for Rabit shifting work Tractor Trips (Loading & Unloading) for D-Bldg | 100 |  | 108690 | 2024-07-01 | 12800 | 1900-01-01 | 0 | PUJARI SHANKAR SHIDLINGPPA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 2nd Fl -Int Flooring Work | 2513.394 | 18 | 0 | 45241.092 | 0 | 2024-07-24 16:23 | Labour Charges for- Vitrified flooring fixing & Floor Guard laying with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -30094.228 | PAPPU BAGELA
Schedule & Quality | No category | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 2nd Fl -Int Flooring Work | 2513.394 | 2 | 0 | 5026.788 | 0 | 2024-07-24 16:23 | Labour Charges for- Schedule & Quality of F Building vitrified flooring work. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -70308.532 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 2nd Floor Toilet Flooring Work | 57.54 | 17 | 0 | 978.18 | 0 | 2024-07-24 16:23 | Labour Charges for- Ceramic flooring (300 x 300mm) fixing & floor guard laying work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -74357.14 | PAPPU BAGELA
Schedule & Quality | No category | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 2nd Floor Toilet Flooring Work | 57.54 | 2 | 0 | 115.08 | 0 | 2024-07-24 16:23 | Charges for- Schedule & Quality of Ceramic flooring work of F Building toilets. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75220.24 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 2nd Floor Toilet Dado | 344.1 | 23 | 0 | 7914.3 | 0 | 2024-07-24 16:23 | Labour charges for Fixing of 300 x 600 mm Dado tile (Lucia DK) for F-Bldg Common Toilet,Gents Toilet,Ladies Toilet,OPD Toilet,Unisex Toilet,Pantry Toilet,Room Toilet,Doctors Toilet,etc. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -67421.02 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 3rd Floor Toilet Flooring Work | 100.69 | 21 | 0 | 2114.49 | 0 | 2024-07-24 16:29 | Labour charges for Fixing of Toilet Flooring (300 x 300) for 3rd floor Common Unisex Toilet-1 & 2. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -73220.83 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 3rd Floor Toilet Dado | 553.53 | 23 | 0 | 12731.19 | 0 | 2024-07-24 16:29 | Labour charges for Fixing of Dado (300 x 600) for 3rd floor Common Unisex Toilet-1 & 2. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -62604.13 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | Stilt Floor Stilt Floor Granite Umbra Patti | 5 | 45 | 0 | 225 | 0 | 2024-07-24 16:30 | Labour charges for Granite Cutting & Fixing work for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75110.32 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | 3rd Floor Stilt Floor Granite Umbra Patti | 5 | 45 | 0 | 225 | 0 | 2024-07-24 16:30 | Labour charges for Granite Cutting & Fixing work for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75110.32 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | Stilt Floor Stilt Floor Granite Umbra Patti | 5 | 10 | 0 | 50 | 0 | 2024-07-24 16:30 | Labour charges for Granite Edge Polish work for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75285.32 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | 3rd Floor Stilt Floor Granite Umbra Patti | 5 | 10 | 0 | 50 | 0 | 2024-07-24 16:30 | Labour charges for Granite Edge Polish work for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75285.32 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | Stilt Floor Granite Work (M) | 3 | 110.7 | 0 | 332.1 | 0 | 2024-07-24 16:30 | Material Supply charges for Granite for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75003.22 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | 3rd Floor Granite Work (M) | 3 | 110.7 | 0 | 332.1 | 0 | 2024-07-24 16:30 | Material Supply charges for Granite for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75003.22 | PAPPU BAGELA
Cleaning Work | N/C | N/C | DURGARAM CHANDURAM BHATEE | 362 | 2022-01-22 | Cleaning Work | 1 | 15000 | 0 | 15000 | 0 | 2024-07-01 | Cleaning work for Labour CampToilet Garbage Collection and Drainage Line for the month of MAY-2024 | 100 |  | 108688 | 2024-07-01 | 30000 | 2024-07-05 11:38 | -15000 | DURGARAM CHANDURAM BHATEE
Cleaning Work | N/C | N/C | DURGARAM CHANDURAM BHATEE | 362 | 2022-01-22 | Cleaning Work | 1 | 15000 | 0 | 15000 | 0 | 2024-07-01 | Cleaning work for Labour CampToilet Garbage Collection and Drainage Line for the month of JUNE-2024 | 100 |  | 108688 | 2024-07-01 | 30000 | 2024-07-05 11:38 | -15000 | DURGARAM CHANDURAM BHATEE
Safety Net Removing- SO | N/C | N/C | GREEN SAFETY SOLUTIONS | 373 | 2022-02-09 | D-Bldg Horizontal Safety net fixing & removing work | 4842 | 1.35 | 0 | 6536.7 | 0 | 2024-07-02 15:16 | Labour Charges for Horizontal Safety net removing work for D Building 14th Floor. | 100 |  | 108760 | 2024-07-02 | 6536.7 | 2024-07-26 12:24 | 0 | FAIJANA KHATUN
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-24th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-30 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-25th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-30 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHINDE PLUMBING CONTRACTOR
Site Expenses -SO | N/C | N/C | ANAND PUNDLIK JADHAV | 376 | 2022-02-12 | Site Expenses | 0.5466 | 30000 | 0 | 16398 | 0 | 2024-07-17 | Petty Cash Site Expenses & Mathadi (Loading/ Unloading) charges for JULY-2024 | 100 |  | 109239 | 2024-07-22 | 25998 | 1900-01-01 | -9600 | ANAND PUNDLIK JADHAV
Site Expenses -SO | N/C | N/C | ANAND PUNDLIK JADHAV | 376 | 2022-02-12 | Site Expenses | 0.32 | 30000 | 0 | 9600 | 0 | 2024-07-17 | Petty Cash Site Expenses & Mathadi (Loading/ Unloading) charges for JULY-2024 | 100 |  | 109239 | 2024-07-22 | 25998 | 1900-01-01 | -16398 | ANAND PUNDLIK JADHAV
Site Expenses -SO | N/C | N/C | ANAND PUNDLIK JADHAV | 376 | 2022-02-12 | Site Expenses | 0.0083 | 30000 | 0 | 249 | 0 | 2024-07-29 | Petty Cash Site Expenses & Mathadi (Loading/ Unloading) charges for JULY-2024 | 100 |  | 109438 | 2024-07-29 | 249 | 1900-01-01 | 0 | ANAND PUNDLIK JADHAV
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 0 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 0 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2103-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 0 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 0 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 0 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 0 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 0 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 0 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 0 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 0 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 0 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2103-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2103-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 0 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 0 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2103-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 0 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUPALI DEEPAK LOKHANDE
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 0 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 0 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 0 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 0 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 0 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 0 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 0 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 0 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2103-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2103-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RUSHIYOGI ENTERPRISES
Testing & Certification Charges | N/C | N/C | ANAND PUNDLIK JADHAV | 391 | 2022-03-04 | Testing & certification of const. material & Structural test | 0.2653 | 100000 | 0 | 2653 | 477.54 | 2024-07-26 | Testing and Certification of Construction Material and Structural Test. | 10 | invoice no- CPL242501209 for concrete cube & beam third party testing | 109404 | 2024-07-29 | 2653 | 1900-01-01 | 0 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2306 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5881.92 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2307 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5920.68 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2308 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5920.68 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2401 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5881.92 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2403 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5920.68 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2406 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5881.92 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2407 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5920.68 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2408 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5920.68 | AJAY KUMAR GUPTA
Paving Block Fixing - AIE | N/C | N/C | PAPPU BAGELA | 439 | 2022-06-04 | D,E,F Bldg.Main Road-Paver Block Fixing | 659.5105 | 13 | 0 | 8573.6365 | 0 | 2024-07-15 12:19 | Labour Charges for Fixing of Paving Block with heavy duty inter locking concrete to internal road D,E,F Building and Main road with proper line,level,Approved Quality,Shap,thickness on a bed of Crushed sand including striking joints and cleaning etc. | 100 |  | 109100 | 2024-07-15 | 8573.64 | 1900-01-01 | -0.0035 | PAPPU BAGELA
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1201-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1202-2BHK(Near Refuse Area) Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1203-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1205-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1206-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1207-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1208-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1301-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1303-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1305-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1402-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1403-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1701-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1702-2BHK(Near Refuse Area) Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1703-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1704-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1706-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1801-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1802-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1803-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1805-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1806-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1807-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1808-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1901-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1903-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1905-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1906-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1907-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1908-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2001-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2002-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2004-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2005-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2006-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2007-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2008-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2101-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2103-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2104-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2105-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2106-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2107-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2108-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2201-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2202-2BHK(Near Refuse Area) Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2203-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2204-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2205-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2206-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2207-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2208-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2301-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2302-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2303-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2304-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2305-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2306-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2307-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2308-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1101-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1107-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1108-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1201-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1202-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1203-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1205-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1206-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1207-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1208-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1301-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1303-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1305-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1402-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:38 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1403-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:38 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1701-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1702-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1704-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1706-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1801-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1802-3BHK Toilet False ceiling work | 22.668 | 60 | 0 | 1360.08 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1803-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1805-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1806-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1807-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1808-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1901-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1903-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1905-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1906-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1907-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1908-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2001-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2002-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2004-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2005-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2006-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2007-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2008-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2101-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2103-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2104-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2105-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2106-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2107-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2108-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2201-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2202-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2203-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2204-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2205-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2206-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2207-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2208-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1305-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1306-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1706-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1801-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1803-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1805-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1806-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1807-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1808-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1901-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1903-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1905-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1906-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1907-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1908-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2001-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2002-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2004-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2005-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2006-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2007-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2008-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2101-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2102-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2103-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2104-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2105-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2106-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2107-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2108-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2201-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2202-2BHK(Near Refuse Area) Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2203-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2204-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2206-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2207-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2208-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2301-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2302-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2303-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2304-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2305-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2306-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2307-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2308-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1305-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:41 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1706-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1801-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1803-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1805-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1807-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1808-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1901-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1903-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1905-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1906-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1907-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1908-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2001-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2002-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2004-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2005-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2006-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2007-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2008-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2101-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2103-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2104-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2105-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2106-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2107-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2108-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2201-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2202-2BHK(Near Refuse Area) Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2203-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2204-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2206-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2207-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2208-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2301-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2302-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2303-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2304-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2305-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2306-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2307-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2308-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 0 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 22nd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-29 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 109437 | 2024-07-29 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 23rd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-29 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 109437 | 2024-07-29 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 24th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-29 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 109437 | 2024-07-29 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495892.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495892.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1305-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495892.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1306-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495892.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495892.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495625.152 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495625.152 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495625.152 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495625.152 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495625.152 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495978.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495978.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2105-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2206-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2307-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2308-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497753.384 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497753.384 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1305-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497753.384 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1306-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497753.384 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497753.384 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497714.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497714.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497714.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497714.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497714.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497799.008 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497799.008 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 70.85 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497767.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 70.85 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497767.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2105-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 70.85 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497767.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2108-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 70.85 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497767.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 70.85 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497767.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496745.056 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496745.056 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1305-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496745.056 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1306-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496745.056 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1307-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.59 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496685.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1308-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.59 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496685.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496745.056 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496621.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496621.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496621.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496621.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496557.32 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496557.32 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2105-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2108-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2206-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2307-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1305-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1306-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1307-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1308-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2105-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2108-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2206-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2307-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 1031.55 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -492430.256 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 1031.55 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -492430.256 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1307-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -492516.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1308-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -492516.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 1031.55 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -492430.256 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491931.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491931.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491931.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491931.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491931.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -492025.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -492025.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2108-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2206-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2307-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -487449.76 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -487449.76 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -487449.76 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 2120.85 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -486378.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 2120.85 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -486378.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 1614.29 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -489192.864 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 1614.29 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -489192.864 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 2120.85 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -486378.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 2120.85 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -486378.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494505.776 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494505.776 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1305-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494505.776 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1306-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494505.776 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494505.776 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494173.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494173.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494173.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1807-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495235.04 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1808-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495235.04 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494173.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494173.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495235.04 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -495235.04 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 570.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494991.2 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 570.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494991.2 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2105-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 570.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494991.2 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 570.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494991.2 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 570.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -494991.2 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 1900-01-01 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2103-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2104-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2107-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2108-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2203-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2204-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2207-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2208-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2303-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2304-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2307-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2308-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2403-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2404-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2407-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2408-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2202-2BHK(Near Refuse Area) FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2101-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2102-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2105-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2106-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2201-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2205-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2206-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2301-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2302-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2305-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2306-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2401-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2402-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2405-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2406-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Brickbat W/P | N/C | N/C | AJAY KUMAR GUPTA | 498 | 2022-07-29 | D-Bldg Terrace Floor Waterproofing Work (L) | 1692.935 | 24 | 0 | 40630.44 | 0 | 2024-07-08 | Labour Charges for Brickbat waterproofing work for Terrace floor P-Line North, P-line South & P-line East west D-Building. | 100 |  | 108932 | 2024-07-08 | 40630.44 | 1900-01-01 | 0 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 2nd Floor Refuge Area Waterproofing Work | 212.696 | 22 | 0 | 4679.312 | 0 | 2024-07-23 | Labour and Material Supply Charges for Chemical waterproofing work at refuge area | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -10634.788 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 7th Floor Refuge Area Waterproofing Work | 212.696 | 22 | 0 | 4679.312 | 0 | 2024-07-23 | Labour and Material Supply Charges for Chemical waterproofing work at refuge area | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -10634.788 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 12th Floor Refuge Area Waterproofing Work | 212.696 | 22 | 0 | 4679.312 | 0 | 2024-07-23 | Labour and Material Supply Charges for Chemical waterproofing work at refuge area | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -10634.788 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 2nd Floor Refuge Area Waterproofing Work | 212.696 | 2 | 0 | 425.392 | 0 | 2024-07-23 | Labour Charges for- Ghadai work including all tools & equipments required to prepare plane floor surface, including, cleaning, shifting debris at one place. | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -14888.708 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 7th Floor Refuge Area Waterproofing Work | 212.696 | 2 | 0 | 425.392 | 0 | 2024-07-23 | Labour Charges for- Ghadai work including all tools & equipments required to prepare plane floor surface, including, cleaning, shifting debris at one place. | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -14888.708 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 12th Floor Refuge Area Waterproofing Work | 212.696 | 2 | 0 | 425.392 | 0 | 2024-07-23 | Labour Charges for- Ghadai work including all tools & equipments required to prepare plane floor surface, including, cleaning, shifting debris at one place. | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -14888.708 | AJAY KUMAR GUPTA
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 522 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4313559.322 | 0 | 1941101.6949 | 349398.3 | 2024-07-08 | After Material Receipt at site | 45 | 08/07/2024 Received | 109105 | 2024-07-15 | 1941101.69 | 1900-01-01 | 0.0049 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 523 | 2022-08-29 | Supply & Installation of Lifts - E Bldg. | 1 | 4313559.322 | 0 | 1078389.8305 | 194110.16 | 2024-07-17 | Material Intimation | 25 | Invoice No-8150296742 DT 09.07.2024 Item- L-C1,PWU15/25-19 31STOPS | 109285 | 2024-07-23 | 1078389.83 | 1900-01-01 | 0.0005 | Kone Elevator (I) Pvt. Ltd
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg LG Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -79977.65 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg Ground Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -79977.65 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P1 Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -79977.65 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P2 Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -79977.65 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P3 Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -79977.65 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P5 Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -79977.65 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg Stilt Fl Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 1st Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 2nd Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 3rd Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 4th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 5th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 6th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 7th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 8th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 9th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 10th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 11th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 12th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 13th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 14th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 15th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 16th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 17th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 18th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 19th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 20th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 21st Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 22nd Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 23rd Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 24th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -81334.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg LG Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg Ground Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P1 Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P2 Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P3 Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P5 Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg Stilt Fl Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 1st Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 2nd Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 3rd Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 4th Fl-Lobby Lift Cladding Work | 41.46 | 10 | 0 | 414.6 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82815.2 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 5th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 6th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 7th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 8th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 9th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 10th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 11th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 12th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 13th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 14th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 15th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 16th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 17th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 18th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 19th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 20th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 21st Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 22nd Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 23rd Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 24th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 1900-01-01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Common area Window Sill | 16 | 45 | 0 | 720 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38905 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Stilt Floor Common area Window Sill | 34 | 45 | 0 | 1530 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38095 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Common area Window Sill | 31 | 45 | 0 | 1395 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38230 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Common area Window Sill | 31 | 45 | 0 | 1395 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38230 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Common area Window Sill | 31 | 45 | 0 | 1395 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38230 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Common area Window Sill | 16 | 10 | 0 | 160 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39465 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Stilt Floor Common area Window Sill | 34 | 10 | 0 | 340 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39285 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Common area Window Sill | 31 | 10 | 0 | 310 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39315 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Common area Window Sill | 31 | 10 | 0 | 310 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39315 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Common area Window Sill | 31 | 10 | 0 | 310 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39315 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Toilet Door Frame | 68 | 45 | 0 | 3060 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -36565 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Toilet Door Frame | 136 | 45 | 0 | 6120 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -33505 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Toilet Door Frame | 136 | 45 | 0 | 6120 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -33505 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Toilet Door Frame | 102 | 10 | 0 | 1020 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38605 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Toilet Door Frame | 204 | 10 | 0 | 2040 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -37585 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Toilet Door Frame | 204 | 10 | 0 | 2040 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -37585 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Ledge Wall Top (Common Toilet) | 2 | 45 | 0 | 90 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39535 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Ledge Wall Top (Common Toilet) | 4 | 45 | 0 | 180 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39445 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Ledge Wall Top (Common Toilet) | 4 | 45 | 0 | 180 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39445 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Ledge Wall Top (Common Toilet) | 2 | 10 | 0 | 20 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39605 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Ledge Wall Top (Common Toilet) | 4 | 10 | 0 | 40 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39585 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Ledge Wall Top (Common Toilet) | 4 | 10 | 0 | 40 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39585 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Umbra Patti | 19 | 45 | 0 | 855 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38770 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Stilt Floor Umbra Patti | 14 | 45 | 0 | 630 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38995 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Umbra Patti | 28 | 45 | 0 | 1260 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38365 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Umbra Patti | 28 | 45 | 0 | 1260 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38365 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Umbra Patti | 28 | 45 | 0 | 1260 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38365 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Terrace Floor Umbra Patti | 7 | 45 | 0 | 315 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39310 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Umbra Patti | 37 | 10 | 0 | 370 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39255 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Stilt Floor Umbra Patti | 23 | 10 | 0 | 230 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39395 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Umbra Patti | 64 | 10 | 0 | 640 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38985 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Umbra Patti | 64 | 10 | 0 | 640 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38985 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Umbra Patti | 64 | 10 | 0 | 640 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38985 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Terrace Floor Umbra Patti | 7 | 10 | 0 | 70 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39555 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Toilet Ventilator (Common Toilet) | 10 | 45 | 0 | 450 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39175 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Toilet Ventilator (Common Toilet) | 19 | 45 | 0 | 855 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38770 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Toilet Ventilator (Common Toilet) | 19 | 45 | 0 | 855 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38770 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Toilet Ventilator (Common Toilet) | 10 | 10 | 0 | 100 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39525 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Toilet Ventilator (Common Toilet) | 19 | 10 | 0 | 190 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39435 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Toilet Ventilator (Common Toilet) | 19 | 10 | 0 | 190 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39435 | PAPPU BAGELA
Brickbat W/P | N/C | N/C | AJAY KUMAR GUPTA | 538 | 2022-09-16 | F-Bldg 3rd Floor Toilet Waterproofing Work | 102.9 | 18 | 0 | 1852.2 | 0 | 2024-07-12 16:01 | Labour charges for Brickbat Waterproofing work for 3rd Floor Toilet area F-Bldg | 100 |  | 109090 | 2024-07-15 | 4116 | 1900-01-01 | -2263.8 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 538 | 2022-09-16 | F-Bldg 3rd Floor Toilet Waterproofing Work | 102.9 | 22 | 0 | 2263.8 | 0 | 2024-07-12 16:01 | Labour and Material Charges for Chemical Waterproofing work for 3rd Floor Toilet Waterproofing work. | 100 |  | 109090 | 2024-07-15 | 4116 | 1900-01-01 | -1852.2 | PRABHURAM VERMA
Departmental Labour - SO | N/C | N/C | KANU KALIPADA BALA | 548 | 2022-10-01 | Demolition of Old Structure & Material shifting work | 20 | 500 | 0 | 10000 | 0 | 2024-07-17 | Departmental labour charges for- Transformer room structure demolition sheet removing work. | 100 |  | 109237 | 2024-07-22 | 22500 | 1900-01-01 | -12500 | PRAKASH SAHU
Departmental Labour - SO | N/C | N/C | KANU KALIPADA BALA | 548 | 2022-10-01 | Demolition of Old Structure & Material shifting work | 25 | 500 | 0 | 12500 | 0 | 2024-07-17 | Departmental labour charges for-Demolition old structure material Shifting work in four stock rooms. | 100 |  | 109237 | 2024-07-22 | 22500 | 1900-01-01 | -10000 | PRAKASH SAHU
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 8000 | 0 | 8000 | 0 | 2024-07-01 | Labour Charges for Housekeeping work (Female Coolie-1) for the month of MAY-2024 | 100 |  | 108689 | 2024-07-01 | 16000 | 2024-07-05 11:38 | -8000 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 8000 | 0 | 8000 | 0 | 2024-07-01 | Labour Charges for Housekeeping work (Female Coolie-1) for the month of JUNE-2024 | 100 |  | 108689 | 2024-07-01 | 16000 | 2024-07-05 11:38 | -8000 | DURGARAM CHANDURAM BHATEE
Hydrant Valve 63mm (M). | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 8 | 18500 | 0 | 103600 | 18648 | 2024-07-07 | Against Material Supply | 70 | Challan No-18537 DT 03.07.2024 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -763190.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Orifice Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 8 | 1100 | 0 | 6160 | 1108.8 | 2024-07-15 | Against Material Supply | 70 | Challan No-18537 DT 03.07.2024 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -860630.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Bucket (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Extinguishers - 1 No. | 4 | 3000 | 0 | 8400 | 1512 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -858390.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Bucket Stand (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Extinguishers - 1 No. | 1 | 639 | 0 | 447.3 | 80.52 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -866343.1 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Strainer "Y" (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Pump Room Equipment | 1 | 7263 | 0 | 5084.1 | 915.14 | 2024-07-07 | Against Material Supply | 70 | Challan No-18493 DT 12.06.2024 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -861706.3 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Double Hydrant Valve (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Internal Hydrant System | 25 | 33000 | 0 | 577500 | 103950 | 2024-07-07 | Against Material Supply | 70 | Challan No-18537 DT03.07.24 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -289290.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Orifice Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Internal Hydrant System | 25 | 1400 | 0 | 24500 | 4410 | 2024-07-07 | Against Material Supply | 70 | Challan No-18537 DT-03.07.2024 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -842290.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 350 | 0 | 14700 | 2646 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -239470 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Vane Type Water Flow (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 25 | 7500 | 0 | 131250 | 23625 | 2024-07-07 | Against Material Supply | 70 | Challan No-18598 DT 27.06.2024 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -735540.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher ABC 6Kg (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Extinguisher & Signages | 18 | 2010 | 0 | 25326 | 4558.68 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT-27/06/2024 | 108665 | 2024-07-01 | 30366 | 2024-07-15 15:03 | -5040 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher ABC 6Kg (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Extinguisher & Signages | 7 | 2010 | 0 | 9849 | 1772.82 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -856941.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 500 | 380 | 0 | 133000 | 23940 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -121170 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 338 | 450 | 0 | 106470 | 19164.6 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -147700 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 22964.5161 | 0.31 | 0 | 7119 | 1281.42 | 2024-07-04 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 108793 | 2024-07-04 | 25119 | 2024-07-15 15:06 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2024-07-04 | Photocopy Machine Rental Charges for Month of JUNE-2024 | 100 |  | 108793 | 2024-07-04 | 25119 | 2024-07-15 15:06 | -7119 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
SITC GI Pipe C Class 250mm dia-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 10 | 4400 | 0 | 30800 | 5544 | 2024-07-07 | Against Material Supply | 70 | Challan No-18542 DT-03.07.2024 Received - 12 mtrs. (2 Mtrs Balance) | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -385980 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Foot Valve 150 mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 17500 | 0 | 12250 | 2205 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT04.07.24 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -404530 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 6500 | 0 | 13650 | 2457 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -403130 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 150mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 10000 | 0 | 21000 | 3780 | 2024-07-14 | Against Material Supply | 70 | Challan No-18548 DT 4/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -395780 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 150mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 10000 | 0 | 21000 | 3780 | 2024-07-16 | Against Material Supply | 70 | Challan No-18548 DT 04.07.2024 | 109155 | 2024-07-18 | 35770 | 1900-01-01 | -14770 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 200mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 16500 | 0 | 23100 | 4158 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -393680 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 14 | 12000 | 0 | 117600 | 21168 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 4/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -299180 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 200mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 25500 | 0 | 35700 | 6426 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 4/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -381080 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
CI Strainer 150 mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 8900 | 0 | 18690 | 3364.2 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -398090 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Strainer "Y" (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 5900 | 0 | 8260 | 1486.8 | 2024-07-10 | Against Material Supply | 70 | Challan No-18546 DT 04.07.24 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -408520 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
C.I.Basket Strainer 200mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 29200 | 0 | 40880 | 7358.4 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -375900 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pressure Switch (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 10 | 2350 | 0 | 16450 | 2961 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT03.07.24 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -400330 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pressure Guage 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 3200 | 0 | 13440 | 2419.2 | 2024-07-15 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -403340 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pressure Guage 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 8 | 3200 | 0 | 17920 | 3225.6 | 2024-07-29 | Against Material Supply | 70 | Challan No-18613 DT 18/07/2024 | 109433 | 2024-07-29 | 20300 | 1900-01-01 | -2380 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC Air Vessel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 27000 | 0 | 37800 | 6804 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT03.07.24 (2 balance =Received -4 Nos.) | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -378980 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
4 Way 63mm,Fire Service inlet (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 7200 | 0 | 10080 | 1814.4 | 2024-07-16 | Against Material Supply | 70 | Challan No-18537 DT 03.07.2024 | 109155 | 2024-07-18 | 35770 | 1900-01-01 | -25690 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 6700 | 0 | 4690 | 844.2 | 2024-07-16 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109155 | 2024-07-18 | 35770 | 1900-01-01 | -31080 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Bucket (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 4 | 1000 | 0 | 2800 | 504 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT 27/06/2024 | 108670 | 2024-07-01 | 95900 | 2024-07-15 15:03 | -93100 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Bucket Stand (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 2500 | 0 | 1750 | 315 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT 27/06/2024 | 108670 | 2024-07-01 | 95900 | 2024-07-15 15:03 | -94150 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler Alarm Valve 150mm dia (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 43500 | 0 | 91350 | 16443 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT-27/06/2024 | 108670 | 2024-07-01 | 95900 | 2024-07-15 15:03 | -4550 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 200mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 3400 | 0 | 2380 | 428.4 | 2024-07-29 | Against Material Supply | 70 | Total Challan Qty-30 Mtrs. RA Bill Released Qty-29 Mtrs(RA-108232 Challan No-18352 (Amendment Qty 1 Mtrs released from this Completion) | 109433 | 2024-07-29 | 20300 | 1900-01-01 | -17920 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI Pipe C Class 250mm dia-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 4400 | 0 | 6160 | 1108.8 | 2024-07-15 | Against Material Supply | 70 | Challan No-18542 DT 03.07.2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -410620 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 4 | 7500 | 0 | 21000 | 3780 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -395780 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 115.913 | 290 | 0 | 33614.77 | 6050.66 | 2024-07-13 18:54 | Labour charges for RCC Work for Super-structure including columns above plinth beam, Beams and slabs for Transformer Room. | 100 |  | 109094 | 2024-07-15 | 33614.77 | 2024-07-26 12:27 | 0 | ROHIT CONSTRUCTION
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | 40kva DG servicing kit | 12 | 736 | 0 | 735.9706 | 132.48 | 2024-07-10 | JUL-2024 | 8.333 | Report No-000680 DT 09.07.2024 | 109102 | 2024-07-15 | 735.97 | 1900-01-01 | 0.00056 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | 82.5 kva DG servicing kit | 12 | 897 | 0 | 896.6412 | 161.4 | 2024-07-10 | JUL-2024 | 8.33 | Report no-000682 DT 09.07.2024 | 109103 | 2024-07-15 | 896.64 | 1900-01-01 | 0.0012 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | 125kva DG servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-07-10 | JUL-2024 | 8.33 | Report No-000679 DT 09.07.2024 | 109101 | 2024-07-15 | 919.63 | 1900-01-01 | 0.002 | MEGAPOWER SOLUTION PVT LTD
Touchproof Jointing Kit (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 1 | 2750 | 0 | 2750 | 495 | 2024-07-29 17:10 | Labour charges for Fixing of 300 sqmm Touchproof jointing kit. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -97130 | ADITI POWER CARE AND ENTERPRISES
95 sqmm Touchproof Jointing Kit (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 1 | 2750 | 0 | 2750 | 495 | 2024-07-03 15:02 | Labour charges for fixing of 95 sqmm Touchproof Jointing Kit. | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -40297.73 | ADITI POWER CARE AND ENTERPRISES
300 sqmm Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 190 | 154 | 0 | 29260 | 5266.8 | 2024-07-03 14:58 | Labour charges for 3C x 300 sqmm Cable Laying work. | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -13787.73 | ADITI POWER CARE AND ENTERPRISES
300 sqmm Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 115 | 154 | 0 | 17710 | 3187.8 | 2024-07-29 17:10 | Labour charges for 3C x 300 sqmm Cable Laying work. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -82170 | ADITI POWER CARE AND ENTERPRISES
300sqmm x 3.5C Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 340 | 99 | 0 | 33660 | 6058.8 | 2024-07-29 17:10 | Labour Charges for 300 sqmm x 3.5C Cable Laying work. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -66220 | ADITI POWER CARE AND ENTERPRISES
LT Earthing Set (m+l) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 7 | 4400 | 0 | 30800 | 5544 | 2024-07-29 17:10 | Supply and Labour Charges for fixing of LT Earthing set including Funnel, GI Patti, Salt, Coal,etc | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -69080 | ADITI POWER CARE AND ENTERPRISES
Excavation & Filling. | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 6 | 176 | 0 | 1056 | 190.08 | 2024-07-03 15:07 | Labour charges for 3 feet Excavation and Filling work (Backside Old Cable removing work) | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -41991.73 | ADITI POWER CARE AND ENTERPRISES
95 sqmm Indoor Jointing Kit (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 0.361 | 6930 | 0 | 2501.73 | 450.32 | 2024-07-03 15:10 | Providing and Fixing of 95 sqmm indoor jointing kit (M+L). | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -40546 | ADITI POWER CARE AND ENTERPRISES
End Termination 300sqmm X 3.5 core cable (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 4 | 1870 | 0 | 7480 | 1346.4 | 2024-07-03 15:02 | Providing and fixing of 300 Sqmm x 3.5 C end termination. | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -35567.73 | ADITI POWER CARE AND ENTERPRISES
End Termination 300sqmm X 3.5 core cable (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 8 | 1870 | 0 | 14960 | 2692.8 | 2024-07-29 17:10 | Providing and fixing of 300 Sqmm x 3.5 C end termination. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -84920 | ADITI POWER CARE AND ENTERPRISES
Murum filling Labour BC | N/C | N/C | PRAKASH SAHU | 649 | 2023-04-03 | F Building Lift Pit Murum Filling work - 1 No. | 572.68 | 3.5 | 0 | 2004.38 | 0 | 2024-07-17 | Charges for Murum Filling work for F Building lift pit area. | 100 |  | 109235 | 2024-07-22 | 2004.38 | 1900-01-01 | 0 | PRAKASH SAHU
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Fire Staircase-01 Flooring Work | 20 | 85 | 0 | 1700 | 306 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90893.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 5th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 17.25 | 85 | 0 | 1466.25 | 263.92 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -91127.65 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 1.19 | 85 | 0 | 101.15 | 18.2 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -92492.75 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 24th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bdlg 5th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 24th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -39644.8 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -39644.8 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -39644.8 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -40512 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -40512 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -40825.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -40825.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 22nd Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -39731.2 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -39731.2 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -39731.2 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -40825.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -40825.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -40508.8 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 1900-01-01 | -40508.8 | PAPPU BAGELA
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 1st Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 2nd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 3rd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 4th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 5th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 6th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 7th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 8th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 9th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 10th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 11th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 12th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 13th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 14th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 15th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 16th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 17th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 18th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 19th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 20th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 21st Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 22nd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 23rd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 24th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg Stilt Fl Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork and Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 1900-01-01 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3419.66 | 10 | 0 | 34196.6 | 6155.38 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -86753.4 | AVCON TECHNICS PVT LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3419.66 | 10 | 0 | 34196.6 | 6155.38 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -86753.4 | AVCON TECHNICS PVT LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3419.66 | 10 | 0 | 34196.6 | 6155.38 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -86753.4 | AVCON TECHNICS PVT LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 15646.66 | 10 | 0 | 156466.6 | 28163.98 | 2024-07-20 18:32 | Schedule for RCC Work | 100 |  | 109264 | 2024-07-22 | 203575.4 | 1900-01-01 | -47108.8 | RITU ENTERPRISES
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 4710.88 | 10 | 0 | 47108.8 | 8479.58 | 2024-07-20 18:32 | Schedule for RCC Work | 100 |  | 109264 | 2024-07-22 | 203575.4 | 1900-01-01 | -156466.6 | RITU ENTERPRISES
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1836.02 | 10 | 0 | 18360.2 | 3304.84 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -102589.8 | AVCON TECHNICS PVT LTD
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | D-Bldg 2nd Floor Refuge Area Waterproofing Work | 211.144 | 24 | 0 | 5067.456 | 0 | 2024-07-23 | Labour Charges for Refuge Area Brickbat Waterproofing work. | 100 |  | 109386 | 2024-07-29 | 16705.53 | 1900-01-01 | -11638.074 | AJAY KUMAR GUPTA
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | D-Bldg 7th Floor Refuge Area Waterproofing Work | 211.144 | 24 | 0 | 5067.456 | 0 | 2024-07-23 | Labour Charges for Refuge Area Brickbat Waterproofing work. | 100 |  | 109386 | 2024-07-29 | 16705.53 | 1900-01-01 | -11638.074 | AJAY KUMAR GUPTA
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | D-Bldg 12th Floor Refuge Area Waterproofing Work | 211.144 | 24 | 0 | 5067.456 | 0 | 2024-07-23 | Labour Charges for Refuge Area Brickbat Waterproofing work. | 100 |  | 109386 | 2024-07-29 | 16705.53 | 1900-01-01 | -11638.074 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | D-Lift No.-1,2,3-IPS Waterproofing in pits | 100.21 | 15 | 0 | 1503.15 | 0 | 2024-07-24 | Labour Charges for IPS Waterproofing work for D-Bldg Lift Pit No- 1, 2, 3. | 100 |  | 109386 | 2024-07-29 | 16705.53 | 1900-01-01 | -15202.38 | AJAY KUMAR GUPTA
Int Plumbing CP & Sanitary Fittings. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 685 | 2023-05-30 | LG Fl- Int. Plumbing Work (L) | 1 | 1440 | 0 | 1440 | 259.2 | 2024-07-15 | Labour Charges for internal plumbing CP & Sanitary fittings work of F Building | 100 |  | 109117 | 2024-07-15 | 18720 | 1900-01-01 | -17280 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing CP & Sanitary Fittings. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 685 | 2023-05-30 | 1st Fl- Int. Plumbing Work (L) | 12 | 1440 | 0 | 17280 | 3110.4 | 2024-07-15 | Labour Charges for internal plumbing CP & Sanitary fittings work of F Building | 100 |  | 109117 | 2024-07-15 | 18720 | 1900-01-01 | -1440 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Fire Repeater Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 45000 | 0 | 31500 | 5670 | 2024-07-29 | Against Material Supply | 70 | Challan No-18179 DT 27/7/2024 | 109419 | 2024-07-29 | 40950 | 1900-01-01 | -9450 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 1034 | 0 | 28952 | 5211.36 | 2024-07-01 | Against Material Supply | 70 | challan No-18491 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -43610 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 380 | 0 | 10640 | 1915.2 | 2024-07-01 | Against Material Supply | 70 | Challan No-18491DT-25/06/2024 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -61922 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Upright (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 30 | 450 | 0 | 9450 | 1701 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/07/2024 Total Received-400 -We have released 338 Nos from D Building Remaining Qty released from F Building (Balance for amendment 32 Nos) | 109419 | 2024-07-29 | 40950 | 1900-01-01 | -31500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 90 | 0 | 2520 | 453.6 | 2024-07-01 | Against Material Supply | 70 | Challan No-18491 DT-25/06/2024 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -70042 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 6 | 3600 | 0 | 15120 | 2721.6 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 4/07/2024 Against D Building Pump Room | 109135 | 2024-07-16 | 17360 | 1900-01-01 | -2240 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3200 | 0 | 2240 | 403.2 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 Against D Building | 109135 | 2024-07-16 | 17360 | 1900-01-01 | -15120 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler Alarm Valve 150mm dia (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 43500 | 0 | 30450 | 5481 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT-27/06/2024 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -42112 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Lift Pit- Brickbat W/P Work | 30.506 | 18 | 0 | 549.108 | 0 | 2024-07-12 16:08 | Labour charges for Brickbat waterproofing work for F-Bldg Lift Pit (Base) 01 & 02. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4581.582 | PRABHURAM VERMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Lift Pit- Chemical W/P Work | 116.252 | 22 | 0 | 2557.544 | 0 | 2024-07-12 16:08 | Material and Labour charges for Chemical Waterproofing work for F-Bldg Lift Walls. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -2573.146 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Stilt Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Labour charges for Chemical Grouting Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg 3rd Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Labour charges for Chemical Grouting Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Stilt Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Material supply charges for Chemical Grouting Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg 3rd Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Material supply charges for Chemical Grouting Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Stilt Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Labour charges for Ghadai Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg 3rd Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Labour charges for Ghadai Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2101-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2102-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2105-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2106-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2201-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2205-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2206-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2301-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2302-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2305-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2306-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2401-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2402-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2405-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2406-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2103-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2104-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2107-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2108-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2203-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2204-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2207-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2208-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2303-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2304-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2307-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2308-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2403-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2404-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2407-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2408-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2202-2BHK(Near Refuse Area) Flat Electrical Work | 1 | 12683 | 0 | 4439.05 | 799.02 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Katch work (internal corner). | N/C | N/C | A K INTERIOR CONTRACTOR | 740 | 2023-07-31 | E-802-3BHK Int. Flat Kach Work | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-14 | Labour Charges for All Dhar Core, Katch,Butt finish,Door Jambs,Window jambs,Horizontal & Vertical Katch & all Gypsum work within flat (Except Punning/Plaster) | 100 |  | 109095 | 2024-07-15 | 72000 | 1900-01-01 | -59000 | G M ENTERPRISES
Katch work (internal corner). | N/C | N/C | A K INTERIOR CONTRACTOR | 740 | 2023-07-31 | E-901-3BHK Int. Flat Kach Work | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-14 | Labour Charges for All Dhar Core, Katch,Butt finish,Door Jambs,Window jambs,Horizontal & Vertical Katch & all Gypsum work within flat (Except Punning/Plaster) | 100 |  | 109095 | 2024-07-15 | 72000 | 1900-01-01 | -59000 | G M ENTERPRISES
Katch work (internal corner). | N/C | N/C | A K INTERIOR CONTRACTOR | 740 | 2023-07-31 | E-902-3BHK Int. Flat Kach Work | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-14 | Labour Charges for All Dhar Core, Katch,Butt finish,Door Jambs,Window jambs,Horizontal & Vertical Katch & all Gypsum work within flat (Except Punning/Plaster) | 100 |  | 109095 | 2024-07-15 | 72000 | 1900-01-01 | -59000 | G M ENTERPRISES
Katch work (internal corner). | N/C | N/C | A K INTERIOR CONTRACTOR | 740 | 2023-07-31 | E-803-2BHK Int. Flat Kach Work | 1 | 11000 | 0 | 11000 | 1980 | 2024-07-14 | Labour Charges for All Dhar Core, Katch,Butt finish,Door Jambs,Window jambs,Horizontal & Vertical Katch & all Gypsum work within flat (Except Punning/Plaster) | 100 |  | 109095 | 2024-07-15 | 72000 | 1900-01-01 | -61000 | G M ENTERPRISES
Katch work (internal corner). | N/C | N/C | A K INTERIOR CONTRACTOR | 740 | 2023-07-31 | E-804-2BHK Int. Flat Kach Work | 1 | 11000 | 0 | 11000 | 1980 | 2024-07-14 | Labour Charges for All Dhar Core, Katch,Butt finish,Door Jambs,Window jambs,Horizontal & Vertical Katch & all Gypsum work within flat (Except Punning/Plaster) | 100 |  | 109095 | 2024-07-15 | 72000 | 1900-01-01 | -61000 | G M ENTERPRISES
Katch work (internal corner). | N/C | N/C | A K INTERIOR CONTRACTOR | 740 | 2023-07-31 | E-903-2BHK Int. Flat Kach Work | 1 | 11000 | 0 | 11000 | 1980 | 2024-07-14 | Labour Charges for All Dhar Core, Katch,Butt finish,Door Jambs,Window jambs,Horizontal & Vertical Katch & all Gypsum work within flat (Except Punning/Plaster) | 100 |  | 109095 | 2024-07-15 | 72000 | 1900-01-01 | -61000 | G M ENTERPRISES
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-07-09 | Professional Fees for the Month of JUNE-2024 | 100 |  | 108953 | 2024-07-09 | 100000 | 2024-07-09 14:36 | 0 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-07-09 | Professional Fees for the Month of JUNE-2024 | 100 |  | 108954 | 2024-07-09 | 100000 | 2024-07-09 14:36 | 0 | KRITESH ATUL GOEL
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 770 | 2023-09-08 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 67.45 | 140 | 0 | 9443 | 0 | 2024-07-02 15:21 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc. | 100 | Debit for Safety net Removing | 108761 | 2024-07-02 | 9443 | 1900-01-01 | 0 | FAIJANA KHATUN
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 770 | 2023-09-08 | E-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1081.9951 | 155 | 0 | 167709.2405 | 29053.66 | 2024-07-23 09:01 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc. | 100 |  | 109315 | 2024-07-26 | 167709.24 | 1900-01-01 | 0.0005 | RITU ENTERPRISES
Lift AMC | N/C | N/C | SPARTAN ENGINEERING INDUSTRIES PVT LTD | 785 | 2023-09-30 | Spartan Material lift- Annual Maintenance Work | 6 | 8000 | 0 | 48000 | 8640 | 2024-07-01 | Charges for Annual maintenance of Passanger/Material lift.(Oct-2023 to Sep 2024).12 Call in year by default cheaking whithin non compressive AMC for one lift overall cheacking.All Ocurance calls & Breakdownalso attending as per sitre condition. | 100 | Report No-1618 DT 31/10/23 Report No-20207 DT 25/12/23 Report No-1800 DT 10/02/24 Report No-6310 DT 26/03/24 Report No-6016 DT 12/04/24 Report No-1924 DT 13/05/24 | 108739 | 2024-07-01 | 48000 | 1900-01-01 | 0 | SPARTAN ENGINEERING INDUSTRIES PVT LTD
GI Sheet Fixing (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 794 | 2023-10-27 | E Bldg. Meter Room Barrication Work | 88 | 5 | 0 | 440 | 0 | 2024-07-15 16:00 | Labour charges for GI Sheet Fixing for Barrication in Meter Room for E-Building. | 100 |  | 109119 | 2024-07-15 | 2150.08 | 1900-01-01 | -1710.08 | SURESH RANGNATH SHITOLE
MS Pipe (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 794 | 2023-10-27 | E Bldg. Meter Room Barrication Work | 44.16 | 12 | 0 | 529.92 | 0 | 2024-07-15 16:00 | Labour charges for (50 x 50 x 2mm) MS Pipe fixing for Barrication in Meter Room for E-Building. | 100 |  | 109119 | 2024-07-15 | 2150.08 | 1900-01-01 | -1620.16 | SURESH RANGNATH SHITOLE
MS Angle 50 x 50 x 5mm | N/C | N/C | SURESH RANGNATH SHITOLE | 794 | 2023-10-27 | E Bldg. Meter Room Barrication Work | 31.68 | 12 | 0 | 380.16 | 0 | 2024-07-15 16:00 | Labour charges for (50 x 50 x 5mm) IS Angle fixing for Barrication in Meter Room for E-Building. | 100 |  | 109119 | 2024-07-15 | 2150.08 | 1900-01-01 | -1769.92 | SURESH RANGNATH SHITOLE
Door Making Fabrication Work | N/C | N/C | SURESH RANGNATH SHITOLE | 794 | 2023-10-27 | E Bldg. Meter Room Barrication Work | 1 | 800 | 0 | 800 | 0 | 2024-07-15 16:00 | Charges for MS Door ( 3ft 6 inch x 8ft) making & fixing for Barrication in Meter Room for E-Building. | 100 |  | 109119 | 2024-07-15 | 2150.08 | 1900-01-01 | -1350.08 | SURESH RANGNATH SHITOLE
Rebarring work 10mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 809 | 2023-11-17 | 265KLD STP Rebaring Work | 493 | 200 | 0 | 98600 | 17748 | 2024-07-14 14:06 | Labour Charges for 10mm Dia. Bar Rebarring work with 200mm depth using Hilti RE-500 for 265 KLD STP. | 100 |  | 109097 | 2024-07-15 | 98600 | 1900-01-01 | 0 | AVCON TECHNICS PVT LTD
Rebarring work 10mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 809 | 2023-11-17 | 265KLD STP Rebaring Work | 56 | 200 | 0 | 11200 | 2016 | 2024-07-23 18:09 | Labour Charges for 10mm Dia. Bar Rebarring work with 200mm depth using Hilti RE-500 for 265 KLD STP. | 100 |  | 109388 | 2024-07-29 | 11200 | 1900-01-01 | 0 | AVCON TECHNICS PVT LTD
Lift Pit Cleaning Work - BC | N/C | N/C | PRAKASH SAHU | 819 | 2023-11-24 | D Building Lift Pit Cleaning | 1 | 4500 | 0 | 4500 | 0 | 2024-07-17 | Labour charges for D-Bldg Lift pit cleaning work including Sludge and debris,breaking work including breaker for further civil work & Erection of lift | 100 |  | 109234 | 2024-07-22 | 4500 | 1900-01-01 | 0 | PRAKASH SAHU
GI Sheet Removing - DCW | N/C | N/C | SURESH RANGNATH SHITOLE | 821 | 2023-11-24 | D-Lift No.3-G.I Sheet & MS Pipe Removing Work | 1681.75 | 2.5 | 0 | 4204.375 | 0 | 2024-07-27 | Labour charges for GI Sheet removing work for D-Bldg Lift-3. | 100 |  | 109405 | 2024-07-29 | 8445.18 | 1900-01-01 | -4240.805 | SURESH RANGNATH SHITOLE
MS Pipe Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 821 | 2023-11-24 | D-Lift No.3-G.I Sheet & MS Pipe Removing Work | 706.8 | 6 | 0 | 4240.8 | 0 | 2024-07-27 | Labour charges for MS Pipe (40mm x 40mm x2mm) removing work for D-Bldg Lift-3. | 100 |  | 109405 | 2024-07-29 | 8445.18 | 1900-01-01 | -4204.38 | SURESH RANGNATH SHITOLE
Fabrication Work | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-MS Jali fabrication work at Lift Shaft door for safety | 634.49 | 10 | 0 | 6344.9 | 0 | 2024-07-15 | Labour charges for Fixing of MS Jali Fabrication work in old steel 18mm & 12mm Bar for Safety purpose for D-Bldg Lift shaft door. | 100 |  | 109116 | 2024-07-15 | 6344.9 | 1900-01-01 | 0 | SURESH RANGNATH SHITOLE
Backfilling | N/C | N/C | SHIVAM ENTERPRISES | 828 | 2023-11-29 | Excavation & Backfilling Work-East Side Compound Wall | 587.895 | 60 | 0 | 35273.7 | 0 | 2024-07-15 | Charges for Backfilling of East Side Compound wall . | 100 |  | 109110 | 2024-07-15 | 35273.7 | 1900-01-01 | 0 | SHIVAM ENTERPRISES
Labour Lumpsum | N/C | N/C | PRAKASH SAHU | 853 | 2023-12-12 | Material Shifting from DBldg. Parking to Amenity Plot | 1 | 20000 | 0 | 20000 | 0 | 2024-07-17 | Labour Charges for Material Shifting from D-Bldg Parking to Amenity Plot Area | 100 |  | 109263 | 2024-07-22 | 20000 | 1900-01-01 | 0 | PRAKASH SAHU
Female Coolie - SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 862 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 91.5 | 350 | 0 | 32025 | 0 | 2024-07-08 | Charges for Female Coolie (6 No/ Day) for Housekeeping & Cleaning work for the month of JUNE-2024 | 100 |  | 108934 | 2024-07-08 | 32025 | 1900-01-01 | 0 | DIAMOND SHINE CLEAN SERVICES
Housekeeping work-SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 863 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 1 | 3000 | 0 | 3000 | 0 | 2024-07-08 | Material Charges for Housekeeping & Cleaning work for the month of JUNE-2024 | 100 |  | 108942 | 2024-07-08 | 3000 | 1900-01-01 | 0 | DIAMOND SHINE CLEAN SERVICES
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 886 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 1.0224 | 300000 | 0 | 306720 | 0 | 2024-07-08 | Charges for Electricity Bills from DEC-2023 to NOV-2024. | 100 |  | 108898 | 2024-07-08 | 306720 | 2024-07-08 17:08 | 0 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 886 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.0025 | 300000 | 0 | 750 | 0 | 2024-07-08 | Charges for Electricity Bills from DEC-2023 to NOV-2024. | 100 |  | 108914 | 2024-07-08 | 750 | 2024-07-08 18:01 | 0 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 886 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.8637 | 300000 | 0 | 259110 | 0 | 2024-07-08 | Charges for Electricity Bills from DEC-2023 to NOV-2024. | 100 |  | 108922 | 2024-07-08 | 259110 | 2024-07-08 18:01 | 0 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 886 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.0022 | 300000 | 0 | 660 | 0 | 2024-07-27 | Charges for Electricity Bills from DEC-2023 to NOV-2024. | 100 | For the month of july 2024 | 109333 | 2024-07-27 | 660 | 2024-07-27 15:37 | 0 | MSEDCL
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.1106 | 80000 | 2 | 8848 | 0 | 2024-07-08 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 |  | 108900 | 2024-07-08 | 8850 | 2024-07-08 17:08 | -2 | TATA TELESERVICES
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.1475 | 80000 | 0 | 11800 | 0 | 2024-07-08 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 |  | 108901 | 2024-07-08 | 11800 | 2024-07-08 17:08 | 0 | TATA TELESERVICES
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.005 | 80000 | 0 | 400 | 0 | 2024-07-09 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 |  | 108976 | 2024-07-09 | 3777 | 2024-07-11 12:29 | -3377 | BHARAT SANCHAR NIGAM LTD
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.005 | 80000 | 0 | 400 | 0 | 2024-07-09 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 |  | 108976 | 2024-07-09 | 3777 | 2024-07-11 12:29 | -3377 | BHARAT SANCHAR NIGAM LTD
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.0024 | 80000 | -3 | 192 | 0 | 2024-07-09 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 |  | 108976 | 2024-07-09 | 3777 | 2024-07-11 12:29 | -3585 | BHARAT SANCHAR NIGAM LTD
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.005 | 80000 | 0 | 400 | 0 | 2024-07-09 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 |  | 108976 | 2024-07-09 | 3777 | 2024-07-11 12:29 | -3377 | BHARAT SANCHAR NIGAM LTD
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.0225 | 80000 | -1 | 1800 | 0 | 2024-07-09 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 |  | 108976 | 2024-07-09 | 3777 | 2024-07-11 12:29 | -1977 | BHARAT SANCHAR NIGAM LTD
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.005 | 80000 | 0 | 400 | 0 | 2024-07-09 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 |  | 108976 | 2024-07-09 | 3777 | 2024-07-11 12:29 | -3377 | BHARAT SANCHAR NIGAM LTD
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.0024 | 80000 | -3 | 192 | 0 | 2024-07-09 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 |  | 108976 | 2024-07-09 | 3777 | 2024-07-11 12:29 | -3585 | BHARAT SANCHAR NIGAM LTD
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.0162 | 80000 | 0 | 1296 | 0 | 2024-07-18 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 | FOR THE MONTH OF JUNE 2024 | 109156 | 2024-07-18 | 1296 | 2024-07-18 12:45 | 0 | BHARTI AIRTEL LIMITED
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.0147 | 80000 | 2 | 1176 | 0 | 2024-07-24 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 | FOR THE MONTH OF JUNE 2024 | 109311 | 2024-07-24 | 1178 | 2024-07-24 18:05 | -2 | BHARTI AIRTEL LIMITED
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.8744 | 80000 | -2 | 69952 | 0 | 2024-07-27 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 | For the month of july 2024 | 109331 | 2024-07-27 | 69950 | 2024-07-27 15:37 | 2 | BHARTI AIRTEL LIMITED
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 887 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.0231 | 80000 | -1 | 1848 | 0 | 2024-07-30 | Charges for Telephone Bills from DEC-2023 to NOV-2024. | 100 |  | 109442 | 2024-07-30 | 1847 | 2024-07-30 15:54 | 1 | BHARTI AIRTEL LIMITED
Site Expenses -SO | N/C | N/C | NITIN D PARDESHI | 888 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.4242 | 25000 | -1 | 10605 | 0 | 2024-07-02 | Charges for Petty Cash Expenses for Head office work from DEC-2023 to NOV-2024. | 100 | DURATION 01JUNE TO 15JUNE | 108758 | 2024-07-02 | 10604 | 2024-07-02 12:54 | 1 | NITIN D PARDESHI
Site Expenses -SO | N/C | N/C | NITIN D PARDESHI | 888 | 2023-12-19 | Electricity, Telephone, mobile & site expenses | 0.552 | 25000 | 1 | 13800 | 0 | 2024-07-30 | Charges for Petty Cash Expenses for Head office work from DEC-2023 to NOV-2024. | 100 |  | 109443 | 2024-07-30 | 13801 | 2024-07-30 15:54 | -1 | NITIN D PARDESHI
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | D&F Bldg. Entrance Gate Rebaring Work | 18 | 260 | 0 | 4680 | 842.4 | 2024-07-22 11:44 | Labour charges for 12mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D & F-Entrance Gate | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -100555 | AVCON TECHNICS PVT LTD
Rebaring work 16mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | D&F Bldg. Entrance Gate Rebaring Work | 2 | 500 | 0 | 1000 | 180 | 2024-07-22 11:44 | Labour charges for 16mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D & F-Entrance Gate | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -104235 | AVCON TECHNICS PVT LTD
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | DBldg.-Podium,Ramp-Rebaring Work | 169 | 260 | 0 | 43940 | 7909.2 | 2024-07-21 11:55 | Labour charges for 12mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D-Bldg Podium Ramp work. | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -61295 | AVCON TECHNICS PVT LTD
Rebaring work 16mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | DBldg.-Podium,Ramp-Rebaring Work | 1 | 500 | 0 | 500 | 90 | 2024-07-22 11:44 | Labour charges for 16mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D-Bldg Podium Ramp work. | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -104735 | AVCON TECHNICS PVT LTD
Rebarring work 10mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | DBldg.-Podium,Ramp-Rebaring Work | 110 | 200 | 0 | 22000 | 3960 | 2024-07-21 11:55 | Labour charges for 10mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D-Bldg Podium Ramp work. | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -83235 | AVCON TECHNICS PVT LTD
Rebarring work 8mm dia- BPo | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | DBldg.-Podium,Ramp-Rebaring Work | 5 | 175 | 0 | 875 | 157.5 | 2024-07-21 11:55 | Labour charges for 8mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D-Bldg Podium Ramp work. | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -104360 | AVCON TECHNICS PVT LTD
Rebarring work 12mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | EBldg.-Podium,Ramp-Rebaring Work | 124 | 260 | 0 | 32240 | 5803.2 | 2024-07-21 11:55 | Labour charges for 12mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for E-Bldg Podium Ramp work. | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -72995 | AVCON TECHNICS PVT LTD
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1202 Dhar Core work-(L) (2BHK) Near Refuge | 1 | 11000 | 0 | 11000 | 1980 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109243 | 2024-07-22 | 63000 | 1900-01-01 | -52000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1706 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109243 | 2024-07-22 | 63000 | 1900-01-01 | -50000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1906 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109243 | 2024-07-22 | 63000 | 1900-01-01 | -50000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2305 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109243 | 2024-07-22 | 63000 | 1900-01-01 | -50000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2306 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109243 | 2024-07-22 | 63000 | 1900-01-01 | -50000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1905 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-23 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109431 | 2024-07-29 | 10000 | 1900-01-01 | -8000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1906 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2005 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2006 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2105 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-23 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109431 | 2024-07-29 | 10000 | 1900-01-01 | -8000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2007 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-23 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109431 | 2024-07-29 | 10000 | 1900-01-01 | -8000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2008 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-23 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109431 | 2024-07-29 | 10000 | 1900-01-01 | -8000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2107 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2108 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-23 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109431 | 2024-07-29 | 10000 | 1900-01-01 | -8000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2301 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109242 | 2024-07-22 | 48000 | 1900-01-01 | -35000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2302 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109242 | 2024-07-22 | 48000 | 1900-01-01 | -35000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2303 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109242 | 2024-07-22 | 48000 | 1900-01-01 | -37000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2304 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109242 | 2024-07-22 | 48000 | 1900-01-01 | -37000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2004 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 0 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2201 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 0 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2304 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 0 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1405 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1606 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.703 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1003 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-14 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 109096 | 2024-07-15 | 4000 | 1900-01-01 | -2000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1103 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-14 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 109096 | 2024-07-15 | 4000 | 1900-01-01 | -2000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1105 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-22 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 109244 | 2024-07-22 | 2000 | 1900-01-01 | 0 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1305 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1404 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-07-24 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 109380 | 2024-07-29 | 2000 | 1900-01-01 | -1000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1408 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-07-24 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 109380 | 2024-07-29 | 2000 | 1900-01-01 | -1000 | A K INTERIOR CONTRACTOR
Excavation Manually | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Excavation & Backfilling Work-East Side Compound Wall | 139.02 | 575 | 0 | 79936.5 | 0 | 2024-07-23 19:06 | Labour charges for Manual Excavation work for compound wall Footing & Retaining wall to East side compound wall. | 100 |  | 109391 | 2024-07-29 | 79936.5 | 1900-01-01 | 0 | VIJAY MOHITE
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg Stilt Fl Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 1st Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 2nd Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 3rd Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 4th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 5th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 6th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 7th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 8th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 9th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 10th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 11th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 12th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 13th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 14th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 15th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 16th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 17th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 18th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 19th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 20th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 21st Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 22nd Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 23rd Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 24th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 1900-01-01 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Surface Mounting Modularized Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 2 | 325000 | 0 | 455000 | 81900 | 2024-07-15 | Against Material Supply | 70 | Challan No-18534 DT 03/07/2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -3677639 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Network Active Repeater (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 1 | 42500 | 0 | 29750 | 5355 | 2024-07-29 | Against Material Supply | 70 | Challan No-18667 DT 27/07/2024 | 109418 | 2024-07-29 | 267750 | 1900-01-01 | -238000 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable smoke detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 857 | 2340 | 0 | 1403766 | 252677.88 | 2024-07-07 | Against Material Supply | 70 | Challan No-18534 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -2728873 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Heat Detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 207 | 2300 | 0 | 333270 | 59988.6 | 2024-07-07 | Against Material Supply | 70 | Challan No-18534 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -3799369 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Gas Leakage Detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 200 | 3600 | 0 | 504000 | 90720 | 2024-07-07 | Against Material Supply | 70 | Challan No-18534 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -3628639 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Zone Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 200 | 3600 | 0 | 504000 | 90720 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -3628639 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Manual call point (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 34 | 5000 | 0 | 119000 | 21420 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4013639 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Combined sounder (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 34 | 4200 | 0 | 99960 | 17992.8 | 2024-07-10 | Against Material Supply | 70 | Challan No-18567 DT 08.07.24 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4032679 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fault Isolator Base / Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 52 | 3100 | 0 | 112840 | 20311.2 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4019799 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Power Supply unit (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 6 | 8500 | 0 | 35700 | 6426 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4096939 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm Armoured cable (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 1000 | 75 | 0 | 52500 | 9450 | 2024-07-29 | Against Material Supply | 70 | Challan No-18602 DT16/07/2024 | 109418 | 2024-07-29 | 267750 | 1900-01-01 | -215250 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 Core x 1.5 Sqmm FRLS Armd. cable (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 955 | 75 | 0 | 50137.5 | 9024.76 | 2024-07-29 | Against Material Supply | 70 | Challan No-18602 DT16/07/2024. | 109418 | 2024-07-29 | 267750 | 1900-01-01 | -217612.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
8 Zone FFT Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FFT System | 1 | 68915 | 0 | 48240.5 | 8683.3 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4084398.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC Fireman's Phone Jack (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FFT System | 34 | 3300 | 0 | 78540 | 14137.2 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4054099 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Telephone Jack/Receiver (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FFT System | 2 | 5200 | 0 | 7280 | 1310.4 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4125359 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 Core x 1.5 Sqmm FRLS Armd. cable (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FFT System | 45 | 75 | 0 | 2362.5 | 425.26 | 2024-07-29 | Against Material Supply | 70 | Challan No-18602 DT16/07/2024. | 109418 | 2024-07-29 | 267750 | 1900-01-01 | -265387.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
6 zone Voice Alarm controller (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 2 | 165000 | 0 | 231000 | 41580 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -3901639 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Battery update & activation card (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 2 | 42000 | 0 | 58800 | 10584 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT-03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4073839 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Push to talk Microphone (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 2 | 16500 | 0 | 23100 | 4158 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4109539 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Wall Mounting Kit (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 2 | 3200 | 0 | 4480 | 806.4 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4128159 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signal initiating devices (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 112 | 750 | 0 | 58800 | 10584 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4073839 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
20 Watt Cabinet Speakers (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 76 | 2500 | 0 | 133000 | 23940 | 2024-07-29 | Against Material Supply | 70 | Challan No-18667 DT 27.07.2024 Total Received-78 Nos. 2 Balnace Relesed from E Building. | 109418 | 2024-07-29 | 267750 | 1900-01-01 | -134750 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Monitor Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 25 | 3135 | 0 | 54862.5 | 9875.26 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4077776.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Insurance Policy | N/C | N/C | IFFCO TOKIO GENERAL INSURANCE Co.Ltd | 914 | 2024-01-24 | Contractor All Risk (CAR) Policy Renewal | 1 | 90550 | 0 | 90550 | 16299 | 2024-07-26 | Charges for Renewal of Contractor All Risk insurance policy for APRIL-2024 | 100 |  | 109318 | 2024-07-26 | 181100 | 2024-07-26 18:20 | -90550 | IFFCO TOKIO GENERAL INSURANCE Co.Ltd
Insurance Policy | N/C | N/C | IFFCO TOKIO GENERAL INSURANCE Co.Ltd | 914 | 2024-01-24 | Contractor All Risk (CAR) Policy Renewal | 1 | 90550 | 0 | 90550 | 16299 | 2024-07-26 | Charges for Renewal of Contractor All Risk insurance policy for JULY-2024 | 100 |  | 109318 | 2024-07-26 | 181100 | 2024-07-26 18:20 | -90550 | IFFCO TOKIO GENERAL INSURANCE Co.Ltd
20 Watt Cabinet Speakers (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 916 | 2024-01-27 | E Bldg.-PA System | 2 | 2500 | 0 | 3500 | 630 | 2024-07-29 | Against Material Supply | 70 | Challan No-18667 DT 27.07.2024 Total Received-78 Nos. 2 Balnace Relesed from E Building.Amendment Needed. | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
1C x 1sqmm Wire (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 916 | 2024-01-27 | E Bldg.-FAS System | 2400 | 33.25 | 0 | 55860 | 10054.8 | 2024-07-15 | Against Material Supply | 70 | Challan No-18558 DT 06.07.2024 Against D building due to unavailabitity of qty in D building. | 109284 | 2024-07-23 | 55860 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
ID Cards with both side Printing | N/C | N/C | PRASAA INFOTECH | 920 | 2024-01-27 | Head Office Expenses | 21 | 25 | 0 | 525 | 94.5 | 2024-07-24 | Charges for ID Cards with both side printing work. | 100 |  | 109306 | 2024-07-24 | 1155 | 2024-07-24 14:45 | -630 | PRASAA INFOTECH
Plastic Card Holder | N/C | N/C | PRASAA INFOTECH | 920 | 2024-01-27 | Head Office Expenses | 25.2 | 25 | 0 | 630 | 113.4 | 2024-07-24 | Charges for Plastic Card Holder for ID Card. | 100 |  | 109306 | 2024-07-24 | 1155 | 2024-07-24 14:45 | -525 | PRASAA INFOTECH
B Check Service Kit | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 932 | 2024-02-03 | 82.5 kva DG servicing kit | 1 | 9062 | 0 | 9062 | 1631.16 | 2024-07-10 | Material supply charges for B-Check Surveying kit (Lubricant oil-10 Ltr, Coolant-01 Ltr, Distill water-01 Ltr , Oil Filter-01 Nos, Fuel Filter-02 Nos) for 82.5 kva DG Set Servicing work. | 100 | Report No-000681 DT 09.07.2024 | 109128 | 2024-07-15 | 9798 | 1900-01-01 | -736 | MEGAPOWER SOLUTION PVT LTD
Transport Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 932 | 2024-02-03 | 82.5 kva DG servicing kit | 1 | 736 | 0 | 736 | 132.48 | 2024-07-10 | Transportation Charges for material delivery charges for 82.5 kva DG Set Servicing work. | 100 | Challan No- 012913 DT 09.07.2024 | 109128 | 2024-07-15 | 9798 | 1900-01-01 | -9062 | MEGAPOWER SOLUTION PVT LTD
Male Coolie | N/C | N/C | JAISAN | 937 | 2024-02-13 | D-Bldg & development- Department Labour (L) | 90 | 600 | 0 | 54000 | 0 | 2024-07-08 | Department Male Coolie Charges for Housekeeping work(3 Male Coolie /Day) of D-Building for JUN-2024 | 100 |  | 108933 | 2024-07-08 | 107700 | 2024-07-26 12:31 | -53700 | JAISAN
Female Coolie | N/C | N/C | JAISAN | 937 | 2024-02-13 | D-Bldg & development- Department Labour (L) | 82.5 | 400 | 0 | 33000 | 0 | 2024-07-08 | Department Female Coolie Charges for Housekeeping work(3 Female Coolie /Day) of D-Building for JUN-2024 | 100 |  | 108933 | 2024-07-08 | 107700 | 2024-07-26 12:31 | -74700 | JAISAN
Male Coolie | N/C | N/C | JAISAN | 937 | 2024-02-13 | D-Bldg & development- Department Labour (L) | 34.5 | 600 | 0 | 20700 | 0 | 2024-07-08 | Department Male Coolie Charges for Housekeeping work of Development for the month of JUN-2024 | 100 |  | 108933 | 2024-07-08 | 107700 | 2024-07-26 12:31 | -87000 | JAISAN
10" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | STP Overflow line-265KLD to Nala Line-(L) | 121.6806 | 28 | 0 | 3407.0568 | 613.28 | 2024-07-28 18:47 | Charges for 10 inch RCC NP2 Hume Pipe laying & Fixing work for STP Overflow line (From 265 KLD to Nala) | 100 |  | 109410 | 2024-07-29 | 12541.76 | 1900-01-01 | -9134.7032 | SAI PLUMBING WORKS
12" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 304.49 | 30 | 0 | 9134.7 | 1644.24 | 2024-07-29 10:14 | Labour Charges for 12 inch RCC Hume pipe fixing and laying work for storm water line work. | 100 |  | 109410 | 2024-07-29 | 12541.76 | 1900-01-01 | -3407.06 | SAI PLUMBING WORKS
Chamber Making -USL | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Blockwork & Plaster Work for Rainwater Harvesting Chamber | 2 | 10000 | 0 | 20000 | 3600 | 2024-07-12 19:19 | Charges for Construction of (7ft 6inch x 5ft x 6 inch x 6ft) Rainwater Harvesting Chamber including PCC, Ghotai, Brickwork9", Internal Ghotai Plaster, Outer Chat Plaster, Chamber cover fixing, etc . | 100 |  | 109121 | 2024-07-15 | 20000 | 1900-01-01 | 0 | SAI PLUMBING WORKS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | Stilt Fl Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 1st Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 2nd Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 3rd Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 4th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 5th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 6th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 7th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 8th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 9th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 10th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 11th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 12th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 13th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 14th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 15th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 16th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 17th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 18th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 19th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 20th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 21st Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 22nd Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 23rd Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 24th Fl-Lobby Fire Staircase- 01 Dhar Core | 2 | 285 | 0 | 570 | 28.5 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -28000.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 24th Fl-Lobby Fire Staircase- 01 Dhar Core | 0.2491 | 285 | 0 | 70.9935 | 3.54 | 2024-07-08 15:28 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/363/2024-25 | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -28499.9965 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | Terrace Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | Stilt Fl Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 1st Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 2nd Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 3rd Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 4th Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 5th Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 6th Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 7th Fl-Lobby Common Staircase- 02 Dhar Core | 2 | 285 | 0 | 570 | 28.5 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -28000.99 | LAXMI STRUCTURES & FIXTURES LLP
Al. Arm. Cable laying 3.5C 300sqmm-UTI | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 100 | 99 | 0 | 9900 | 1782 | 2024-07-29 17:03 | Charges for Laying of 300 Sqmm 3.5 Core Alu. Armoud cable to D, E, F Building | 100 |  | 109420 | 2024-07-29 | 92600 | 1900-01-01 | -82700 | ADITI POWER CARE AND ENTERPRISES
Al. Arm. Cable laying 3.5C 300sqmm-UTI | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 60 | 99 | 0 | 5940 | 1069.2 | 2024-07-29 17:19 | Charges for Laying of 300 Sqmm 3.5 Core Alu. Armoud cable to D, E, F Building | 100 |  | 109420 | 2024-07-29 | 92600 | 1900-01-01 | -86660 | ADITI POWER CARE AND ENTERPRISES
End Termination 300sqmm X 3.5 core cable (M+L) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 8 | 1870 | 0 | 14960 | 2692.8 | 2024-07-29 17:03 | Charges for providing & making of End Termination of 300 Sqmm 3.5 Core Alu. Armoud Cable | 100 |  | 109420 | 2024-07-29 | 92600 | 1900-01-01 | -77640 | ADITI POWER CARE AND ENTERPRISES
End Termination 120sqmm X 3.5 core cable (M+L) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 20 | 990 | 0 | 19800 | 3564 | 2024-07-29 17:24 | Charges for providing & making of End Termination of 120 Sqmm 3.5 Core Alu. Armoud Cable | 100 |  | 109420 | 2024-07-29 | 92600 | 1900-01-01 | -72800 | ADITI POWER CARE AND ENTERPRISES
Meter Panel (L) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 14 | 3000 | 0 | 42000 | 7560 | 2024-07-29 17:03 | Charges for Meter Panel fixing (24 Nos of Meter in 1 Pannel)fr D, E & F Bldg. | 100 |  | 109420 | 2024-07-29 | 92600 | 1900-01-01 | -50600 | ADITI POWER CARE AND ENTERPRISES
GI Earthing Patti 25x3 (M) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 961 | 2024-04-09 | D,E, F & Development-Earthing Patti Work | 54.31 | 101.2 | 0 | 5496.172 | 989.32 | 2024-07-29 17:32 | Material supply charges for providing of 25mm x 3mm GI Earthing patti for D, E & F Bldg Development work. | 100 |  | 109427 | 2024-07-29 | 39309.62 | 1900-01-01 | -33813.448 | ADITI POWER CARE AND ENTERPRISES
GI Earthing Patti 50x6 (M) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 961 | 2024-04-09 | D,E, F & Development-Earthing Patti Work | 334.125 | 101.2 | 0 | 33813.45 | 6086.42 | 2024-07-29 17:32 | Material supply charges for providing of 50mm x 6mm GI Earthing patti for D, E & F building Development work. | 100 |  | 109427 | 2024-07-29 | 39309.62 | 1900-01-01 | -5496.17 | ADITI POWER CARE AND ENTERPRISES
GI Earthing Patti 50 x 6mm (L) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 962 | 2024-04-09 | D,E, F & Development-Earthing Patti Work | 133.65 | 80 | 0 | 10692 | 1924.56 | 2024-07-29 17:33 | Labour charges for Erection, testing& commissioning GI earthing Patti(50mmx 6mm) of approved makes confirming to IS 3043:1987. The strip shall run on floor/ ceiling/ walls, from the equipments to the nearest pit with necessary accessories. | 100 |  | 109429 | 2024-07-29 | 15218 | 1900-01-01 | -4526 | ADITI POWER CARE AND ENTERPRISES
Earthing Patti 25x3 (L) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 962 | 2024-04-09 | D,E, F & Development-Earthing Patti Work | 90.52 | 50 | 0 | 4526 | 814.68 | 2024-07-29 17:33 | Labour charges for Erection, testing& commissioning GI earthing Patti(25mmx 3mm) of approved makes confirming to IS 3043:1987. The strip shall run on floor/ ceiling/ walls, from the equipments to the nearest pit with necessary accessories. | 100 |  | 109429 | 2024-07-29 | 15218 | 1900-01-01 | -10692 | ADITI POWER CARE AND ENTERPRISES
PVC Pipe fixing 4"- SO | N/C | N/C | SAI PLUMBING WORKS | 969 | 2024-04-24 | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | 890 | 40 | 0 | 35600 | 6408 | 2024-07-12 19:08 | Labour charges for Laying of PVC Pipe 4 inch for storm water line at D & E Parking area. | 100 |  | 109091 | 2024-07-15 | 53100 | 1900-01-01 | -17500 | SAI PLUMBING WORKS
PVC Pipe fixing 6"- SO | N/C | N/C | SAI PLUMBING WORKS | 969 | 2024-04-24 | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | 250 | 50 | 0 | 12500 | 2250 | 2024-07-12 19:08 | Labour charges for Laying of PVC Pipe 6 inch for storm water line at D & E Parking area. | 100 |  | 109091 | 2024-07-15 | 53100 | 1900-01-01 | -40600 | SAI PLUMBING WORKS
Bullet Fastner Fixing (L) | N/C | N/C | SAI PLUMBING WORKS | 969 | 2024-04-24 | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | 250 | 20 | 0 | 5000 | 900 | 2024-07-12 19:08 | Labour charges for Bullet Fastner Fixing for Drainage line & Storm water line pipe fixing at D & E Parking area. | 100 |  | 109091 | 2024-07-15 | 53100 | 1900-01-01 | -48100 | SAI PLUMBING WORKS
Dismantling work | N/C | N/C | ANANDI ENTERPRISES | 974 | 2024-05-02 | Tower Crane Dismantling work | 1 | 375000 | 0 | 375000 | 67500 | 2024-07-08 | Charges for Tower Crane Potent. MCT 85 (110 Mtr.) Dismantling work with Gadam (within 15 - 20 days) | 100 | Report No-107 DT06.07.2024 | 108947 | 2024-07-08 | 375000 | 2024-07-15 12:55 | 0 | ANANDI ENTERPRISES
Loading - BRE | N/C | N/C | ANANDI ENTERPRISES | 974 | 2024-05-02 | Tower Crane Loading,Unloading | 1 | 16000 | 0 | 16000 | 2880 | 2024-07-13 | Charges for Tower Crane Potent MCT85 Loading work with supervision & Skilled Trained Manpower (Transfer from Ganga Altus to Ganga Asmi) | 100 | Report No-108 DT 4.7.24 | 109092 | 2024-07-15 | 16000 | 1900-01-01 | 0 | ANANDI ENTERPRISES
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 975 | 2024-05-02 | ONLINE / DIGITAL Social / Digital Activity | 10.5673 | 750000 | -2.61 | 660453.6082 | 118881.18 | 2024-07-05 | 3) JUNE 2024 | 8.3333 | ONLINE SOCAIL , DIGITAL MEDIA / MARKETING / BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM - FOR THE MONTH OF JUNE 2024 | 108799 | 2024-07-05 | 660451 | 2024-07-08 11:34 | 2.6082 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
SMS / WHATSAPP / E-MAILERS / CHATS | N/C | N/C | PINNACLE TELESERVICES PVT LTD | 976 | 2024-05-04 | ONLINE / DIGITAL Social / Digital Activity | 0.0221 | 80000 | 1 | 1768 | 318.42 | 2024-07-05 | GOEL GANGA GROUP - WHATSAPP MESSAGES ( MARKETING, RECOVERY, ETC RELATED WITH SALES PROMOTION, BRANDING INFORMATION, WHATSAPP MESSAGE THROUGH THINK PINNACLE | 100 | GOEL GANGA GROUP - WHATSAPP MESSAGES ( MARKETING, RECOVERY, ETC RELATED WITH SALES PROMOTION, BRANDING, INFORMATION, WHATSAPP MESSAGES TROUGH PINNACLE | 108802 | 2024-07-05 | 1769 | 2024-07-08 11:34 | -1 | PINNACLE TELESERVICES PVT LTD
SMS / WHATSAPP / E-MAILERS / CHATS | N/C | N/C | PINNACLE TELESERVICES PVT LTD | 976 | 2024-05-04 | ONLINE / DIGITAL Social / Digital Activity | 0.0194 | 80000 | -3 | 1552 | 278.82 | 2024-07-18 | GOEL GANGA GROUP - WHATSAPP MESSAGES ( MARKETING, RECOVERY, ETC RELATED WITH SALES PROMOTION, BRANDING INFORMATION, WHATSAPP MESSAGE THROUGH THINK PINNACLE | 100 | GOEL GANGA GROUP - WHATSAPP MESSAGES ( MARKETING, RECOVERY, ETC RELATED WITH SALES PROMOTION, BRANDING, INFORMATION, WHATSAPP MESSAGES TROUGH PINNACLE FOR THE MONTH OF JUNE 2024 | 109157 | 2024-07-18 | 1549 | 2024-07-19 11:57 | 3 | PINNACLE TELESERVICES PVT LTD
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 982 | 2024-05-09 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2024-07-05 | 3) June 2024 | 8.3333 | MONTHLY MARKETING / MARKETING SOCIAL / DIGITAL MONTHLY RETAINERSHIP CHARGES @ 40,000/-RS + TAX PER MONTH | 108803 | 2024-07-05 | 39999.84 | 2024-07-08 11:34 | 0 | GOOD OLD DELIGHT
Composite Pipe (Size-1216) (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 290 | 248 | 0 | 50344 | 9061.92 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -720385.4 | SARV ENTERPRISES
Composite Pipe (Size-1620) (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 110 | 295 | 0 | 22715 | 4088.7 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -748014.4 | SARV ENTERPRISES
Composite Pipe (Size-2025) (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 370 | 361 | 0 | 93499 | 16829.82 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -677230.4 | SARV ENTERPRISES
Composite Pipe (Size-2532) (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 420 | 460 | 0 | 135240 | 24343.2 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -635489.4 | SARV ENTERPRISES
Supply of NRV 15mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 140 | 1660 | 0 | 162680 | 29282.4 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -608049.4 | SARV ENTERPRISES
Supply of Spring NRV 25mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 4 | 2400 | 0 | 6720 | 1209.6 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -764009.4 | SARV ENTERPRISES
Supply of NRV 32mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 10 | 3060 | 0 | 21420 | 3855.6 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -749309.4 | SARV ENTERPRISES
Supply of Ball Valve 15mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 150 | 353 | 0 | 37065 | 6671.7 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -733664.4 | SARV ENTERPRISES
Supply of Ball Valve 20mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 54 | 440 | 0 | 16632 | 2993.76 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -754097.4 | SARV ENTERPRISES
Supply of Ball Valve 32mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 20 | 1960 | 0 | 27440 | 4939.2 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -743289.4 | SARV ENTERPRISES
Supply of Air Vent 15mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 4 | 950 | 0 | 2660 | 478.8 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -768069.4 | SARV ENTERPRISES
Supply of GI Air Pipe 15mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 70 | 2000 | 0 | 98000 | 17640 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -672729.4 | SARV ENTERPRISES
Supply of Pressure Relief Valve 15mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 4 | 3800 | 0 | 10640 | 1915.2 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -760089.4 | SARV ENTERPRISES
Supply of MS Fabricated Support (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 179.9 | 80 | 0 | 10074.4 | 1813.4 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -760655 | SARV ENTERPRISES
Supply of Pressure reducing valve (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 20 | 5400 | 0 | 75600 | 13608 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -695129.4 | SARV ENTERPRISES