## Work_Completion_Browse638581127
Work Completion Browse
Project : GANGA ASMI
From Date : 01/07/2024 To date: 01/07/2024
Page 1 of 1
Total Records: 129 Records 1 to 129
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Fogging work-SO | N/C | N/C | S.R.Enterprises | 166 | 2021-09-16 | Sales Office,Lab Camp,Site Office area-Fogging Work | 1 | 8000 | 0 | 8000 | 1440 | 2024-07-02 | Sales office area, Labour camp, Site office Pest control & Fogging work (8 times in month) for the Month of JUNE-2024. | 100 |  | 108846 | 2024-07-08 | 8000 | 1900-01-01 | 0 | S.R.Enterprises
Department Labour - Day | N/C | N/C | SWAMI GOLAPPA | 222 | 2022-02-08 | Goel House Monthly Department Labour | 30 | 600 | 0 | 18000 | 0 | 2024-07-23 18:37 | Labour Charges for Department work for the month of JUNE-2024 ( 1 MC + Rent & Transportation included) | 100 |  | 109305 | 2024-07-23 | 24000 | 1900-01-01 | -6000 | GOLLALPPA SOMRAY SOMJALA
Department Labour - Day | N/C | N/C | SWAMI GOLAPPA | 222 | 2022-02-08 | Goel House Monthly Department Labour | 10 | 600 | 0 | 6000 | 0 | 2024-07-23 18:37 | Labour Charges for Department work for the month of JULY-2024 ( 1 MC + Rent & Transportation included) | 100 |  | 109305 | 2024-07-23 | 24000 | 1900-01-01 | -18000 | GOLLALPPA SOMRAY SOMJALA
Shuttering Work-Mkt | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - RCC Retaining wall Shuttering (L) | 36.47 | 500 | 0 | 18235 | 3282.3 | 2024-07-20 | Labour charges for Shuttering work for Retaining wall Paradi and Intermiate Tie Beam (At Ground Level) Wing 1. | 100 |  | 109219 | 2024-07-22 | 674797 | 1900-01-01 | -656562 | SAIRAJ CONSTRUCTION
Concreting Work | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - RCC retaining wall Concrete (L) | 7.3 | 300 | 0 | 2190 | 394.2 | 2024-07-20 | Labour charges for Concreting work for Retaining wall Paradi and Intermiate Tie Beam (At Ground Level) Wing 1. | 100 |  | 109219 | 2024-07-22 | 674797 | 1900-01-01 | -672607 | SAIRAJ CONSTRUCTION
Reinforcement (L) | No category | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - RCC Retaining wall Steel Binding (L) | 986 | 8 | 0 | 7888 | 1419.84 | 2024-07-20 | Labour charges for Reinforcement work for Retaining wall Paradi and Intermiate Tie Beam (At Ground Level) Wing 1. | 100 |  | 109219 | 2024-07-22 | 674797 | 1900-01-01 | -666909 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 3rd Slab (P4 Lvl) Qty Diff Elevational Chajja RCC | 232.42 | 200 | 0 | 46484 | 8367.12 | 2024-07-20 | Labour charges for Shuttering, Reinforcement and RCC Work for Wing-1 Flower Bed Elevational Chajja. | 100 |  | 109219 | 2024-07-22 | 674797 | 1900-01-01 | -628313 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | 400 | 400 | 0 | 160000 | 28800 | 2024-07-26 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 109360 | 2024-07-29 | 560000 | 1900-01-01 | -400000 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1000 | 200 | 0 | 200000 | 36000 | 2024-07-26 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 109360 | 2024-07-29 | 560000 | 1900-01-01 | -360000 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1000 | 200 | 0 | 200000 | 36000 | 2024-07-20 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 109219 | 2024-07-22 | 674797 | 1900-01-01 | -474797 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1000 | 200 | 0 | 200000 | 36000 | 2024-07-20 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 109219 | 2024-07-22 | 674797 | 1900-01-01 | -474797 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | 1000 | 200 | 0 | 200000 | 36000 | 2024-07-20 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 109219 | 2024-07-22 | 674797 | 1900-01-01 | -474797 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 241 | 2022-02-14 | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | 1000 | 200 | 0 | 200000 | 36000 | 2024-07-26 | Labour Charges for-Quantity differance of Shuttering,reinforcement and Concreting work for Slab,beam,Staircase and all Shear walls | 100 |  | 109360 | 2024-07-29 | 560000 | 1900-01-01 | -360000 | SAIRAJ CONSTRUCTION
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-07-10 | Testing and Certification of Construction material and structure test. | 10 |  | 109006 | 2024-07-15 | 48300 | 1900-01-01 | -38300 | DUROCRETE ENGINEERING SERVICES PVT LTD
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-07-10 | Testing and Certification of Construction material and structure test. | 10 |  | 109006 | 2024-07-15 | 48300 | 1900-01-01 | -38300 | DUROCRETE ENGINEERING SERVICES PVT LTD
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-07-10 | Testing and Certification of Construction material and structure test. | 10 |  | 109006 | 2024-07-15 | 48300 | 1900-01-01 | -38300 | DUROCRETE ENGINEERING SERVICES PVT LTD
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-07-10 | Testing and Certification of Construction material and structure test. | 10 |  | 109006 | 2024-07-15 | 48300 | 1900-01-01 | -38300 | DUROCRETE ENGINEERING SERVICES PVT LTD
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 0.83 | 100000 | 0 | 8300 | 1494 | 2024-07-10 | Testing and Certification of Construction material and structure test. | 10 |  | 109006 | 2024-07-15 | 48300 | 1900-01-01 | -40000 | DUROCRETE ENGINEERING SERVICES PVT LTD
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 0.42 | 100000 | 0 | 4200 | 756 | 2024-07-15 | Testing and Certification of Construction material and structure test. | 10 |  | 109143 | 2024-07-16 | 4200 | 1900-01-01 | 0 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-07-15 | Testing and Certification of Construction material and structure test. | 10 |  | 109126 | 2024-07-15 | 11795 | 1900-01-01 | -1795 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 0.1795 | 100000 | 0 | 1795 | 323.1 | 2024-07-15 | Testing and Certification of Construction material and structure test. | 10 |  | 109126 | 2024-07-15 | 11795 | 1900-01-01 | -10000 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-07-15 | Testing and Certification of Construction material and structure test. | 10 |  | 109127 | 2024-07-15 | 17360 | 1900-01-01 | -7360 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 0.736 | 100000 | 0 | 7360 | 1324.8 | 2024-07-15 | Testing and Certification of Construction material and structure test. | 10 |  | 109127 | 2024-07-15 | 17360 | 1900-01-01 | -10000 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Rent for Tent | N/C | N/C | B.S. KATURE | 30 | 2020-07-20 | Sales Office&Show Flats -Rent for Mandap | 1 | 100000 | 0 | 100000 | 18000 | 2024-07-02 | Rent for Sales office Mandap for the month of JUNE-2024 | 100 |  | 108847 | 2024-07-08 | 100000 | 1900-01-01 | 0 | B.S. KATURE
Garbage Collection UGC | N/C | N/C | VIKAS GARADE | 315 | 2022-06-06 | Site Infra Misc Work | 1 | 1000 | 0 | 1000 | 0 | 2024-07-02 | Labour charges for Collection of Garbage from sales office & Labour camp 1,2 & 3 for month of JUNE-2024 | 100 |  | 108836 | 2024-07-08 | 2000 | 2024-07-26 12:33 | -1000 | VIKAS GARADE
Maintanance Work - SMS | N/C | N/C | VIKAS GARADE | 315 | 2022-06-06 | Site Infra Misc Work | 1 | 1000 | 0 | 1000 | 0 | 2024-07-02 | MSEB Maintenance for month of JUNE-2024 | 100 |  | 108836 | 2024-07-08 | 2000 | 2024-07-26 12:33 | -1000 | VIKAS GARADE
Security Services. | N/C | N/C | SHREE GANESH SECURITY SERVICES | 333 | 2022-07-09 | H.O. Admin Security Services | 0.1485 | 140873 | 5.36 | 20919.6405 | 3766.5 | 2024-07-09 | Security services for the month of JUNE-2024 | 100 |  | 108965 | 2024-07-09 | 20925 | 2024-07-09 15:12 | -5.3595 | SHREE GANESH SECURITY SERVICES
Site Expenses -SO | N/C | N/C | VIKAS GARADE | 38 | 2020-09-24 | Site Expenses | 1 | 10000 | 0 | 10000 | 0 | 2024-07-02 | Petty Cash expenses for the month of JUNE-2024 | 100 |  | 109270 | 2024-07-22 | 10000 | 1900-01-01 | 0 | VIKAS GARADE
Insurance Policy | N/C | N/C | SBI GENERAL INSURANCE COMPANY LIMITED | 385 | 2022-12-30 | Contractor All Risk (CAR) Policy Renewal | 1 | 346942 | 0 | 346942 | 62449.56 | 2024-07-26 | Charges for Renewal of Contractor All Risk insurance policy for MARCH-2024 | 100 |  | 109317 | 2024-07-26 | 693884 | 2024-07-26 18:20 | -346942 | SBI GENERAL INSURANCE COMPANY LIMITED
Insurance Policy | N/C | N/C | SBI GENERAL INSURANCE COMPANY LIMITED | 385 | 2022-12-30 | Contractor All Risk (CAR) Policy Renewal | 1 | 346942 | 0 | 346942 | 62449.56 | 2024-07-26 | Charges for Renewal of Contractor All Risk insurance policy for JUNE-2024 | 100 |  | 109317 | 2024-07-26 | 693884 | 2024-07-26 18:20 | -346942 | SBI GENERAL INSURANCE COMPANY LIMITED
Architectural Consultancy | N/C | N/C | SPACE DESIGNERS SYNDICATE | 394 | 2023-01-20 | Phase-A Wing-2 Architectural Consultancy | 40000.136 | 19 | 0 | 200000 | 36000 | 2024-07-01 | PREPARATION OF WORKING DRAWING | 26.3157 |  | 108666 | 2024-07-01 | 200000 | 2024-07-01 15:16 | -2.312e-06 | SPACE DESIGNERS SYNDICATE
Rent Charges | N/C | N/C | JAIPRAKASH RAMRATAN BAJAARI | 402 | 2023-02-01 | H.O. Admin Rental Charges | 12 | 166668 | 0 | 166667.3333 | 0 | 2024-07-01 | JULY-2024 | 8.3333 |  | 108668 | 2024-07-01 | 166667.33 | 2024-07-01 15:16 | 0.003328 | JAIPRAKASH RAMRATAN BAJAARI
Septic Tank Cleaning services | N/C | N/C | KAM FOUNDATION | 403 | 2023-02-01 | Site Infra Septic Tank Cleaning | 3 | 1500 | 0 | 4500 | 810 | 2024-07-02 | Charges for Sales office and labour camp Septic tank Cleaning (Sludge removing) Evacuation work.4 Times in a year from JAN-2024 to DEC-2024. | 100 |  | 108849 | 2024-07-08 | 9000 | 1900-01-01 | -4500 | KAM FOUNDATION
Septic Tank Cleaning services | N/C | N/C | KAM FOUNDATION | 403 | 2023-02-01 | Site Infra Septic Tank Cleaning | 3 | 1500 | 0 | 4500 | 810 | 2024-07-02 | Charges for Sales office & Labour camp septic tank cleaning work (Sludge removing). | 100 |  | 108849 | 2024-07-08 | 9000 | 1900-01-01 | -4500 | KAM FOUNDATION
Marketing Operating Expenses | N/C | N/C | SUMIT SATISHCHANDRA SHARMA | 406 | 2023-02-09 | Marketing Expenses | 5.1585 | 10000 | 0 | 3438.6561 | 0 | 2024-07-02 | JUNE 2024 | 6.666 |  | 108827 | 2024-07-08 | 3438.66 | 2024-07-20 13:00 | -0.0039 | SUMIT SATISHCHANDRA SHARMA
Marketing Operating Expenses | N/C | N/C | SUMIT SATISHCHANDRA SHARMA | 406 | 2023-02-09 | Marketing Expenses | 6.186 | 10000 | 0 | 4123.5876 | 0 | 2024-07-16 | JULY 2024 | 6.666 |  | 109224 | 2024-07-22 | 4123.59 | 2024-07-30 16:38 | -0.0024 | SUMIT SATISHCHANDRA SHARMA
UGWT Labour | N/C | N/C | PURVA CONSTRUCTION | 415 | 2023-02-21 | UGWT RCC Work (L) | 342156.18 | 2.25 | 0 | 269447.9917 | 46043.64 | 2024-07-23 | RCC Work for all Pardi work | 35 |  | 109354 | 2024-07-29 | 269447.99 | 1900-01-01 | 0.00175 | PURVA CONSTRUCTION
Reinforcement Work-Mkt | N/C | N/C | PURVA CONSTRUCTION | 415 | 2023-02-21 | UGWT RCC Work (L) | 5000 | 8 | 0 | 40000 | 7200 | 2024-07-30 | Labour Charges for UGWT Pumproom reinforcement work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | PURVA CONSTRUCTION
Shuttering Work-Mkt | N/C | N/C | PURVA CONSTRUCTION | 415 | 2023-02-21 | UGWT RCC Work (L) | 150 | 550 | 0 | 82500 | 14850 | 2024-07-30 | Labour Charges for UGWT Pumproom Shuttering work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | PURVA CONSTRUCTION
Concrete Work - UTI | N/C | N/C | PURVA CONSTRUCTION | 415 | 2023-02-21 | UGWT RCC Work (L) | 60 | 350 | 0 | 21000 | 3780 | 2024-07-30 | Labour Charges for UGWT Pumproom Concrete work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | PURVA CONSTRUCTION
Housekeeping -SM | N/C | N/C | SPRINGTIME MAINTENANCE SERVICES PVT LTD | 421 | 2023-02-23 | Head Office Expenses | 11.5998 | 32500 | 0 | 31415.9993 | 5654.88 | 2024-07-03 | JUNE-2024 | 8.3333 |  | 108767 | 2024-07-03 | 31416 | 2024-07-04 10:59 | -0.0006645 | SPRINGTIME MAINTENANCE SERVICES PVT LTD
Housekeeping -SM | N/C | N/C | SPRINGTIME MAINTENANCE SERVICES PVT LTD | 422 | 2023-02-23 | Head Office Housekeeping | 12 | 4500 | 0 | 4499.982 | 810 | 2024-07-03 | JUNE-2024 | 8.3333 |  | 108768 | 2024-07-03 | 4499.98 | 2024-07-04 10:59 | 0.002 | SPRINGTIME MAINTENANCE SERVICES PVT LTD
Debris Chute system (M+L) | N/C | N/C | AAKAAR INDUSTRIES | 473 | 2023-04-11 | Debris Chute System for Wing-1 | 6.16 | 1925 | 0 | 11858 | 2134.44 | 2024-07-23 | Supply & Installation Debris Chute system | 100 |  | 109352 | 2024-07-29 | 11858 | 1900-01-01 | 0 | AAKAAR INDUSTRIES
Garden Maintenance | N/C | N/C | SITARAM GANGADHAR AUTI | 477 | 2023-04-14 | Garden Work | 1 | 20000 | 0 | 20000 | 0 | 2024-07-02 | Charges for Garden and all plants/trees Maintenance including cutting,trimming,watering,cleaning of all area for month JUNE-2024. | 100 |  | 108831 | 2024-07-08 | 20000 | 1900-01-01 | 0 | SITARAM GANGADHAR AUTI
Professional Fees | N/C | N/C | SUNITA S MISHRA | 487 | 2023-05-01 | Professional Fees | 1 | 500000 | 0 | 500000 | 90000 | 2024-07-01 | Professioanl Consultancy Charges for the month of JUNE-2024. | 100 |  | 108656 | 2024-07-01 | 500000 | 2024-07-01 15:11 | 0 | SUNITA S MISHRA
Legal Consultancy | N/C | N/C | UMESH SHANTARAM VASTE | 510 | 2023-06-06 | Legal Consultancy | 1 | 35000 | 0 | 35000 | 0 | 2024-07-09 | Professional Consultancy Charges for the month of JUNE-2024 | 100 |  | 108962 | 2024-07-09 | 35000 | 2024-07-09 14:33 | 0 | UMESH SHANTARAM VASTE
Blockwork 5" - BC - | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 556 | 2023-08-28 | MHADA - Second Floor (P3) Block Work (L) | 251.62 | 20 | 0 | 5032.4 | 905.84 | 2024-07-26 15:56 | Labour Charges for 5 inch Blockwork including scaffolding, with proper joint preparaton with proper line level, valamba, right angle etc. Loading, shifting &unloading of estimated raw material from store to required place to be done by Contractor | 100 | Remaining Bill | 109365 | 2024-07-29 | 19498.74 | 1900-01-01 | -14466.34 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 556 | 2023-08-28 | MHADA - Third Floor (P4) Block Work (L) | 251.62 | 20 | 0 | 5032.4 | 905.84 | 2024-07-26 16:00 | Labour Charges for 5 inch Blockwork including scaffolding, with proper joint preparaton with proper line level, valamba, right angle etc. Loading, shifting &unloading of estimated raw material from store to required place to be done by Contractor | 100 |  | 109365 | 2024-07-29 | 19498.74 | 1900-01-01 | -14466.34 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 556 | 2023-08-28 | MHADA - Fourth Floor (P5) Block Work (L) | 251.62 | 20 | 0 | 5032.4 | 905.84 | 2024-07-26 16:01 | Labour Charges for 5 inch Blockwork including scaffolding, with proper joint preparaton with proper line level, valamba, right angle etc. Loading, shifting &unloading of estimated raw material from store to required place to be done by Contractor | 100 |  | 109365 | 2024-07-29 | 19498.74 | 1900-01-01 | -14466.34 | JAI SEVALAL CONSTRUCTION
Blockwork 8" - BC | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 556 | 2023-08-28 | MHADA - Second Floor (P3) Block Work (L) | 66.69 | 22 | 0 | 1467.18 | 264.1 | 2024-07-26 16:08 | Labour Charges for 8 inch Blockwork including scaffolding, with proper joint preparaton with proper line level, valamba, right angle etc. Loading, shifting &unloading of estimated raw material from store to required place to be done by Contractor | 100 |  | 109365 | 2024-07-29 | 19498.74 | 1900-01-01 | -18031.56 | JAI SEVALAL CONSTRUCTION
Blockwork 8" - BC | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 556 | 2023-08-28 | MHADA - Third Floor (P4) Block Work (L) | 66.69 | 22 | 0 | 1467.18 | 264.1 | 2024-07-26 16:08 | Labour Charges for 8 inch Blockwork including scaffolding, with proper joint preparaton with proper line level, valamba, right angle etc. Loading, shifting &unloading of estimated raw material from store to required place to be done by Contractor | 100 |  | 109365 | 2024-07-29 | 19498.74 | 1900-01-01 | -18031.56 | JAI SEVALAL CONSTRUCTION
Blockwork 8" - BC | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 556 | 2023-08-28 | MHADA - Fourth Floor (P5) Block Work (L) | 66.69 | 22 | 0 | 1467.18 | 264.1 | 2024-07-26 16:08 | Labour Charges for 8 inch Blockwork including scaffolding, with proper joint preparaton with proper line level, valamba, right angle etc. Loading, shifting &unloading of estimated raw material from store to required place to be done by Contractor | 100 |  | 109365 | 2024-07-29 | 19498.74 | 1900-01-01 | -18031.56 | JAI SEVALAL CONSTRUCTION
TAX CONSULTANCY | N/C | N/C | SHAH KHANDELWAL JAIN AND ASSOCIATES | 565 | 2023-09-14 | Professional Fees | 12 | 50000 | 0 | 49998 | 8999.64 | 2024-07-05 | JUNE 2024 | 8.333 |  | 108796 | 2024-07-05 | 49998 | 2024-07-05 14:57 | 0 | SHAH KHANDELWAL JAIN AND ASSOCIATES
TAX CONSULTANCY | N/C | N/C | SHAH KHANDELWAL JAIN AND ASSOCIATES | 565 | 2023-09-14 | Professional Fees | 12 | 50000 | 0 | 49998 | 8999.64 | 2024-07-31 | JULY 2024 | 8.333 |  | 109453 | 2024-07-31 | 49998 | 1900-01-01 | 0 | SHAH KHANDELWAL JAIN AND ASSOCIATES
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-101 (3BHK) Electrical Work (L) | 0.1 | 16792 | 0 | 587.72 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11281.44 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-102 (3BHK) Electrical Work (L) | 0.1 | 16792 | 0 | 587.72 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11281.44 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-106 (3BHK) Electrical Work (L) | 0.1 | 16792 | 0 | 587.72 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11281.44 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-107 (3BHK) Electrical Work (L) | 0.1 | 16792 | 0 | 587.72 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11281.44 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-201 (3BHK) Electrical Work (L) | 0.1 | 16792 | 0 | 587.72 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11281.44 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-202 (3BHK) Electrical Work (L) | 0.1 | 16792 | 0 | 587.72 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11281.44 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-206 (3BHK) Electrical Work (L) | 0.1 | 16792 | 0 | 587.72 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11281.44 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-207 (3BHK) Electrical Work (L) | 0.1 | 16792 | 0 | 587.72 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11281.44 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-401 (3BHK) Electrical Work (L) | 0.9 | 16792 | 0 | 5289.48 | 0 | 2024-07-20 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109218 | 2024-07-22 | 41899.12 | 1900-01-01 | -36609.64 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-402 (3BHK) Electrical Work (L) | 0.9 | 16792 | 0 | 5289.48 | 0 | 2024-07-20 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109218 | 2024-07-22 | 41899.12 | 1900-01-01 | -36609.64 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-406 (3BHK) Electrical Work (L) | 0.9 | 16792 | 0 | 5289.48 | 0 | 2024-07-20 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109218 | 2024-07-22 | 41899.12 | 1900-01-01 | -36609.64 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-407 (3BHK) Electrical Work (L) | 0.9 | 16792 | 0 | 5289.48 | 0 | 2024-07-20 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109218 | 2024-07-22 | 41899.12 | 1900-01-01 | -36609.64 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-P1 (3BHK) Electrical Work (L) | 0.1 | 16792 | 0 | 587.72 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11281.44 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-P2 (3BHK) Electrical Work (L) | 0.1 | 16792 | 0 | 587.72 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11281.44 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-103 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-104 (2BHK) (Refuge Area) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-105 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-108 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-109 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-203 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-204 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-205 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-208 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-209 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-403 (2BHK) Electrical Work (L) | 0.9 | 13169 | 0 | 4148.235 | 0 | 2024-07-20 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109218 | 2024-07-22 | 41899.12 | 1900-01-01 | -37750.885 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-404 (2BHK) Electrical Work (L) | 0.9 | 13169 | 0 | 4148.235 | 0 | 2024-07-20 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109218 | 2024-07-22 | 41899.12 | 1900-01-01 | -37750.885 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-405 (2BHK) Electrical Work (L) | 0.9 | 13169 | 0 | 4148.235 | 0 | 2024-07-20 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109218 | 2024-07-22 | 41899.12 | 1900-01-01 | -37750.885 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-408 (2BHK) Electrical Work (L) | 0.9 | 13169 | 0 | 4148.235 | 0 | 2024-07-20 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109218 | 2024-07-22 | 41899.12 | 1900-01-01 | -37750.885 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-409 (2BHK) Electrical Work (L) | 0.9 | 13169 | 0 | 4148.235 | 0 | 2024-07-20 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109218 | 2024-07-22 | 41899.12 | 1900-01-01 | -37750.885 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-P3 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-P4 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-P5 (2BHK) Electrical Work (L) | 0.1 | 13169 | 0 | 460.915 | 0 | 2024-07-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109349 | 2024-07-29 | 11869.16 | 1900-01-01 | -11408.245 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Elect Meters UTI | N/C | N/C | ARYA CONSULTANCY | 606 | 2023-11-08 | Electrical Work Project Meter & Permissions | 1093 | 3000 | 0 | 1639500 | 295110 | 2024-07-15 | sanction in Hand | 50 |  | 109077 | 2024-07-15 | 1639500 | 1900-01-01 | 0 | ARYA CONSULTANCY
Int Plumbing PPRC Work | N/C | N/C | PRASNA PLUMBING SERVICE | 608 | 2023-11-08 | Wing-1 Flat No 201 (3BHK) Internal Plumbing (L) | 1 | 5700 | 0 | 5700 | 0 | 2024-07-24 11:36 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 109357 | 2024-07-29 | 51300 | 1900-01-01 | -45600 | PRASNA PLUMBING SERVICE
Int Plumbing PPRC Work | N/C | N/C | PRASNA PLUMBING SERVICE | 608 | 2023-11-08 | Wing-1 Flat No 202 (3BHK) Internal Plumbing (L) | 1 | 5700 | 0 | 5700 | 0 | 2024-07-24 11:36 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 109357 | 2024-07-29 | 51300 | 1900-01-01 | -45600 | PRASNA PLUMBING SERVICE
Int Plumbing PPRC Work | N/C | N/C | PRASNA PLUMBING SERVICE | 608 | 2023-11-08 | Wing-1 Flat No 203 (2BHK) Internal Plumbing (L) | 1 | 5700 | 0 | 5700 | 0 | 2024-07-24 11:36 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 109357 | 2024-07-29 | 51300 | 1900-01-01 | -45600 | PRASNA PLUMBING SERVICE
Int Plumbing PPRC Work | N/C | N/C | PRASNA PLUMBING SERVICE | 608 | 2023-11-08 | Wing-1 Flat No 204 (2BHK) Internal Plumbing (L) | 1 | 5700 | 0 | 5700 | 0 | 2024-07-24 11:36 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 109357 | 2024-07-29 | 51300 | 1900-01-01 | -45600 | PRASNA PLUMBING SERVICE
Int Plumbing PPRC Work | N/C | N/C | PRASNA PLUMBING SERVICE | 608 | 2023-11-08 | Wing-1 Flat No 205 (2BHK) Internal Plumbing (L) | 1 | 5700 | 0 | 5700 | 0 | 2024-07-24 11:36 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 109357 | 2024-07-29 | 51300 | 1900-01-01 | -45600 | PRASNA PLUMBING SERVICE
Int Plumbing PPRC Work | N/C | N/C | PRASNA PLUMBING SERVICE | 608 | 2023-11-08 | Wing-1 Flat No 206 (3BHK) Internal Plumbing (L) | 1 | 5700 | 0 | 5700 | 0 | 2024-07-24 11:36 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 109357 | 2024-07-29 | 51300 | 1900-01-01 | -45600 | PRASNA PLUMBING SERVICE
Int Plumbing PPRC Work | N/C | N/C | PRASNA PLUMBING SERVICE | 608 | 2023-11-08 | Wing-1 Flat No 207 (3BHK) Internal Plumbing (L) | 1 | 5700 | 0 | 5700 | 0 | 2024-07-24 11:36 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 109357 | 2024-07-29 | 51300 | 1900-01-01 | -45600 | PRASNA PLUMBING SERVICE
Int Plumbing PPRC Work | N/C | N/C | PRASNA PLUMBING SERVICE | 608 | 2023-11-08 | Wing-1 Flat No 208 (2BHK) Internal Plumbing (L) | 1 | 5700 | 0 | 5700 | 0 | 2024-07-24 11:36 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 109357 | 2024-07-29 | 51300 | 1900-01-01 | -45600 | PRASNA PLUMBING SERVICE
Int Plumbing PPRC Work | N/C | N/C | PRASNA PLUMBING SERVICE | 608 | 2023-11-08 | Wing-1 Flat No 209 (2BHK) Internal Plumbing (L) | 1 | 5700 | 0 | 5700 | 0 | 2024-07-24 11:36 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 109357 | 2024-07-29 | 51300 | 1900-01-01 | -45600 | PRASNA PLUMBING SERVICE
Site Expenses -SO | N/C | N/C | VIKAS GARADE | 614 | 2023-11-16 | Site Expenses for Hydra & Crane | 0.4924 | 100000 | 0 | 49240 | 0 | 2024-07-12 | Charges for Rent of Hydra, Crane and Pharana etc. | 100 |  | 109314 | 2024-07-25 | 49240 | 1900-01-01 | 0 | MUKUL CRANE SERVICES
Housekeeping-SMS | N/C | N/C | KARAN JAGRAM BALMIKI | 619 | 2023-11-18 | Site Expenses Curing & House Keeping | 1 | 25000 | 0 | 25000 | 0 | 2024-07-02 | Charges for all Labour Camp Cleaning & Housekeeping work for Month JUNE-2024. | 100 |  | 108844 | 2024-07-08 | 25000 | 2024-07-26 12:33 | 0 | KARAN JAGRAM BALMIKI
Total Station Point marking. | N/C | N/C | SP ENGINEERS AND LAND SURVEYORS | 629 | 2023-11-21 | Survey Work | 84 | 100 | 0 | 8400 | 1512 | 2024-07-26 | Charges for Total Station Point marking for Development work at Non Tower Area. | 100 |  | 109362 | 2024-07-29 | 29900 | 1900-01-01 | -21500 | SP ENGINEERS AND LAND SURVEYORS
Visiting Charges-AIE | N/C | N/C | SP ENGINEERS AND LAND SURVEYORS | 629 | 2023-11-21 | Survey Work | 1 | 8000 | 0 | 8000 | 1440 | 2024-07-26 | Charges for DGPS Land Survey (Tree Survey) Visit . | 100 |  | 109362 | 2024-07-29 | 29900 | 1900-01-01 | -21900 | SP ENGINEERS AND LAND SURVEYORS
Visiting Charges-AIE | N/C | N/C | SP ENGINEERS AND LAND SURVEYORS | 629 | 2023-11-21 | Survey Work | 3 | 4500 | 0 | 13500 | 2430 | 2024-07-26 | Charges for Level for Excavation work visit & Report given . | 100 |  | 109362 | 2024-07-29 | 29900 | 1900-01-01 | -16400 | SP ENGINEERS AND LAND SURVEYORS
Miscellaneous Expenses. - SO | N/C | N/C | VITHAL DHARMA KAMBLE | 632 | 2023-11-22 | Site Staff Misc. Expanses | 0.8033 | 15000 | 0 | 12049.5 | 0 | 2024-07-12 | Miscellaneous Site Expenses for Month APR-2024. | 100 |  | 109010 | 2024-07-15 | 25498.5 | 1900-01-01 | -13449 | VIKAS GARADE
Miscellaneous Expenses. - SO | N/C | N/C | VITHAL DHARMA KAMBLE | 632 | 2023-11-22 | Site Staff Misc. Expanses | 0.8966 | 15000 | 0 | 13449 | 0 | 2024-07-12 | Miscellaneous Site Expenses for Month MAY-2024. | 100 |  | 109010 | 2024-07-15 | 25498.5 | 1900-01-01 | -12049.5 | VIKAS GARADE
RCC Work - Mkt | N/C | N/C | SAIRAJ CONSTRUCTION | 641 | 2023-11-30 | NTA Substructure (L) RCC Lab Parking,soling,PB,PCC,Ftng,Colu | 1236.9 | 60 | 0 | 74214 | 13358.52 | 2024-07-13 | Labour Charges for Non tower area Substructre RCC Work inluding,PCC,Footing,Coloumn,Plinth beam,Soling,PCC Work and all work up to Grid Slab etc. | 100 |  | 109014 | 2024-07-15 | 74214 | 1900-01-01 | 0 | A K CONSTRUCTION
RCC Work - Mkt | N/C | N/C | SAIRAJ CONSTRUCTION | 641 | 2023-11-30 | NTA Substructure (L) RCC Lab Parking,soling,PB,PCC,Ftng,Colu | 6400.929 | 60 | 0 | 384055.74 | 69130.04 | 2024-07-16 | Labour Charges for Non tower area Substructre RCC Work inluding,PCC,Footing,Coloumn,Plinth beam,Soling,PCC Work and all work up to Grid Slab etc. | 100 |  | 109223 | 2024-07-22 | 384055.74 | 1900-01-01 | 0 | SAIRAJ CONSTRUCTION
Panel Fixing (L) | N/C | N/C | LAXMI ELECTRICALS (Prop.Mayur Raskar) | 650 | 2023-12-09 | Wing.1 Industrial Panel Fixing | 3 | 600 | 0 | 1800 | 324 | 2024-07-30 | Labour charges for Industrial Panal Fixing work including Laying of 4C x 10sqmm Flexible cable and End Termination for Wing-1 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Lumpsum work- DCW | N/C | N/C | LAXMI ELECTRICALS (Prop.Mayur Raskar) | 650 | 2023-12-09 | Wing.1 Industrial Panel Fixing | 1 | 2000 | 0 | 2000 | 360 | 2024-07-30 | Labour charges for Cable Laying work 4C x 10sqmm from Meter Room to Mhada 1st Floor for Wing-1 Industrial Panel Fixing work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 652 | 2023-12-09 | Goel House Electricity expenses | 1.0555 | 75000 | -2.5 | 79162.5 | 0 | 2024-07-08 | Charges for Electricity Bills for Goel House for Year 2023-24 | 100 |  | 108923 | 2024-07-08 | 79160 | 2024-07-08 18:02 | 2.5 | MSEDCL
Hoarding display charges | N/C | N/C | SHUBHANGI ADVERTISING | 671 | 2023-12-16 | PRINTING PRINTING-NO.-(NA) | 12 | 50000 | 0 | 49998 | 8999.64 | 2024-07-05 | 6) DURATION 20/05/2023 TO 19/06/2024 | 8.333 |  | 108800 | 2024-07-05 | 49998 | 2024-07-08 11:35 | 0 | SHUBHANGI ADVERTISING
Hoarding display charges | N/C | N/C | SHUBHANGI ADVERTISING | 671 | 2023-12-16 | PRINTING PRINTING-NO.-(NA) | 12 | 50000 | 0 | 49998 | 8999.64 | 2024-07-22 | 7)DURATION 20/06/2023 TO 19/07/2024 | 8.333 | WAKAD - HINJEWADI ROAD NR TVS SHOWROOM, WAKADCHOWK, WAKAD FACING AUNDH DURATION 20/06/2024 TO 19/07/2024 . | 109280 | 2024-07-22 | 49998 | 2024-07-25 13:28 | 0 | SHUBHANGI ADVERTISING
Rental Charges. | N/C | N/C | NITIN D PARDESHI | 675 | 2023-12-19 | Photocopy-Xerox Machine Rental Charges. | 7.3099 | 15000 | -0.01 | 9137.0095 | 1644.66 | 2024-07-03 | Rental Charges for JUNE 2024 | 8.333 |  | 108766 | 2024-07-03 | 9137 | 2024-07-04 10:59 | 0.009505 | CANAN ENTERPRISES
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 677 | 2023-12-19 | Site Electricity expenses | 1.0125 | 350000 | -15 | 354375 | 0 | 2024-07-11 | Charges for Electricity Bills from DEC-2023 to NOV-2024 | 100 | For the month June 2024 | 108985 | 2024-07-11 | 354360 | 2024-07-11 11:07 | 15 | MSEDCL
Tea Expenses-SO | N/C | N/C | ANIL SHRIHARI MEDHAKE | 685 | 2023-12-30 | Site Expenses | 0.9346 | 9000 | 0 | 8411.4 | 0 | 2024-07-02 | Tea Expenses for the month of JUNE-2024 | 100 |  | 108850 | 2024-07-08 | 8411.4 | 2024-07-26 12:34 | 0 | VIKAS GARADE
Housekeeping (M) | N/C | N/C | VIKAS GARADE | 698 | 2024-01-18 | Sales office & Sample flat Housekeeping Material | 1 | 2000 | 0 | 2000 | 0 | 2024-07-02 | Charges for Housekeeping material for the month of JUNE-2024 | 100 |  | 108841 | 2024-07-08 | 2000 | 2024-07-26 12:33 | 0 | VIKAS GARADE
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | RED TREE DESIGN STUDIO PRIVATE LIMITED | 734 | 2024-04-02 | ONLINE / DIGITAL Social / Digital Activity | 12 | 300000 | 0 | 299999.88 | 53999.98 | 2024-07-05 | 3) MONTH OF JUNE 2024 | 8.3333 | GOEL GANGA GROUP + REAL RICH - ONLINE SOCAIL + DIGITAL MEDIA MONTHLY BASIS RETAINERSHIP CHARGES @ 3,00,000/- + TAX PER MONTH . | 108805 | 2024-07-05 | 299999.88 | 2024-07-08 11:35 | 0 | RED TREE DESIGN STUDIO PRIVATE LIMITED
Pile Breaking on R.ft Basis | N/C | N/C | BASAV ENTERPRISES | 738 | 2024-04-10 | Non Tower Area Pile MS Casing Removing | 17.3 | 350 | 0 | 6055 | 0 | 2024-07-22 | Charges for Pile breaking with breaker for Parking at Non Tower Area. | 100 |  | 109220 | 2024-07-22 | 14255 | 1900-01-01 | -8200 | BASAV ENTERPRISES
Pile Casing Cutting - No. | N/C | N/C | BASAV ENTERPRISES | 738 | 2024-04-10 | Non Tower Area Pile MS Casing Removing | 7 | 800 | 0 | 5600 | 0 | 2024-07-22 | Charges for MS Pile casing removing by Gas Cutter for Parking at Non Tower Area. | 100 |  | 109220 | 2024-07-22 | 14255 | 1900-01-01 | -8655 | BASAV ENTERPRISES
Breaking Work - Dld | N/C | N/C | BASAV ENTERPRISES | 738 | 2024-04-10 | Site Infra Labour Camp Toilet Base Breaking | 2 | 1300 | 0 | 2600 | 0 | 2024-07-22 | Charges for Toilet- Concrete base breaking work For Parking Toilets at Non Tower Area. | 100 |  | 109220 | 2024-07-22 | 14255 | 1900-01-01 | -11655 | BASAV ENTERPRISES
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | ANIMOTIONSZ | 746 | 2024-04-22 | ONLINE / DIGITAL Social / Digital Activity | 3 | 15000 | 0 | 15000.03 | 2700 | 2024-07-24 | 3) JUNE 2024 | 33.3334 | GANGA ASMI- MANAGING THE CAMPAIGN FOR INCREASING THE ROI + CREATION OF ADS + LANDING PAGE + FACEBOOK PAIND CAMPAING = MONITORING CHARGES 15,000/-RS PER MONTH + TAX PERIOD JUNE 2024. | 109312 | 2024-07-24 | 15000.03 | 2024-07-25 13:27 | 0 | ANIMOTIONSZ
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | ANIMOTIONSZ | 747 | 2024-04-22 | ONLINE / DIGITAL Social / Digital Activity | 3 | 7500 | 0 | 7500.015 | 1350 | 2024-07-24 | 3) JUNE 2024 | 33.3334 | WTC NAGPUR- MANAGING THE CAMPAIGN FOR INCREASING THE ROI + CREATION OF ADS + LANDING PAGE + FACEBOOK PAIND CAMPAING = MONITORING CHARGES 7,500/-RS PER MONTH + TAX PERIOD JUNE 2024. | 109313 | 2024-07-24 | 7500.02 | 2024-07-25 13:27 | -0.005 | ANIMOTIONSZ
Vastu Consultancy | N/C | N/C | SACHIN SHANTARAM SONAR | 754 | 2024-05-03 | Vastu Consultancy Visit Charges | 1 | 15000 | 0 | 15000 | 0 | 2024-07-09 | Charges for Head office Vastu Visit & Further Planning. | 100 |  | 108964 | 2024-07-09 | 15000 | 2024-07-09 16:00 | 0 | SACHIN SHANTARAM SONAR
Fabrication Work Fixing | N/C | N/C | SHREE SAI SAMARTH ENTERPRISES | 755 | 2024-05-04 | New Labour Camp & Development Fabrication Work | 550 | 14 | 0 | 7700 | 0 | 2024-07-26 | Labour Charges for making fabricated shed for domestic & drinking water tank,Fixing of Fabricated gate for meter room,repairing miscellaneous leakage at new labour camp,Partition making for ladies bath and toilet at new labour camp. | 100 |  | 109364 | 2024-07-29 | 12950 | 1900-01-01 | -5250 | SHREE SAI SAMARTH ENTERPRISES
Fabrication work Removing Sq.Ft | N/C | N/C | SHREE SAI SAMARTH ENTERPRISES | 755 | 2024-05-04 | New Labour Camp & Development Fabrication Work | 1050 | 5 | 0 | 5250 | 0 | 2024-07-26 | Labour Charges for Removing of Fabricated shed for NTA Slab working,removing of ladies bath shed for development work activity,removing of partition fabricated GI Sheetsm, MS Pipe ,angles and channels,Removing fabricated rooms shed. | 100 |  | 109364 | 2024-07-29 | 12950 | 1900-01-01 | -7700 | SHREE SAI SAMARTH ENTERPRISES
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 769 | 2024-05-09 | ONLINE / DIGITAL Social / Digital Activity | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2024-07-05 | 3) JUNE 2024 | 8.3333 | MONTHLY MARKETING / MARKETING SOCIAL / DIGITAL MONTHLY RETAINERSHIP CHARGES @ 40,000/-RS + TAX PER MONTH | 108801 | 2024-07-05 | 39999.84 | 2024-07-08 11:35 | 0 | GOOD OLD DELIGHT
Visiting Charges-AIE | N/C | N/C | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD. | 778 | 2024-05-24 | Pile Integrity Test | 1 | 2250 | 0 | 2250 | 405 | 2024-07-26 | Site Visit charges for Pile Integrity test for Non Tower area. | 100 |  | 109369 | 2024-07-29 | 2250 | 1900-01-01 | 0 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Integrity Test | N/C | N/C | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD. | 778 | 2024-05-24 | Pile Integrity Test | 7 | 600 | 0 | 4200 | 756 | 2024-07-16 | Charges for Pile Integrity Test-Low strain for Non Tower Area. | 100 |  | 109222 | 2024-07-22 | 4200 | 1900-01-01 | 0 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Labour Lumsum | N/C | N/C | SAIRAJ CONSTRUCTION | 793 | 2024-06-28 | New Labour Camp Bathroom & Toilet PCC Work | 1 | 18000 | 0 | 18000 | 3240 | 2024-07-26 | Charges for Labour camp PCC work for Bathroom, Toilet & Common Area including Shuttering & Concreting. | 100 |  | 109367 | 2024-07-29 | 18000 | 1900-01-01 | 0 | SAIRAJ CONSTRUCTION
Rental Charges - So | N/C | N/C | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | 84 | 2021-02-26 | Sales Office - AC Rental charges | 1 | 60000 | 0 | 60000 | 10800 | 2024-07-02 | AC Rental Charges for the Month of JUNE-2024 | 100 |  | 108829 | 2024-07-08 | 60000 | 1900-01-01 | 0 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD
Excavation By Bucket (Shifting Inside) | N/C | N/C | DRAUPADA EARTHMOVERS | 97 | 2021-03-20 | Wing-3 Substructure Excavation Work | 1451.89 | 60 | 0 | 87113.4 | 15680.42 | 2024-07-23 | Excavation work by Bucket & Shifting Inside the Plot. Excavation in earth, soils of all types, sand, gravel & soft murum up to required depth including removing the excavated material with all tool, machinery & Equipments. Ensuring all required safety. | 100 |  | 109346 | 2024-07-29 | 87113.4 | 1900-01-01 | 0 | DRAUPADA EARTHMOVERS