## Work_Completion_Browse638581128
Work Completion Browse
Project : WTC NAGPUR
From Date : 01/07/2024 To date: 01/07/2024
Page 1 of 1
Total Records: 82 Records 1 to 82
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Rental Charges. | N/C | N/C | JP OFFICE EQUIPMENTS | 1140 | 2020-08-25 | Xerox Maching Rental Charges | 1 | 8000 | 0 | 8000 | 1440 | 2024-07-08 | Photocopy Machine Rental Charges for MAY-2024 (Rate include Upto 10000 No of Print after that 0.4 Rs/Print) | 100 |  | 108921 | 2024-07-08 | 10203.2 | 2024-07-15 11:33 | -2203.2 | JP OFFICE EQUIPMENTS
Rental Charges. | N/C | N/C | JP OFFICE EQUIPMENTS | 1140 | 2020-08-25 | Xerox Maching Rental Charges | 1 | 8000 | 0 | 8000 | 1440 | 2024-07-20 | Photocopy Machine Rental Charges for JUNE-2024 (Rate include Upto 10000 No of Print after that 0.4 Rs/Print) | 100 |  | 109266 | 2024-07-22 | 9390 | 1900-01-01 | -1390 | JP OFFICE EQUIPMENTS
Xerox Printout | N/C | N/C | JP OFFICE EQUIPMENTS | 1140 | 2020-08-25 | Xerox Printouts | 3683 | 0.4 | 0 | 1473.2 | 265.18 | 2024-07-08 | Extra Printout Charges for AUG-2023 to JULY-2026 (if limit of 10000 number of Print per month exceed) | 100 |  | 108921 | 2024-07-08 | 10203.2 | 2024-07-15 11:33 | -8730 | JP OFFICE EQUIPMENTS
Colour Printout | N/C | N/C | JP OFFICE EQUIPMENTS | 1140 | 2020-08-25 | Xerox Printouts | 146 | 5 | 0 | 730 | 131.4 | 2024-07-08 | Charges for Colour Printout from AUG-2023 to JULY-2026 | 100 |  | 108921 | 2024-07-08 | 10203.2 | 2024-07-15 11:33 | -9473.2 | JP OFFICE EQUIPMENTS
Colour Printout | N/C | N/C | JP OFFICE EQUIPMENTS | 1140 | 2020-08-25 | Xerox Printouts | 278 | 5 | 0 | 1390 | 250.2 | 2024-07-20 | Charges for Colour Printout from AUG-2023 to JULY-2026 | 100 |  | 109266 | 2024-07-22 | 9390 | 1900-01-01 | -8000 | JP OFFICE EQUIPMENTS
Rental Charges - So | N/C | N/C | SS ENTERPRISES - (PROP. SARANG DEEPAK FADNAVIS) | 1142 | 2020-09-11 | Monthly charges for canteen materal | 1 | 2500 | 0 | 2500 | 450 | 2024-07-08 | Machine Rental Charges for the month of JUNE-2024 | 100 |  | 108924 | 2024-07-08 | 2500 | 2024-07-15 11:28 | 0 | SS ENTERPRISES - (PROP. SARANG DEEPAK FADNAVIS)
Canteen Material | N/C | N/C | SS ENTERPRISES - (PROP. SARANG DEEPAK FADNAVIS) | 1142 | 2020-09-11 | Monthly charges for canteen materal | 0.094 | 10000 | 0 | 940 | 47 | 2024-07-08 | Canteen Material Expenses for the month of JUNE-2024 | 100 |  | 109000 | 2024-07-13 | 940 | 2024-07-15 11:29 | 0 | SS ENTERPRISES - (PROP. SARANG DEEPAK FADNAVIS)
Pest Control | N/C | N/C | PEST CONTROL INITIAL | 1204 | 2020-12-15 | Pest control For technical office part A LG & GF | 1 | 12000 | 0 | 12000 | 2160 | 2024-07-02 | Charges for Sales office,Lobby 6,Kalibar,Technical office,Store & Labour Camp Pest Control for JUNE-2024 (8 Visit in Month) | 100 |  | 108757 | 2024-07-02 | 12000 | 1900-01-01 | 0 | PEST CONTROL INITIAL
Security Guard-SMS | N/C | N/C | BABA | 1221 | 2021-01-20 | Security Service - (Jan24 - Dec24) | 356 | 500 | 0 | 178000 | 31230 | 2024-07-01 | Charges for Security Guard Services for the month of JUNE-2024 (14 Security Guard for L.G., 1st, 2nd, 3rd Floor) | 100 |  | 108740 | 2024-07-02 | 192166.5 | 2024-07-15 11:33 | -14166.5 | BABA
Security Supervisor-SMS | N/C | N/C | BABA | 1221 | 2021-01-20 | Security Service - (Jan24 - Dec24) | 25 | 566.66 | 0 | 14166.5 | 2549.98 | 2024-07-01 | Charges for Security Supervisor for the month of JUNE-2024 | 100 |  | 108740 | 2024-07-02 | 192166.5 | 2024-07-15 11:33 | -178000 | BABA
Supervision Charges | N/C | N/C | SPICK AND SPAN SERVICES | 1425 | 2021-08-12 | Housekeeping work | 0.9333 | 18000 | 0 | 16799.4 | 3023.9 | 2024-07-02 | Charges for Supervision of Housekeeping work for the Month of JUNE-2024 | 100 |  | 108786 | 2024-07-03 | 16799.4 | 2024-07-15 11:31 | 0 | SPICK AND SPAN SERVICES
Rent for Guest House- AIE | N/C | N/C | MILINDKUMAR WAMANRAO SALWE | 1556 | 2022-02-12 | Rent for Guest House | 12 | 40793 | 0 | 40792.8368 | 0 | 2024-07-01 | JULY-2024 | 8.3333 |  | 108667 | 2024-07-01 | 40792.84 | 2024-07-01 15:15 | -0.003172 | MILINDKUMAR WAMANRAO SALWE
Exh pipe, Cables, Alternator, Junction box as per BOQ | N/C | N/C | GENPOWER SYSTEMS | 1582 | 2022-03-10 | Supply & Installation of DG Set | 0.0332 | 1515660 | 30.09 | 50319.912 | 9063 | 2024-07-02 | Supply of Material such as Exh. pipe, cable, alternator junction Box complete as per BOQ. | 100 |  | 108754 | 2024-07-02 | 50350 | 2024-07-15 15:07 | -30.088 | GENPOWER SYSTEMS
Exh pipe, Cables, Alternator, Junction box as per BOQ | N/C | N/C | GENPOWER SYSTEMS | 1582 | 2022-03-10 | Supply & Installation of DG Set | 0.0409 | 1515660 | 59.51 | 61990.494 | 11169 | 2024-07-02 | Supply of Material such as Exh. pipe, cable, alternator junction Box complete as per BOQ. | 100 |  | 108755 | 2024-07-02 | 62050 | 2024-07-15 15:09 | -59.506 | GENPOWER SYSTEMS
Exh pipe, Cables, Alternator, Junction box as per BOQ | N/C | N/C | GENPOWER SYSTEMS | 1582 | 2022-03-10 | Supply & Installation of DG Set | 0.0518 | 1515660 | 0 | 78511.188 | 14132.02 | 2024-07-08 | Supply of Material such as Exh. pipe, cable, alternator junction Box complete as per BOQ. | 100 |  | 108967 | 2024-07-09 | 78511.19 | 1900-01-01 | -0.002 | GENPOWER SYSTEMS
MS Piping (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1609 | 2022-04-07 | First Floor HVAC Work | 12 | 1020 | 0 | 2448 | 440.64 | 2024-07-31 | Advance | 20 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1609 | 2022-04-07 | First Floor HVAC Work | 12 | 1020 | 0 | 8568 | 1542.24 | 2024-07-31 | Before Material Dispatch | 70 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 1 | 4012.89 | 0 | 802.578 | 144.46 | 2024-07-31 | Advance | 20 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 1 | 4012.89 | 0 | 2809.023 | 505.62 | 2024-07-31 | Before Material Dispatch | 70 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 4 | 3506.55 | 0 | 2805.24 | 504.94 | 2024-07-31 | Advance | 20 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 4 | 3506.55 | 0 | 9818.34 | 1767.3 | 2024-07-31 | Before Material Dispatch | 70 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 12 | 1881.8 | 0 | 4516.32 | 812.94 | 2024-07-31 | Advance | 20 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 12 | 1881.8 | 0 | 15807.12 | 2845.28 | 2024-07-31 | Before Material Dispatch | 70 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | NEPTUNE ENGINEERS PRIVATE LIMITED
Ball Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 9 | 1577.22 | 0 | 2838.996 | 511.02 | 2024-07-31 | Advance | 20 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | NEPTUNE ENGINEERS PRIVATE LIMITED
Ball Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 9 | 1577.22 | 0 | 9936.486 | 1788.56 | 2024-07-31 | Before Material Dispatch | 70 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | NEPTUNE ENGINEERS PRIVATE LIMITED
Cleaning work- SO. | N/C | N/C | RIYA SUNIL MAHATO | 1668 | 2022-07-26 | Labour Camp Cleaning Work | 0.9667 | 3000 | 0 | 2900.1 | 0 | 2024-07-01 | Charges for Basement Labour Camp cleaning & Garbage collection for the month of JUNE-2024 | 100 |  | 108744 | 2024-07-02 | 2900.1 | 2024-07-09 19:35 | 0 | RIYA SUNIL MAHATO
MS Channel. (L) | N/C | N/C | GENPOWER SYSTEMS | 1717 | 2023-01-02 | Exhaust Stack for DG set | 4500 | 28 | 0 | 126000 | 22680 | 2024-07-08 | Labour Charges for- MS Channels/Angles for 30meter Self Supporting Exhaust stack for 2250 KVA DG Set. | 100 |  | 108920 | 2024-07-08 | 148500 | 1900-01-01 | -22500 | GENPOWER SYSTEMS
Crane Charges - | N/C | N/C | GENPOWER SYSTEMS | 1717 | 2023-01-02 | Exhaust Stack for DG set | 1 | 7500 | 0 | 7500 | 1350 | 2024-07-08 | Labour Charges for-Unloading of material at Site for 30meter Self Supporting Exhaust stack for 2250 KVA DG Set. | 100 |  | 108920 | 2024-07-08 | 148500 | 1900-01-01 | -141000 | GENPOWER SYSTEMS
Transport Charges | N/C | N/C | GENPOWER SYSTEMS | 1717 | 2023-01-02 | Exhaust Stack for DG set | 1 | 15000 | 0 | 15000 | 2700 | 2024-07-08 | Transport Charges for Material | 100 |  | 108920 | 2024-07-08 | 148500 | 1900-01-01 | -133500 | GENPOWER SYSTEMS
Site Expenses -SO | N/C | N/C | ZAK BUSINESS SERVICES PVT LTD | 1720 | 2023-01-04 | Site Expenses.. | 12 | 11250 | 0 | 11249.955 | 0 | 2024-07-09 | JULY-2024 | 8.3333 |  | 108949 | 2024-07-09 | 11249.96 | 2024-07-09 14:34 | -0.005 | ZAK BUSINESS SERVICES PVT LTD
Toilet Cleaning- S.O. | N/C | N/C | RIYA SUNIL MAHATO | 1723 | 2023-01-10 | Labour Camp Toilet Cleaning | 0.966 | 3500 | 0 | 3381 | 0 | 2024-07-01 | Charges for Basement Labour Camp Toilet cleaning work for th e month of JUNE-2024 | 100 |  | 108743 | 2024-07-02 | 3381 | 2024-07-09 19:35 | 0 | RIYA SUNIL MAHATO
Security Guard-SMS | N/C | N/C | ALLEVIATE MANAGEMENT SERVICES PRIVATE LIMITED | 1724 | 2023-01-10 | Security Service . (Jan 24 . Dec 24) | 228 | 466.66 | 0 | 106398.48 | 19151.72 | 2024-07-01 | Charges for Security Guard Services for the month of JUNE-2024 (14 Security Guard at Day & 14 Security Guard at Night) | 100 |  | 108973 | 2024-07-09 | 106398.48 | 2024-07-26 12:32 | 0 | ALLEVIATE MANAGEMENT SERVICES PRIVATE LIMITED
Housekeeping Work- | N/C | N/C | SPICK AND SPAN SERVICES | 1728 | 2023-01-13 | New Sales Office Housekeeping Work | 90 | 508.33 | 0 | 45749.7 | 8234.94 | 2024-07-02 | Charges for manpower for Housekeeping work (3 M/C) for the month of JUNE-2024 | 100 |  | 108780 | 2024-07-03 | 45749.7 | 2024-07-15 11:31 | 0 | SPICK AND SPAN SERVICES
Housekeeping Work- | N/C | N/C | SPICK AND SPAN SERVICES | 1729 | 2023-01-13 | Housekeeping - Ground Floor & First Floor | 58 | 508.33 | 0 | 29483.14 | 5306.96 | 2024-07-02 | Charges for manpower for Housekeeping work (6 M/C) for the month of JUNE-2024 | 100 |  | 108788 | 2024-07-03 | 82857.79 | 2024-07-15 11:30 | -53374.65 | SPICK AND SPAN SERVICES
Housekeeping Work- | N/C | N/C | SPICK AND SPAN SERVICES | 1729 | 2023-01-13 | Housekeeping - Ground Floor & First Floor | 105 | 508.33 | 0 | 53374.65 | 9607.44 | 2024-07-02 | Charges for manpower for Housekeeping work (6 M/C) for the month of JUNE-2024 | 100 |  | 108788 | 2024-07-03 | 82857.79 | 2024-07-15 11:30 | -29483.14 | SPICK AND SPAN SERVICES
Cleaning work.-SO | N/C | N/C | SPICK AND SPAN SERVICES | 1730 | 2023-01-13 | LG-Common toilet cleaning at part A & C - 1 No. | 116 | 508.333 | 0 | 58966.628 | 10614 | 2024-07-02 | Charges for Common toilet and shops Cleaning work(4 M/C) at part C LG Floor for the month of JUNE-2024. | 100 |  | 108784 | 2024-07-03 | 58966.63 | 1900-01-01 | -0.002 | SPICK AND SPAN SERVICES
Cleaning work.-SO | N/C | N/C | SPICK AND SPAN SERVICES | 1731 | 2023-01-14 | Part C Mezzanine Floor common toilet housekeeping work | 116 | 508.333 | 0 | 58966.628 | 10614 | 2024-07-02 | Charges for Basement Labour Camp Toilet cleaning work for th e month of JUNE-2024 | 100 |  | 108782 | 2024-07-03 | 58966.63 | 2024-07-15 11:31 | -0.002 | SPICK AND SPAN SERVICES
Housekeeping Work- | N/C | N/C | SPICK AND SPAN SERVICES | 1732 | 2023-01-14 | Housekeeping work | 90 | 508.333 | 0 | 45749.97 | 8235 | 2024-07-02 | Charges for Housekeeping work for site office for the month of JUNE-2024 | 100 |  | 108779 | 2024-07-03 | 45749.97 | 2024-07-15 11:30 | 0 | SPICK AND SPAN SERVICES
Food Expenses. | N/C | N/C | OAM INDUSTRIES INDIA PRIVATE LIMITED | 1735 | 2023-01-16 | Admin Expense - Milk & Food Charges | 0.5535 | 30000 | 0 | 16605 | 0 | 2024-07-13 | Milk and Food supply for Guest of sales office & Company Employees for month of APRIL -2024 | 100 |  | 109002 | 2024-07-13 | 22773 | 2024-07-15 15:26 | -6168 | DHARMA DELIGHTS
Food Expenses. | N/C | N/C | OAM INDUSTRIES INDIA PRIVATE LIMITED | 1735 | 2023-01-16 | Admin Expense - Milk & Food Charges | 0.2056 | 30000 | 0 | 6168 | 0 | 2024-07-13 | Milk and Food supply for Guest of sales office & Company Employees for month of JUNE -2024 | 100 |  | 109002 | 2024-07-13 | 22773 | 2024-07-15 15:26 | -16605 | DHARMA DELIGHTS
Food Expenses. | N/C | N/C | OAM INDUSTRIES INDIA PRIVATE LIMITED | 1735 | 2023-01-16 | Admin Expense - Milk & Food Charges | 0.3736 | 30000 | 0 | 11208 | 0 | 2024-07-13 | Milk and Food supply for Guest of sales office & Company Employees for month of JULY -2024 | 100 |  | 109086 | 2024-07-15 | 11208 | 1900-01-01 | 0 | OAM INDUSTRIES INDIA PRIVATE LIMITED
Food Expenses. | N/C | N/C | OAM INDUSTRIES INDIA PRIVATE LIMITED | 1735 | 2023-01-16 | Admin Expense - Milk & Food Charges | 0.3155 | 30000 | 0 | 9465 | 0 | 2024-07-22 | Milk and Food supply for Guest of sales office & Company Employees for month of JULY -2024 | 100 |  | 109274 | 2024-07-22 | 9465 | 1900-01-01 | 0 | DHARMA DELIGHTS
Admin Expenses | N/C | N/C | DARVEKAR GENERAL STORES | 1741 | 2023-01-21 | Admin Expense - Material Charges | 0.3798 | 7000 | 0 | 2658.6 | 478.54 | 2024-07-08 | Material Supply for Sales Office (Paper cup and Coffee Powder ) for the month of JUNE-2024. | 100 |  | 108918 | 2024-07-08 | 2658.6 | 2024-07-15 11:33 | 0 | DARVEKAR GENERAL STORES
Admin Expenses | N/C | N/C | DARVEKAR GENERAL STORES | 1741 | 2023-01-21 | Admin Expense - Material Charges | 0.5974 | 7000 | 0 | 4181.8 | 0 | 2024-07-13 | Material Supply for Sales Office (Paper cup and Coffee Powder ) for the month of JULY-2024. | 100 |  | 109291 | 2024-07-23 | 4181.8 | 1900-01-01 | 0 | DARVEKAR GENERAL STORES
Drawing Printing Charges | N/C | N/C | TRUE COPY CENTRE PRIVATE LIMITED | 1754 | 2023-01-31 | Admin Expense - Drawing Printing | 0.04 | 10000 | 0 | 400 | 72 | 2024-07-08 | Charges for Auto CAD Drawing printing A1, A2 size pages for the Month of JUNE-2024 | 100 |  | 108917 | 2024-07-08 | 400 | 2024-07-15 11:33 | 0 | TRUE COPY CENTRE PRIVATE LIMITED
Design work. | N/C | N/C | SHRI SATYA STONE ARTS | 1807 | 2023-03-14 | Heritage Gate Beautification work | 40 | 500 | 0 | 20000 | 0 | 2024-07-02 | Labour Charges for Design work for elephant,tiger,hourse etc. work for Heritage Gate beautification. | 100 |  | 108748 | 2024-07-02 | 393080 | 2024-07-15 11:34 | -373080 | SHRI SATYA STONE ARTS
Grinding work- BC | N/C | N/C | SHRI SATYA STONE ARTS | 1807 | 2023-03-14 | Heritage Gate Beautification work | 397 | 40 | 0 | 15880 | 0 | 2024-07-02 | Labour Charges for Grinding finishing work for Heritage Gate beautification. | 100 |  | 108748 | 2024-07-02 | 393080 | 2024-07-15 11:34 | -377200 | SHRI SATYA STONE ARTS
Jaisalmer Stone Fixing | N/C | N/C | SHRI SATYA STONE ARTS | 1807 | 2023-03-14 | Heritage Gate Beautification work | 1200 | 50 | 0 | 60000 | 0 | 2024-07-02 | Labour Charges for Jaisalmer Stone 18mm fixing work for Heritage Gate beautification. | 100 |  | 108748 | 2024-07-02 | 393080 | 2024-07-15 11:34 | -333080 | SHRI SATYA STONE ARTS
Jali fixing (M+L) | N/C | N/C | SHRI SATYA STONE ARTS | 1807 | 2023-03-14 | Heritage Gate Beautification work | 50 | 400 | 0 | 20000 | 0 | 2024-07-02 | Labour Charges for Jali Fixing work for Heritage Gate beautification. | 100 |  | 108748 | 2024-07-02 | 393080 | 2024-07-15 11:34 | -373080 | SHRI SATYA STONE ARTS
Jali Pole (M+L) | N/C | N/C | SHRI SATYA STONE ARTS | 1807 | 2023-03-14 | Heritage Gate Beautification work | 4 | 500 | 0 | 2000 | 0 | 2024-07-02 | Charges for Jali Pole work for Heritage Gate beautification. | 100 |  | 108748 | 2024-07-02 | 393080 | 2024-07-15 11:34 | -391080 | SHRI SATYA STONE ARTS
Kerb Stone (M+L) | N/C | N/C | SHRI SATYA STONE ARTS | 1807 | 2023-03-14 | Heritage Gate Beautification work | 350 | 350 | 0 | 122500 | 0 | 2024-07-02 | Charges for Kerb Stone fixing work for Heritage Gate beautification. | 100 |  | 108748 | 2024-07-02 | 393080 | 2024-07-15 11:34 | -270580 | SHRI SATYA STONE ARTS
Putty Filling (M+L) | N/C | N/C | SHRI SATYA STONE ARTS | 1807 | 2023-03-14 | Heritage Gate Beautification work | 300 | 200 | 0 | 60000 | 0 | 2024-07-02 | Charges for Putty Filling work for Heritage Gate beautification. | 100 |  | 108748 | 2024-07-02 | 393080 | 2024-07-15 11:34 | -333080 | SHRI SATYA STONE ARTS
Stone Cladding (M+L) | N/C | N/C | SHRI SATYA STONE ARTS | 1807 | 2023-03-14 | Heritage Gate Beautification work | 50 | 350 | 0 | 17500 | 0 | 2024-07-02 | Charges for Stone Cladding work for Heritage Gate beautification. | 100 |  | 108748 | 2024-07-02 | 393080 | 2024-07-15 11:34 | -375580 | SHRI SATYA STONE ARTS
stone Hand Railing (M+L) | N/C | N/C | SHRI SATYA STONE ARTS | 1807 | 2023-03-14 | Heritage Gate Beautification work | 14 | 800 | 0 | 11200 | 0 | 2024-07-02 | Charges for Stone Hand Railing work for Heritage Gate beautification. | 100 |  | 108748 | 2024-07-02 | 393080 | 2024-07-15 11:34 | -381880 | SHRI SATYA STONE ARTS
Stone Jali (M+L) | N/C | N/C | SHRI SATYA STONE ARTS | 1807 | 2023-03-14 | Heritage Gate Beautification work | 80 | 800 | 0 | 64000 | 0 | 2024-07-02 | Charges for Stone Jali (Frame) work for Heritage Gate beautification. | 100 |  | 108748 | 2024-07-02 | 393080 | 2024-07-15 11:34 | -329080 | SHRI SATYA STONE ARTS
DumperTrips | N/C | N/C | PVR TRADERS AND SERVICES | 1914 | 2023-08-09 | Dumper on trips for shifting of debris out of premises at LG | 13.5 | 500 | 0 | 6750 | 1215 | 2024-07-01 | Charges for Debris removing from site (Gypsum, blockwork, etc) & shifting it outside of premises for month of JUNE-2024 | 100 |  | 108745 | 2024-07-02 | 15750 | 1900-01-01 | -9000 | PVR TRADERS AND SERVICES
Dumper 6 Brass with JCB | N/C | N/C | PVR TRADERS AND SERVICES | 1914 | 2023-08-09 | Dumper on trips for shifting of debris out of premises at LG | 3 | 3000 | 0 | 9000 | 1620 | 2024-07-01 | Charges for Tipper 4 Brass with JCB Debris Removing from site (Gypsum, Blockwork, etc) & Shifting it outside of Premises for month of JUNE-2024 | 100 |  | 108745 | 2024-07-02 | 15750 | 1900-01-01 | -6750 | PVR TRADERS AND SERVICES
Professional Fees | N/C | N/C | SHAH KHANDELWAL JAIN AND ASSOCIATES | 1935 | 2023-09-14 | Professional Fees For Monthly Retainership Services | 12 | 50000 | 0 | 49998 | 8999.64 | 2024-07-05 | JUNE 2024 | 8.333 |  | 108798 | 2024-07-05 | 49998 | 2024-07-05 14:57 | 0 | SHAH KHANDELWAL JAIN AND ASSOCIATES
Professional Fees | N/C | N/C | SHAH KHANDELWAL JAIN AND ASSOCIATES | 1935 | 2023-09-14 | Professional Fees For Monthly Retainership Services | 12 | 50000 | 0 | 49998 | 8999.64 | 2024-07-31 | JULY 2024 | 8.333 |  | 109454 | 2024-07-31 | 49998 | 1900-01-01 | 0 | SHAH KHANDELWAL JAIN AND ASSOCIATES
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 1993 | 2023-12-09 | WTC Electricity expenses | 0.49 | 1500000 | 18 | 735000 | 0 | 2024-07-08 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 108899 | 2024-07-08 | 735018 | 2024-07-08 17:08 | -18 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 1993 | 2023-12-09 | WTC Electricity expenses | 0.097 | 1500000 | 60 | 145500 | 0 | 2024-07-22 | Charges for Electricity Bills for Year 2023-24 | 100 | FOR THE MONTH OF JUNE 2024 | 109269 | 2024-07-22 | 145560 | 2024-07-22 15:34 | -60 | MSEDCL
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 1995 | 2023-12-19 | Telephone, mobile & water supply expenses | 3.2347 | 45000 | -1.5 | 145561.5 | 26200.8 | 2024-07-22 | Charges for Telephone & Mobile Bills from DEC-2023 to NOV-2024. | 100 | FOR THE MONTH OF JUNE 2024 | 109273 | 2024-07-22 | 145560 | 1900-01-01 | 1.5 | MSEDCL
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 1995 | 2023-12-19 | Telephone, mobile & water supply expenses | 0.0876 | 45000 | -2 | 3942 | 0 | 2024-07-27 | Charges for Telephone & Mobile Bills from DEC-2023 to NOV-2024. | 100 |  | 109326 | 2024-07-27 | 3940 | 2024-07-31 10:50 | 2 | AIRTEL DIGITAL LIMITED
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 1995 | 2023-12-19 | Telephone, mobile & water supply expenses | 0.0078 | 45000 | 2 | 351 | 0 | 2024-07-27 | Charges for Telephone & Mobile Bills from DEC-2023 to NOV-2024. | 100 | For the month of July 2024 | 109329 | 2024-07-27 | 353 | 2024-07-27 15:36 | -2 | BHARTI AIRTEL LIMITED
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 1995 | 2023-12-19 | Telephone, mobile & water supply expenses | 0.0443 | 45000 | 1.5 | 1993.5 | 0 | 2024-07-27 | Charges for Telephone & Mobile Bills from DEC-2023 to NOV-2024. | 100 | For the month of july 2024 | 109330 | 2024-07-27 | 1995 | 1900-01-01 | -1.5 | BHARTI AIRTEL LIMITED
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 1995 | 2023-12-19 | Telephone, mobile & water supply expenses | 0.6874 | 45000 | -1 | 30933 | 0 | 2024-07-27 | Charges for Telephone & Mobile Bills from DEC-2023 to NOV-2024. | 100 | For the month of july 2024 | 109335 | 2024-07-27 | 30932 | 2024-07-27 17:37 | 1 | BHARTI AIRTEL LIMITED
Water Supply | N/C | N/C | NITIN D PARDESHI | 1996 | 2023-12-19 | Telephone, mobile & water supply expenses | 1.0854 | 40000 | 0 | 43416 | 0 | 2024-07-08 | Charges for Water Supply (Municipal corporation) from DEC-2023 to NOV-2024. | 100 |  | 108915 | 2024-07-08 | 43416 | 2024-07-08 18:02 | 0 | EXECUTIVE ENGINEER WATER WORKS DEPARTMENT NMC NAGPUR
Housekeeping Work- | N/C | N/C | SPICK AND SPAN SERVICES | 1999 | 2024-01-02 | Housekeeping work | 145 | 508.333 | 0 | 73708.285 | 13267.5 | 2024-07-02 | Charges for Housekeeping work for Extra man power required at 2nd &3rd floor for the month of JUNE-2024 | 100 |  | 108778 | 2024-07-03 | 73708.29 | 2024-07-15 11:32 | -0.005 | SPICK AND SPAN SERVICES
Consultancy Charges | N/C | N/C | S.K.MISHRA | 2004 | 2024-01-12 | Proffessional Consultancy (HO Admin) | 1 | 400000 | 0 | 400000 | 0 | 2024-07-01 | Professional Consultancy Charges for the month of JUNE-2024 | 100 |  | 108669 | 2024-07-01 | 400000 | 2024-07-01 15:15 | 0 | S.K.MISHRA
Split Unit AMC 1 TR | N/C | N/C | ABHI-ANSH INDUSTRIES | 2034 | 2024-04-06 | New Sales Office VRF & Split AC System (L) | 12 | 1188 | 0 | 1187.9525 | 213.84 | 2024-07-01 | JUNE- 2024 | 8.333 |  | 108746 | 2024-07-02 | 12106.59 | 1900-01-01 | -10918.6375 | ABHI-ANSH INDUSTRIES
Split Unit AMC 1 TR | N/C | N/C | ABHI-ANSH INDUSTRIES | 2034 | 2024-04-06 | New Sales Office VRF & Split AC System (L) | 12 | 1188 | 0 | 1187.5248 | 213.76 | 2024-07-01 | JUN-2024 | 8.33 |  | 108746 | 2024-07-02 | 12106.59 | 1900-01-01 | -10919.0652 | ABHI-ANSH INDUSTRIES
Split Unit AMC 1.5 TR | N/C | N/C | ABHI-ANSH INDUSTRIES | 2034 | 2024-04-06 | New Sales Office VRF & Split AC System (L) | 12 | 1757 | 0 | 1756.2972 | 316.14 | 2024-07-01 | JUN-2024 | 8.33 |  | 108746 | 2024-07-02 | 12106.59 | 1900-01-01 | -10350.2928 | ABHI-ANSH INDUSTRIES
Split Unit AMC 1.5 TR | N/C | N/C | ABHI-ANSH INDUSTRIES | 2034 | 2024-04-06 | New Sales Office VRF & Split AC System (L) | 12 | 1757 | 0 | 1756.2972 | 316.14 | 2024-07-01 | JUN-2024 | 8.33 |  | 108746 | 2024-07-02 | 12106.59 | 1900-01-01 | -10350.2928 | ABHI-ANSH INDUSTRIES
Split Unit AMC 1.5 TR | N/C | N/C | ABHI-ANSH INDUSTRIES | 2034 | 2024-04-06 | New Sales Office VRF & Split AC System (L) | 12 | 1757 | 0 | 1756.2972 | 316.14 | 2024-07-01 | JUN-2024 | 8.33 |  | 108746 | 2024-07-02 | 12106.59 | 1900-01-01 | -10350.2928 | ABHI-ANSH INDUSTRIES
Split Unit AMC 2TR | N/C | N/C | ABHI-ANSH INDUSTRIES | 2034 | 2024-04-06 | New Sales Office VRF & Split AC System (L) | 12 | 2232 | 0 | 2231.1072 | 401.6 | 2024-07-01 | JUN-2024 | 8.33 |  | 108746 | 2024-07-02 | 12106.59 | 1900-01-01 | -9875.4828 | ABHI-ANSH INDUSTRIES
Split Unit AMC 2TR | N/C | N/C | ABHI-ANSH INDUSTRIES | 2034 | 2024-04-06 | New Sales Office VRF & Split AC System (L) | 12 | 2232 | 0 | 2231.1072 | 401.6 | 2024-07-01 | JUN-2024 | 8.33 |  | 108746 | 2024-07-02 | 12106.59 | 1900-01-01 | -9875.4828 | ABHI-ANSH INDUSTRIES
Consultancy Charges | N/C | N/C | DHARIA LABOUR LAW CONSULTANCY PVT. LTD.(OPC) | 457 | 2017-10-28 | Proffessional Consultancy (HO Admin) | 12 | 3000 | 0 | 3000.132 | 540.02 | 2024-07-09 | JUNE-2024 | 8.3337 |  | 108959 | 2024-07-09 | 3000.13 | 2024-07-09 14:38 | 0.002 | DHARIA LABOUR LAW CONSULTANCY PVT. LTD.(OPC)
Security Services. | N/C | N/C | SHREE GANESH SECURITY SERVICES | 485 | 2017-12-06 | Glocal Square Security Services | 8.3414 | 150000 | -0.33 | 104263.3293 | 18767.34 | 2024-07-09 | JUNE 2024 | 8.333 |  | 108966 | 2024-07-09 | 104263 | 2024-07-09 15:13 | 0.3293 | SHREE GANESH SECURITY SERVICES
DG Hiring Charges | N/C | N/C | K.R.S. HEAVY EQUIPMENT SERVICES | 634 | 2018-07-09 | 320 KVA DG Hiring for Ashish NX | 1 | 90000 | 0 | 90000 | 16200 | 2024-07-02 | Hiring Charges for DG Set of 320 KVA for Ashish NX Shop LG Floor for JUNE-2024 | 100 |  | 108756 | 2024-07-02 | 102000 | 2024-07-15 11:32 | -12000 | K.R.S. HEAVY EQUIPMENT SERVICES
Operator Charges. | N/C | N/C | K.R.S. HEAVY EQUIPMENT SERVICES | 634 | 2018-07-09 | 320 KVA DG Hiring for Ashish NX | 1 | 12000 | 0 | 12000 | 2160 | 2024-07-02 | Operator Charges for DG Set of 320 KVA for Ashish NX Shop LG floor for JUNE-2024 | 100 |  | 108756 | 2024-07-02 | 102000 | 2024-07-15 11:32 | -90000 | K.R.S. HEAVY EQUIPMENT SERVICES
Site Expenses -SO | N/C | N/C | PARSHURAM TEKADE | 85 | 2013-12-13 | Site Expenses | 0.1758 | 30000 | 0 | 5274 | 0 | 2024-07-22 | Site Expenses for the month of MAY-2024 | 100 |  | 109267 | 2024-07-22 | 19524 | 1900-01-01 | -14250 | PARSHURAM TEKADE
Site Expenses -SO | N/C | N/C | PARSHURAM TEKADE | 85 | 2013-12-13 | Site Expenses | 0.475 | 30000 | 0 | 14250 | 0 | 2024-07-22 | Site Expenses for the month of JUNE-2024 | 100 |  | 109267 | 2024-07-22 | 19524 | 1900-01-01 | -5274 | PARSHURAM TEKADE