## Work_Completion_Browse638581131
Work Completion Browse
Project : SRA MORWADI
From Date : 01/07/2024 To date: 01/07/2024
Page 1 of 1
Total Records: 78 Records 1 to 78
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Barrication work (L) | N/C | N/C | SHAFIK SHAIKH | 116 | 2024-05-20 | Plot Barrication & Gate Fixing | 1450 | 20 | 0 | 29000 | 0 | 2024-07-08 | Charges for Plot Barrication work with Pit Excavation, Plum Concrete, Cement, Sand, Metal& Rubble, ISMC 100MM, Horizontal MS Square Tube (40 x 40 x2mm) with Red Oxide GI Sheet 10feet x 3.5feet with self tapping Screw. | 100 |  | 108943 | 2024-07-08 | 29000 | 1900-01-01 | 0 | SHAFIK SHAIKH
Barrication work (M) | N/C | N/C | SHAFIK SHAIKH | 117 | 2024-05-20 | Plot Barrication & Gate Fixing | 1450 | 90 | 0 | 130500 | 0 | 2024-07-08 | Material Supply Charges for Plot Barrication work with Pit Excavation, Plum Concrete, Cement, Sand, Metal& Rubble, ISMC 100MM, Horizontal MS Square Tube (40 x 40 x2mm) with Red Oxide GI Sheet 10feet x 3.5feet with self tapping Screw. | 100 |  | 108944 | 2024-07-08 | 130500 | 1900-01-01 | 0 | SHAFIK SHAIKH
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 119 | 2024-05-23 | B1- 1st Slab RCC (L) | 200.889 | 192 | 0 | 38570.688 | 6942.72 | 2024-07-18 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase. | 100 |  | 109194 | 2024-07-22 | 38570.69 | 1900-01-01 | -0.002 | KRISHNA CONSTRUCTION (Prop BHISE)
Visiting Charges-AIE | N/C | N/C | GLOBAL GEOTECHNICS | 121 | 2024-05-24 | Geo-technical Consultancy | 2 | 10000 | 0 | 10000 | 1800 | 2024-07-13 | Advance along with work order | 50 |  | 109083 | 2024-07-15 | 20000 | 1900-01-01 | -10000 | GLOBAL GEOTECHNICS
Visiting Charges-AIE | N/C | N/C | GLOBAL GEOTECHNICS | 121 | 2024-05-24 | Geo-technical Consultancy | 2 | 10000 | 0 | 10000 | 1800 | 2024-07-13 | On Submission of Report | 50 |  | 109083 | 2024-07-15 | 20000 | 1900-01-01 | -10000 | GLOBAL GEOTECHNICS
Total Station Point marking- BC | N/C | N/C | VECTOR SURVEYORS | 122 | 2024-05-24 | F -Total Station Visit | 4 | 4500 | 0 | 18000 | 0 | 2024-07-13 | Labour charges for Total Station Survey work for Phase-2 F-Bldg area. | 100 |  | 109079 | 2024-07-15 | 18000 | 1900-01-01 | 0 | VECTOR SURVEYORS
Fabrication work lumpsum- MWB | N/C | N/C | SHAFIK SHAIKH | 127 | 2024-05-24 | fabrication Canopy For security | 1 | 2000 | 0 | 2000 | 0 | 2024-07-16 | Lumpsum labour charges for Canopy for security place in GI Sheet | 100 |  | 109186 | 2024-07-22 | 2000 | 1900-01-01 | 0 | SHAFIK SHAIKH
Department Labour - DEn | N/C | N/C | SHAFIK SHAIKH | 133 | 2024-05-31 | Phase 2 Department Labour | 42 | 650 | 0 | 27300 | 0 | 2024-07-09 | Charges for Male Coolie for Departmental work (Cube Casting, Curing, Dewatering, Material Loading & unloading, etc) for Phase-2 for the month of JUNE-2024 | 100 |  | 108975 | 2024-07-09 | 27300 | 1900-01-01 | 0 | SHAFIK SHAIKH
Misc. Expenses-Mkt | N/C | N/C | VIPUL & COMPANY | 154 | 2024-06-14 | Miscellaneous Work | 1 | 356715 | 0 | 356715 | 64208.7 | 2024-07-08 | Charges for Misc. Work for G M Work. | 100 |  | 108904 | 2024-07-08 | 356715 | 2024-07-09 11:58 | 0 | VIPUL & COMPANY
Misc. Expenses-Mkt | N/C | N/C | INAR DESIGNS | 155 | 2024-06-14 | Miscellaneous Work | 1 | 381356 | 0 | 381356 | 68644.08 | 2024-07-08 | Charges for Misc. work for G M Work. | 100 |  | 108905 | 2024-07-08 | 381356 | 2024-07-08 15:17 | 0 | INAR DESIGNS
Misc. Expenses-Mkt | N/C | N/C | INAR DESIGNS | 155 | 2024-06-14 | Miscellaneous Work | 1 | 285000 | 0 | 285000 | 51300 | 2024-07-08 | Charges for Misc. Work for G M Work. | 100 |  | 108906 | 2024-07-08 | 285000 | 2024-07-08 15:17 | 0 | INAR DESIGNS
Membrane Horizontal Waterproofing (L) | N/C | N/C | WATER DROP SOLUTION | 159 | 2024-06-19 | UGWT Waterproofing Membrane W/P (Horizontal) | 2374.58 | 15 | 0 | 35618.7 | 6411.36 | 2024-07-03 | Labour charges for UGWT Horizontal Waterproofing,Cleaning 120GSM fleeces as cushion on entire pcc area 250 GSM Rigidex-F Membrane over fleece just 300mm,make Rigidex-F Membrane joint waterproof,After joint treatment lay 120GSM Clothes to protect Rigidex-F | 100 |  | 108812 | 2024-07-08 | 35618.7 | 1900-01-01 | 0 | WATER DROP SOLUTION
Membrane Horizontal Waterproofing (L) | N/C | N/C | WATER DROP SOLUTION | 159 | 2024-06-19 | UGWT Waterproofing Membrane W/P (Horizontal) | 434.05 | 15 | 0 | 6510.75 | 1171.94 | 2024-07-12 | Labour charges for UGWT Horizontal Waterproofing,Cleaning 120GSM fleeces as cushion on entire pcc area 250 GSM Rigidex-F Membrane over fleece just 300mm,make Rigidex-F Membrane joint waterproof,After joint treatment lay 120GSM Clothes to protect Rigidex-F | 100 |  | 109018 | 2024-07-15 | 6510.75 | 1900-01-01 | 0 | WATER DROP SOLUTION
Membrane Horizontal Waterproofing (L) | N/C | N/C | WATER DROP SOLUTION | 159 | 2024-06-19 | UGWT Waterproofing Membrane W/P (Horizontal) | 312.07 | 15 | 0 | 4681.05 | 842.58 | 2024-07-18 | Labour charges for UGWT Horizontal Waterproofing,Cleaning 120GSM fleeces as cushion on entire pcc area 250 GSM Rigidex-F Membrane over fleece just 300mm,make Rigidex-F Membrane joint waterproof,After joint treatment lay 120GSM Clothes to protect Rigidex-F | 100 |  | 109189 | 2024-07-22 | 4681.05 | 1900-01-01 | 0 | WATER DROP SOLUTION
Transit Mixer | N/C | N/C | VIKAS GARADE | 16 | 2023-08-25 | TM Charge | 50.8571 | 350 | 0 | 17799.985 | 0 | 2024-07-05 | Charges for TM weight for the month of May, June & July-2024 | 100 |  | 108814 | 2024-07-08 | 17799.99 | 1900-01-01 | -0.005 | VIKAS GARADE
Membrane Horizontal Waterproofing (M) | N/C | N/C | WATER DROP SOLUTION | 160 | 2024-06-19 | UGWT Waterproofing Membrane W/P (Horizontal) | 2374.58 | 35 | 0 | 83110.3 | 14959.86 | 2024-07-03 | Material Supply Charges for UGWT Horizontal Membrane Waterproofing with Rigidex-F Membrane. | 100 |  | 108813 | 2024-07-08 | 83110.3 | 1900-01-01 | 0 | WATER DROP SOLUTION
Membrane Horizontal Waterproofing (M) | N/C | N/C | WATER DROP SOLUTION | 160 | 2024-06-19 | UGWT Waterproofing Membrane W/P (Horizontal) | 746.12 | 35 | 0 | 26114.2 | 4700.56 | 2024-07-12 | Material Supply Charges and Qty. Diff. for UGWT Horizontal Membrane Waterproofing with Rigidex-F Membrane. | 100 |  | 109021 | 2024-07-15 | 26114.2 | 1900-01-01 | 0 | WATER DROP SOLUTION
Misc. Expenses-Mkt | N/C | N/C | SATHE RAJENDRA BANSILAL | 164 | 2024-06-28 | New HO Dismantaling Work at 2nd Floor | 0.04 | 50000 | 0 | 2000 | 0 | 2024-07-26 | Charges for Miscellaneous Expenses for 2nd Floor office at sanmahu complex. | 100 |  | 109320 | 2024-07-26 | 2000 | 2024-07-26 18:51 | 0 | SATHE RAJENDRA BANSILAL
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 171 | 2024-07-03 | UGWT Rebaring Work | 56 | 180 | 0 | 10080 | 1814.4 | 2024-07-18 | Labour charges for 12mm Dia. Bar Rebarring work with 150mm Depth using Hilti RE-500 for UGWT | 100 |  | 109190 | 2024-07-22 | 24080 | 1900-01-01 | -14000 | AVCON TECHNICS PVT LTD
Rebaring work 16mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 171 | 2024-07-03 | UGWT Rebaring Work | 28 | 500 | 0 | 14000 | 2520 | 2024-07-18 | Labour charges for 16mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for UGWT | 100 |  | 109190 | 2024-07-22 | 24080 | 1900-01-01 | -10080 | AVCON TECHNICS PVT LTD
Misc. Expenses-Mkt | N/C | N/C | PM ELECTRICALS | 174 | 2024-07-05 | Miscellaneous Work | 1 | 33135.5 | 0 | 33135.5 | 5964.4 | 2024-07-08 | Charges for Misc. Work for G M Work. | 100 |  | 108913 | 2024-07-08 | 33135.5 | 2024-07-09 11:54 | 0 | PM ELECTRICALS
Misc. Expenses-Mkt | N/C | N/C | RANGOLI CERA TILES | 175 | 2024-07-05 | Miscellaneous Work | 1 | 37939 | 0 | 37939 | 6829.02 | 2024-07-08 | Charges for Misc. Work for G M Work. | 100 |  | 108912 | 2024-07-08 | 37939 | 2024-07-09 11:55 | 0 | RANGOLI CERA TILES
Misc. Expenses-Mkt | N/C | N/C | THEMES HOME FURNISHINGS | 176 | 2024-07-05 | Miscellaneous Work | 0.8057 | 502927 | -8.28 | 405208.2839 | 72936 | 2024-07-08 | Charges for Misc. Work for G M Work. | 100 |  | 108907 | 2024-07-08 | 405200 | 2024-07-09 11:56 | 8.2839 | THEMES HOME FURNISHINGS
Misc. Expenses-Mkt | N/C | N/C | THEMES HOME FURNISHINGS | 176 | 2024-07-05 | Miscellaneous Work | 0.1943 | 502927 | 8.28 | 97718.7161 | 4886.36 | 2024-07-08 | Charges for Misc. Work for G M Work. | 100 |  | 108908 | 2024-07-08 | 97727 | 2024-07-09 11:56 | -8.2839 | THEMES HOME FURNISHINGS
Misc. Expenses-Mkt | N/C | N/C | MAHARASHTRA ELECTRONICS CORPORATION | 177 | 2024-07-05 | Miscellaneous Work | 0.1949 | 210390.5 | 9.89 | 41005.1084 | 11484.2 | 2024-07-08 | Charges for Misc. Work for G M Work. | 100 |  | 108909 | 2024-07-08 | 41015 | 2024-07-09 11:57 | -9.8916 | MAHARASHTRA ELECTRONICS CORPORATION
Misc. Expenses-Mkt | N/C | N/C | MAHARASHTRA ELECTRONICS CORPORATION | 177 | 2024-07-05 | Miscellaneous Work | 0.2425 | 210390.5 | -4.7 | 51019.6963 | 14284.2 | 2024-07-08 | Charges for Misc. Work for G M Work. | 100 |  | 108910 | 2024-07-08 | 51015 | 2024-07-09 11:58 | 4.6963 | MAHARASHTRA ELECTRONICS CORPORATION
Misc. Expenses-Mkt | N/C | N/C | MAHARASHTRA ELECTRONICS CORPORATION | 177 | 2024-07-05 | Miscellaneous Work | 0.3676 | 210390.5 | 3.45 | 77339.5478 | 21656.04 | 2024-07-08 | Charges for Misc. Work for G M Work. | 100 |  | 108911 | 2024-07-08 | 77343 | 2024-07-09 11:58 | -3.4522 | MAHARASHTRA ELECTRONICS CORPORATION
Misc. Expenses-Mkt | N/C | N/C | MAHARASHTRA ELECTRONICS CORPORATION | 177 | 2024-07-05 | Miscellaneous Work | 0.1949 | 210390.5 | 9.89 | 41005.1084 | 11484.2 | 2024-07-12 | Charges for Misc. Work for G M Work. | 100 |  | 108997 | 2024-07-12 | 41015 | 2024-07-12 17:18 | -9.8916 | MAHARASHTRA ELECTRONICS CORPORATION
Site Expenses -SO | N/C | N/C | MANGESH ASHOK KSHIRSAGAR | 179 | 2024-07-06 | Phase 2 Site Expenses | 0.7271 | 10000 | 0 | 7271 | 0 | 2024-07-30 | Petty cash Site Expenses for the month of JULY-2024 for Phase-2 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MANGESH ASHOK KSHIRSAGAR
JCB Charges | N/C | N/C | SHASHANK ENTERPRISES | 180 | 2024-07-06 | Phase 2 JCB Hiring Charges | 17.5 | 850 | 0 | 14875 | 2677.5 | 2024-07-23 | Charges for JCB Hiring for Pit Excavation, Murum levelling, Weighbridge, Office Setup & Road Levelling, etc for Phase-2. | 100 |  | 109341 | 2024-07-29 | 14875 | 1900-01-01 | 0 | SHASHANK ENTERPRISES
Miscellaneous Expenses. - SO | N/C | N/C | SATISH RAMCHANDRA JAGTAP | 184 | 2024-07-06 | Site Staff Misc. Expenses | 0.9888 | 15000 | 0 | 14832 | 0 | 2024-07-29 | Charges for Miscellaneous Site Expenses for MAY-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VIKAS GARADE
Miscellaneous Expenses. - SO | N/C | N/C | SATISH RAMCHANDRA JAGTAP | 184 | 2024-07-06 | Site Staff Misc. Expenses | 0.9667 | 15000 | 0 | 14500.5 | 0 | 2024-07-29 | Charges for Miscellaneous Site Expenses for JUNE-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VIKAS GARADE
Misc. Expenses-Mkt | N/C | N/C | NIRNAY ELECTRONICS | 187 | 2024-07-08 | Miscellaneous Work | 1 | 37500 | 0 | 37500 | 0 | 2024-07-09 | Charges for Miscellaneous work for G M Work | 100 |  | 108963 | 2024-07-09 | 37500 | 2024-07-09 12:23 | 0 | NIRNAY ELECTRONICS
Site Expenses -SO | N/C | N/C | SUNIL VASANTRAO PATIL | 24 | 2023-09-06 | Site Expenses | 1 | 10000 | 0 | 10000 | 0 | 2024-07-08 | Petty Cash Site Expenses for the month of JUNE-2024 | 100 |  | 108948 | 2024-07-08 | 10000 | 1900-01-01 | 0 | VIKAS GARADE
Security Guard-SMS | N/C | N/C | SHRI RAJMUDRA ENTERPRISES | 27 | 2023-09-08 | July 23 To June 24 Security Guard & Supervisor (Day) | 60 | 466.66 | 0 | 27999.6 | 5039.92 | 2024-07-05 | Security Guard Charges for month JUNE-2024 | 100 |  | 108815 | 2024-07-08 | 87999 | 1900-01-01 | -59999.4 | SHRI RAJMUDRA ENTERPRISES
Security Guard-SMS | N/C | N/C | SHRI RAJMUDRA ENTERPRISES | 27 | 2023-09-08 | July 23 To June 24 Security Guard & Supervisor (Night) | 60 | 466.66 | 0 | 27999.6 | 5039.92 | 2024-07-12 | Security Guard Charges for month JUNE-2024 | 100 |  | 109025 | 2024-07-15 | 27999.6 | 1900-01-01 | 0 | SHRI RAJMUDRA ENTERPRISES
Security Supervisor-SMS | N/C | N/C | SHRI RAJMUDRA ENTERPRISES | 27 | 2023-09-08 | July 23 To June 24 Security Guard & Supervisor (Day) | 30 | 533.33 | 0 | 15999.9 | 2879.98 | 2024-07-05 | Security Supervisor Charges for month JUNE-2024 | 100 |  | 108815 | 2024-07-08 | 87999 | 1900-01-01 | -71999.1 | SHRI RAJMUDRA ENTERPRISES
Security Supervisor-SMS | N/C | N/C | SHRI RAJMUDRA ENTERPRISES | 27 | 2023-09-08 | July 23 To June 24 Security Guard & Supervisor (Night) | 30 | 533.33 | 0 | 15999.9 | 2879.98 | 2024-07-05 | Security Supervisor Charges for month JUNE-2024 | 100 |  | 108815 | 2024-07-08 | 87999 | 1900-01-01 | -71999.1 | SHRI RAJMUDRA ENTERPRISES
Security Guard | N/C | N/C | SHRI RAJMUDRA ENTERPRISES | 27 | 2023-09-08 | Security Guard Security Gard (Extra ) | 60 | 466.66 | 0 | 27999.6 | 5039.92 | 2024-07-05 | Security Guard charges for Month JUNE-2024 for Aluform Yard. | 100 |  | 108815 | 2024-07-08 | 87999 | 1900-01-01 | -59999.4 | SHRI RAJMUDRA ENTERPRISES
R & D Purpose | N/C | N/C | SUNIL VASANTRAO PATIL | 29 | 2023-09-21 | Quality Lab Setup- R&D Purpose | 0.0818 | 100000 | 2 | 8180 | 0 | 2024-07-06 | Charges for Testing and Certification of Various material as per requirement. | 100 |  | 108807 | 2024-07-06 | 8182 | 2024-07-11 11:26 | -2 | NILESH POTE
R & D Purpose | N/C | N/C | SUNIL VASANTRAO PATIL | 29 | 2023-09-21 | Quality Lab Setup- R&D Purpose | 0.0021 | 100000 | 0 | 210 | 37.8 | 2024-07-15 | Charges for Testing and Certification of Various material as per requirement. | 100 | Invoice No. - CPL242501208 | 109324 | 2024-07-26 | 210 | 1900-01-01 | 0 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
R & D Purpose | N/C | N/C | SUNIL VASANTRAO PATIL | 29 | 2023-09-21 | Quality Lab Setup- R&D Purpose | 0.0021 | 100000 | 0 | 210 | 37.8 | 2024-07-19 | Charges for Testing and Certification of Various material as per requirement. | 100 | INVOICE NO. - CPL242501347 | 109325 | 2024-07-26 | 210 | 1900-01-01 | 0 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
R & D Purpose | N/C | N/C | SUNIL VASANTRAO PATIL | 29 | 2023-09-21 | Quality Lab Setup- R&D Purpose | 0.287 | 100000 | 0 | 28700 | 5166 | 2024-07-27 | Charges for Testing and Certification of Various material as per requirement. | 100 | Tax Invoice No. - 202425PUN361 | 109343 | 2024-07-29 | 28700 | 1900-01-01 | 0 | DUROCRETE ENGINEERING SERVICES PVT LTD
JCB Charges | N/C | N/C | SHASHANK ENTERPRISES | 31 | 2023-09-25 | A Bldg. Hiring of JCB | 246.89 | 850 | 0 | 209856.5 | 37774.18 | 2024-07-16 | Charges for JCB Hiring with Bucket Including Operator & Diesel for Excavation, murum filling, levelling, etc for the month of January, February & March. | 100 |  | 109183 | 2024-07-22 | 217356.5 | 1900-01-01 | -7500 | SHASHANK ENTERPRISES
Rubble Soling DJT | N/C | N/C | SHASHANK ENTERPRISES | 31 | 2023-09-25 | A-Soling 230mm Thk. Soling | 300 | 25 | 0 | 7500 | 1350 | 2024-07-16 | Charges for Rubble Soling work for A-Bldg, UGWT & B-Bldg. | 100 |  | 109183 | 2024-07-22 | 217356.5 | 1900-01-01 | -209856.5 | SHASHANK ENTERPRISES
Fabrication work (L) | N/C | N/C | SHAFIK SHAIKH | 34 | 2023-10-06 | Labour camp Room fixing & Removing | 1360 | 15 | 0 | 20400 | 0 | 2024-07-02 | Labour Charges for Labour Camp room fixing work including MS Jali,GI Sheet,MS Pipe,Door & Other hardware etc. | 100 |  | 108809 | 2024-07-08 | 32160 | 2024-07-26 12:26 | -11760 | SHAFIK SHAIKH
Fabrication work Removing Sq.Ft | N/C | N/C | SHAFIK SHAIKH | 34 | 2023-10-06 | Labour camp Room fixing & Removing | 1960 | 6 | 0 | 11760 | 0 | 2024-07-02 | Labour Charges for labour camp removing work,GI Sheet removing with frame. | 100 |  | 108809 | 2024-07-08 | 32160 | 2024-07-26 12:26 | -20400 | SHAFIK SHAIKH
Fabrication work (L) No. | N/C | N/C | SHAFIK SHAIKH | 34 | 2023-10-06 | Fabrication Canopy for Electrical Board | 3 | 250 | 0 | 750 | 0 | 2024-07-16 | Labour Charges for Fixing of Canopy for electric board area. | 100 |  | 109187 | 2024-07-22 | 2550 | 1900-01-01 | -1800 | SHAFIK SHAIKH
Fabrication Work (M)-DCH | N/C | N/C | SHAFIK SHAIKH | 34 | 2023-10-06 | Fabrication Canopy for Electrical Board | 3 | 600 | 0 | 1800 | 0 | 2024-07-16 | Material Supply Charges for Canopy for electric board area. | 100 |  | 109187 | 2024-07-22 | 2550 | 1900-01-01 | -750 | SHAFIK SHAIKH
Welding work (L) | N/C | N/C | SHAFIK SHAIKH | 39 | 2023-10-17 | SRA A Bldg MISC. Work Scrap Steel Cutting, Straight & Weldin | 1000 | 5 | 0 | 5000 | 0 | 2024-07-20 | Labour charges for Steel welding work (only scrap) for A-Bldg | 100 |  | 109200 | 2024-07-22 | 23600 | 1900-01-01 | -18600 | SHAFIK SHAIKH
Steel Cutting | N/C | N/C | SHAFIK SHAIKH | 39 | 2023-10-17 | SRA A Bldg MISC. Work Scrap Steel Cutting, Straight & Weldin | 1860 | 10 | 0 | 18600 | 0 | 2024-07-20 | Labour charges for Steel Cutting & Welding work (Scrap) for A-Bldg | 100 |  | 109200 | 2024-07-22 | 23600 | 1900-01-01 | -5000 | SHAFIK SHAIKH
Department Labour-Dev | N/C | N/C | SHAFIK SHAIKH | 39 | 2023-10-17 | Departmental Labour for Misc. site work (Mason and Male Cool | 134 | 650 | 0 | 87100 | 0 | 2024-07-22 | Charges for Male Coolie for Cube casting, Curing, Dewatering, Material loading & Unloading work for MAY-2024 (5 M/C per day). | 100 |  | 109268 | 2024-07-22 | 157300 | 1900-01-01 | -70200 | SHAFIK SHAIKH
Department Labour-Dev | N/C | N/C | SHAFIK SHAIKH | 39 | 2023-10-17 | Departmental Labour for Misc. site work (Mason and Male Cool | 108 | 650 | 0 | 70200 | 0 | 2024-07-22 | Charges for Male Coolie for Cube casting, Curing, Dewatering, Material loading & Unloading work for JUNE-2024 (5 M/C per day). | 100 |  | 109268 | 2024-07-22 | 157300 | 1900-01-01 | -87100 | SHAFIK SHAIKH
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 40 | 2023-10-24 | PARKING RCC (L)-A BLDG. 1st Slab RCC Work | 712.103 | 156 | 0 | 111088.068 | 17727.86 | 2024-07-18 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase. | 100 |  | 109184 | 2024-07-22 | 599793.36 | 1900-01-01 | -488705.292 | KRISHNA CONSTRUCTION (Prop BHISE)
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 40 | 2023-10-24 | PARKING RCC (L)-A BLDG. 1st Slab RCC Work | 356.0515 | 156 | 0 | 55544.034 | 9997.92 | 2024-07-19 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase. | 100 |  | 109184 | 2024-07-22 | 599793.36 | 1900-01-01 | -544249.326 | KRISHNA CONSTRUCTION (Prop BHISE)
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 40 | 2023-10-24 | PARKING RCC (L)-A BLDG. 2nd Slab RCC Work | 712.103 | 156 | 0 | 111088.068 | 19995.86 | 2024-07-18 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase. | 100 |  | 109184 | 2024-07-22 | 599793.36 | 1900-01-01 | -488705.292 | KRISHNA CONSTRUCTION (Prop BHISE)
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 40 | 2023-10-24 | PARKING RCC (L)-A BLDG. 2nd Slab RCC Work | 356.0515 | 156 | 0 | 55544.034 | 9997.92 | 2024-07-19 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase. | 100 |  | 109184 | 2024-07-22 | 599793.36 | 1900-01-01 | -544249.326 | KRISHNA CONSTRUCTION (Prop BHISE)
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 40 | 2023-10-24 | PARKING RCC (L)-A BLDG. 3rd Slab RCC Work | 640.21 | 208 | 0 | 133163.68 | 23969.46 | 2024-07-18 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase | 100 |  | 109184 | 2024-07-22 | 599793.36 | 1900-01-01 | -466629.68 | KRISHNA CONSTRUCTION (Prop BHISE)
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 40 | 2023-10-24 | PARKING RCC (L)-A BLDG. 3rd Slab RCC Work | 320.105 | 208 | 0 | 66581.84 | 11984.74 | 2024-07-19 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase | 100 |  | 109184 | 2024-07-22 | 599793.36 | 1900-01-01 | -533211.52 | KRISHNA CONSTRUCTION (Prop BHISE)
Staging Work | No category | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 40 | 2023-10-24 | A-RCC Extra Work For Cantilever Area | 447.5671 | 75 | 0 | 33567.5325 | 6042.16 | 2024-07-16 | Charges for Staging for Scaffolding for A-Building North side. | 100 |  | 109184 | 2024-07-22 | 599793.36 | 1900-01-01 | -566225.8275 | KRISHNA CONSTRUCTION (Prop BHISE)
Staging Work | No category | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 40 | 2023-10-24 | A-RCC Extra Work For Cantilever Area | 885.7629 | 37.5 | 0 | 33216.1087 | 5978.9 | 2024-07-16 | Charges for Staging for Scaffolding for A-Building South side. | 100 |  | 109184 | 2024-07-22 | 599793.36 | 1900-01-01 | -566577.2512 | KRISHNA CONSTRUCTION (Prop BHISE)
Precoated Sheet Fixing - DEn | N/C | N/C | SHAFIK SHAIKH | 42 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 2432 | 5 | 0 | 12160 | 0 | 2024-07-02 | Labour Charges for Fixing of Precoated Sheet for labour camp room. | 100 |  | 108810 | 2024-07-08 | 21683.8 | 1900-01-01 | -9523.8 | SHAFIK SHAIKH
MS Pipe (L) | N/C | N/C | SHAFIK SHAIKH | 42 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 325.6 | 29.25 | 0 | 9523.8 | 0 | 2024-07-02 | Labour Charges for Fixing of 40 x 40 x 1.5mm MS Pipe for labour camp room. | 100 |  | 108810 | 2024-07-08 | 21683.8 | 1900-01-01 | -12160 | SHAFIK SHAIKH
Fabrication work Lumpsum-BCo | N/C | N/C | SHAFIK SHAIKH | 42 | 2023-10-24 | Main Gate Height Fabrication Work | 1 | 2500 | 0 | 2500 | 0 | 2024-07-16 | Lumpsum labour Charges for Fabrication work of Main Gate Height increased by 6 inch. | 100 |  | 109185 | 2024-07-22 | 2500 | 1900-01-01 | 0 | SHAFIK SHAIKH
Precoated Sheet (M) | N/C | N/C | SHAFIK SHAIKH | 43 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 62.85 | 1200 | 0 | 75420 | 0 | 2024-07-02 | Material Supply Charges for Precoated Sheet for labour camp room. | 100 |  | 108811 | 2024-07-08 | 96584 | 1900-01-01 | -21164 | SHAFIK SHAIKH
MS Pipe (M) | N/C | N/C | SHAFIK SHAIKH | 43 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 325.6 | 65 | 0 | 21164 | 0 | 2024-07-02 | Material Supply charges for MS Pipe 40 x 40 x 1.5mm for labour camp room. | 100 |  | 108811 | 2024-07-08 | 96584 | 1900-01-01 | -75420 | SHAFIK SHAIKH
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 60 | 2023-12-09 | Site Electricity expenses | 0.5953 | 100000 | 0 | 59530 | 0 | 2024-07-09 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 108977 | 2024-07-09 | 59530 | 2024-07-11 12:35 | 0 | MSEDCL
Hiring Charges | N/C | N/C | VIKAS GARADE | 68 | 2024-01-03 | SRA-Crane Services | 0.7758 | 50000 | 0 | 38790 | 6982.2 | 2024-07-12 | Charges for rent of Crane,Hydra and Pharana as per site requirement | 100 |  | 109181 | 2024-07-22 | 67000 | 1900-01-01 | -28210 | M M CRANE SERVICES
Hiring Charges | N/C | N/C | VIKAS GARADE | 68 | 2024-01-03 | SRA-Crane Services | 0.2821 | 100000 | 0 | 28210 | 5077.8 | 2024-07-17 | Charges for Rent of Crane, Hydra & Pharana for unloading site material as per site requirement. | 100 |  | 109181 | 2024-07-22 | 67000 | 1900-01-01 | -38790 | M M CRANE SERVICES
Security Guard-SMS | N/C | N/C | SHRI RAJMUDRA ENTERPRISES | 72 | 2024-01-12 | Security Guard Security Gard (Extra ) | 30 | 466.66 | 0 | 13999.8 | 2519.96 | 2024-07-05 | Charges for Security Guard for A-Bldg for the month of JUN-2024 ( 1 Security Guard for Day-12 Hrs Duty) | 100 |  | 108816 | 2024-07-08 | 27999.6 | 1900-01-01 | -13999.8 | SHRI RAJMUDRA ENTERPRISES
Security Guard-SMS | N/C | N/C | SHRI RAJMUDRA ENTERPRISES | 72 | 2024-01-12 | Security Guard Security Gard (Extra ) | 30 | 466.66 | 0 | 13999.8 | 2519.96 | 2024-07-05 | Charges for Security Guard for A-Bldg for the month of JUN-2024 ( 1 Security Guard for Night-12 Hrs Duty) | 100 |  | 108816 | 2024-07-08 | 27999.6 | 1900-01-01 | -13999.8 | SHRI RAJMUDRA ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 78 | 2024-02-07 | PARKING RCC (L)-B BLDG. 1st Slab RCC Work | 171.643 | 150 | 0 | 25746.45 | 4634.36 | 2024-07-18 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase. | 100 |  | 109188 | 2024-07-22 | 320621.77 | 1900-01-01 | -294875.32 | KRISHNA CONSTRUCTION (Prop BHISE)
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 78 | 2024-02-07 | PARKING RCC (L)-B BLDG. 2nd Slab RCC Work | 648.585 | 165 | 0 | 107016.525 | 19262.98 | 2024-07-18 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase. | 100 |  | 109188 | 2024-07-22 | 320621.77 | 1900-01-01 | -213605.245 | KRISHNA CONSTRUCTION (Prop BHISE)
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 78 | 2024-02-07 | PARKING RCC (L)-B BLDG. 3rd Slab RCC Work | 648.585 | 205.222 | 0 | 133103.9109 | 23958.7 | 2024-07-18 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase. | 100 |  | 109188 | 2024-07-22 | 320621.77 | 1900-01-01 | -187517.8591 | KRISHNA CONSTRUCTION (Prop BHISE)
Staging Work | No category | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 78 | 2024-02-07 | B-RCC Extra Work For Cantilever Area | 523.0228 | 37.5 | 0 | 19613.355 | 3530.4 | 2024-07-16 | Charges for Staging for Scaffolding for B-Building North side. | 100 |  | 109188 | 2024-07-22 | 320621.77 | 1900-01-01 | -301008.415 | KRISHNA CONSTRUCTION (Prop BHISE)
Staging Work | No category | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 78 | 2024-02-07 | B-RCC Extra Work For Cantilever Area | 937.1072 | 37.5 | 0 | 35141.52 | 6325.48 | 2024-07-16 | Charges for Staging for Scaffolding for B-Building South side. | 100 |  | 109188 | 2024-07-22 | 320621.77 | 1900-01-01 | -285480.25 | KRISHNA CONSTRUCTION (Prop BHISE)
Site Staff | N/C | N/C | JAI MALHAR TEA AND SNACKS CENTER | 81 | 2024-02-22 | Site Staff Site Staff Tea Expences | 1 | 2500 | 0 | 2500 | 0 | 2024-07-08 | Charges for Tea Expenses for the month of JUL-2024 | 100 |  | 108946 | 2024-07-08 | 2500 | 2024-07-26 12:25 | 0 | VIKAS GARADE
RCC Raft - cc | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 86 | 2024-03-19 | UGWT Between A&B Bldg RCC Work (L) | 589.144 | 100 | 0 | 58914.4 | 10604.6 | 2024-07-18 | Labour charges for RCC Raft work of UGWT Pump Room including Schedule & Quality of work. | 100 |  | 109191 | 2024-07-22 | 58914.4 | 1900-01-01 | 0 | KRISHNA CONSTRUCTION (Prop BHISE)