## Work_Completion_Browse638581235
Work Completion Browse
Project : GANGA DHAM TOWERS
Executed By : UNIQUE ENTERPRISES
From Date : 01/07/2021 To date: 01/07/2021
Page 1 of 1
Total Records: 30 Records 1 to 30
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
PCC Work | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg Substructure PCC work - | 10500 | 3 | 0 | 31500 | 5670 | 2021-09-22 | PCC Work | 100 |  | 91624 | 2021-09-23 | 453861.45 | 2022-01-20 15:56 | -422361.45 | UNIQUE ENTERPRISES
Footing & Column | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg Substructure Footing & Column work | 8447.229 | 50 | 0 | 422361.45 | 76025.06 | 2021-09-21 | Footing & Column | 100 |  | 91624 | 2021-09-23 | 453861.45 | 2022-01-20 15:56 | -31500 | UNIQUE ENTERPRISES
RCC Beam | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg Substructure Plinth Beam work | 10500 | 31 | 0 | 325500 | 58590 | 2022-01-07 | RCC (Plinth) Beam | 100 |  | 93068 | 2022-01-08 | 441000 | 2022-01-20 15:58 | -115500 | UNIQUE ENTERPRISES
Soling & PCC | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg Substructure work Soling & PCC work | 10500 | 11 | 0 | 115500 | 20790 | 2022-01-07 | Soiling & PCC Work | 100 |  | 93068 | 2022-01-08 | 441000 | 2022-01-20 15:58 | -325500 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 1st RCC Slab Built-up Area (L) | 5430.366 | 170 | 0 | 923162.22 | 166169.2 | 2022-01-08 | RCC for Column,Beam & Slab | 100 |  | 93073 | 2022-01-10 | 1846322.91 | 2022-01-20 15:57 | -923160.69 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 1st RCC Slab Built-up Area (L) | 603.3353 | 170 | 0 | 102567.001 | 18462.06 | 2022-11-08 | RCC for Column,Beam & Slab | 100 |  | 96983 | 2022-11-09 | 530962.1 | 2022-12-02 17:02 | -428395.099 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 1st RCC Slab Built-up Area (L) | 5430.357 | 170 | 0 | 923160.69 | 166168.92 | 2022-01-08 | RCC for Column,Beam & Slab | 100 |  | 93073 | 2022-01-10 | 1846322.91 | 2022-01-20 15:57 | -923162.22 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 1st RCC Slab Built-up Area (L) | 603.373 | 170 | 0 | 102573.41 | 18463.22 | 2022-11-08 | RCC for Column,Beam & Slab | 100 |  | 96983 | 2022-11-09 | 530962.1 | 2022-12-02 17:02 | -428388.69 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 2nd RCC Slab Built-up Area (L) | 6033.74 | 175 | 0 | 1055904.5 | 190062.82 | 2022-03-15 | RCC for Column,Beam & Slab | 100 |  | 94369 | 2022-04-13 | 2111807.25 | 2022-04-13 19:53 | -1055902.75 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 2nd RCC Slab Built-up Area (L) | 6033.73 | 175 | 0 | 1055902.75 | 190062.5 | 2022-03-15 | RCC for Column,Beam & Slab | 100 |  | 94369 | 2022-04-13 | 2111807.25 | 2022-04-13 19:53 | -1055904.5 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 3rd RCC Slab Built-up Area (L) | 4525.305 | 180 | 0 | 814554.9 | 146619.88 | 2022-10-13 | RCC for Column,Beam & Slab | 100 |  | 96751 | 2022-10-14 | 1629108.45 | 2022-11-08 10:42 | -814553.55 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 3rd RCC Slab Built-up Area (L) | 905.061 | 180 | 0 | 162910.98 | 29323.98 | 2022-11-08 | RCC for Column,Beam & Slab | 100 |  | 96983 | 2022-11-09 | 530962.1 | 2022-12-02 17:02 | -368051.12 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 3rd RCC Slab Built-up Area (L) | 4525.2975 | 180 | 0 | 814553.55 | 146619.64 | 2022-10-13 | RCC for Column,Beam & Slab | 100 |  | 96751 | 2022-10-14 | 1629108.45 | 2022-11-08 10:42 | -814554.9 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 3rd RCC Slab Built-up Area (L) | 905.0595 | 180 | 0 | 162910.71 | 29323.92 | 2022-11-08 | RCC for Column,Beam & Slab | 100 |  | 96983 | 2022-11-09 | 530962.1 | 2022-12-02 17:02 | -368051.39 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 4th RCC Slab Built-up Area (L) | 4525.305 | 185 | 0 | 837181.425 | 150692.66 | 2023-02-28 | RCC for Column,Beam & Slab | 100 |  | 98398 | 2023-03-01 | 1674361.47 | 2023-03-29 11:52 | -837180.045 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 4th RCC Slab Built-up Area (L) | 1508.435 | 185 | 0 | 279060.475 | 50230.88 | 2023-05-24 | RCC for Column,Beam & Slab | 100 | Tower -c 4th slab and fire ramp casting work completed | 99771 | 2023-05-24 | 558120.49 | 2023-06-09 19:54 | -279060.015 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 4th RCC Slab Built-up Area (L) | 4525.2975 | 185 | 0 | 837180.0375 | 150692.4 | 2023-02-28 | RCC for Column,Beam & Slab | 100 |  | 98398 | 2023-03-01 | 1674361.47 | 2023-03-29 11:52 | -837181.4325 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 4th RCC Slab Built-up Area (L) | 1508.4325 | 185 | 0 | 279060.0125 | 50230.8 | 2023-05-24 | RCC for Column,Beam & Slab | 100 | Tower -c 4th slab and fire ramp casting work completed | 99771 | 2023-05-24 | 558120.49 | 2023-06-09 19:54 | -279060.4775 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 5th RCC Slab Built-up Area (L) | 4223.618 | 215 | 0 | 908077.87 | 163454.02 | 2023-10-10 | RCC for Column,Beam & Slab | 100 |  | 102528 | 2023-10-12 | 1816155.74 | 2023-11-01 14:36 | -908077.87 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 5th RCC Slab Built-up Area (L) | 4223.618 | 215 | 0 | 908077.87 | 163454.02 | 2023-10-10 | RCC for Column,Beam & Slab | 100 |  | 102528 | 2023-10-12 | 1816155.74 | 2023-11-01 14:36 | -908077.87 | UNIQUE ENTERPRISES
RCC Rate Diferance BC | No category | No category | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 5th RCC Slab Built-up Area (L) | 8447.229 | 110 | 0 | 929195.19 | 167255.14 | 2023-10-17 | RCC Rate difference for Column,Beam & Slab | 100 |  | 102738 | 2023-10-18 | 929195.19 | 2023-11-01 14:36 | 0 | UNIQUE ENTERPRISES
Shuttering Work-Dev | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C SW32, SW33, P66 Footing Jacketing Work - | 66.45 | 450 | 0 | 29902.5 | 5382.46 | 2021-09-30 | Shuttering for Footing Jacketing - Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 91738 | 2021-09-30 | 46838 | 2022-01-20 15:56 | -16935.5 | UNIQUE ENTERPRISES
Reinforcement Work-Dev | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C SW32, SW33, P66 Footing Jacketing Work - | 1234 | 7 | 0 | 8638 | 1554.84 | 2021-09-30 | Reinforcement for Footing -Fixing in position reinforcement of various diameters for construction of Ramp including Cutting & Bending as per BBS/drawing,Shifting to the Required place from steel yard fixing in position etc. complete as per final drawing. | 100 |  | 91738 | 2021-09-30 | 46838 | 2022-01-20 15:56 | -38200 | UNIQUE ENTERPRISES
Concrete Work - BCP | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C SW32, SW33, P66 Footing Jacketing Work - | 33.19 | 250 | 0 | 8297.5 | 1493.56 | 2021-09-30 | RCC Footing Concrete of specified grade of concrete including compaction by vibrator, with proper line level and roughening them if special finish is to be provided.Loading,shifting,unloading of estimated raw material from store in Contractors Scope. | 100 |  | 91738 | 2021-09-30 | 46838 | 2022-01-20 15:56 | -38540.5 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 1st RCC Slab Built-up Area (L) | 635.13 | 170 | 0 | 107972.1 | 19434.98 | 2023-06-16 | RCC for Column, Beam and Slab (Qty Diff.) | 100 |  | 100190 | 2023-06-17 | 450942.3 | 2023-07-07 11:38 | -342970.2 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 2nd RCC Slab Built-up Area (L) | 635.13 | 175 | 0 | 111147.75 | 20006.6 | 2023-06-16 | RCC for Column, Beam and Slab (Qty Diff.) | 100 |  | 100190 | 2023-06-17 | 450942.3 | 2023-07-07 11:38 | -339794.55 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 3rd RCC Slab Built-up Area (L) | 635.13 | 180 | 0 | 114323.4 | 20578.22 | 2023-06-16 | RCC for Column, Beam and Slab (Qty Diff.) | 100 |  | 100190 | 2023-06-17 | 450942.3 | 2023-07-07 11:38 | -336618.9 | UNIQUE ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | UNIQUE ENTERPRISES | 1119 | 2021-07-08 | C Bldg 4th RCC Slab Built-up Area (L) | 635.13 | 185 | 0 | 117499.05 | 21149.82 | 2023-06-16 | RCC for Column, Beam and Slab (Qty Diff.) | 100 |  | 100190 | 2023-06-17 | 450942.3 | 2023-07-07 11:38 | -333443.25 | UNIQUE ENTERPRISES
Cleaning Work - Dld | N/C | N/C | UNIQUE ENTERPRISES | 1120 | 2021-07-08 | C SW 36 & C9 Footing Cleaning work | 1 | 5000 | 0 | 5000 | 900 | 2021-09-21 | Tower C Footing Excavation & Cleaning work. | 100 |  | 91599 | 2021-09-21 | 5000 | 2022-01-20 15:56 | 0 | UNIQUE ENTERPRISES
Labour Lumpsum | N/C | N/C | UNIQUE ENTERPRISES | 168 | 2017-01-23 | C 4th to 5th Slab Shear Reinforcement removing | 1 | 40000 | 0 | 40000 | 7200 | 2023-06-20 | Labour Charges for- Tower C 4th to 5th Slab Shear wall reinforcement removing and binding work (Rework due to 25mm Dia Steel test report failure in lab). | 100 | 4th slab to 5th slab steel failure in durocate lab | 100221 | 2023-06-20 | 40000 | 2023-07-07 11:38 | 0 | UNIQUE ENTERPRISES