## Work_Completion_Browse638581300
Work Completion Browse
Project : GANGA ALTUS
Contractor : LAXMI ELECTRICALS ENTERPRISES
Executed By : ADITI POWER CARE AND ENTERPRISES
From Date : 15/07/2024 To date: 15/07/2024
Page 1 of 1
Total Records: 5 Records 1 to 5
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Touchproof Jointing Kit (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 1 | 2750 | 0 | 2750 | 495 | 2024-07-29 17:10 | Labour charges for Fixing of 300 sqmm Touchproof jointing kit. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -97130 | ADITI POWER CARE AND ENTERPRISES
300 sqmm Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 115 | 154 | 0 | 17710 | 3187.8 | 2024-07-29 17:10 | Labour charges for 3C x 300 sqmm Cable Laying work. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -82170 | ADITI POWER CARE AND ENTERPRISES
300sqmm x 3.5C Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 340 | 99 | 0 | 33660 | 6058.8 | 2024-07-29 17:10 | Labour Charges for 300 sqmm x 3.5C Cable Laying work. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -66220 | ADITI POWER CARE AND ENTERPRISES
LT Earthing Set (m+l) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 7 | 4400 | 0 | 30800 | 5544 | 2024-07-29 17:10 | Supply and Labour Charges for fixing of LT Earthing set including Funnel, GI Patti, Salt, Coal,etc | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -69080 | ADITI POWER CARE AND ENTERPRISES
End Termination 300sqmm X 3.5 core cable (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 8 | 1870 | 0 | 14960 | 2692.8 | 2024-07-29 17:10 | Providing and fixing of 300 Sqmm x 3.5 C end termination. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -84920 | ADITI POWER CARE AND ENTERPRISES