## Work_Completion_Browse638584843
Work Completion Browse
Project : GANGA ALTUS
Executed By : TEJASHREE ENTERPRISES
From Date : 01/08/2024 To date: 01/08/2024
Page 1 of 1
Total Records: 137 Records 1 to 137
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1003-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1101-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1103-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1105-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1106-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1108-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1402-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1403-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1404-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1405-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1406-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1408-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1701-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1703-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1704-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1705-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1706-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1707-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1708-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1901-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1903-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1905-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1906-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1907-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1908-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2106-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73703 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2107-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2108-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-08-05 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73847 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1003-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1101-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1103-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1105-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1106-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1108-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1402-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1403-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1404-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1405-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1406-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1408-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1701-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1703-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1704-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1705-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1706-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1707-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1708-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1003-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73708 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1101-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73516 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1103-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73708 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1105-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73516 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1106-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73516 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1108-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73708 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1901-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1903-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1905-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1906-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1907-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1908-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2106-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72907.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2107-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2108-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-08-05 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73261.25 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1003-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72927 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1101-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72455 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1402-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72455 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1403-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72927 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1901-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72455 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1903-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72927 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1905-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72455 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1906-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72455 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1907-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72927 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1908-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72927 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2106-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72455 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2107-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72927 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2108-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-08-05 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -72927 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1402-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73516 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1403-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73708 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1404-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73708 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1405-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73516 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1406-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73516 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1408-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-08-05 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 109579 | 2024-08-05 | 74264 | 1900-01-01 | -73708 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1706-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-08-02 | Labour Charges for- Wall touch up work. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39356.91 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2106-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-08-02 | Labour Charges for- Wall touch up work. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39356.91 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2108-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-08-02 | Labour Charges for- Wall touch up work. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39586.41 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1706-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-08-02 | Labour Charges for- Ceiling Touch up work | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39877.91 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1905-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-08-02 | Labour Charges for- Ceiling Touch up work | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39877.91 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1906-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-08-02 | Labour Charges for- Ceiling Touch up work | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39877.91 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2106-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-08-02 | Labour Charges for- Ceiling Touch up work | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39877.91 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2108-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-08-02 | Labour Charges for- Ceiling Touch up work | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39974.41 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1905-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-08-02 | Labour Charges for- Wall touch up work. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39356.91 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1906-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-08-02 | Labour Charges for- Wall touch up work. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39356.91 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1706-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-08-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38450.91 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1905-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-08-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38450.91 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1906-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-08-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38450.91 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2106-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-08-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38450.91 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2107-2BHK Putty Work (L) | 270.5 | 1 | 0 | 270.5 | 48.7 | 2024-08-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39992.41 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2108-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-08-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38909.91 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1706-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-08-03 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39492.91 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1901-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2024-08-03 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40108.91 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1903-2BHK Putty Work (L) | 0.105 | 1 | 0 | 0.105 | 0.02 | 2024-08-03 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40262.805 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1905-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-08-03 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39492.91 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1906-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-08-03 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39492.91 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1907-2BHK Putty Work (L) | 105 | 1 | 0 | 105 | 18.9 | 2024-08-03 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40157.91 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1908-2BHK Putty Work (L) | 105 | 1 | 0 | 105 | 18.9 | 2024-08-03 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40157.91 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2106-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-08-03 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39492.91 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2107-2BHK Putty Work (L) | 105 | 1 | 0 | 105 | 18.9 | 2024-08-03 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40157.91 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2108-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-08-03 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39685.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1701-3BHK Putty Work (L) | 362 | 1 | 0 | 362 | 65.16 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39900.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1703-2BHK Putty Work (L) | 270 | 1 | 0 | 270 | 48.6 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39992.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1704-2BHK Putty Work (L) | 270 | 1 | 0 | 270 | 48.6 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39992.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1705-3BHK Putty Work (L) | 362 | 1 | 0 | 362 | 65.16 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39900.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1706-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38450.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1708-2BHK Putty Work (L) | 270 | 1 | 0 | 270 | 48.6 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39992.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1901-3BHK Putty Work (L) | 362.3 | 1 | 0 | 362.3 | 65.22 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39900.61 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1903-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38909.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1905-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38450.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1906-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38450.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1907-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38909.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1908-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38909.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2106-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38450.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2107-2BHK Putty Work (L) | 270 | 1 | 0 | 270 | 48.6 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39992.91 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2108-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-08-03 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -38909.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1701-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40108.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1703-2BHK Putty Work (L) | 115 | 1 | 0 | 115 | 20.7 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40147.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1704-2BHK Putty Work (L) | 115 | 1 | 0 | 115 | 20.7 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40147.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1705-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40108.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1706-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39492.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1708-2BHK Putty Work (L) | 115 | 1 | 0 | 115 | 20.7 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40147.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1901-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40108.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1903-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39685.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1905-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39492.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1906-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39492.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1907-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39685.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1908-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39685.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2106-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39492.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2107-2BHK Putty Work (L) | 115 | 1 | 0 | 115 | 20.7 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -40147.91 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2108-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-08-03 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109522 | 2024-08-05 | 40262.91 | 1900-01-01 | -39685.91 | TEJASHREE ENTERPRISES