## Work_Completion_Browse638584893
Work Completion Browse
Project : GANGA ALTUS
Contractor : VEER BHADRA ENTERPRISES
From Date : 05/07/2024 To date: 05/07/2024
Page 1 of 1
Total Records: 2 Records 1 to 2
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Labour lumpsum | N/C | N/C | VEER BHADRA ENTERPRISES | 1035 | 2024-07-01 | D&E-Entrance Gate-External Texture Work | 0.6 | 48000 | 0 | 28800 | 5184 | 2024-07-27 16:31 | Labour charges for Applying Texture Paint for D & E-Bldg Entrance Gate including scaffolding fixing & removing, 1 coat water base Primer, 2 coat Acrylic Paint work. | 100 |  | 109406 | 2024-07-29 | 72000 | 1900-01-01 | -43200 | VEER BHADRA ENTERPRISES
Labour lumpsum | N/C | N/C | VEER BHADRA ENTERPRISES | 1035 | 2024-07-01 | F-Entrance Gate-External Texture Work | 0.9 | 48000 | 0 | 43200 | 7776 | 2024-07-27 16:55 | Labour charges for Applying Texture Paint for F-Bldg Entrance Gate including scaffolding fixing & removing, 1 coat water base Primer, 2 coat Acrylic Paint work. | 100 | 90% Bill | 109406 | 2024-07-29 | 72000 | 1900-01-01 | -28800 | VEER BHADRA ENTERPRISES