Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1305-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1907-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1803-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2004-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2007-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2106-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2108-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1306-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14637.52 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1906-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1908-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1807-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2005-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2103-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1903-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2201-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2203-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2204-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2202-2BHK(Near Refuse Area) Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2006-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2008-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1901-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1905-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1806-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2107-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2206-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2208-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2307-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2207-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2308-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1808-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2104-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2304-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2305-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2306-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2102-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2302-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-101-3BHK Toilet Cement Paint | 135.008 | 2 | 0 | 270.016 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1857.624 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-105-3BHK Toilet Cement Paint | 135.008 | 2 | 0 | 270.016 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1857.624 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-102-3BHK Toilet Cement Paint | 135.008 | 2 | 0 | 270.016 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1857.624 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-106-3BHK Toilet Cement Paint | 135.008 | 2 | 0 | 270.016 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1857.624 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-104-2BHK Toilet Cement Paint | 130.944 | 2 | 0 | 261.888 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1865.752 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-103-2BHK Toilet Cement Paint | 130.944 | 2 | 0 | 261.888 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1865.752 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-108-2BHK Toilet Cement Paint | 130.944 | 2 | 0 | 261.888 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1865.752 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-107-2BHK Toilet Cement Paint | 130.944 | 2 | 0 | 261.888 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1865.752 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-501-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-901-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1004-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-403-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-805-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-807-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1101-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1301-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1005-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-405-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1204-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-307-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-401-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-902-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1203-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1205-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1403-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-408-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-502-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-601-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-603-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-801-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-803-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1104-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-702-2BHK(Near Refuse Area) Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1407-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1404-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1408-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1307-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1308-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1304-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2105-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1801-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2001-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2002-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 1900-01-01 | -14468.76 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2004-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2203-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1805-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2206-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1305-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:41 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2008-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2208-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2302-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2002-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2005-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2107-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2207-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1807-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1901-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1906-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1908-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2204-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2104-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2105-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2303-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2306-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2307-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2201-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1907-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1803-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2202-2BHK(Near Refuse Area) Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2103-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2106-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2006-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1808-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2001-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1801-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2301-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2305-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2304-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1903-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1905-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2007-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2101-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2108-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2308-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1706-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 1900-01-01 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1307-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.08 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1408-2BHK Toilet Cement Paint | 163.5 | 2 | 0 | 327 | 0 | 2024-03-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.44 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1308-2BHK Toilet Cement Paint | 163.5 | 2 | 0 | 327 | 0 | 2024-03-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.44 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1304-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.08 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1404-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.08 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1407-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.08 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-503-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-802-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-401-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-603-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-705-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1001-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1108-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1402-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-808-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1101-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-506-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-507-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-707-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-908-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-305-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-708-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1107-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1203-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-301-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-308-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-604-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1004-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-805-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-407-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1008-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1301-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1303-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1201-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1202-2BHK(Near Refuse Area) Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-404-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-405-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-606-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-607-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-807-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-901-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1007-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-402-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-508-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-903-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-905-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-501-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-703-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1104-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-403-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-408-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-502-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-306-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-906-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1403-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-303-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-602-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-804-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1005-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1207-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-304-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-307-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-504-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-505-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-706-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-907-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-601-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-904-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1204-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-702-2BHK(Near Refuse Area) Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-902-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1206-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1006-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-605-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-806-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-704-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-803-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1208-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1302-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1205-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-801-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-102-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2322 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-108-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2332.16 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-105-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2322 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-103-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2332.16 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-107-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2332.16 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-104-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2332.16 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-106-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2322 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-101-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2322 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1508-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1504-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1603-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1506-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1608-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1607-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1502-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1503-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1601-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1602-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2003-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1904-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1505-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1507-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1501-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1902-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Lumpsum work- DCW | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 482 | 2022-07-11 | E-Bldg Dewatering & Curing line (L)- - 1 No. | 1 | 8000 | 0 | 8000 | 0 | 2022-07-22 | Labour charges for Curing line Fitting for E-Building including 2 inch, 1.5 inch, 1 inch ASTM Line and 1/2 inch Ball valve fixing. | 100 |  | 95605 | 2022-07-22 | 8000 | 2022-08-16 11:56 | 0 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Brickwork 9" --DEn | N/C | N/C | K RAMU RATHOD | 483 | 2022-07-11 | Compound wall-9" brickwork,plaster,coping (L) | 288 | 18 | 0 | 5184 | 0 | 2022-09-26 | Labour Charges for- 9 Inch Brickwork with proper joint filling,line,level,right angle & Plumb. | 100 |  | 96378 | 2022-09-27 | 5184 | 2022-10-03 11:04 | 0 | K RAMU RATHOD
Brickwork 9" --DEn | N/C | N/C | K RAMU RATHOD | 483 | 2022-07-11 | Compound wall-9" brickwork,plaster,coping (L) | 288 | 18 | 0 | 5184 | 0 | 2022-08-24 | Labour Charges for- 9 Inch Brickwork with proper joint filling,line,level,right angle & Plumb. | 100 |  | 95989 | 2022-08-25 | 5184 | 1900-01-01 | 0 | K RAMU RATHOD
Ghadai work- BCP | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 3rd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:34 | Labour Charges for Ghadai work for 3rd Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 2nd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:34 | Labour Charges for Ghadai work for 2nd Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F- Bldg Common Lobby Stilt Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:34 | Labour charges for Chemical Grouting work for Stilt Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common LobbyTerrace Floor Chemical Grouting Work | 90.89 | 2 | 0 | 181.78 | 0 | 2023-08-17 17:34 | Labour Charges for Ghadai work for Terrace Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14947.18 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 1st Floor Chemical Grouting Work | 2266.21 | 2 | 0 | 4532.42 | 0 | 2023-08-17 17:34 | Labour charges for Chemical Grouting work for 1st Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -10596.54 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 2nd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:34 | Labour charges for Chemical Grouting work for 2nd Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 3rd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:34 | Labour charges for Chemical Grouting work for 3rd Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F- Bldg Common Lobby Stilt Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 14:27 | Labour Charges for Ghadai work for Stilt Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common LobbyTerrace Floor Chemical Grouting Work | 90.89 | 2 | 0 | 181.78 | 0 | 2023-08-17 17:34 | Labour charges for Chemical Grouting work for Terrace Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14947.18 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 1st Floor Chemical Grouting Work | 2261.21 | 2 | 0 | 4522.42 | 0 | 2023-08-17 14:44 | Labour Charges for Ghadai work for 1st Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -10606.54 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 485 | 2022-07-11 | F-Bldg Common Lobby 1st Floor Chemical Grouting Work | 2266.21 | 2 | 0 | 4532.42 | 0 | 2023-08-17 14:49 | Material supply for Chemical Grouting work for 1st Floor F-Bldg Common Lobby. | 100 |  | 101311 | 2023-08-18 | 7569.48 | 2023-09-04 11:44 | -3037.06 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 485 | 2022-07-11 | F-Bldg Common LobbyTerrace Floor Chemical Grouting Work | 90.89 | 2 | 0 | 181.78 | 0 | 2023-08-17 17:45 | Material supply for Chemical Grouting work for Terrace Floor F-Bldg Common Lobby. | 100 |  | 101311 | 2023-08-18 | 7569.48 | 2023-09-04 11:44 | -7387.7 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 485 | 2022-07-11 | F-Bldg Common Lobby 2nd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:45 | Material supply for Chemical Grouting work for 2nd Floor F-Bldg Common Lobby. | 100 |  | 101311 | 2023-08-18 | 7569.48 | 2023-09-04 11:44 | -6617.72 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 485 | 2022-07-11 | F-Bldg Common Lobby 3rd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:45 | Material supply for Chemical Grouting work for 3rd Floor F-Bldg Common Lobby. | 100 |  | 101311 | 2023-08-18 | 7569.48 | 2023-09-04 11:44 | -6617.72 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 485 | 2022-07-11 | F- Bldg Common Lobby Stilt Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 14:49 | Material supply for Chemical Grouting work for Stilt Floor F-Bldg Common Lobby. | 100 |  | 101311 | 2023-08-18 | 7569.48 | 2023-09-04 11:44 | -6617.72 | PRABHURAM VERMA
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 17th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 18th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 9th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 10th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 11th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 16th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 14th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 12th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 19th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 20th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 15th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 13th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 8th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 24th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-29 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 109437 | 2024-07-29 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 23rd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-29 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 109437 | 2024-07-29 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 22nd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-29 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 109437 | 2024-07-29 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - Stilt Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-09-27 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 96393 | 2022-09-28 | 13000 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 3rd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-03-18 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 98823 | 2023-03-20 | 52000 | 1900-01-01 | -39000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 1st Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-03-18 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 98823 | 2023-03-20 | 52000 | 1900-01-01 | -39000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 2nd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-03-18 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 98823 | 2023-03-20 | 52000 | 1900-01-01 | -39000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 4th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-03-18 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 98823 | 2023-03-20 | 52000 | 1900-01-01 | -39000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 5th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-22 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 99749 | 2023-05-23 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 6th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-22 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 99749 | 2023-05-23 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 7th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-22 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 99749 | 2023-05-23 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 21st Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-01-27 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104862 | 2024-01-29 | 13000 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16240.6 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16560.4 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17512.82 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17292.34 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16240.6 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Vitrified Flooring Work | 133.88 | 2 | 0 | 267.76 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17311.76 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17512.82 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16240.6 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17245.84 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16560.4 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17512.82 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -5878.68 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -6564.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -5878.68 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -6610.62 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -5558.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -6610.62 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -5878.68 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -6610.62 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -5878.68 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -6610.62 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14292.62 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13560.68 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Vitrified Flooring Work | 101 | 2 | 0 | 202 | 0 | 2024-03-22 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14377.8 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Flooring & Tiling Work | 28.5 | 2 | 0 | 57 | 0 | 2024-03-22 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14522.8 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14292.62 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13560.68 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191967.802 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -186664.322 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -189863.65 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192919.042 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192856.618 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188452.498 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188452.498 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192016.898 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191463.61 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191967.802 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -187954.162 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191839.498 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -187954.162 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188523.786 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191451.554 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192919.042 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192817.786 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191893.762 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188523.786 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191451.554 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192016.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188032.954 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -190195.954 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191693.354 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191693.354 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -184617.602 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191184.61 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192887.554 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -187954.162 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192919.042 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188032.954 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188032.954 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192856.618 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192887.554 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188523.786 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188523.786 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Toilet Dado Work | 60.8696 | 23 | 0 | 1400.0008 | 0 | 2023-08-31 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101543 | 2023-09-01 | 2901 | 2023-09-01 13:01 | -1500.9992 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Toilet Dado Work | 61.0526 | 19 | 0 | 1159.9994 | 0 | 2023-08-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101220 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -3840.0006 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Toilet Dado Work | 61.0526 | 19 | 0 | 1159.9994 | 0 | 2023-08-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101220 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -3840.0006 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Toilet Dado Work | 62.1053 | 19 | 0 | 1180.0007 | 0 | 2023-08-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101220 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -3819.9993 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Toilet Dado Work | 62.1053 | 19 | 0 | 1180.0007 | 0 | 2023-08-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101220 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -3819.9993 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Toilet Dado Work | 16.8421 | 19 | 0 | 319.9999 | 0 | 2023-08-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101220 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4680.0001 | PAWAR SHIVAPPA TARANAIK
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107531.31 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108518.662 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2203-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107531.31 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107531.31 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -106381.278 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2203-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 0 | 2024-05-17 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -98918.734 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 0 | 2024-05-17 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -98918.734 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108518.662 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -106381.278 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2304-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107531.31 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2304-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110339.118 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1202-2BHK(Near Refuse Area) Vitrified Skirting | 148.744 | 22 | 0 | 3272.368 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107428.862 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107045.886 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -106381.278 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2203-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110339.118 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -106381.278 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110254.662 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2304-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108165.262 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108398 | 2024-06-17 | 3345.2 | 1900-01-01 | -3011.52 | MAULI ENTERPRISES
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108398 | 2024-06-17 | 3345.2 | 1900-01-01 | -2006.28 | MAULI ENTERPRISES
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108398 | 2024-06-17 | 3345.2 | 1900-01-01 | -2006.28 | MAULI ENTERPRISES
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108398 | 2024-06-17 | 3345.2 | 1900-01-01 | -3011.52 | MAULI ENTERPRISES
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Flooring & Tiling Work | 5.7895 | 19 | 0 | 110.0005 | 0 | 2023-08-31 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101543 | 2023-09-01 | 2901 | 2023-09-01 13:01 | -2790.9995 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Toilet Dado Work | 57.8947 | 19 | 0 | 1099.9993 | 0 | 2023-08-31 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101543 | 2023-09-01 | 2901 | 2023-09-01 13:01 | -1801.0007 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Flooring & Tiling Work | 15.3158 | 19 | 0 | 291.0002 | 0 | 2023-08-31 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101543 | 2023-09-01 | 2901 | 2023-09-01 13:01 | -2609.9998 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186876.326 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183138.654 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186945.198 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -181770.022 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186290.31 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -178652.166 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -182561.526 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186945.198 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183138.654 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -181770.022 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186999.462 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186569.31 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -181770.022 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -179723.302 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183059.862 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186945.198 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186569.31 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186023.366 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -179723.302 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -179723.302 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186999.462 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186290.31 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -179723.302 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183059.862 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115464.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114624.908 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114059.564 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -112803.964 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -113600.14 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114059.564 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114059.564 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -112803.964 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -112803.964 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -113600.14 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -108296.748 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114059.564 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -108296.748 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114624.908 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115464.628 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114624.908 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115464.628 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -112803.964 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -113600.14 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -108296.748 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -113600.14 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115464.628 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -108296.748 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114624.908 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2022-09-26 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -57420.938 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60184.698 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60255.986 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60255.986 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60184.698 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -63749.098 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2022-09-26 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64588.818 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60184.698 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60255.986 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-08-13 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -162772.736 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169974.56 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172187.192 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169730.72 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172276.248 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170937.464 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170996.896 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169089.92 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172276.248 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171853.968 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172113.824 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172082.336 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172113.824 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -168757.616 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171853.968 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171853.968 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -166768.392 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -166682.096 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172082.336 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172005.224 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169974.56 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-08-13 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170460.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170937.464 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172082.336 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169089.92 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169422.224 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169089.92 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -166682.096 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172082.336 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172113.824 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172005.224 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Vitrified Skirting | 62.307 | 20 | 0 | 1246.14 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171166.82 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183138.654 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187733.398 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -182561.526 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183059.862 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186945.198 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186023.366 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186876.326 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183138.654 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186290.31 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186569.31 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -178652.166 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183059.862 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186290.31 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183059.862 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186999.462 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186569.31 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -181770.022 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186999.462 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186999.462 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186290.31 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187733.398 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -179723.302 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -91223.874 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -92854.466 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -89480.77 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2024-02-26 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -98239.306 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -89480.77 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -89480.77 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2024-02-26 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -98009.562 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -88409.634 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -92039.17 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2024-02-26 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -98456.994 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -92039.17 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -90551.906 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -92039.17 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Vitrified Skirting | 76.2 | 20 | 0 | 1524 | 0 | 2022-12-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60139.66 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2022-12-12 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -61294.756 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2022-12-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60370.732 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2022-12-12 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -61364.524 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2022-12-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60370.732 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2022-12-12 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -61294.756 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-202-2BHK(Near Refuse Area) Flooring & Tiling Work | 57.864 | 13 | 0 | 752.232 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60911.428 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2022-12-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60316.468 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2022-12-12 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -53094.572 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Vitrified Skirting | 103.845 | 20 | 0 | 2076.9 | 0 | 2022-12-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59586.76 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Vitrified Skirting | 76.2 | 20 | 0 | 1524 | 0 | 2022-12-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60139.66 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2022-12-12 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -55141.292 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59661.58 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59940.58 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2022-12-12 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -61364.524 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-202-2BHK(Near Refuse Area) Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2022-12-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -56929.468 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2022-12-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -58672.924 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59940.58 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2022-12-12 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -53094.572 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59928.524 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2022-12-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60316.468 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59661.58 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Vitrified Skirting | 103.845 | 20 | 0 | 2076.9 | 0 | 2022-12-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59586.76 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2022-12-12 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -55141.292 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -190748.29 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191463.61 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192856.618 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192016.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191967.802 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -185688.738 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -187479.618 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -186664.322 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -189863.65 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191451.554 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191967.802 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192817.786 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188452.498 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -190748.29 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191693.354 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188452.498 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -187954.162 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -190195.954 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -190992.13 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191893.762 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191839.498 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -184617.602 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191184.61 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192919.042 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188032.954 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -185688.738 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191693.354 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-09-26 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -62724.33 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60255.986 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60255.986 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-09-26 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -62724.33 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60255.986 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60184.698 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-003-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 1027.28 | 2023-12-01 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103604 | 2023-12-04 | 5707.07 | 2023-12-11 14:13 | 0.002 | SUNIL CONSTRUCTION AND CONTRACTORS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234040.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Comm Passage wash basin-Dado Work | 5.944 | 27 | 0 | 160.488 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234028.662 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Comm Passage wash basin-Dado Work | 9.816 | 27 | 0 | 265.032 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233924.118 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -228544.582 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232585.35 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-702-2BHK(Near Refuse Area) Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -228956.622 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233983.014 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -229454.958 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233963.382 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233581.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-703-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233983.014 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232585.35 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234052.438 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234052.438 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111750.136 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-03-06 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -103112.504 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108093.112 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2024-03-06 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -110357.68 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111634.192 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109154.68 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108093.112 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109154.68 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -107760.808 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-03-06 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -103112.504 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-202-2BHK(Near Refuse Area) Vitrified Skirting | 148.744 | 18 | 0 | 2677.392 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109403.368 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111718.648 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-702-2BHK(Near Refuse Area) Vitrified Skirting | 148.744 | 20 | 0 | 2974.88 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109105.88 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108910.84 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-702-2BHK(Near Refuse Area) Flooring & Tiling Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-03-06 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111212.8 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111718.648 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 0 | 2024-03-06 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -100298.264 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108910.84 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111634.192 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108093.112 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109154.68 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -107760.808 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111718.648 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109154.68 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109154.68 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-03-06 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -103112.504 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108093.112 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109398.52 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108910.84 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-702-2BHK(Near Refuse Area) Vitrified Flooring Work | 465.536 | 16 | 0 | 7448.576 | 0 | 2024-03-06 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -104632.184 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108910.84 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111634.192 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111718.648 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388417.316 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387030.996 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390324.228 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390239.772 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388150.372 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -386698.692 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390278.604 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387760.26 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390127.348 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390440.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389147.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388150.372 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -386698.692 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389147.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387030.996 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -383348.676 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1702-2BHK(Near Refuse Area) Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387760.26 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388004.1 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390278.604 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390324.228 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390239.772 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390537.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -386698.692 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387030.996 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388004.1 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387760.26 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390239.772 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390324.228 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390324.228 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390356.268 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387760.26 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387695.604 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387030.996 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387030.996 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Vitrified Skirting | 45.72 | 20 | 0 | 914.4 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171498.56 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172187.192 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172044.056 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171853.968 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-08-13 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -165075.296 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -168757.616 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-08-13 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170143.936 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-08-13 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170460.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172276.248 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170996.896 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172187.192 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172044.056 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-08-13 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170460.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171853.968 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-08-13 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -165075.296 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Vitrified Skirting | 62.307 | 20 | 0 | 1246.14 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171166.82 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -168757.616 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169089.92 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169730.72 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172044.056 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169730.72 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -166768.392 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-08-13 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170460.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -166768.392 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -166768.392 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172044.056 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172113.824 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-08-13 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -165075.296 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172276.248 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170937.464 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171853.968 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169089.92 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Vitrified Skirting | 45.72 | 20 | 0 | 914.4 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171498.56 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170937.464 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172187.192 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-08-13 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170143.936 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172005.224 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169974.56 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170218.4 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170218.4 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172044.056 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172005.224 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-08-13 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -165075.296 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170218.4 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169974.56 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169730.72 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -379974.98 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390537.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390537.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389147.14 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -381046.116 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390440.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1103-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388733.516 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1003-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389210.844 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -381046.116 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390549.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390549.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390440.94 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -379974.98 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389147.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387760.26 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -379974.98 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384955.476 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390537.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389147.14 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388417.316 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388150.372 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -381046.116 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -383348.676 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390460.572 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390440.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388150.372 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -383188.388 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389270.276 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388150.372 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -379974.98 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -386698.692 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -379974.98 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389270.276 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390440.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388004.1 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390239.772 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -383348.676 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1003-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -385041.772 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390460.572 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384955.476 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100664.394 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100664.394 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -99603.922 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1003-2BHK Vitrified Flooring Work | 70 | 18 | 0 | 1260 | 0 | 2023-10-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102548 | 2023-10-12 | 2520 | 2023-11-24 10:35 | -1260 | PAWAR SHIVAPPA TARANAIK
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Vitrified Flooring Work | 70 | 18 | 0 | 1260 | 0 | 2023-10-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102548 | 2023-10-12 | 2520 | 2023-11-24 10:35 | -1260 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100723.826 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96495.322 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -95910.69 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100664.394 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -99603.922 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101532.29 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -99870.866 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101809.266 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100723.826 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101809.266 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101732.154 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96409.026 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100187.066 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-10-10 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -92499.666 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96409.026 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100600.69 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101532.29 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100187.066 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101809.266 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100723.826 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96495.322 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100187.066 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101732.154 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96495.322 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-10-10 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -92499.666 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -95910.69 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -99870.866 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -99870.866 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101732.154 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96409.026 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100600.69 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Comm Passage wash basin-Dado Work | 9.816 | 27 | 0 | 265.032 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233924.118 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Comm Passage wash basin-Dado Work | 9.816 | 27 | 0 | 265.032 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233924.118 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233963.382 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233943.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2304-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -228053.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233678.766 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -228053.75 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -225220.894 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232649.95 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Comm Passage wash basin-Dado Work | 5.944 | 27 | 0 | 160.488 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234028.662 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233943.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232585.35 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -222406.654 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -225220.894 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232713.654 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233630.158 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234040.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2304-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233943.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -228053.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232841.958 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227959.95 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2304-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -225220.894 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232526.814 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232526.814 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233727.374 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232526.814 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232526.814 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234040.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -229035.414 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233943.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233019.358 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233581.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1202-2BHK(Near Refuse Area) Vitrified Flooring Work | 465.536 | 18 | 0 | 8379.648 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -225809.502 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233581.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232526.814 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2203-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -225220.894 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233943.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Comm Passage wash basin-Dado Work | 5.944 | 27 | 0 | 160.488 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234028.662 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233581.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Comm Passage wash basin-Dado Work | 9.816 | 27 | 0 | 265.032 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233924.118 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232526.814 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-002-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -34300.418 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-002-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-11-02 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37299.474 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-003-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-11-02 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37541.274 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-002-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2023-11-02 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -31536.658 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-001-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -38572.834 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-001-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2023-11-02 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -31536.658 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-001-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37864.818 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-002-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37864.818 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-002-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -38572.834 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-003-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -38572.834 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-001-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-11-02 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37299.474 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-003-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 219.4 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37815.722 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-001-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -34300.418 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-003-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 839.32 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -34371.706 | SUNIL CONSTRUCTION AND CONTRACTORS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11581.92 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10896.48 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11581.92 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11628.42 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10576.68 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11628.42 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10896.48 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11581.92 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10576.68 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10576.68 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11628.42 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11628.42 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10576.68 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10896.48 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11581.92 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10896.48 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Vitrified Flooring Work | 133.88 | 2 | 0 | 267.76 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17311.76 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17245.84 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Vitrified Flooring Work | 133.892 | 2 | 0 | 267.784 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17311.736 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Vitrified Flooring Work | 133.88 | 2 | 0 | 267.76 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17311.76 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Vitrified Flooring Work | 133.88 | 2 | 0 | 267.76 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17311.76 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-02-05 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17292.34 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Vitrified Flooring Work | 133.88 | 2 | 0 | 267.76 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17311.76 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17292.34 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16240.6 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17512.82 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16560.4 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16560.4 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17292.34 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17245.84 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17512.82 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16560.4 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Flooring & Tiling Work | 33.368 | 2 | 0 | 66.736 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17512.784 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17245.84 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17292.34 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-407-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6756.92 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-308-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6903.32 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-308-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6756.92 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-407-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6903.32 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-205-3BHK Vitrified Flooring Work | 133.88 | 2 | 0 | 267.76 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6692.96 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-305-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6894.02 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-408-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6903.32 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-506-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6627.04 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-708-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6756.92 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-506-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -5621.8 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-507-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6673.54 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-206-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6894.02 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-505-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -5621.8 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-408-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6756.92 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-307-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6903.32 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-305-3BHK Vitrified Flooring Work | 133.88 | 2 | 0 | 267.76 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6692.96 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-205-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6894.02 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-708-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6903.32 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-505-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6627.04 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-507-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -5941.6 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-206-3BHK Vitrified Flooring Work | 133.8 | 2 | 0 | 267.6 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6693.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-307-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105070 | 2024-02-05 | 6960.72 | 2024-02-20 12:25 | -6756.92 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1006-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-02 13:07 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -8904.08 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1207-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-02 15:19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -9223.88 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1607-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-02 13:07 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -9223.88 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1206-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-02 13:07 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -8904.08 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1208-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-02 13:07 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -9223.88 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1608-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-02 13:07 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -9223.88 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1607-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-06-02 15:19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -9955.82 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1206-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-06-02 15:19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -9909.32 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1207-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-06-02 15:19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -9955.82 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1605-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-06-02 15:19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -9909.32 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1006-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-06-02 15:19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -9909.32 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1605-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-02 13:07 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -8904.08 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1208-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-06-02 15:19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -9955.82 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1608-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-06-02 15:19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107918 | 2024-06-03 | 10243 | 2024-06-26 11:42 | -9955.82 | MARSH HOUSEKEEPING SOLUTIONS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-007-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -37120.914 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-006-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -37120.914 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-008-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 839.32 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -32919.786 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-005-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-11-02 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -35847.554 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-006-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-11-02 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -35847.554 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-007-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 219.4 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -36363.802 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-006-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -32848.498 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-007-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-11-02 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -36089.354 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-006-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -36412.898 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-008-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-11-02 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -36089.354 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-005-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -37120.914 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-008-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 219.4 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -36363.802 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-005-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -36412.898 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-008-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -37120.914 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-007-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 839.32 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -32919.786 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-007-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 1027.28 | 2023-11-02 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -31875.618 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-005-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103247 | 2023-11-04 | 37582.69 | 2023-11-23 11:39 | -32848.498 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1006-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159299.268 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-906-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 232.73 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158565.332 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-907-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 242.49 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158511.068 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1006-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 1031.55 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -154127.396 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-905-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 941.86 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -154625.732 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-907-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.03 | 2023-10-27 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -153335.892 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-906-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2023-10-27 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159489.356 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-908-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 310.15 | 2023-10-27 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158135.18 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1005-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158442.196 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-205-3BHK Vitrified Flooring Work | 180 | 14 | 0 | 2520 | 0 | 2023-10-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 | Debit For Shivappa Pawar for Housekeeping | 102549 | 2023-10-12 | 2520 | 2023-11-24 10:35 | 0 | PAWAR SHIVAPPA TARANAIK
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1508-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 1467.53 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -403955.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1707-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 1467.53 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -403955.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1607-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409182.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1807-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409925.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1707-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411746.228 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1605-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1608-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410504.54 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1806-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1107-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 351.51 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410155.516 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1406-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 1031.55 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -406377.476 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1608-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1108-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 482.8 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409426.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1407-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.59 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410632.844 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1607-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405972.94 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1705-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405879.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1507-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409925.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1605-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409572.372 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1406-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411700.604 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1407-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.51 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411777.716 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1505-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411661.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1807-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411746.228 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1808-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411746.228 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1107-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.59 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410632.844 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1507-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410504.54 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1707-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405972.94 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1608-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409925.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1805-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411661.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1605-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -408120.692 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1805-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409572.372 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1705-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411661.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1108-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -406463.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1408-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411549.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1708-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410504.54 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1805-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410569.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1708-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 1467.53 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -403955.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1107-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -404770.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1407-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 482.8 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409426.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1505-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -408120.692 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1408-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 351.51 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410155.516 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1607-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409925.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1108-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411549.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1705-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1805-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -401396.98 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1505-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409572.372 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1108-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.51 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411777.716 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1307-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.51 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411777.716 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1408-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -406463.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1507-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1307-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -404770.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1408-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 482.8 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409426.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1407-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 351.51 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410155.516 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1508-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411746.228 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1107-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411549.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1505-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410569.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1708-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1807-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410504.54 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1808-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405972.94 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1808-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409925.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1707-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1807-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405972.94 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1808-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410504.54 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1307-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 482.8 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409426.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1707-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409182.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1806-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -408120.692 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1708-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405972.94 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1806-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405879.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1607-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 1467.53 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -403955.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1608-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 1467.53 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -403955.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1707-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409925.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1107-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -406463.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1507-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405972.94 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1507-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 1467.53 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -403955.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1605-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -401396.98 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1806-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -401396.98 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1406-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409839.316 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1107-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.51 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411777.716 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1605-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411661.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1407-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -406463.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1505-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405879.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1508-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1607-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410504.54 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1705-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410569.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1705-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -401396.98 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1107-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 482.8 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409426.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1308-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 351.51 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410155.516 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1708-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409925.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1806-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409572.372 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1608-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411746.228 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1505-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1605-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405879.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1806-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410569.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1807-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495978.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1308-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -492516.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496557.32 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2105-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2206-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 2120.85 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -486378.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494173.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494173.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497714.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496745.056 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2108-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 1614.29 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -489192.864 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495892.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497714.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1305-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2307-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -487449.76 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 2120.85 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -486378.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494505.776 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 570.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494991.2 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497714.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 70.85 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497767.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496745.056 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1307-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -492516.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2108-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494173.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495235.04 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1308-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.59 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496685.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2206-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491931.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -487449.76 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495625.152 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2105-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2307-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497714.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497799.008 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 70.85 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497767.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1308-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2206-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2108-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 2120.85 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -486378.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1807-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495235.04 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497753.384 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495625.152 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497714.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 70.85 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497767.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 1614.29 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -489192.864 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 570.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494991.2 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 570.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494991.2 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497753.384 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491931.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491931.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494505.776 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491931.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1306-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496745.056 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2206-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2108-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 1614.28 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -164487.944 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1807-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 1467.54 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -165303.24 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 2120.86 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -161673.704 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 2120.86 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -161673.704 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1305-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -163815.976 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2105-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 2120.86 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -161673.704 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 1614.28 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -164487.944 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 1614.28 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -164487.944 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -163815.976 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -162744.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1306-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -163815.976 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -163815.976 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1808-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 1467.54 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -165303.24 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 1467.54 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -165303.24 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -163815.976 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -162744.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 1467.54 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -165303.24 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 1614.28 | 2024-06-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107916 | 2024-06-03 | 173456.2 | 2024-06-10 11:24 | -164487.944 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-607-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 242.5 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162593.858 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-608-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 927.68 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -158787.314 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-408-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162447.714 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-207-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-308-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 839.32 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159278.146 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-307-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163673.402 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-206-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162205.914 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-407-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162447.714 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-606-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -161938.97 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-608-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162217.97 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-407-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-608-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163641.914 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-305-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162771.258 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-405-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-406-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-305-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162205.914 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-308-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162447.714 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-605-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -161938.97 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-205-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162205.914 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-406-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162205.914 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-206-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159206.858 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-207-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 219.4 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162722.162 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-208-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 839.32 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159278.146 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-606-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 941.86 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -158708.522 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-305-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163610.978 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-506-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163572.146 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-306-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-308-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-207-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162447.714 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-405-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162205.914 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-606-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 232.72 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162648.122 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-607-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162217.97 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-505-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163572.146 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-205-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162771.258 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-305-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-307-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-406-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162771.258 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-206-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-306-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162205.914 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-207-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163673.402 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-505-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 232.72 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162648.122 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-306-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159206.858 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-607-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.86 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163430.666 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-505-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -161938.97 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-406-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163610.978 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-306-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163610.978 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-408-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 219.4 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162722.162 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-605-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 232.72 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162648.122 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-208-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162447.714 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-206-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163610.978 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-607-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163641.914 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-306-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162771.258 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-506-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 941.86 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -158708.522 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-408-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 839.32 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159278.146 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-207-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 839.32 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159278.146 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-208-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-307-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162447.714 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-508-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.86 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163430.666 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-605-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 941.86 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -158708.522 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-607-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 927.68 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -158787.314 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-608-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 242.5 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162593.858 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-407-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 839.32 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159278.146 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-606-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163572.146 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-208-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 219.4 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162722.162 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-307-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 219.4 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162722.162 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-505-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 941.86 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -158708.522 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-405-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159206.858 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-506-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.86 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163430.666 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-205-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163610.978 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-605-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.86 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163430.666 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-608-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.86 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163430.666 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-508-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162217.97 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-407-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163673.402 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-408-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163673.402 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-305-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159206.858 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-307-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 839.32 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159278.146 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-506-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2023-06-29 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -161938.97 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-308-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163673.402 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-405-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163610.978 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-208-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163673.402 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-605-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163572.146 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-308-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 219.4 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162722.162 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-408-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-506-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 232.72 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162648.122 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-508-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 242.5 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162593.858 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-205-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163479.274 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-606-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.86 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163430.666 | R.M.Marbles
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-508-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2023-06-29 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163641.914 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-205-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159206.858 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-206-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162771.258 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-407-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 219.4 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162722.162 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-508-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 927.68 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -158787.314 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-405-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -162771.258 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-406-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -159206.858 | R.M.Marbles
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-505-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.86 | 2023-06-29 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 100355 | 2023-06-30 | 163941.05 | 2023-07-29 10:57 | -163430.666 | R.M.Marbles
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1208-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 351.5 | 2023-10-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 102396 | 2023-10-07 | 19982.4 | 2023-10-30 15:44 | -18029.576 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1206-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.9 | 2023-09-13 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -65922.796 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1207-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2023-09-13 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -61694.292 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1207-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 482.8 | 2023-09-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -64656.62 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1205-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2023-09-13 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -66779.868 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1205-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.9 | 2023-09-13 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -65922.796 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1207-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.6 | 2023-09-13 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -65863.364 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1207-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.52 | 2023-09-13 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -67008.236 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1205-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 1031.56 | 2023-09-13 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -61607.996 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1206-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.4 | 2023-09-13 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -66931.124 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1206-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2023-09-13 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -57698.636 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1205-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2023-09-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -63683.516 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1207-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2023-09-13 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -60001.196 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1206-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2023-09-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -63683.516 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1206-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2023-09-13 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -65069.836 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1205-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2023-09-13 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -65069.836 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1206-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2023-09-13 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -66779.868 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1207-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2023-09-13 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -66779.868 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1207-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 351.5 | 2023-09-13 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -65386.036 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1205-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.4 | 2023-09-13 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -66931.124 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1206-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 1031.56 | 2023-09-13 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -61607.996 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1205-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2023-09-13 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 101848 | 2023-09-15 | 67338.86 | 2023-09-20 12:26 | -57698.636 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-705-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 941.86 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -151940.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-708-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 927.67 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -152019.264 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-706-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 598.15 | 2023-09-11 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -153849.96 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-708-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 242.49 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155825.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-806-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156662.616 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-808-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156662.616 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-706-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.37 | 2023-09-11 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155170.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-707-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 310.15 | 2023-09-11 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155449.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-805-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 232.73 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155880.072 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-808-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 927.67 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -152019.264 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-706-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 941.86 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -151940.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-806-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2023-09-11 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -148603.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-705-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 232.73 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155880.072 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-805-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156662.616 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-807-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.85 | 2023-09-11 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156873.864 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-807-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.03 | 2023-09-11 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -150650.632 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-707-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.91 | 2023-09-11 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -154734.6 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-706-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156662.616 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-808-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.91 | 2023-09-11 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -154734.6 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-806-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 232.73 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155880.072 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-808-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 310.15 | 2023-09-11 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155449.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-707-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 927.67 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -152019.264 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-805-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2023-09-11 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156804.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-806-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2023-09-11 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156804.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-808-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.85 | 2023-09-11 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156873.864 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-808-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.03 | 2023-09-11 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -150650.632 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-708-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.91 | 2023-09-11 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -154734.6 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-805-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 598.15 | 2023-09-11 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -153849.96 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-807-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 927.67 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -152019.264 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-808-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 242.49 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155825.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-806-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.37 | 2023-09-11 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155170.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-706-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2023-09-11 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156804.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-706-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2023-09-11 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -148603.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-708-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.03 | 2023-09-11 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -150650.632 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-807-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.91 | 2023-09-11 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -154734.6 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-708-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156662.616 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-806-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 941.86 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -151940.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-805-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.37 | 2023-09-11 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155170.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-707-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.85 | 2023-09-11 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156873.864 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-805-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2023-09-11 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -148603.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-806-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 598.15 | 2023-09-11 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -153849.96 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-706-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 232.73 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155880.072 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-708-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 310.15 | 2023-09-11 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155449.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-707-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156662.616 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-708-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.85 | 2023-09-11 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156873.864 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-705-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156662.616 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-805-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 941.86 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -151940.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-807-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 242.49 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155825.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-807-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 310.15 | 2023-09-11 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155449.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-705-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2023-09-11 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156804.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-705-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2023-09-11 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -148603.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-707-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.03 | 2023-09-11 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -150650.632 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-707-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 242.49 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155825.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-705-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.37 | 2023-09-11 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -155170.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-807-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-09-11 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -156662.616 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-705-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 598.15 | 2023-09-11 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101811 | 2023-09-12 | 157173 | 2023-09-30 11:35 | -153849.96 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1208-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.6 | 2023-10-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102396 | 2023-10-07 | 19982.4 | 2023-10-30 15:44 | -18506.904 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1208-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.52 | 2023-10-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102396 | 2023-10-07 | 19982.4 | 2023-10-30 15:44 | -19651.776 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1208-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2023-10-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102396 | 2023-10-07 | 19982.4 | 2023-10-30 15:44 | -14337.832 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1208-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2023-10-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102396 | 2023-10-07 | 19982.4 | 2023-10-30 15:44 | -19423.408 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1208-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2023-10-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 102396 | 2023-10-07 | 19982.4 | 2023-10-30 15:44 | -12644.736 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1208-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 482.8 | 2023-10-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102396 | 2023-10-07 | 19982.4 | 2023-10-30 15:44 | -17300.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-507-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105858 | 2024-03-11 | 10683.85 | 2024-03-20 15:37 | -8245.45 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-507-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2024-03-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 105858 | 2024-03-11 | 10683.85 | 2024-03-20 15:37 | -4161.482 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-507-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2024-03-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105858 | 2024-03-11 | 10683.85 | 2024-03-20 15:37 | -8960.77 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-206-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -8972.496 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-305-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -8168.304 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-206-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -8168.304 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-407-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -9009.696 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-308-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -9009.696 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-308-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -8424.144 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-407-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -8424.144 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-205-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -8972.496 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-307-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -8424.144 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-307-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -9009.696 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-708-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -8424.144 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-205-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -8168.304 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-408-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -9009.696 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-305-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -8972.496 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-708-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -9009.696 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-408-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104620 | 2024-01-15 | 9239.44 | 2024-02-05 11:47 | -8424.144 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-508-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108371 | 2024-06-17 | 4285.2 | 2024-07-05 11:24 | -3266.08 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-607-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108371 | 2024-06-17 | 4285.2 | 2024-07-05 11:24 | -3998.02 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-906-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108371 | 2024-06-17 | 4285.2 | 2024-07-05 11:24 | -2946.28 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-607-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108371 | 2024-06-17 | 4285.2 | 2024-07-05 11:24 | -3266.08 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-906-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108371 | 2024-06-17 | 4285.2 | 2024-07-05 11:24 | -3951.52 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-508-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108371 | 2024-06-17 | 4285.2 | 2024-07-05 11:24 | -3998.02 | A R CLEANING SERVICS
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1305-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494505.776 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2105-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495625.152 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495625.152 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497753.384 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1306-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1306-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497753.384 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497799.008 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491931.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1906-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496621.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1306-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494505.776 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494173.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 570.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494991.2 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1706-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -487449.76 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494505.776 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1306-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495892.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 70.85 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497767.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2105-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1307-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.59 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496685.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496745.056 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -492025.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -492025.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2005-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 311.78 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496429.016 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2307-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494173.472 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2108-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 70.85 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497767.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2105-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 299.22 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496498.784 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 2120.85 | 2024-07-06 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -486378.624 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1808-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495235.04 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2207-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2305-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2307-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495892.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1908-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495978.552 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2006-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 504.52 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495358.208 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2308-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2306-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 87.37 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497675.72 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1905-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496621.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497553.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2007-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 570.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -494991.2 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2107-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1305-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2024-07-06 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497753.384 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 1031.55 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -492430.256 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2008-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 1192.72 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491534.888 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495235.04 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 777.59 | 2024-07-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -493841.168 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496621.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1405-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 1031.55 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -492430.256 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1606-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496621.92 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1907-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496557.32 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2106-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 118.12 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497504.912 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2205-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 1210.96 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -491433.584 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1305-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495892.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-2208-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 434.22 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495748.808 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 1031.55 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -492430.256 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1305-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -496745.056 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1307-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-07-06 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -497602.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1106-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495892.096 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-07-06 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 109175 | 2024-07-19 | 498161.12 | 2024-08-05 13:58 | -495625.152 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-005-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2023-12-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103605 | 2023-12-04 | 20702.97 | 2023-12-11 14:13 | -13205.018 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-008-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 1027.28 | 2023-12-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103605 | 2023-12-04 | 20702.97 | 2023-12-11 14:13 | -14995.898 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-006-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2023-12-01 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103605 | 2023-12-04 | 20702.97 | 2023-12-11 14:13 | -13205.018 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-907-2BHK Vitrified Skirting | 91.44 | 20 | 0 | 1828.8 | 329.18 | 2023-10-27 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158029.46 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-908-2BHK Vitrified Skirting | 91.44 | 20 | 0 | 1828.8 | 329.18 | 2023-10-27 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158029.46 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-905-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 232.73 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158565.332 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1006-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2023-10-27 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157589.236 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1008-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 351.51 | 2023-10-27 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157905.436 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1007-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -154213.692 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-908-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.03 | 2023-10-27 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -153335.892 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1008-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2023-10-27 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -152520.596 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1007-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 351.51 | 2023-10-27 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157905.436 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1007-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.59 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158382.764 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1008-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 1016.02 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -154213.692 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-908-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159347.876 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1005-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2023-10-27 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -150218.036 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1005-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2023-10-27 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159450.524 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-905-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2023-10-27 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159489.356 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-907-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.85 | 2023-10-27 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159559.124 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-906-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 941.86 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -154625.732 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1005-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159299.268 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-907-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159347.876 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-906-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2023-10-27 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -151289.172 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-906-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.37 | 2023-10-27 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157856.18 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1007-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159299.268 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1008-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159299.268 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-908-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 242.49 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158511.068 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-905-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159347.876 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1006-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2023-10-27 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -150218.036 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1005-3BHK Vitrified Skirting | 124.614 | 22 | 0 | 2741.508 | 493.47 | 2023-10-27 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157116.752 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1005-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2023-10-27 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157589.236 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-906-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 91.87 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159347.876 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-908-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.85 | 2023-10-27 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159559.124 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1006-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158442.196 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1007-2BHK Vitrified Skirting | 91.44 | 22 | 0 | 2011.68 | 362.1 | 2023-10-27 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157846.58 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-907-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 310.15 | 2023-10-27 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158135.18 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-905-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2023-10-27 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -151289.172 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1006-3BHK Vitrified Skirting | 124.614 | 22 | 0 | 2741.508 | 493.47 | 2023-10-27 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157116.752 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1008-2BHK Vitrified Skirting | 91.44 | 22 | 0 | 2011.68 | 362.1 | 2023-10-27 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157846.58 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-905-3BHK Vitrified Skirting | 124.614 | 20 | 0 | 2492.28 | 448.61 | 2023-10-27 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157365.98 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1006-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.39 | 2023-10-27 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159450.524 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1005-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 1031.55 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -154127.396 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-907-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 927.67 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -154704.524 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1008-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.59 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -158382.764 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-905-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.37 | 2023-10-27 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157856.18 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1007-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.51 | 2023-10-27 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159527.636 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1008-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.51 | 2023-10-27 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -159527.636 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-908-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 927.67 | 2023-10-27 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -154704.524 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1007-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2023-10-27 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -152520.596 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-906-3BHK Vitrified Skirting | 124.614 | 20 | 0 | 2492.28 | 448.61 | 2023-10-27 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103063 | 2023-10-30 | 159858.26 | 2023-11-08 16:30 | -157365.98 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-305-3BHK Vitrified Flooring Work | 334.73 | 14 | 0 | 4686.22 | 0 | 2024-05-09 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107495 | 2024-05-13 | 47190.66 | 2024-06-15 11:47 | -42504.44 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-608-2BHK Vitrified Flooring Work | 254.78 | 16 | 0 | 4076.48 | 0 | 2024-05-09 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107495 | 2024-05-13 | 47190.66 | 2024-06-15 11:47 | -43114.18 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-607-2BHK Vitrified Flooring Work | 254.78 | 16 | 0 | 4076.48 | 0 | 2024-05-09 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107495 | 2024-05-13 | 47190.66 | 2024-06-15 11:47 | -43114.18 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-306-3BHK Vitrified Flooring Work | 334.73 | 14 | 0 | 4686.22 | 0 | 2024-05-09 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107495 | 2024-05-13 | 47190.66 | 2024-06-15 11:47 | -42504.44 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-307-2BHK Vitrified Flooring Work | 254.78 | 14 | 0 | 3566.92 | 0 | 2024-05-09 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107495 | 2024-05-13 | 47190.66 | 2024-06-15 11:47 | -43623.74 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-405-3BHK Vitrified Flooring Work | 334.73 | 14 | 0 | 4686.22 | 0 | 2024-05-09 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107495 | 2024-05-13 | 47190.66 | 2024-06-15 11:47 | -42504.44 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-407-2BHK Vitrified Flooring Work | 254.78 | 14 | 0 | 3566.92 | 0 | 2024-05-09 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107495 | 2024-05-13 | 47190.66 | 2024-06-15 11:47 | -43623.74 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-308-2BHK Vitrified Flooring Work | 254.78 | 14 | 0 | 3566.92 | 0 | 2024-05-09 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107495 | 2024-05-13 | 47190.66 | 2024-06-15 11:47 | -43623.74 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-605-3BHK Vitrified Flooring Work | 334.73 | 16 | 0 | 5355.68 | 0 | 2024-05-09 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107495 | 2024-05-13 | 47190.66 | 2024-06-15 11:47 | -41834.98 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-606-3BHK Vitrified Flooring Work | 334.73 | 16 | 0 | 5355.68 | 0 | 2024-05-09 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107495 | 2024-05-13 | 47190.66 | 2024-06-15 11:47 | -41834.98 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-408-2BHK Vitrified Flooring Work | 254.78 | 14 | 0 | 3566.92 | 0 | 2024-05-09 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 107495 | 2024-05-13 | 47190.66 | 2024-06-15 11:47 | -43623.74 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1108-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -404770.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1705-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -408120.692 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1507-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409182.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1307-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 351.51 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410155.516 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1607-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411746.228 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1407-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411549.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1508-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405972.94 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1707-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410504.54 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1308-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -404770.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1508-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409182.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1406-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 100.62 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411549.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1808-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1108-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 351.51 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410155.516 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1408-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.51 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411777.716 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1508-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 288.68 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410504.54 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1607-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1705-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 456.47 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409572.372 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1308-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.51 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411777.716 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1507-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411746.228 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1708-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 65.18 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411746.228 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1805-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 109.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411500.74 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1406-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -402468.116 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1608-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409182.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1806-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 80.38 | 2024-01-12 | Labour Charges for- Ceramic Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -411661.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1406-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 254.89 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410692.276 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1408-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.59 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410632.844 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1608-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 1104.37 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405972.94 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1406-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 657.96 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -408452.996 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1708-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 526.69 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409182.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1805-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 717.78 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -408120.692 | S S ENTERISES (PROP. SOBRAN SINGH)
Ceramic Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1508-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 392.86 | 2024-01-12 | Labour Charges for- Ceramic Flooring (300 x 300mm) work with floor guard laying .Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409925.772 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1108-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 265.59 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410632.844 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1605-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 277.06 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -410569.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Dado BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1805-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 1121.26 | 2024-01-12 | Labour Charges for- Fixing of Ceramic Dado in Toilet (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -405879.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1407-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -404770.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1408-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -404770.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1505-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 1928.04 | 2024-01-12 | Labour Charges for- Vitrified Flooring (600 x 600mm) work with floor guard laying . Including Proper line,level,right angle & joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -401396.98 | S S ENTERISES (PROP. SOBRAN SINGH)
Vitrified Skirting BC | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1308-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 482.8 | 2024-01-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 104548 | 2024-01-15 | 412108.34 | 2024-02-05 11:45 | -409426.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-207-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108397 | 2024-06-17 | 1306.3 | 1900-01-01 | -1019.12 | MAULI ENTERPRISES
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-207-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108397 | 2024-06-17 | 1306.3 | 1900-01-01 | -287.18 | MAULI ENTERPRISES
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-706-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105458 | 2024-02-23 | 6690.4 | 2024-03-02 12:06 | -5351.48 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-306-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105458 | 2024-02-23 | 6690.4 | 2024-03-02 12:06 | -6356.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-406-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105458 | 2024-02-23 | 6690.4 | 2024-03-02 12:06 | -5351.48 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-805-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105458 | 2024-02-23 | 6690.4 | 2024-03-02 12:06 | -6356.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-306-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105458 | 2024-02-23 | 6690.4 | 2024-03-02 12:06 | -5351.48 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-406-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105458 | 2024-02-23 | 6690.4 | 2024-03-02 12:06 | -6356.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-805-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105458 | 2024-02-23 | 6690.4 | 2024-03-02 12:06 | -5351.48 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-706-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105458 | 2024-02-23 | 6690.4 | 2024-03-02 12:06 | -6356.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-905-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17539.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-907-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17586.22 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-905-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16534.48 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-608-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16854.28 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-705-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16534.48 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-806-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17539.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-807-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16854.28 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-405-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16534.48 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-705-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17539.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-908-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16854.28 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-808-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17586.22 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-807-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17586.22 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-806-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16534.48 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-808-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16854.28 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-605-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16534.48 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-608-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17586.22 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-908-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17586.22 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-707-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17586.22 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-707-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16854.28 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-405-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17539.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-907-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16854.28 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-605-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17539.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-606-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -17539.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-606-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106213 | 2024-03-18 | 17873.4 | 2024-03-28 14:38 | -16534.48 | A R CLEANING SERVICS
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-202-2BHK(Near Refuse Area) Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-02-03 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-203-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-302-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-403-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-504-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-306-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-507-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-606-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 0 | 2024-03-18 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 107242 | 2024-04-30 | 2500 | 2024-05-03 13:23 | -2250 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-607-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 0 | 2024-03-18 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 107242 | 2024-04-30 | 2500 | 2024-05-03 13:23 | -2250 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-508-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 0 | 2024-03-18 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 107242 | 2024-04-30 | 2500 | 2024-05-03 13:23 | -2250 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-601-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 0 | 2024-03-18 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 107242 | 2024-04-30 | 2500 | 2024-05-03 13:23 | -2250 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-506-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 0 | 2024-03-18 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 107242 | 2024-04-30 | 2500 | 2024-05-03 13:23 | -2250 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-605-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 0 | 2024-03-18 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 107242 | 2024-04-30 | 2500 | 2024-05-03 13:23 | -2250 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-604-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 0 | 2024-03-18 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 107242 | 2024-04-30 | 2500 | 2024-05-03 13:23 | -2250 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-603-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 0 | 2024-03-18 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 107242 | 2024-04-30 | 2500 | 2024-05-03 13:23 | -2250 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-608-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 0 | 2024-03-18 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 107242 | 2024-04-30 | 2500 | 2024-05-03 13:23 | -2250 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-502-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 0 | 2024-03-18 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 107242 | 2024-04-30 | 2500 | 2024-05-03 13:23 | -2250 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1007-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1208-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-907-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-703-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-806-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1205-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-707-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1207-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-706-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-807-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1005-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-906-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-805-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-705-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-901-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1002-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1203-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1008-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1904-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-904-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1902-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-708-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1401-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1006-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1206-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-804-2BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-701-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-902-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1201-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-802-3BHK Kadappa Black Oil Paint Work | 1 | 500 | 0 | 500 | 0 | 2024-04-12 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 106781 | 2024-04-15 | 15000 | 2024-04-30 15:25 | -14500 | BHARAT KASHINATH KARCHE
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-307-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-308-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-408-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-903-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-304-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-401-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-908-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-303-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-305-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-404-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-204-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-505-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-208-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-201-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-206-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1102-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-207-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-301-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-905-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-503-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-02-05 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-205-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-405-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-406-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-407-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-402-3BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
Oil Paint lumpsum- BC | N/C | N/C | YUGESH KUMAR | 489 | 2022-07-16 | D-1004-2BHK Kadappa Black Oil Paint Work | 0.5 | 500 | 0 | 250 | 45 | 2024-01-31 | Material and Labour charges for Applying 2 coat Black oil Paint for Kadappa for D-Building Internal Flats. | 100 |  | 105086 | 2024-02-05 | 8250 | 2024-02-19 15:15 | -8000 | RUSHIYOGI ENTERPRISES
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2007-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-004-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-15 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-801-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1003-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1105-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1401-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1802-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-808-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1602-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1606-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1608-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1704-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2008-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-106-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-204-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-305-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-403-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-502-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-701-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1004-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1008-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1601-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2002-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2006-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-503-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-303-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-304-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-602-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1005-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1103-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1104-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-001-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-15 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-508-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1304-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1307-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1801-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1306-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1402-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1703-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1805-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1901-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-203-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1201-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1405-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1604-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1806-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-903-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-904-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-907-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1308-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1804-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1504-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1506-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1902-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1905-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2001-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2003-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-408-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-504-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-802-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1302-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1305-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-806-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1301-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1706-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-105-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-201-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-206-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-307-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1102-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1107-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1505-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1508-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1903-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2005-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-301-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-205-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-601-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-605-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-703-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-704-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1108-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1203-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1502-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-404-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-501-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-505-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-603-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-702-2BHK(Near Refuse Area) FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-705-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1002-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1007-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1407-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-002-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-15 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-402-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-406-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1403-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1701-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1702-2BHK(Near Refuse Area) FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1705-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1707-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1708-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1803-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-607-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-804-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-906-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1204-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1208-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1503-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1807-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2206-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2208-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2304-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2408-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2101-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2103-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2305-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2307-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2201-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2203-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2207-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2406-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2402-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2403-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2308-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2401-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2404-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2108-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2303-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2104-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2202-2BHK(Near Refuse Area) FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2204-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2105-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2205-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2407-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2306-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2405-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2302-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2102-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2301-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2106-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40500 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2107-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-07-30 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 109563 | 2024-08-05 | 41917.5 | 1900-01-01 | -40702.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-202-2BHK(Near Refuse Area) FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-506-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-608-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-803-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1001-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1106-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1205-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1303-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1808-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-005-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-15 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-007-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-101-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-006-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-102-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-302-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-306-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-008-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-104-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-401-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-207-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-308-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-707-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-708-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1006-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1501-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1507-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1907-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-103-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-107-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-405-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-507-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-805-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-901-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-902-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-908-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1206-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-003-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-15 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-604-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-807-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-905-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1408-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1607-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1904-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-208-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-606-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1101-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1406-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1603-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1906-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1908-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-2004-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-108-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-407-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-706-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1202-2BHK(Near Refuse Area) FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1207-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1404-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -219105 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 491 | 2022-07-16 | E-1605-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2024-01-18 | Labour Charges for FAS Conduit & Cabel laying work.E Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 104669 | 2024-01-22 | 220320 | 1900-01-01 | -218902.5 | HARISH CHANDRA JADHAV ELECTRICALS
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg Terrace Slab+LMR+OHWT - Brickbat W/P (L) | 189.66 | 24 | 0 | 4551.84 | 0 | 2024-06-28 16:46 | Labour charges for Brickbat Waterproofing work for LMR Top Slab for F-Bldg. | 100 |  | 108685 | 2024-07-01 | 56632.26 | 1900-01-01 | -52080.42 | PRABHURAM VERMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg OHWT-Internal Waterproofing Work (L) | 88.377 | 22 | 0 | 1944.294 | 0 | 2024-06-28 16:46 | Labour and Material Charges for Vertical Pardi Chemical Grouting work for Flushing water tank, Domestic water tank and Fire water tank for OHWT Internal waterproofing work. | 100 |  | 108685 | 2024-07-01 | 56632.26 | 1900-01-01 | -54687.966 | PRABHURAM VERMA
Pressure Grouting (M+L) | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg OHWT-Internal Waterproofing Work (L) | 40 | 160 | 0 | 6400 | 0 | 2024-06-28 16:46 | Labour Charges for Vertical Pardi Chemical Grouting work for Flushing water tank, Domestic water tank and Fire water tank for OHWT Internal waterproofing work. | 100 |  | 108685 | 2024-07-01 | 56632.26 | 1900-01-01 | -50232.26 | PRABHURAM VERMA
Ghotai Plaster - DPo | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg OHWT-Internal Waterproofing Work (L) | 88.377 | 15 | 0 | 1325.655 | 0 | 2024-06-28 16:46 | Labour Charges for Vertical Pardi Ghotai work for Flushing water tank, Domestic water tank and Fire water tank for OHWT Internal waterproofing work. | 100 |  | 108685 | 2024-07-01 | 56632.26 | 1900-01-01 | -55306.605 | PRABHURAM VERMA
Screeding work- UST | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg OHWT-Internal Waterproofing Work (L) | 32.407 | 15 | 0 | 486.105 | 0 | 2024-06-28 16:46 | Labour charges for Horizontal Base Bottom Screeding work for Flushing Water tank, Domestic water tank, Fire water tank for OHWT Internal waterproofing work F-Bldg. | 100 |  | 108685 | 2024-07-01 | 56632.26 | 1900-01-01 | -56146.155 | PRABHURAM VERMA
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg Terrace Slab+LMR+OHWT - Brickbat W/P (L) | 1396.392 | 24 | 0 | 33513.408 | 0 | 2024-06-28 16:46 | Labour charges for Brickbat Waterproofing work for Terrace Area, Terrace Between ST & OHT and Regular ST & Front Lobby for F-Bldg. | 100 |  | 108685 | 2024-07-01 | 56632.26 | 1900-01-01 | -23118.852 | PRABHURAM VERMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg OHWT-Internal Waterproofing Work (L) | 32.407 | 22 | 0 | 712.954 | 0 | 2024-06-28 16:46 | Material and Labour Charges for Horizontal Base Chemical Grouting work for Flushing water tank, Domestic water tank and Fire water tank for OHWT Internal waterproofing work. | 100 |  | 108685 | 2024-07-01 | 56632.26 | 1900-01-01 | -55919.306 | PRABHURAM VERMA
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg Terrace Slab+LMR+OHWT - Brickbat W/P (L) | 320.75 | 24 | 0 | 7698 | 0 | 2024-06-28 16:46 | Labour charges for Brickbat Waterproofing work for OHWT Top Slab for F-Bldg. | 100 |  | 108685 | 2024-07-01 | 56632.26 | 1900-01-01 | -48934.26 | PRABHURAM VERMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg OHWT-Internal Waterproofing Work (L) | 795.393 | 22 | 0 | 17498.646 | 3149.76 | 2023-01-05 | Labour and Material Charges for Vertical Pardi Chemical Grouting work for Flushing water tank, Domestic water tank and Fire water tank for OHWT Internal waterproofing work. | 100 |  | 97661 | 2023-01-06 | 40221.09 | 2023-01-31 12:04 | -22722.444 | GANGAPRASAD K VARMA
Ghotai Plaster - DPo | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg OHWT-Internal Waterproofing Work (L) | 795.393 | 15 | 0 | 11930.895 | 2147.56 | 2023-01-05 | Labour Charges for Vertical Pardi Ghotai work for Flushing water tank, Domestic water tank and Fire water tank for OHWT Internal waterproofing work. | 100 |  | 97661 | 2023-01-06 | 40221.09 | 2023-01-31 12:04 | -28290.195 | GANGAPRASAD K VARMA
Screeding work- UST | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg OHWT-Internal Waterproofing Work (L) | 291.663 | 15 | 0 | 4374.945 | 787.5 | 2023-01-05 | Labour charges for Horizontal Base Bottom Screeding work for Flushing Water tank, Domestic water tank, Fire water tank for OHWT Internal waterproofing work F-Bldg. | 100 |  | 97661 | 2023-01-06 | 40221.09 | 2023-01-31 12:04 | -35846.145 | GANGAPRASAD K VARMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg OHWT-Internal Waterproofing Work (L) | 291.663 | 22 | 0 | 6416.586 | 1154.98 | 2023-01-05 | Material and Labour Charges for Horizontal Base Chemical Grouting work for Flushing water tank, Domestic water tank and Fire water tank for OHWT Internal waterproofing work. | 100 |  | 97661 | 2023-01-06 | 40221.09 | 2023-01-31 12:04 | -33804.504 | GANGAPRASAD K VARMA
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 492 | 2022-07-21 | F-Bldg Terrace Slab+LMR+OHWT - Brickbat W/P (L) | 5585.568 | 24 | 0 | 134053.632 | 24129.66 | 2023-02-23 | Labour charges for Brickbat Waterproofing work for Terrace Area, Terrace Between ST & OHT and Regular ST & Front Lobby for F-Bldg. | 100 |  | 98316 | 2023-02-24 | 134053.63 | 2023-03-20 11:51 | 0.002 | GANGAPRASAD K VARMA
P.U. Paint Patta (M+L) | N/C | N/C | SHINE COATS | 497 | 2022-07-29 | D-P3 Fl Marking Paint | 432.8 | 20 | 0 | 8656 | 1558.08 | 2024-06-02 | Labour charges for Marking P.U. Paint Patta work (50 mm) for D-Building Parking P3 Floor. | 100 |  | 107929 | 2024-06-03 | 29712 | 2024-06-26 11:45 | -21056 | SHINE COATS
P.U. Paint Patta (M+L) | N/C | N/C | SHINE COATS | 497 | 2022-07-29 | D-P1 Fl Marking Paint | 367 | 20 | 0 | 7340 | 1321.2 | 2024-06-02 | Labour charges for Marking P.U. Paint Patta work (50 mm) for D-Building Parking P1 Floor. | 100 |  | 107929 | 2024-06-03 | 29712 | 2024-06-26 11:45 | -22372 | SHINE COATS
P.U. Paint Patta (M+L) | N/C | N/C | SHINE COATS | 497 | 2022-07-29 | F-Bldg Parking Patta Marking | 240.8 | 20 | 0 | 4816 | 866.88 | 2024-06-02 | Labour Charges for- P.U.Paint patta (75mm in width & 5mm thick) work for F Building parking area. | 100 |  | 107929 | 2024-06-03 | 29712 | 2024-06-26 11:45 | -24896 | SHINE COATS
P.U. Paint Patta (M+L) | N/C | N/C | SHINE COATS | 497 | 2022-07-29 | D-P2 Fl Marking Paint | 445 | 20 | 0 | 8900 | 1602 | 2024-06-02 | Labour charges for Marking P.U. Paint Patta work (50 mm) for D-Building Parking P2 Floor. | 100 |  | 107929 | 2024-06-03 | 29712 | 2024-06-26 11:45 | -20812 | SHINE COATS
Ghotai Plaster - DPo | N/C | N/C | AJAY KUMAR GUPTA | 498 | 2022-07-29 | D-Bldg OHWT Internal Waterproofing | 1336.013 | 15 | 0 | 20040.195 | 0 | 2024-03-16 | Labour charges for Vertical Pardi Ghotai work for Flushing water tank, Domestic water tank, Fire Water tank, Utility water tank for OHWT Internal waterproofing work D-Building | 100 |  | 106105 | 2024-03-18 | 72457.34 | 2024-03-26 14:52 | -52417.145 | PRABHURAM VERMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AJAY KUMAR GUPTA | 498 | 2022-07-29 | D-Bldg OHWT Internal Waterproofing | 622.293 | 22 | 0 | 13690.446 | 0 | 2024-03-16 | Labour and Material charges for Horizontal surface Chemical Grouting work for Flushing water tank, Domestic water tank, Fire Water tank, Utility water tank for OHWT Internal waterproofing work D-Building. | 100 |  | 106105 | 2024-03-18 | 72457.34 | 2024-03-26 14:52 | -58766.894 | PRABHURAM VERMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AJAY KUMAR GUPTA | 498 | 2022-07-29 | D-Bldg OHWT Internal Waterproofing | 1336.013 | 22 | 0 | 29392.286 | 0 | 2024-03-16 | Labour and Material charges for Vertical Pardi Chemical Grouting work for Flushing water tank, Domestic water tank, Fire Water tank, Utility water tank for OHWT Internal waterproofing work D-Building. | 100 |  | 106105 | 2024-03-18 | 72457.34 | 2024-03-26 14:52 | -43065.054 | PRABHURAM VERMA
Screeding work- UST | N/C | N/C | AJAY KUMAR GUPTA | 498 | 2022-07-29 | D-Bldg OHWT Internal Waterproofing | 622.293 | 15 | 0 | 9334.395 | 0 | 2024-03-16 | Labour charges for Horizontal surface Screeding work for Flushing water tank, Domestic water tank, Fire Water tank, Utility water tank for OHWT Internal waterproofing work D-Building. | 100 |  | 106105 | 2024-03-18 | 72457.34 | 2024-03-26 14:52 | -63122.945 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | AJAY KUMAR GUPTA | 498 | 2022-07-29 | D-Bldg Terrace Floor Waterproofing Work (L) | 1692.935 | 24 | 0 | 40630.44 | 0 | 2024-07-08 | Labour Charges for Brickbat waterproofing work for Terrace floor P-Line North, P-line South & P-line East west D-Building. | 100 |  | 108932 | 2024-07-08 | 40630.44 | 2024-08-05 14:03 | 0 | PRABHURAM VERMA
Pressure Grouting (M+L) | N/C | N/C | AJAY KUMAR GUPTA | 498 | 2022-07-29 | D-Bldg OHWT Internal Waterproofing | 56 | 160 | 0 | 8960 | 1612.8 | 2024-03-16 | Labour and Material charges for Vertical Pardi Pressure Grouting work for Flushing water tank, Domestic water tank, Fire Water tank, Utility water tank for OHWT Internal waterproofing work D-Building | 100 |  | 106103 | 2024-03-18 | 8960 | 1900-01-01 | 0 | TEJASHREE ENTERPRISES
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 500 | 2022-07-30 | D-Bldg 2nd Floor Gypsum Work-Int Flat Near Refuge Area | 294.29 | 10 | 0 | 2942.9 | 529.72 | 2024-06-14 | Labour charges for Gypsum Plaster work on wall for Flats near Refuge Area D-Building. | 100 |  | 108380 | 2024-06-17 | 5885.8 | 2024-07-15 14:57 | -2942.9 | SHREE RAM INTERIOR & DECORATORS
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 500 | 2022-07-30 | D-Bldg 7th Floor Gypsum Work-Int Flat Near Refuge Area | 294.29 | 10 | 0 | 2942.9 | 529.72 | 2024-06-14 | Labour charges for Gypsum Plaster work on wall for Flats near Refuge Area D-Building. | 100 |  | 108380 | 2024-06-17 | 5885.8 | 2024-07-15 14:57 | -2942.9 | SHREE RAM INTERIOR & DECORATORS
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 501 | 2022-07-30 | D-Bldg 2nd Floor Gypsum Work-Int Flat Near Refuge Area | 294.29 | 10 | 0 | 2942.9 | 147.14 | 2023-10-17 | Material Supply for Gypsum Plaster work on wall for Flats near Refuse Area D-Building. | 100 | Invoice No-LSF/826/2023-24 | 102739 | 2023-10-18 | 8828.7 | 2024-01-16 15:51 | -5885.8 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 501 | 2022-07-30 | D-Bldg 7th Floor Gypsum Work-Int Flat Near Refuge Area | 294.29 | 10 | 0 | 2942.9 | 147.14 | 2023-10-17 | Material Supply for Gypsum Plaster work on wall for Flats near Refuse Area D-Building. | 100 | Invoice No-LSF/826/2023-24 | 102739 | 2023-10-18 | 8828.7 | 2024-01-16 15:51 | -5885.8 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 501 | 2022-07-30 | D-Bldg 12th Floor Gypsum Work-Int Flat Near Refuge Area | 294.29 | 10 | 0 | 2942.9 | 147.14 | 2023-10-17 | Material Supply for Gypsum Plaster work on wall for Flats near Refuse Area D-Building. | 100 | Invoice No-LSF/826/2023-24 | 102739 | 2023-10-18 | 8828.7 | 2024-01-16 15:51 | -5885.8 | LAXMI STRUCTURES & FIXTURES LLP
Skirting Fixing - AIE | N/C | N/C | PAPPU BAGELA | 502 | 2022-08-01 | D-Bldg 7th Floor Refuge Area Skirting Work | 59.456 | 20 | 0 | 1189.12 | 0 | 2024-06-07 | Labour Charges for- Cutting and Fixing of Skiring with proper line,level & Right angle. | 100 |  | 108205 | 2024-06-10 | 13776.77 | 1900-01-01 | -12587.65 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | PAPPU BAGELA | 502 | 2022-08-01 | D-Bldg 12th Floor Refuge Area Skirting Work | 59.456 | 22 | 0 | 1308.032 | 0 | 2024-06-07 | Labour Charges for- Cutting and Fixing of Skiring with proper line,level & Right angle. | 100 |  | 108205 | 2024-06-10 | 13776.77 | 1900-01-01 | -12468.738 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 502 | 2022-08-01 | D-Bldg 12th Floor Refuge Area Flooring Work | 212.696 | 18 | 0 | 3828.528 | 0 | 2024-06-07 | Labour Charges for- Floor Guard laying & Floring work with proper line, level & right angle. | 100 |  | 108205 | 2024-06-10 | 13776.77 | 1900-01-01 | -9948.242 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 502 | 2022-08-01 | D-Bldg 2nd Floor Refuge Area Flooring Work | 212.696 | 14 | 0 | 2977.744 | 0 | 2024-06-07 | Labour Charges for- Floor Guard laying & Floring work with proper line, level & right angle. | 100 |  | 108205 | 2024-06-10 | 13776.77 | 1900-01-01 | -10799.026 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 502 | 2022-08-01 | D-Bldg 7th Floor Refuge Area Flooring Work | 212.696 | 16 | 0 | 3403.136 | 0 | 2024-06-07 | Labour Charges for- Floor Guard laying & Floring work with proper line, level & right angle. | 100 |  | 108205 | 2024-06-10 | 13776.77 | 1900-01-01 | -10373.634 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | PAPPU BAGELA | 502 | 2022-08-01 | D-Bldg 2nd Floor Refuge Area Skirting Work | 59.456 | 18 | 0 | 1070.208 | 0 | 2024-06-07 | Labour Charges for- Cutting and Fixing of Skiring with proper line,level & Right angle. | 100 |  | 108205 | 2024-06-10 | 13776.77 | 1900-01-01 | -12706.562 | PAPPU BAGELA
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg Stilt Floor Duct External Plaster Work | 300 | 20 | 0 | 6000 | 0 | 2023-05-13 | Labour Charges for-F Building Duct Single Coat Sand Face External plaster work with specified proportion incl. Scaffolding fixing & removing with proper joint using Chiken mesh,nails,drill machine etc to be in contractor Scope. | 100 |  | 99650 | 2023-05-16 | 30664 | 2023-06-10 10:37 | -24664 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg Terrace Floor Duct External Plaster Work | 333.2 | 20 | 0 | 6664 | 0 | 2023-05-13 | Labour Charges for-F Building Duct Single Coat Sand Face External plaster work with specified proportion incl. Scaffolding fixing & removing with proper joint using Chiken mesh,nails,drill machine etc to be in contractor Scope. | 100 |  | 99650 | 2023-05-16 | 30664 | 2023-06-10 10:37 | -24000 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg 3rd Floor Duct External Plaster Work | 300 | 20 | 0 | 6000 | 0 | 2023-05-13 | Labour Charges for-F Building Duct Single Coat Sand Face External plaster work with specified proportion incl. Scaffolding fixing & removing with proper joint using Chiken mesh,nails,drill machine etc to be in contractor Scope. | 100 |  | 99650 | 2023-05-16 | 30664 | 2023-06-10 10:37 | -24664 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg 1st Floor Duct External Plaster Work | 300 | 20 | 0 | 6000 | 0 | 2023-05-13 | Labour Charges for-F Building Duct Single Coat Sand Face External plaster work with specified proportion incl. Scaffolding fixing & removing with proper joint using Chiken mesh,nails,drill machine etc to be in contractor Scope. | 100 |  | 99650 | 2023-05-16 | 30664 | 2023-06-10 10:37 | -24664 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg 2nd Floor Duct External Plaster Work | 300 | 20 | 0 | 6000 | 0 | 2023-05-13 | Labour Charges for-F Building Duct Single Coat Sand Face External plaster work with specified proportion incl. Scaffolding fixing & removing with proper joint using Chiken mesh,nails,drill machine etc to be in contractor Scope. | 100 |  | 99650 | 2023-05-16 | 30664 | 2023-06-10 10:37 | -24664 | K RAMU RATHOD
PCC Work | N/C | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg OPD No- 10 Customer Changes | 240.8 | 6 | 0 | 1444.8 | 0 | 2023-10-10 15:04 | Labour Charges for PCC Work for OPD No 10 at 1st floor. | 100 |  | 102498 | 2023-10-11 | 1984.3 | 2023-10-23 12:32 | -539.5 | PRABHURAM VERMA
Siporex Filling-DLd | N/C | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg OPD No- 10 Customer Changes | 83 | 6.5 | 0 | 539.5 | 0 | 2023-10-10 15:04 | Labour Charges for Siprox filling Work for OPD No 10 at 1st floor. | 100 |  | 102498 | 2023-10-11 | 1984.3 | 2023-10-23 12:32 | -1444.8 | PRABHURAM VERMA
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg Terrace Floor Duct External Plaster Work | 467.49 | 20 | 0 | 9349.8 | 0 | 2022-12-09 | Labour Charges for-F Building Duct Single Coat Sand Face External plaster work with specified proportion incl. Scaffolding fixing & removing with proper joint using Chiken mesh,nails,drill machine etc to be in contractor Scope. | 100 |  | 97325 | 2022-12-10 | 22273.85 | 2022-12-23 11:40 | -12924.05 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg 3rd Floor Duct External Plaster Work | 646.2025 | 20 | 0 | 12924.05 | 0 | 2022-12-09 | Labour Charges for-F Building Duct Single Coat Sand Face External plaster work with specified proportion incl. Scaffolding fixing & removing with proper joint using Chiken mesh,nails,drill machine etc to be in contractor Scope. | 100 |  | 97325 | 2022-12-10 | 22273.85 | 2022-12-23 11:40 | -9349.8 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg 2nd Floor Duct External Plaster Work | 1938.6075 | 20 | 0 | 38772.15 | 0 | 2023-01-17 | Labour Charges for-F Building Duct Single Coat Sand Face External plaster work with specified proportion incl. Scaffolding fixing & removing with proper joint using Chiken mesh,nails,drill machine etc to be in contractor Scope. | 100 |  | 97844 | 2023-01-18 | 143912.2 | 2023-01-31 11:45 | -105140.05 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg Stilt Floor Duct External Plaster Work | 2048.5125 | 20 | 0 | 40970.25 | 0 | 2023-01-17 | Labour Charges for-F Building Duct Single Coat Sand Face External plaster work with specified proportion incl. Scaffolding fixing & removing with proper joint using Chiken mesh,nails,drill machine etc to be in contractor Scope. | 100 |  | 97844 | 2023-01-18 | 143912.2 | 2023-01-31 11:45 | -102941.95 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg 3rd Floor Duct External Plaster Work | 1292.405 | 20 | 0 | 25848.1 | 0 | 2023-01-17 | Labour Charges for-F Building Duct Single Coat Sand Face External plaster work with specified proportion incl. Scaffolding fixing & removing with proper joint using Chiken mesh,nails,drill machine etc to be in contractor Scope. | 100 |  | 97844 | 2023-01-18 | 143912.2 | 2023-01-31 11:45 | -118064.1 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg 1st Floor Duct External Plaster Work | 1916.085 | 20 | 0 | 38321.7 | 0 | 2023-01-17 | Labour Charges for-F Building Duct Single Coat Sand Face External plaster work with specified proportion incl. Scaffolding fixing & removing with proper joint using Chiken mesh,nails,drill machine etc to be in contractor Scope. | 100 |  | 97844 | 2023-01-18 | 143912.2 | 2023-01-31 11:45 | -105590.5 | K RAMU RATHOD
Siporex Filling-DLd | N/C | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg 2nd Slab Sunk Filling Work (L) | 979.96 | 6.5 | 0 | 6369.74 | 0 | 2023-05-02 | Labour Charges for- Siporex block filling (Broken) for sunk filling at 2nd slab of F Building (Hospital) | 100 |  | 99384 | 2023-05-03 | 12342.7 | 2023-06-10 10:37 | -5972.96 | K RAMU RATHOD
PCC Work | N/C | N/C | K RAMU RATHOD | 503 | 2022-08-01 | F-Bldg 2nd Slab Sunk Filling Work (L) | 1493.24 | 4 | 0 | 5972.96 | 0 | 2023-05-02 | Labour Charges for- PCC Work for sunk filling at 2nd slab of F Building (Hospital).PCC to be done by RMC. | 100 |  | 99384 | 2023-05-03 | 12342.7 | 2023-06-10 10:37 | -6369.74 | K RAMU RATHOD
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 7th Floor Refuge Area Waterproofing Work | 212.696 | 22 | 0 | 4679.312 | 0 | 2024-07-23 | Labour and Material Supply Charges for Chemical waterproofing work at refuge area | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -10634.788 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 7th Floor Refuge Area Waterproofing Work | 212.696 | 2 | 0 | 425.392 | 0 | 2024-07-23 | Labour Charges for- Ghadai work including all tools & equipments required to prepare plane floor surface, including, cleaning, shifting debris at one place. | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -14888.708 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 12th Floor Refuge Area Waterproofing Work | 212.696 | 22 | 0 | 4679.312 | 0 | 2024-07-23 | Labour and Material Supply Charges for Chemical waterproofing work at refuge area | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -10634.788 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 2nd Floor Refuge Area Waterproofing Work | 212.696 | 2 | 0 | 425.392 | 0 | 2024-07-23 | Labour Charges for- Ghadai work including all tools & equipments required to prepare plane floor surface, including, cleaning, shifting debris at one place. | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -14888.708 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 12th Floor Refuge Area Waterproofing Work | 212.696 | 2 | 0 | 425.392 | 0 | 2024-07-23 | Labour Charges for- Ghadai work including all tools & equipments required to prepare plane floor surface, including, cleaning, shifting debris at one place. | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -14888.708 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | D-Bldg 2nd Floor Refuge Area Waterproofing Work | 212.696 | 22 | 0 | 4679.312 | 0 | 2024-07-23 | Labour and Material Supply Charges for Chemical waterproofing work at refuge area | 100 |  | 109383 | 2024-07-29 | 15314.1 | 1900-01-01 | -10634.788 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | Core Cutting Work- Rate Difference | 76 | 90 | 0 | 6840 | 0 | 2023-10-12 | Labour Charges for Rate differance of Horizontal 2 inch Core Cutting work at D Bldg | 100 |  | 102593 | 2023-10-13 | 14310 | 2023-11-07 13:58 | -7470 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | Core Cutting Work- Rate Difference | 83 | 90 | 0 | 7470 | 0 | 2023-10-12 | Labour Charges for Rate differance of Horizontal 5 inch Core Cutting work at D Bldg | 100 |  | 102593 | 2023-10-13 | 14310 | 2023-11-07 13:58 | -6840 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | Core Cutting Work- Rate Difference | 20 | 90 | 0 | 1800 | 0 | 2023-05-11 | Labour Charges for Rate differance of Horizontal 5 inch Core Cutting work at D Bldg | 100 |  | 99606 | 2023-05-12 | 10620 | 2023-05-29 13:08 | -8820 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | Core Cutting Work- Rate Difference | 98 | 90 | 0 | 8820 | 0 | 2023-05-11 | Labour Charges for Rate differance of Horizontal 2 inch Core Cutting work at D Bldg | 100 |  | 99606 | 2023-05-12 | 10620 | 2023-05-29 13:08 | -1800 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | Core Cutting Work- Rate Difference | 221 | 90 | 0 | 19890 | 0 | 2023-03-09 | Labour Charges for Rate differance of Horizontal 2 inch Core Cutting work at D Bldg | 100 |  | 98602 | 2023-03-09 | 28170 | 2023-03-29 11:33 | -8280 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | AJAY KUMAR GUPTA | 504 | 2022-08-01 | Core Cutting Work- Rate Difference | 92 | 90 | 0 | 8280 | 0 | 2023-03-09 | Labour Charges for Rate differance of Horizontal 5 inch Core Cutting work at D Bldg | 100 |  | 98602 | 2023-03-09 | 28170 | 2023-03-29 11:33 | -19890 | AJAY KUMAR GUPTA
Elect Meters UTI | N/C | N/C | ARYA CONSULTANCY | 507 | 2022-08-02 | Electricity Infrastructure | 500 | 2620.8 | 0 | 131040 | 23587.2 | 2022-10-14 | File Submission | 10 |  | 96759 | 2022-10-14 | 1310400 | 2022-10-14 12:25 | -1179360 | ARYA CONSULTANCY
Elect Meters UTI | N/C | N/C | ARYA CONSULTANCY | 507 | 2022-08-02 | Electricity Infrastructure | 500 | 2620.8 | 0 | 196560 | 35380.8 | 2022-10-14 | Site Visit | 15 |  | 96759 | 2022-10-14 | 1310400 | 2022-10-14 12:25 | -1113840 | ARYA CONSULTANCY
Elect Meters UTI | N/C | N/C | ARYA CONSULTANCY | 507 | 2022-08-02 | Electricity Infrastructure | 500 | 2620.8 | 0 | 262080 | 47174.4 | 2022-10-14 | Sanction Estimate Draft copy | 20 |  | 96759 | 2022-10-14 | 1310400 | 2022-10-14 12:25 | -1048320 | ARYA CONSULTANCY
Elect Meters UTI | N/C | N/C | ARYA CONSULTANCY | 507 | 2022-08-02 | Electricity Infrastructure | 500 | 2620.8 | 0 | 655200 | 117936 | 2022-10-14 | Sanction in Hand | 50 |  | 96759 | 2022-10-14 | 1310400 | 2022-10-14 12:25 | -655200 | ARYA CONSULTANCY
Elect Meters UTI | N/C | N/C | ARYA CONSULTANCY | 507 | 2022-08-02 | Electricity Infrastructure | 500 | 2620.8 | 0 | 65520 | 11793.6 | 2022-10-14 | Retention | 5 |  | 96759 | 2022-10-14 | 1310400 | 2022-10-14 12:25 | -1244880 | ARYA CONSULTANCY
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1603-2BHK Granite Work (M) | 2.52 | 110.7 | 0 | 278.964 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39956.026 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1304-2BHK Granite Work (M) | 89.46 | 110.7 | 0 | 9903.222 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -30331.768 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2001-3BHK Granite Work (M) | 12.8 | 110.7 | 0 | 1416.96 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -38818.03 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1802-3BHK Granite Work (M) | 12.8 | 110.7 | 0 | 1416.96 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -38818.03 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1602-3BHK Granite Work (M) | 4.5 | 110.7 | 0 | 498.15 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39736.84 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1904-2BHK Granite Work (M) | 10.94 | 110.7 | 0 | 1211.058 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39023.932 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1502-3BHK Granite Work (M) | 4.5 | 110.7 | 0 | 498.15 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39736.84 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1604-2BHK Granite Work (M) | 2.52 | 110.7 | 0 | 278.964 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39956.026 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1701-3BHK Granite Work (M) | 4.5 | 110.7 | 0 | 498.15 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39736.84 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2104-2BHK Granite Work (M) | 28.07 | 110.7 | 0 | 3107.349 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -37127.641 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2103-2BHK Granite Work (M) | 10.99 | 110.7 | 0 | 1216.593 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39018.397 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1901-3BHK Granite Work (M) | 12.82 | 110.7 | 0 | 1419.174 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -38815.816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2003-2BHK Granite Work (M) | 10.99 | 110.7 | 0 | 1216.593 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39018.397 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1501-3BHK Granite Work (M) | 4.5 | 110.7 | 0 | 498.15 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39736.84 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1804-2BHK Granite Work (M) | 89.46 | 110.7 | 0 | 9903.222 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -30331.768 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2002-3BHK Granite Work (M) | 12.8 | 110.7 | 0 | 1416.96 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -38818.03 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2004-2BHK Granite Work (M) | 10.99 | 110.7 | 0 | 1216.593 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39018.397 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1503-2BHK Granite Work (M) | 2.5 | 110.7 | 0 | 276.75 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39958.24 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1601-3BHK Granite Work (M) | 4.5 | 110.7 | 0 | 498.15 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39736.84 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1704-2BHK Granite Work (M) | 2.52 | 110.7 | 0 | 278.964 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39956.026 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1903-2BHK Granite Work (M) | 10.94 | 110.7 | 0 | 1211.058 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39023.932 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1801-3BHK Granite Work (M) | 12.82 | 110.7 | 0 | 1419.174 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -38815.816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1504-2BHK Granite Work (M) | 2.5 | 110.7 | 0 | 276.75 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39958.24 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1703-2BHK Granite Work (M) | 2.52 | 110.7 | 0 | 278.964 | 0 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 105888 | 2024-03-11 | 40234.99 | 2024-03-18 12:11 | -39956.026 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2004-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2002-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1304-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2201-3BHK Granite Work (M) | 61.39 | 110.7 | 0 | 6795.873 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -163388.727 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1903-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1902-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2103-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2302-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2203-2BHK Granite Work (M) | 61.39 | 110.7 | 0 | 6795.873 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -163388.727 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2001-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2002-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2001-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1903-2BHK Granite Work (M) | 78.47 | 110.7 | 0 | 8686.629 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -161497.971 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2301-3BHK Granite Work (M) | 61.39 | 110.7 | 0 | 6795.873 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -163388.727 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2304-2BHK Granite Work (M) | 61.39 | 110.7 | 0 | 6795.873 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -163388.727 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2003-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2302-3BHK Granite Work (M) | 61.39 | 110.7 | 0 | 6795.873 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -163388.727 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2104-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2203-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2003-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1904-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1901-3BHK Granite Work (M) | 77.69 | 110.7 | 0 | 8600.283 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -161584.317 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2303-2BHK Granite Work (M) | 61.39 | 110.7 | 0 | 6795.873 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -163388.727 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1901-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1903-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2303-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1901-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2004-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2301-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2003-2BHK Granite Work (M) | 78.47 | 110.7 | 0 | 8686.629 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -161497.971 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2302-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2101-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2002-3BHK Granite Work (M) | 77.69 | 110.7 | 0 | 8600.283 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -161584.317 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2004-2BHK Granite Work (M) | 78.47 | 110.7 | 0 | 8686.629 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -161497.971 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2101-3BHK Granite Work (M) | 61.39 | 110.7 | 0 | 6795.873 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -163388.727 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2103-2BHK Granite Work (M) | 78.47 | 110.7 | 0 | 8686.629 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -161497.971 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2304-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1904-2BHK Granite Work (M) | 78.47 | 110.7 | 0 | 8686.629 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -161497.971 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2201-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2204-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2203-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2104-2BHK Granite Work (M) | 61.39 | 110.7 | 0 | 6795.873 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -163388.727 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1904-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2101-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2103-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2304-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1604-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2104-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2303-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2001-3BHK Granite Work (M) | 77.69 | 110.7 | 0 | 8600.283 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -161584.317 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2301-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1604-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2204-2BHK Granite Work (M) | 61.39 | 110.7 | 0 | 6795.873 | 0 | 2024-01-10 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -163388.727 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1304-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -168538.7493 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2201-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2204-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2024-01-10 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104542 | 2024-01-15 | 170184.6 | 2024-01-23 14:18 | -169822.98 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-503-2BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-501-3BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-404-2BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-304-2BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-601-3BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-401-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2022-10-14 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -106213.3993 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-404-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2022-10-14 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -106213.3993 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-402-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2022-10-14 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -106213.3993 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-602-3BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-603-2BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-501-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2022-10-14 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -106213.3993 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-403-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2022-10-14 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -106213.3993 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-502-3BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-402-3BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-403-2BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-301-3BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-303-2BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-604-2BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-401-3BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-504-2BHK Granite Work (M) | 60 | 110.7 | 0 | 6642 | 0 | 2022-10-14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 96769 | 2022-10-15 | 107859.25 | 2022-10-17 18:50 | -101217.25 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-302-3BHK Granite Work (M) | 90.512 | 110.7 | 0 | 10019.6784 | 1803.54 | 2024-06-24 14:14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108589 | 2024-06-24 | 10019.68 | 1900-01-01 | -0.0016 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2302-3BHK Granite Work (M) | 29.12 | 110.7 | 0 | 3223.584 | 0 | 2024-06-07 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108230 | 2024-06-10 | 52585.81 | 2024-06-24 12:16 | -49362.226 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2204-2BHK Granite Work (M) | 28.07 | 110.7 | 0 | 3107.349 | 0 | 2024-06-07 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108230 | 2024-06-10 | 52585.81 | 2024-06-24 12:16 | -49478.461 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2403-2BHK Granite Work (M) | 82.4 | 110.7 | 0 | 9121.68 | 0 | 2024-06-07 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108230 | 2024-06-10 | 52585.81 | 2024-06-24 12:16 | -43464.13 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2201-3BHK Granite Work (M) | 29.12 | 110.7 | 0 | 3223.584 | 0 | 2024-06-07 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108230 | 2024-06-10 | 52585.81 | 2024-06-24 12:16 | -49362.226 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2303-2BHK Granite Work (M) | 28.07 | 110.7 | 0 | 3107.349 | 0 | 2024-06-07 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108230 | 2024-06-10 | 52585.81 | 2024-06-24 12:16 | -49478.461 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2301-3BHK Granite Work (M) | 29.12 | 110.7 | 0 | 3223.584 | 0 | 2024-06-07 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108230 | 2024-06-10 | 52585.81 | 2024-06-24 12:16 | -49362.226 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2304-2BHK Granite Work (M) | 28.07 | 110.7 | 0 | 3107.349 | 0 | 2024-06-07 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108230 | 2024-06-10 | 52585.81 | 2024-06-24 12:16 | -49478.461 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2203-2BHK Granite Work (M) | 28.07 | 110.7 | 0 | 3107.349 | 0 | 2024-06-07 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108230 | 2024-06-10 | 52585.81 | 2024-06-24 12:16 | -49478.461 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2404-2BHK Granite Work (M) | 82.4 | 110.7 | 0 | 9121.68 | 0 | 2024-06-07 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108230 | 2024-06-10 | 52585.81 | 2024-06-24 12:16 | -43464.13 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2401-3BHK Granite Work (M) | 81.47 | 110.7 | 0 | 9018.729 | 0 | 2024-06-07 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108230 | 2024-06-10 | 52585.81 | 2024-06-24 12:16 | -43567.081 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2101-3BHK Granite Work (M) | 29.12 | 110.7 | 0 | 3223.584 | 0 | 2024-06-07 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108230 | 2024-06-10 | 52585.81 | 2024-06-24 12:16 | -49362.226 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1302-3BHK Granite Work (M) | 54.3072 | 110.7 | 0 | 6011.807 | 0 | 2023-05-03 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 99415 | 2023-05-04 | 41803.15 | 2023-05-16 12:30 | -35791.343 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1303-2BHK Granite Work (M) | 53.676 | 110.7 | 0 | 5941.9332 | 0 | 2023-05-03 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 99415 | 2023-05-04 | 41803.15 | 2023-05-16 12:30 | -35861.2168 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1104-2BHK Granite Work (M) | 53.676 | 110.7 | 0 | 5941.9332 | 0 | 2023-05-03 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 99415 | 2023-05-04 | 41803.15 | 2023-05-16 12:30 | -35861.2168 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1204-2BHK Granite Work (M) | 53.676 | 110.7 | 0 | 5941.9332 | 0 | 2023-05-03 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 99415 | 2023-05-04 | 41803.15 | 2023-05-16 12:30 | -35861.2168 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1101-3BHK Granite Work (M) | 54.3072 | 110.7 | 0 | 6011.807 | 0 | 2023-05-03 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 99415 | 2023-05-04 | 41803.15 | 2023-05-16 12:30 | -35791.343 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1203-2BHK Granite Work (M) | 53.676 | 110.7 | 0 | 5941.9332 | 0 | 2023-05-03 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 99415 | 2023-05-04 | 41803.15 | 2023-05-16 12:30 | -35861.2168 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1301-3BHK Granite Work (M) | 54.3072 | 110.7 | 0 | 6011.807 | 0 | 2023-05-03 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 99415 | 2023-05-04 | 41803.15 | 2023-05-16 12:30 | -35791.343 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1802-3BHK Granite Work (M) | 16.3 | 110.7 | 0 | 1804.41 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -49918.73 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1504-2BHK Granite Work (M) | 8.469 | 110.7 | 0 | 937.5183 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -50785.6217 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1801-3BHK Granite Work (M) | 16.3 | 110.7 | 0 | 1804.41 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -49918.73 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1301-3BHK Granite Work (M) | 31.709 | 110.7 | 0 | 3510.1863 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -48212.9537 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1604-2BHK Granite Work (M) | 25.547 | 110.7 | 0 | 2828.0529 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -48895.0871 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1701-3BHK Granite Work (M) | 24.618 | 110.7 | 0 | 2725.2126 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -48997.9274 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1403-2BHK Granite Work (M) | 8.469 | 110.7 | 0 | 937.5183 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -50785.6217 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1503-2BHK Granite Work (M) | 8.469 | 110.7 | 0 | 937.5183 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -50785.6217 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1302-3BHK Granite Work (M) | 31.709 | 110.7 | 0 | 3510.1863 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -48212.9537 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1601-3BHK Granite Work (M) | 24.617 | 110.7 | 0 | 2725.1019 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -48998.0381 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1704-2BHK Granite Work (M) | 25.547 | 110.7 | 0 | 2828.0529 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -48895.0871 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1303-2BHK Granite Work (M) | 33.269 | 110.7 | 0 | 3682.8783 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -48040.2617 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1401-3BHK Granite Work (M) | 86.009 | 110.7 | 0 | 9521.1963 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -42201.9437 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1502-3BHK Granite Work (M) | 8.313 | 110.7 | 0 | 920.2491 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -50802.8909 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1703-2BHK Granite Work (M) | 25.547 | 110.7 | 0 | 2828.0529 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -48895.0871 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1404-2BHK Granite Work (M) | 8.469 | 110.7 | 0 | 937.5183 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -50785.6217 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1501-3BHK Granite Work (M) | 8.313 | 110.7 | 0 | 920.2491 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -50802.8909 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1602-3BHK Granite Work (M) | 24.617 | 110.7 | 0 | 2725.1019 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -48998.0381 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1803-2BHK Granite Work (M) | 17.08 | 110.7 | 0 | 1890.756 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -49832.384 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1402-3BHK Granite Work (M) | 8.319 | 110.7 | 0 | 920.9133 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -50802.2267 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1603-2BHK Granite Work (M) | 25.547 | 110.7 | 0 | 2828.0529 | 0 | 2023-12-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103817 | 2023-12-11 | 51723.14 | 2023-12-22 11:37 | -48895.0871 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-402-3BHK Granite Work (M) | 19.4239 | 110.7 | 0 | 2150.2257 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118273.5543 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-403-2BHK Granite Work (M) | 19.1981 | 110.7 | 0 | 2125.2297 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118298.5503 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-802-3BHK Granite Work (M) | 63.3584 | 110.7 | 0 | 7013.7749 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -113410.0051 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-804-2BHK Granite Work (M) | 62.622 | 110.7 | 0 | 6932.2554 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -113491.5246 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-502-3BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-904-2BHK Granite Work (M) | 62.622 | 110.7 | 0 | 6932.2554 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -113491.5246 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-602-3BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-603-2BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1004-2BHK Granite Work (M) | 62.622 | 110.7 | 0 | 6932.2554 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -113491.5246 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-501-3BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-901-3BHK Granite Work (M) | 63.3584 | 110.7 | 0 | 7013.7749 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -113410.0051 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-503-2BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-803-2BHK Granite Work (M) | 62.622 | 110.7 | 0 | 6932.2554 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -113491.5246 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1001-3BHK Granite Work (M) | 63.3584 | 110.7 | 0 | 7013.7749 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -113410.0051 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-304-2BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-601-3BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-903-2BHK Granite Work (M) | 62.622 | 110.7 | 0 | 6932.2554 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -113491.5246 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-401-3BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-504-2BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-801-3BHK Granite Work (M) | 63.3584 | 110.7 | 0 | 7013.7749 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -113410.0051 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1002-3BHK Granite Work (M) | 63.3584 | 110.7 | 0 | 7013.7749 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -113410.0051 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-404-2BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-902-3BHK Granite Work (M) | 63.3584 | 110.7 | 0 | 7013.7749 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -113410.0051 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-301-3BHK Granite Work (M) | 21.4604 | 110.7 | 0 | 2375.6663 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118048.1137 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-303-2BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-604-2BHK Granite Work (M) | 21.4634 | 110.7 | 0 | 2375.9984 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -118047.7816 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-701-3BHK Granite Work (M) | 76.9352 | 110.7 | 0 | 8516.7266 | 0 | 2023-03-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 98763 | 2023-03-17 | 120423.78 | 2023-03-29 11:34 | -111907.0534 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-703-2BHK Granite Work (M) | 89.46 | 110.7 | 0 | 9903.222 | 0 | 2024-06-24 14:29 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108590 | 2024-06-24 | 92595.01 | 1900-01-01 | -82691.788 | SONA MARBLE
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1003-2BHK Granite Work (M) | 89.46 | 110.7 | 0 | 9903.222 | 0 | 2024-06-24 14:14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108590 | 2024-06-24 | 92595.01 | 1900-01-01 | -82691.788 | SONA MARBLE
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2202-2BHK(Near Refuse Area) Granite Work (M) | 40.46 | 110.7 | 0 | 4478.922 | 0 | 2024-06-24 15:14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108590 | 2024-06-24 | 92595.01 | 1900-01-01 | -88116.088 | SONA MARBLE
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-704-2BHK Granite Work (M) | 89.46 | 110.7 | 0 | 9903.222 | 0 | 2024-06-24 14:14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108590 | 2024-06-24 | 92595.01 | 1900-01-01 | -82691.788 | SONA MARBLE
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-702-2BHK(Near Refuse Area) Granite Work (M) | 85.642 | 110.7 | 0 | 9480.5694 | 0 | 2024-06-24 14:29 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108590 | 2024-06-24 | 92595.01 | 1900-01-01 | -83114.4406 | SONA MARBLE
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2403-2BHK Granite Work (M) | 0.2 | 110.7 | 0 | 22.14 | 0 | 2024-06-24 15:24 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108590 | 2024-06-24 | 92595.01 | 1900-01-01 | -92572.87 | SONA MARBLE
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1103-2BHK Granite Work (M) | 89.46 | 110.7 | 0 | 9903.222 | 0 | 2024-06-24 14:14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108590 | 2024-06-24 | 92595.01 | 1900-01-01 | -82691.788 | SONA MARBLE
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1702-2BHK(Near Refuse Area) Granite Work (M) | 85.642 | 110.7 | 0 | 9480.5694 | 0 | 2024-06-24 14:14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108590 | 2024-06-24 | 92595.01 | 1900-01-01 | -83114.4406 | SONA MARBLE
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1102-3BHK Granite Work (M) | 90.512 | 110.7 | 0 | 10019.6784 | 0 | 2024-06-24 14:14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108590 | 2024-06-24 | 92595.01 | 1900-01-01 | -82575.3316 | SONA MARBLE
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1202-2BHK(Near Refuse Area) Granite Work (M) | 85.642 | 110.7 | 0 | 9480.5694 | 0 | 2024-06-24 14:14 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108590 | 2024-06-24 | 92595.01 | 1900-01-01 | -83114.4406 | SONA MARBLE
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-2102-3BHK Granite Work (M) | 90.512 | 110.7 | 0 | 10019.6784 | 0 | 2024-06-24 15:04 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 108590 | 2024-06-24 | 92595.01 | 1900-01-01 | -82575.3316 | SONA MARBLE
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1701-3BHK Granite Work (M) | 61.392 | 110.7 | 0 | 6796.0944 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -121712.8256 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1502-3BHK Granite Work (M) | 77.692 | 110.7 | 0 | 8600.5044 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -119908.4156 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1501-3BHK Granite Work (M) | 77.692 | 110.7 | 0 | 8600.5044 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -119908.4156 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1403-2BHK Granite Work (M) | 78.47 | 110.7 | 0 | 8686.629 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -119822.291 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1503-2BHK Granite Work (M) | 78.47 | 110.7 | 0 | 8686.629 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -119822.291 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1504-2BHK Granite Work (M) | 78.47 | 110.7 | 0 | 8686.629 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -119822.291 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1801-3BHK Granite Work (M) | 61.392 | 110.7 | 0 | 6796.0944 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -121712.8256 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1802-3BHK Granite Work (M) | 61.392 | 110.7 | 0 | 6796.0944 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -121712.8256 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1602-3BHK Granite Work (M) | 61.392 | 110.7 | 0 | 6796.0944 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -121712.8256 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1803-2BHK Granite Work (M) | 61.392 | 110.7 | 0 | 6796.0944 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -121712.8256 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1404-2BHK Granite Work (M) | 78.47 | 110.7 | 0 | 8686.629 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -119822.291 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1703-2BHK Granite Work (M) | 61.392 | 110.7 | 0 | 6796.0944 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -121712.8256 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1604-2BHK Granite Work (M) | 61.392 | 110.7 | 0 | 6796.0944 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -121712.8256 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1601-3BHK Granite Work (M) | 61.392 | 110.7 | 0 | 6796.0944 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -121712.8256 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1704-2BHK Granite Work (M) | 61.392 | 110.7 | 0 | 6796.0944 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -121712.8256 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1402-3BHK Granite Work (M) | 77.692 | 110.7 | 0 | 8600.5044 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -119908.4156 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1603-2BHK Granite Work (M) | 61.392 | 110.7 | 0 | 6796.0944 | 0 | 2023-10-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102616 | 2023-10-14 | 128508.92 | 2023-10-28 11:59 | -121712.8256 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-601-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1002-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1401-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-601-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-902-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1001-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1002-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1704-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1303-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1401-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1402-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1803-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1601-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1603-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1203-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1101-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1204-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1403-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-502-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-504-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1303-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1802-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1701-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1703-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-501-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-604-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1703-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-903-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1402-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1403-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1801-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1803-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-503-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1802-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1504-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1104-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1503-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-803-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1701-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1804-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-403-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-803-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-604-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-901-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1301-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-401-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-602-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1301-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1404-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1502-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1804-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-503-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-904-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1001-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1704-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-504-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-903-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-802-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1603-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1601-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1602-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1504-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1501-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-701-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1302-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-701-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-603-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-802-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1004-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1502-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1203-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1404-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-804-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1501-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-801-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1104-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-801-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1602-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-602-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-901-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1004-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-804-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-902-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1101-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1204-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1503-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-502-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-904-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1801-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1302-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -88490.9293 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-402-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-404-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-603-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-05-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 99388 | 2023-05-03 | 90136.78 | 2023-05-16 12:30 | -89775.16 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-404-2BHK Granite Work (M) | 7.9946 | 110.7 | 0 | 885.0022 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75965.0878 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-902-3BHK Granite Work (M) | 27.1536 | 110.7 | 0 | 3005.9035 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -73844.1865 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-304-2BHK Granite Work (M) | 7.9855 | 110.7 | 0.01 | 883.9949 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75966.0951 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-601-3BHK Granite Work (M) | 9.0425 | 110.7 | 0 | 1001.0047 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75849.0853 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-903-2BHK Granite Work (M) | 26.838 | 110.7 | 0 | 2970.9666 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -73879.1234 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1201-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 0 | 2023-08-16 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75204.2393 | PAPPU BAGELA
Kadappa Double Polish | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1201-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 0 | 2023-08-16 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -76488.47 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-803-2BHK Granite Work (M) | 26.838 | 110.7 | 0 | 2970.9666 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -73879.1234 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-501-3BHK Granite Work (M) | 9.0425 | 110.7 | 0 | 1001.0047 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75849.0853 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-901-3BHK Granite Work (M) | 27.1536 | 110.7 | 0 | 3005.9035 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -73844.1865 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1204-2BHK Granite Work (M) | 35.784 | 110.7 | 0 | 3961.2888 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -72888.8012 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-401-3BHK Granite Work (M) | 9.0425 | 110.7 | 0 | 1001.0047 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75849.0853 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-504-2BHK Granite Work (M) | 7.9946 | 110.7 | 0 | 885.0022 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75965.0878 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-801-3BHK Granite Work (M) | 27.1536 | 110.7 | 0 | 3005.9035 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -73844.1865 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1002-3BHK Granite Work (M) | 27.1536 | 110.7 | 0 | 3005.9035 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -73844.1865 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1201-3BHK Granite Work (M) | 90.512 | 110.7 | 0 | 10019.6784 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -66830.4116 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1001-3BHK Granite Work (M) | 27.1536 | 110.7 | 0 | 3005.9035 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -73844.1865 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1004-2BHK Granite Work (M) | 26.838 | 110.7 | 0 | 2970.9666 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -73879.1234 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1101-3BHK Granite Work (M) | 36.2048 | 110.7 | 0 | 4007.8714 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -72842.2186 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-502-3BHK Granite Work (M) | 9.0425 | 110.7 | 0 | 1001.0047 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75849.0853 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-904-2BHK Granite Work (M) | 26.838 | 110.7 | 0 | 2970.9666 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -73879.1234 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1203-2BHK Granite Work (M) | 35.784 | 110.7 | 0 | 3961.2888 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -72888.8012 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-503-2BHK Granite Work (M) | 7.9946 | 110.7 | 0 | 885.0022 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75965.0878 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-402-3BHK Granite Work (M) | 11.084 | 110.7 | 0 | 1226.9988 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75623.0912 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-403-2BHK Granite Work (M) | 10.0361 | 110.7 | 0 | 1110.9963 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75739.0937 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-802-3BHK Granite Work (M) | 27.1536 | 110.7 | 0 | 3005.9035 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -73844.1865 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-804-2BHK Granite Work (M) | 26.838 | 110.7 | 0 | 2970.9666 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -73879.1234 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-604-2BHK Granite Work (M) | 7.9946 | 110.7 | 0 | 885.0022 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75965.0878 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-701-3BHK Granite Work (M) | 13.5768 | 110.7 | 0 | 1502.9518 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75347.1382 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-1104-2BHK Granite Work (M) | 35.784 | 110.7 | 0 | 3961.2888 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -72888.8012 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-301-3BHK Granite Work (M) | 9.0515 | 110.7 | 0 | 1002.001 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75848.089 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-303-2BHK Granite Work (M) | 1.0479 | 110.7 | 0 | 116.0025 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -76734.0875 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-303-2BHK Granite Work (M) | 6.9377 | 110.7 | 0 | 768.0034 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -76082.0866 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-602-3BHK Granite Work (M) | 9.0425 | 110.7 | 0 | 1001.0047 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75849.0853 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | D-603-2BHK Granite Work (M) | 7.9946 | 110.7 | 0 | 885.0022 | 0 | 2023-08-16 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101284 | 2023-08-17 | 76850.09 | 2023-08-23 18:28 | -75965.0878 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | F-Bldg 2nd Floor Granite Work (M) | 57 | 110.7 | 0 | 6309.9 | 0 | 2023-09-22 12:26 | Material Supply Charges for Granite with polish including transportation & loading,unloading of material. | 100 |  | 102042 | 2023-09-22 | 58728.57 | 2023-09-30 12:12 | -52418.67 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | F-Bldg 1st Floor Granite Work (M) | 194 | 110.7 | 0 | 21475.8 | 0 | 2023-09-22 12:26 | Material Supply Charges for Granite with polish including transportation & loading,unloading of material. | 100 |  | 102042 | 2023-09-22 | 58728.57 | 2023-09-30 12:12 | -37252.77 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | F-Bldg Terrace Floor Granite Work (M) - 1 Floor | 5 | 110.7 | 0 | 553.5 | 0 | 2023-09-22 12:26 | Material Supply Charges for Granite with polish including transportation & loading,unloading of material. | 100 |  | 102042 | 2023-09-22 | 58728.57 | 2023-09-30 12:12 | -58175.07 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | F-Bldg LG Floor Granite Work (M) | 32 | 110.7 | 0 | 3542.4 | 0 | 2023-09-22 12:26 | Material Supply Charges for Granite with polish including transportation & loading,unloading of material. | 100 |  | 102042 | 2023-09-22 | 58728.57 | 2023-09-30 12:12 | -55186.17 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | F-Bldg 2nd Floor Granite Work (M) | 76.84 | 110.7 | 0 | 8506.188 | 0 | 2023-09-22 12:26 | Material Supply Charges for Granite with polish including transportation & loading,unloading of material. | 100 |  | 102042 | 2023-09-22 | 58728.57 | 2023-09-30 12:12 | -50222.382 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | F-Bldg 1st Floor Granite Work (M) | 57 | 110.7 | 0 | 6309.9 | 0 | 2023-09-22 12:26 | Material Supply Charges for Granite with polish including transportation & loading,unloading of material. | 100 |  | 102042 | 2023-09-22 | 58728.57 | 2023-09-30 12:12 | -52418.67 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 509 | 2022-08-03 | F-Bldg 2nd Floor Granite Work (M) | 108.68 | 110.7 | 0 | 12030.876 | 0 | 2023-09-22 12:59 | Material Supply Charges for Granite with polish including transportation & loading,unloading of material. | 100 |  | 102042 | 2023-09-22 | 58728.57 | 2023-09-30 12:12 | -46697.694 | PAPPU BAGELA
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1808-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1505-3BHK Granite Work (M) | 90.51 | 113.4 | 0 | 10263.834 | 1847.49 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -179940.006 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-806-3BHK Granite Work (M) | 4.505 | 113.4 | 0 | 510.867 | 91.96 | 2024-01-12 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189692.973 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1108-2BHK Granite Work (M) | 10.99 | 113.4 | 0 | 1246.266 | 224.33 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188957.574 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1508-2BHK Granite Work (M) | 89.46 | 113.4 | 0 | 10144.764 | 1826.06 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -180059.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1807-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -181305.342 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1608-2BHK Granite Work (M) | 89.46 | 113.4 | 0 | 10144.764 | 1826.06 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -180059.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1807-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1508-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1805-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1407-2BHK Granite Work (M) | 10.99 | 113.4 | 0 | 1246.266 | 224.33 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188957.574 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1006-3BHK Granite Work (M) | 20.837 | 113.4 | 0 | 2362.9158 | 425.33 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -24076.9842 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1006-3BHK Granite Work (M) | 3.78 | 113.4 | 0 | 428.652 | 77.16 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -26011.248 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1007-2BHK Granite Work (M) | 37.867 | 113.4 | 0 | 4294.1178 | 772.94 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -22145.7822 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1007-2BHK Granite Work (M) | 3.93 | 113.4 | 0 | 445.662 | 80.22 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -25994.238 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1005-3BHK Granite Work (M) | 20.837 | 113.4 | 0 | 2362.9158 | 425.33 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -24076.9842 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-907-2BHK Granite Work (M) | 25.547 | 113.4 | 0 | 2897.0298 | 521.47 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -23542.8702 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1005-3BHK Granite Work (M) | 3.78 | 113.4 | 0 | 428.652 | 77.16 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -26011.248 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-908-2BHK Granite Work (M) | 25.547 | 113.4 | 0 | 2897.0298 | 521.47 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -23542.8702 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-906-3BHK Granite Work (M) | 24.617 | 113.4 | 0 | 2791.5678 | 502.48 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -23648.3322 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-905-3BHK Granite Work (M) | 24.617 | 113.4 | 0 | 2791.5678 | 502.48 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -23648.3322 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1008-2BHK Granite Work (M) | 37.867 | 113.4 | 0 | 4294.1178 | 772.94 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -22145.7822 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1008-2BHK Granite Work (M) | 3.93 | 113.4 | 0 | 445.662 | 80.22 | 2023-10-27 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103065 | 2023-10-30 | 26439.9 | 2023-11-18 14:35 | -25994.238 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-905-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-12-31 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -14244.0766 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-905-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-12-31 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -15559.63 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1007-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-12-31 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -14244.0766 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-906-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-12-31 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -14244.0766 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-908-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-12-31 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -14244.0766 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-907-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-12-31 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -14244.0766 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1008-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-12-31 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -15559.63 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1006-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-12-31 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -14244.0766 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1008-2BHK Kadappa Work (M) | 23.7 | 49.14 | 0 | 1164.618 | 209.64 | 2023-12-31 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -14765.452 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1006-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-12-31 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -15559.63 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1007-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-12-31 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -15559.63 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1005-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-12-31 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -15559.63 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-907-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-12-31 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -15559.63 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-906-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-12-31 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -15559.63 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-908-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-12-31 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -15559.63 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1005-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-12-31 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104251 | 2024-01-01 | 15930.07 | 2024-01-23 14:24 | -14244.0766 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1208-2BHK Granite Work (M) | 25.54 | 113.4 | 0 | 2896.236 | 521.32 | 2023-10-06 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 102399 | 2023-10-07 | 2896.24 | 2023-10-30 15:43 | -0.004 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-807-2BHK Granite Work (M) | 25.547 | 113.4 | 0 | 2897.0298 | 521.47 | 2023-09-12 11:08 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101867 | 2023-09-15 | 22754.4 | 2023-09-30 11:37 | -19857.3702 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-706-3BHK Granite Work (M) | 24.617 | 113.4 | 0 | 2791.5678 | 502.48 | 2023-09-12 11:08 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101867 | 2023-09-15 | 22754.4 | 2023-09-30 11:37 | -19962.8322 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-808-2BHK Granite Work (M) | 25.547 | 113.4 | 0 | 2897.0298 | 521.47 | 2023-09-12 11:08 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101867 | 2023-09-15 | 22754.4 | 2023-09-30 11:37 | -19857.3702 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-708-2BHK Granite Work (M) | 25.547 | 113.4 | 0 | 2897.0298 | 521.47 | 2023-09-12 11:08 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101867 | 2023-09-15 | 22754.4 | 2023-09-30 11:37 | -19857.3702 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-806-3BHK Granite Work (M) | 24.617 | 113.4 | 0 | 2791.5678 | 502.48 | 2023-09-12 11:08 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101867 | 2023-09-15 | 22754.4 | 2023-09-30 11:37 | -19962.8322 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-707-2BHK Granite Work (M) | 25.547 | 113.4 | 0 | 2897.0298 | 521.47 | 2023-09-12 11:08 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101867 | 2023-09-15 | 22754.4 | 2023-09-30 11:37 | -19857.3702 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-705-3BHK Granite Work (M) | 24.617 | 113.4 | 0 | 2791.5678 | 502.48 | 2023-09-12 11:08 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101867 | 2023-09-15 | 22754.4 | 2023-09-30 11:37 | -19962.8322 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-805-3BHK Granite Work (M) | 24.617 | 113.4 | 0 | 2791.5678 | 502.48 | 2023-09-12 11:08 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101867 | 2023-09-15 | 22754.4 | 2023-09-30 11:37 | -19962.8322 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1806-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-807-2BHK Granite Work (M) | 2.52 | 113.4 | 0 | 285.768 | 51.44 | 2024-01-12 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189918.072 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1605-3BHK Granite Work (M) | 90.512 | 113.4 | 0 | 10264.0608 | 1847.53 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -179939.7792 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1705-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1507-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1605-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1308-2BHK Granite Work (M) | 10.99 | 113.4 | 0 | 1246.266 | 224.33 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188957.574 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1406-3BHK Granite Work (M) | 12.82 | 113.4 | 0 | 1453.788 | 261.68 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188750.052 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1607-2BHK Granite Work (M) | 89.46 | 113.4 | 0 | 10144.764 | 1826.06 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -180059.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1307-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1408-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1505-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1008-2BHK Granite Work (M) | 2.525 | 113.4 | 0 | 286.335 | 51.54 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189917.505 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1607-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1508-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1607-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1707-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-706-3BHK Granite Work (M) | 4.0776 | 113.4 | 0 | 462.3998 | 83.23 | 2024-01-12 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189741.4402 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-706-3BHK Granite Work (M) | 0.42 | 113.4 | 0 | 47.628 | 8.57 | 2024-01-12 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -190156.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1307-2BHK Granite Work (M) | 10.99 | 113.4 | 0 | 1246.266 | 224.33 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188957.574 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1505-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1805-3BHK Granite Work (M) | 77.69 | 113.4 | 0 | 8810.046 | 1585.81 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -181393.794 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1608-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1407-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1805-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1806-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1007-2BHK Granite Work (M) | 2.525 | 113.4 | 0 | 286.335 | 51.54 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189917.505 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1507-2BHK Granite Work (M) | 89.46 | 113.4 | 0 | 10144.764 | 1826.06 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -180059.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1808-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -181305.342 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1508-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1107-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1705-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1705-3BHK Granite Work (M) | 77.69 | 113.4 | 0 | 8810.046 | 1585.81 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -181393.794 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1806-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1507-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1708-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -181305.342 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1505-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1808-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1607-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1708-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1605-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1708-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-805-3BHK Granite Work (M) | 4.505 | 113.4 | 0 | 510.867 | 91.96 | 2024-01-12 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189692.973 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1006-3BHK Granite Work (M) | 4.505 | 113.4 | 0 | 510.867 | 91.96 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189692.973 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1107-2BHK Granite Work (M) | 10.99 | 113.4 | 0 | 1246.266 | 224.33 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188957.574 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1806-3BHK Granite Work (M) | 77.69 | 113.4 | 0 | 8810.046 | 1585.81 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -181393.794 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1707-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1807-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-705-3BHK Granite Work (M) | 4.0776 | 113.4 | 0 | 462.3998 | 83.23 | 2024-01-12 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189741.4402 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-705-3BHK Granite Work (M) | 0.42 | 113.4 | 0 | 47.628 | 8.57 | 2024-01-12 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -190156.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1005-3BHK Granite Work (M) | 4.505 | 113.4 | 0 | 510.867 | 91.96 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189692.973 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1507-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1707-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1705-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1308-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1807-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1808-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1408-2BHK Granite Work (M) | 10.99 | 113.4 | 0 | 1246.266 | 224.33 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188957.574 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1108-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1608-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1608-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-01-12 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189833.4 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-808-2BHK Granite Work (M) | 2.52 | 113.4 | 0 | 285.768 | 51.44 | 2024-01-12 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -189918.072 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1707-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2024-01-13 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -181305.342 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1406-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1708-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1805-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-01-12 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188517.8466 | S S ENTERISES (PROP. SOBRAN SINGH)
Araldite | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1605-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-01-13 | Material Supply Charges for- Araldite including transportation,loading /unloading of material. | 100 |  | 104551 | 2024-01-15 | 190203.84 | 2024-01-31 15:46 | -188843.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1908-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2207-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2006-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2007-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1305-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2105-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1906-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1907-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2307-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2308-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1905-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1907-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2108-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1306-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2205-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2207-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1908-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1706-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1606-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1105-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1106-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1205-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-09-13 16:32 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -42866.3966 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1205-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-09-13 16:39 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -44181.95 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1206-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-09-13 16:39 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -44181.95 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1207-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-09-13 16:32 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -42866.3966 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1207-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-09-13 16:39 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -44181.95 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1207-2BHK Granite Work (M) | 86.937 | 113.4 | 0 | 9858.6558 | 1774.56 | 2023-09-13 16:44 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -34693.7342 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1208-2BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.1 | 2023-09-13 16:44 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -37590.764 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1206-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-09-13 16:32 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -42866.3966 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1205-3BHK Granite Work (M) | 86.007 | 113.4 | 0 | 9753.1938 | 1755.58 | 2023-09-13 16:44 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -34799.1962 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1208-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-09-13 16:39 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -44181.95 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1208-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-09-13 16:32 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -42866.3966 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1206-3BHK Granite Work (M) | 86.007 | 113.4 | 0 | 9753.1938 | 1755.58 | 2023-09-13 16:44 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 101866 | 2023-09-15 | 44552.39 | 2023-09-20 12:27 | -34799.1962 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-407-2BHK Granite Work (M) | 80.95 | 113.4 | 0 | 9179.73 | 1652.36 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -194704.62 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-808-2BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.1 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -196922.724 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-708-2BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.1 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -196922.724 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-806-3BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.1 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -196922.724 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-508-2BHK Granite Work (M) | 89.46 | 113.4 | 0 | 10144.764 | 1826.06 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -193739.586 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-405-3BHK Granite Work (M) | 90.51 | 113.4 | 0 | 10263.834 | 1847.48 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -193620.516 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-505-3BHK Granite Work (M) | 90.51 | 113.4 | 0 | 10263.834 | 1847.48 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -193620.516 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-408-2BHK Granite Work (M) | 89.46 | 113.4 | 0 | 10144.764 | 1826.06 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -193739.586 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-807-2BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.1 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -196922.724 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-706-3BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.1 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -196922.724 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-406-3BHK Granite Work (M) | 82 | 113.4 | 0 | 9298.8 | 1673.78 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -194585.55 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-607-2BHK Granite Work (M) | 89.46 | 113.4 | 0 | 10144.764 | 1826.06 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -193739.586 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-308-2BHK Granite Work (M) | 85.53 | 113.4 | 0 | 9699.102 | 1745.84 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -194185.248 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-606-3BHK Granite Work (M) | 90.51 | 113.4 | 0 | 10263.834 | 1847.48 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -193620.516 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-705-3BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.1 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -196922.724 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-306-3BHK Granite Work (M) | 75.67 | 113.4 | 0 | 8580.978 | 1544.58 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -195303.372 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-307-2BHK Granite Work (M) | 89.46 | 113.4 | 0 | 10144.764 | 1826.06 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -193739.586 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-506-3BHK Granite Work (M) | 90.51 | 113.4 | 0 | 10263.834 | 1847.48 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -193620.516 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-805-3BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.1 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -196922.724 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-305-3BHK Granite Work (M) | 90.512 | 113.4 | 0 | 10264.0608 | 1847.54 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -193620.2892 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-608-2BHK Granite Work (M) | 85.53 | 113.4 | 0 | 9699.102 | 1745.84 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -194185.248 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-605-3BHK Granite Work (M) | 86.73 | 113.4 | 0 | 9835.182 | 1770.34 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -194049.168 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-707-2BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.1 | 2023-06-22 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 100258 | 2023-06-23 | 203884.35 | 2023-08-09 17:05 | -196922.724 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-707-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-805-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-505-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-708-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-508-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-405-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-706-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-806-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-606-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-607-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-705-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-705-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-805-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-605-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-706-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-508-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-707-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-605-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-506-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-607-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-608-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-608-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-606-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-708-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-405-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-505-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-408-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-807-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-407-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-506-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-407-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-808-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-406-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-806-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-06-23 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -37386.1766 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-406-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-408-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-807-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-808-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-06-23 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 100268 | 2023-06-24 | 39072.17 | 2023-07-26 12:45 | -38701.73 | R.M.Marbles
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2008-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -141447.262 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2205-3BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.09 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -143384.134 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2207-2BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.09 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -143384.134 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2105-3BHK Granite Work (M) | 77.69 | 113.4 | 0 | 8810.046 | 1585.81 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -141535.714 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2106-3BHK Granite Work (M) | 77.69 | 113.4 | 0 | 8810.046 | 1585.81 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -141535.714 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2108-2BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.09 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -143384.134 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2107-2BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.09 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -143384.134 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2305-3BHK Granite Work (M) | 44.36 | 113.4 | 0 | 5030.424 | 905.48 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -145315.336 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2308-2BHK Granite Work (M) | 44.36 | 113.4 | 0 | 5030.424 | 905.48 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -145315.336 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1908-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -141447.262 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2006-3BHK Granite Work (M) | 77.69 | 113.4 | 0 | 8810.046 | 1585.81 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -141535.714 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2306-3BHK Granite Work (M) | 44.36 | 113.4 | 0 | 5030.424 | 905.48 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -145315.336 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2307-2BHK Granite Work (M) | 44.36 | 113.4 | 0 | 5030.424 | 905.48 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -145315.336 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1905-3BHK Granite Work (M) | 77.69 | 113.4 | 0 | 8810.046 | 1585.81 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -141535.714 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2007-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -141447.262 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2005-3BHK Granite Work (M) | 77.69 | 113.4 | 0 | 8810.046 | 1585.81 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -141535.714 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2208-2BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.09 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -143384.134 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2206-3BHK Granite Work (M) | 61.39 | 113.4 | 0 | 6961.626 | 1253.09 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -143384.134 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1907-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -141447.262 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1906-3BHK Granite Work (M) | 77.69 | 113.4 | 0 | 8810.046 | 1585.81 | 2024-03-09 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 107599 | 2024-05-15 | 150345.76 | 2024-05-15 17:10 | -141535.714 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2007-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2005-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2008-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2206-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2108-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1606-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2308-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2205-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2206-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2306-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2305-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1105-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2306-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1106-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1405-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2006-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1905-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2208-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2307-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1906-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2305-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1306-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1305-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1706-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2008-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2106-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2107-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2107-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2005-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2208-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1405-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2105-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2024-02-20 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -55153.17 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-2106-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2024-02-20 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 107617 | 2024-05-17 | 55523.61 | 2024-05-28 19:04 | -53837.6166 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1308-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-11-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -97736.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1107-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-11-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -96420.6666 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1107-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -89208.162 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1408-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -89208.162 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1005-3BHK Granite Work (M) | 44.362 | 113.4 | 0 | 5030.6508 | 905.52 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -93076.0092 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-907-2BHK Granite Work (M) | 3.06 | 113.4 | 0 | 347.004 | 62.46 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -97759.656 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-905-3BHK Granite Work (M) | 3.06 | 113.4 | 0 | 347.004 | 62.46 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -97759.656 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1308-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -89208.162 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1406-3BHK Granite Work (M) | 77.69 | 113.4 | 0 | 8810.046 | 1585.81 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -89296.614 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1307-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -89208.162 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1108-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-11-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -96420.6666 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1406-3BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-11-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -96420.6666 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1108-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-11-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -97736.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1307-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-11-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -96420.6666 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1407-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -89208.162 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1408-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-11-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -97736.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1408-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-11-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -96420.6666 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-906-3BHK Granite Work (M) | 3.06 | 113.4 | 0 | 347.004 | 62.46 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -97759.656 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-908-2BHK Granite Work (M) | 3.06 | 113.4 | 0 | 347.004 | 62.46 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -97759.656 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1406-3BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-11-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -97736.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1407-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-11-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -97736.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1407-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-11-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -96420.6666 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1006-3BHK Granite Work (M) | 44.362 | 113.4 | 0 | 5030.6508 | 905.52 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -93076.0092 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1107-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-11-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -97736.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Single Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1308-2BHK Kadappa Work (M) | 34.31 | 49.14 | 0 | 1685.9934 | 303.48 | 2023-11-02 | Material Supply Charges for- Kadappa Single Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -96420.6666 | S S ENTERISES (PROP. SOBRAN SINGH)
Kadappa Double Polish | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1307-2BHK Kadappa Work (M) | 6 | 61.74 | 0 | 370.44 | 66.68 | 2023-11-02 | Material Supply Charges for- Kadappa Double Polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -97736.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1008-2BHK Granite Work (M) | 44.362 | 113.4 | 0 | 5030.6508 | 905.52 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -93076.0092 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1007-2BHK Granite Work (M) | 44.362 | 113.4 | 0 | 5030.6508 | 905.52 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -93076.0092 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite work (M) | N/C | N/C | R.M.Marbles | 510 | 2022-08-03 | D-1108-2BHK Granite Work (M) | 78.47 | 113.4 | 0 | 8898.498 | 1601.73 | 2023-11-02 | Material Supply Charges for- Granite with polish including transportation,loading /unloading of material. | 100 |  | 103206 | 2023-11-02 | 98106.66 | 2023-11-22 11:30 | -89208.162 | S S ENTERISES (PROP. SOBRAN SINGH)
SMS / WHATSAPP / E-MAILERS / CHATS | N/C | N/C | PINNACLE TELESERVICES PVT LTD | 512 | 2022-08-03 | ONLINE / DIGITAL Social / Digital Activity | 10243.6506 | 0.4843 | 0 | 4961 | 892.98 | 2023-06-09 | BULK WHATSAPP MESSAGES/ CHATS LINK SHARE FOR MARKETING ACTIVITY - SALES PROMOTION, LEAD GENERATION, PROJECT RELATED INFORMATION ETC. RS. 0.4843/-+ TAX PER WHATSAPP MESSAGES | 100 |  | 100031 | 2023-06-09 | 4961 | 2023-06-09 13:15 | -1.442e-05 | PINNACLE TELESERVICES PVT LTD
MONTHLY - CHARGES / RENTAL/ FEES/ | N/C | N/C | PINNACLE TELESERVICES PVT LTD | 512 | 2022-08-03 | ONLINE / DIGITAL Social / Digital Activity | 1 | 2000 | 0 | 2000 | 360 | 2023-03-31 | MONTHLY FIXED CHARGES THINK PINNACLE MESSAGES BOARDRS. 2000/- + TAX PER MONTH AS ON 01ST AUGUST 2022 | 100 |  | 100057 | 2023-03-31 | 2000 | 2023-06-10 13:01 | 0 | PINNACLE TELESERVICES PVT LTD
MONTHLY - CHARGES / RENTAL/ FEES/ | N/C | N/C | PINNACLE TELESERVICES PVT LTD | 512 | 2022-08-03 | ONLINE / DIGITAL Social / Digital Activity | 1 | 2000 | 0 | 2000 | 360 | 2023-03-31 | MONTHLY FIXED CHARGES THINK PINNACLE MESSAGES BOARDRS. 2000/- + TAX PER MONTH AS ON 01ST AUGUST 2022 | 100 |  | 100058 | 2023-03-31 | 2000 | 2023-06-10 13:01 | 0 | PINNACLE TELESERVICES PVT LTD
MONTHLY - CHARGES / RENTAL/ FEES/ | N/C | N/C | PINNACLE TELESERVICES PVT LTD | 512 | 2022-08-03 | ONLINE / DIGITAL Social / Digital Activity | 1 | 2000 | 0 | 2000 | 360 | 2023-03-31 | MONTHLY FIXED CHARGES THINK PINNACLE MESSAGES BOARDRS. 2000/- + TAX PER MONTH AS ON 01ST AUGUST 2022 | 100 |  | 100059 | 2023-03-31 | 2000 | 2023-06-10 13:02 | 0 | PINNACLE TELESERVICES PVT LTD
MONTHLY - CHARGES / RENTAL/ FEES/ | N/C | N/C | PINNACLE TELESERVICES PVT LTD | 512 | 2022-08-03 | ONLINE / DIGITAL Social / Digital Activity | 1 | 2000 | 0 | 2000 | 360 | 2023-03-31 | MONTHLY FIXED CHARGES THINK PINNACLE MESSAGES BOARDRS. 2000/- + TAX PER MONTH AS ON 01ST AUGUST 2022 | 100 |  | 100060 | 2023-03-31 | 2000 | 2023-06-10 13:02 | 0 | PINNACLE TELESERVICES PVT LTD
SMS / WHATSAPP / E-MAILERS / CHATS | N/C | N/C | PINNACLE TELESERVICES PVT LTD | 512 | 2022-08-03 | ONLINE / DIGITAL Social / Digital Activity | 183266.6667 | 0.03 | 0 | 5498 | 989.64 | 2023-03-31 | SESSION MESSAGES RS. 0.03/- +TAX PER WHATSAPP MESSAGES | 100 |  | 100061 | 2023-03-31 | 5498 | 2023-06-10 13:02 | 1e-06 | PINNACLE TELESERVICES PVT LTD
SMS / WHATSAPP / E-MAILERS / CHATS | N/C | N/C | PINNACLE TELESERVICES PVT LTD | 512 | 2022-08-03 | ONLINE / DIGITAL Social / Digital Activity | 5666.6667 | 0.03 | 0 | 170 | 30.6 | 2023-03-31 | SESSION MESSAGES RS. 0.03/- +TAX PER WHATSAPP MESSAGES | 100 |  | 100062 | 2023-03-31 | 170 | 2023-06-10 13:02 | 1e-06 | PINNACLE TELESERVICES PVT LTD
Bulk SMS | N/C | N/C | PINNACLE TELESERVICES PVT LTD | 512 | 2022-08-03 | ONLINE / DIGITAL Social / Digital Activity | 1000000 | 0.11 | 0 | 110000 | 19800 | 2022-09-14 | BULK SMS FOR SALESPROMOTIONAL , LEAD GENERATION, LINK ETC. MARKETING RELATED ACTIVITY RS.0.11/- + TAX PER SMS | 100 |  | 96264 | 2022-09-14 | 110000 | 2022-09-14 17:29 | 0 | PINNACLE TELESERVICES PVT LTD
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 513 | 2022-08-04 | D-Bldg 17th Floor Wall Texture Paint Work | 261.73 | 7.25 | 0 | 1897.5425 | 341.56 | 2024-04-15 | Material Supply of Texture Paint for D-Bldg Refuse Area Wall Surface. | 100 |  | 106987 | 2024-04-22 | 1897.54 | 2024-06-24 12:18 | 0.0025 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg P1 Floor Wall Texture Paint - 869.41 Sq.Ft | 782.469 | 7.25 | 0 | 5672.9002 | 1021.12 | 2024-06-17 | Material supply of Texture Paint for Common Lobby Wall D-Bldg Parking. | 100 |  | 108425 | 2024-06-17 | 11345.8 | 2024-06-24 12:19 | -5672.8997 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg P2 Floor Wall Texture Paint - 869.41 Sq.Ft | 782.469 | 7.25 | 0 | 5672.9002 | 1021.12 | 2024-06-17 | Material supply of Texture Paint for Common Lobby Wall D-Bldg Parking. | 100 |  | 108425 | 2024-06-17 | 11345.8 | 2024-06-24 12:19 | -5672.8997 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 15th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-07 16:12 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108208 | 2024-06-10 | 110069.5 | 2024-06-24 12:18 | -99062.55 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 12th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-07 16:12 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108208 | 2024-06-10 | 110069.5 | 2024-06-24 12:18 | -99062.55 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 14th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-07 16:12 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108208 | 2024-06-10 | 110069.5 | 2024-06-24 12:18 | -99062.55 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 16th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-07 16:12 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108208 | 2024-06-10 | 110069.5 | 2024-06-24 12:18 | -99062.55 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 11th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-07 16:12 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108208 | 2024-06-10 | 110069.5 | 2024-06-24 12:18 | -99062.55 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 17th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-07 16:12 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108208 | 2024-06-10 | 110069.5 | 2024-06-24 12:18 | -99062.55 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 18th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-07 16:12 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108208 | 2024-06-10 | 110069.5 | 2024-06-24 12:18 | -99062.55 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 19th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-07 16:12 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108208 | 2024-06-10 | 110069.5 | 2024-06-24 12:18 | -99062.55 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 13th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-07 16:12 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108208 | 2024-06-10 | 110069.5 | 2024-06-24 12:18 | -99062.55 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 10th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-07 16:12 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108208 | 2024-06-10 | 110069.5 | 2024-06-24 12:18 | -99062.55 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 21st Fl-Lobby Wall Texture Paint Work | 1897.57 | 7.25 | 0 | 13757.3825 | 2476.32 | 2024-08-05 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 109612 | 2024-08-05 | 68786.9 | 1900-01-01 | -55029.5175 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 20th Fl-Lobby Wall Texture Paint Work | 1897.57 | 7.25 | 0 | 13757.3825 | 2476.32 | 2024-08-05 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 109612 | 2024-08-05 | 68786.9 | 1900-01-01 | -55029.5175 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 23rd Fl-Lobby Wall Texture Paint Work | 1897.57 | 7.25 | 0 | 13757.3825 | 2476.32 | 2024-08-05 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 109612 | 2024-08-05 | 68786.9 | 1900-01-01 | -55029.5175 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 22nd Fl-Lobby Wall Texture Paint Work | 1897.57 | 7.25 | 0 | 13757.3825 | 2476.32 | 2024-08-05 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 109612 | 2024-08-05 | 68786.9 | 1900-01-01 | -55029.5175 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 24th Fl-Lobby Wall Texture Paint Work | 1897.57 | 7.25 | 0 | 13757.3825 | 2476.32 | 2024-08-05 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 109612 | 2024-08-05 | 68786.9 | 1900-01-01 | -55029.5175 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 6th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108465 | 2024-06-19 | 122243.31 | 2024-06-24 12:19 | -108660.725 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 2nd Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108465 | 2024-06-19 | 122243.31 | 2024-06-24 12:19 | -108660.725 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 8th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108465 | 2024-06-19 | 122243.31 | 2024-06-24 12:19 | -108660.725 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 5th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108465 | 2024-06-19 | 122243.31 | 2024-06-24 12:19 | -108660.725 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 1st Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108465 | 2024-06-19 | 122243.31 | 2024-06-24 12:19 | -108660.725 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 3rd Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108465 | 2024-06-19 | 122243.31 | 2024-06-24 12:19 | -108660.725 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 4th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108465 | 2024-06-19 | 122243.31 | 2024-06-24 12:19 | -108660.725 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 7th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108465 | 2024-06-19 | 122243.31 | 2024-06-24 12:19 | -108660.725 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 514 | 2022-08-08 | D-Bldg 9th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Material supply of Texture Paint for D-Bldg Common Lobby Wall. | 100 |  | 108465 | 2024-06-19 | 122243.31 | 2024-06-24 12:19 | -108660.725 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg P2 Floor Wall Texture Paint - 869.41 Sq.Ft | 695.528 | 7.25 | 0 | 5042.578 | 907.66 | 2024-06-17 | Labour charges for Applying Texture Paint for D-Bldg Parking Painting work on Wall. | 100 |  | 108424 | 2024-06-17 | 10085.16 | 2024-06-24 12:09 | -5042.582 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg P1 Floor Wall Texture Paint - 869.41 Sq.Ft | 695.528 | 7.25 | 0 | 5042.578 | 907.66 | 2024-06-17 | Labour charges for Applying Texture Paint for D-Bldg Parking Painting work on Wall. | 100 |  | 108424 | 2024-06-17 | 10085.16 | 2024-06-24 12:09 | -5042.582 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 8th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 108464 | 2024-06-19 | 122243.31 | 2024-06-24 12:17 | -108660.725 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 1st Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 108464 | 2024-06-19 | 122243.31 | 2024-06-24 12:17 | -108660.725 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 2nd Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 108464 | 2024-06-19 | 122243.31 | 2024-06-24 12:17 | -108660.725 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 3rd Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 108464 | 2024-06-19 | 122243.31 | 2024-06-24 12:17 | -108660.725 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 6th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 108464 | 2024-06-19 | 122243.31 | 2024-06-24 12:17 | -108660.725 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 9th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 108464 | 2024-06-19 | 122243.31 | 2024-06-24 12:17 | -108660.725 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 4th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 108464 | 2024-06-19 | 122243.31 | 2024-06-24 12:17 | -108660.725 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 5th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 108464 | 2024-06-19 | 122243.31 | 2024-06-24 12:17 | -108660.725 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 7th Fl-Lobby Wall Texture Paint Work | 1873.46 | 7.25 | 0 | 13582.585 | 2444.86 | 2024-06-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 108464 | 2024-06-19 | 122243.31 | 2024-06-24 12:17 | -108660.725 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 12th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-02 11:37 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 107939 | 2024-06-03 | 110069.5 | 2024-06-15 11:52 | -99062.55 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 13th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-02 11:37 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 107939 | 2024-06-03 | 110069.5 | 2024-06-15 11:52 | -99062.55 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 16th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-02 11:37 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 107939 | 2024-06-03 | 110069.5 | 2024-06-15 11:52 | -99062.55 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 11th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-02 11:37 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 107939 | 2024-06-03 | 110069.5 | 2024-06-15 11:52 | -99062.55 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 14th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-02 11:37 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 107939 | 2024-06-03 | 110069.5 | 2024-06-15 11:52 | -99062.55 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 17th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-02 11:37 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 107939 | 2024-06-03 | 110069.5 | 2024-06-15 11:52 | -99062.55 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 19th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-02 11:37 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 107939 | 2024-06-03 | 110069.5 | 2024-06-15 11:52 | -99062.55 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 15th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-02 11:37 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 107939 | 2024-06-03 | 110069.5 | 2024-06-15 11:52 | -99062.55 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 10th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-02 11:37 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 107939 | 2024-06-03 | 110069.5 | 2024-06-15 11:52 | -99062.55 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 18th Fl-Lobby Wall Texture Paint Work | 1518.2 | 7.25 | 0 | 11006.95 | 1981.26 | 2024-06-02 11:37 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 107939 | 2024-06-03 | 110069.5 | 2024-06-15 11:52 | -99062.55 | RAHUL PATIL
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 3rd Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 5th Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 7th Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 12th Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 8th Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 2nd Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 6th Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 4th Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 6th Fl-Lobby Ceiling Putty Work | 129 | 0.5 | 0 | 64.5 | 0 | 2024-04-15 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 106988 | 2024-04-22 | 580.5 | 1900-01-01 | -516 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 9th Fl-Lobby Ceiling Putty Work | 129 | 0.5 | 0 | 64.5 | 0 | 2024-04-15 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 106988 | 2024-04-22 | 580.5 | 1900-01-01 | -516 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 2nd Fl-Lobby Ceiling Putty Work | 129 | 0.5 | 0 | 64.5 | 0 | 2024-04-15 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 106988 | 2024-04-22 | 580.5 | 1900-01-01 | -516 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 1st Fl-Lobby Ceiling Putty Work | 129 | 0.5 | 0 | 64.5 | 0 | 2024-04-15 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 106988 | 2024-04-22 | 580.5 | 1900-01-01 | -516 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 4th Fl-Lobby Ceiling Putty Work | 129 | 0.5 | 0 | 64.5 | 0 | 2024-04-15 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 106988 | 2024-04-22 | 580.5 | 1900-01-01 | -516 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 8th Fl-Lobby Ceiling Putty Work | 129 | 0.5 | 0 | 64.5 | 0 | 2024-04-15 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 106988 | 2024-04-22 | 580.5 | 1900-01-01 | -516 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 3rd Fl-Lobby Ceiling Putty Work | 129 | 0.5 | 0 | 64.5 | 0 | 2024-04-15 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 106988 | 2024-04-22 | 580.5 | 1900-01-01 | -516 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 5th Fl-Lobby Ceiling Putty Work | 129 | 0.5 | 0 | 64.5 | 0 | 2024-04-15 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 106988 | 2024-04-22 | 580.5 | 1900-01-01 | -516 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 7th Fl-Lobby Ceiling Putty Work | 129 | 0.5 | 0 | 64.5 | 0 | 2024-04-15 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 106988 | 2024-04-22 | 580.5 | 1900-01-01 | -516 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 11th Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 9th Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 10th Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 1st Fl-Lobby Ceiling Putty Work | 517.448 | 0.5 | 0 | 258.724 | 0 | 2023-05-19 | Labour charges for Applying Touch up on Ceiling for D-Bldg Common Lobby Painting work. | 100 |  | 99718 | 2023-05-19 | 3104.64 | 2023-06-10 10:34 | -2845.916 | YUGESH KUMAR
Fabrication removing work Lumpsum | N/C | N/C | R.T.S. STEEL SERVICES | 518 | 2022-08-19 | Labour Camp Removing | 0.1325 | 150000 | 0 | 19875 | 0 | 2023-01-10 | Labour charges for Labour Camp Removing work. | 100 |  | 101293 | 2023-08-17 | 19875 | 2023-11-07 13:56 | 0 | PARTH ENTERPRISES
Fabrication removing work Lumpsum | N/C | N/C | R.T.S. STEEL SERVICES | 518 | 2022-08-19 | Labour Camp Removing | 0.32 | 150000 | 0 | 48000 | 8640 | 2023-01-10 | Labour charges for Labour Camp Removing work. | 100 |  | 97748 | 2023-01-11 | 48000 | 2023-02-23 15:18 | 0 | RAJ INSDUSTRIAL FABRICATORS
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 1st Fl-Lobby Floor -Skirting Work | 125.03 | 18 | 0 | 2250.54 | 0 | 2022-12-12 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 97363 | 2022-12-13 | 9594.17 | 2022-12-26 17:59 | -7343.63 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 1st Fl-Lobby Flooring Work | 524.545 | 14 | 0 | 7343.63 | 0 | 2022-12-12 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 97363 | 2022-12-13 | 9594.17 | 2022-12-26 17:59 | -2250.54 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 19th Fl-Lobby Floor -Skirting Work | 200.048 | 25 | 0 | 5001.2 | 0 | 2024-06-07 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 108202 | 2024-06-10 | 81136.6 | 2024-06-24 12:17 | -76135.4 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 21st Fl-Lobby Floor -Skirting Work | 200.048 | 29.25 | 0 | 5851.404 | 0 | 2024-06-07 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 108202 | 2024-06-10 | 81136.6 | 2024-06-24 12:17 | -75285.196 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 21st Fl-Lobby Flooring Work | 599.48 | 25.24 | 0 | 15130.8752 | 0 | 2024-06-07 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 108202 | 2024-06-10 | 81136.6 | 2024-06-24 12:17 | -66005.7248 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 23rd Fl-Lobby Flooring Work | 599.48 | 25.24 | 0 | 15130.8752 | 0 | 2024-06-07 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 108202 | 2024-06-10 | 81136.6 | 2024-06-24 12:17 | -66005.7248 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 22nd Fl-Lobby Flooring Work | 599.48 | 25.24 | 0 | 15130.8752 | 0 | 2024-06-07 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 108202 | 2024-06-10 | 81136.6 | 2024-06-24 12:17 | -66005.7248 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 19th Fl-Lobby Flooring Work | 599.48 | 22 | 0 | 13188.56 | 0 | 2024-06-07 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 108202 | 2024-06-10 | 81136.6 | 2024-06-24 12:17 | -67948.04 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 23rd Fl-Lobby Floor -Skirting Work | 200.048 | 29.25 | 0 | 5851.404 | 0 | 2024-06-07 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 108202 | 2024-06-10 | 81136.6 | 2024-06-24 12:17 | -75285.196 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 22nd Fl-Lobby Floor -Skirting Work | 200.048 | 29.25 | 0 | 5851.404 | 0 | 2024-06-07 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 108202 | 2024-06-10 | 81136.6 | 2024-06-24 12:17 | -75285.196 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 18th Fl-Lobby Floor -Skirting Work | 200.048 | 25 | 0 | 5001.2 | 900.22 | 2024-05-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 107401 | 2024-05-07 | 30183.34 | 2024-06-15 11:46 | -25182.14 | SUNIL CONSTRUCTION AND CONTRACTORS
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | Stilt Fl Lobby Floor -Skirting Work | 200.048 | 18 | 0 | 3600.864 | 648.16 | 2024-05-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 107401 | 2024-05-07 | 30183.34 | 2024-06-15 11:46 | -26582.476 | SUNIL CONSTRUCTION AND CONTRACTORS
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 18th Fl-Lobby Flooring Work | 599.48 | 22 | 0 | 13188.56 | 2373.94 | 2024-05-06 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 107401 | 2024-05-07 | 30183.34 | 2024-06-15 11:46 | -16994.78 | SUNIL CONSTRUCTION AND CONTRACTORS
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | Stilt Fl Lobby Flooring Work | 599.48 | 14 | 0 | 8392.72 | 1510.68 | 2024-05-06 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 107401 | 2024-05-07 | 30183.34 | 2024-06-15 11:46 | -21790.62 | SUNIL CONSTRUCTION AND CONTRACTORS
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 5th Fl-Lobby Flooring Work | 524.545 | 16 | 0 | 8392.72 | 0 | 2023-10-14 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 102651 | 2023-10-16 | 30423.61 | 2023-10-28 11:59 | -22030.89 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 2nd Fl-Lobby Flooring Work | 524.545 | 14 | 0 | 7343.63 | 0 | 2023-10-14 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 102651 | 2023-10-16 | 30423.61 | 2023-10-28 11:59 | -23079.98 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 3rd Fl-Lobby Flooring Work | 524.545 | 14 | 0 | 7343.63 | 0 | 2023-10-14 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 102651 | 2023-10-16 | 30423.61 | 2023-10-28 11:59 | -23079.98 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 4th Fl-Lobby Flooring Work | 524.545 | 14 | 0 | 7343.63 | 0 | 2023-10-14 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 102651 | 2023-10-16 | 30423.61 | 2023-10-28 11:59 | -23079.98 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 16th Fl-Lobby Flooring Work | 599.48 | 22 | 0 | 13188.56 | 2373.94 | 2024-02-20 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105556 | 2024-02-26 | 84952.68 | 2024-03-18 12:02 | -71764.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 14th Fl-Lobby Flooring Work | 599.48 | 18 | 0 | 10790.64 | 1942.32 | 2024-02-20 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105556 | 2024-02-26 | 84952.68 | 2024-03-18 12:02 | -74162.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 17th Fl-Lobby Floor -Skirting Work | 200.048 | 25 | 0 | 5001.2 | 900.22 | 2024-02-20 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105556 | 2024-02-26 | 84952.68 | 2024-03-18 12:02 | -79951.48 | SUNIL CONSTRUCTION AND CONTRACTORS
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 15th Fl-Lobby Floor -Skirting Work | 200.048 | 25 | 0 | 5001.2 | 900.22 | 2024-02-20 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105556 | 2024-02-26 | 84952.68 | 2024-03-18 12:02 | -79951.48 | SUNIL CONSTRUCTION AND CONTRACTORS
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 13th Fl-Lobby Floor -Skirting Work | 200.048 | 22 | 0 | 4401.056 | 792.2 | 2024-02-20 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105556 | 2024-02-26 | 84952.68 | 2024-03-18 12:02 | -80551.624 | SUNIL CONSTRUCTION AND CONTRACTORS
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 13th Fl-Lobby Flooring Work | 599.48 | 18 | 0 | 10790.64 | 1942.32 | 2024-02-20 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105556 | 2024-02-26 | 84952.68 | 2024-03-18 12:02 | -74162.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 16th Fl-Lobby Floor -Skirting Work | 200.048 | 25 | 0 | 5001.2 | 900.22 | 2024-02-20 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105556 | 2024-02-26 | 84952.68 | 2024-03-18 12:02 | -79951.48 | SUNIL CONSTRUCTION AND CONTRACTORS
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 15th Fl-Lobby Flooring Work | 599.48 | 22 | 0 | 13188.56 | 2373.94 | 2024-02-20 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105556 | 2024-02-26 | 84952.68 | 2024-03-18 12:02 | -71764.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 17th Fl-Lobby Flooring Work | 599.48 | 22 | 0 | 13188.56 | 2373.94 | 2024-02-20 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105556 | 2024-02-26 | 84952.68 | 2024-03-18 12:02 | -71764.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 14th Fl-Lobby Floor -Skirting Work | 200.048 | 22 | 0 | 4401.056 | 792.2 | 2024-02-20 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105556 | 2024-02-26 | 84952.68 | 2024-03-18 12:02 | -80551.624 | SUNIL CONSTRUCTION AND CONTRACTORS
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 11th Fl-Lobby Floor -Skirting Work | 200.048 | 22 | 0 | 4401.056 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -131330.424 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 10th Fl-Lobby Flooring Work | 599.48 | 18 | 0 | 10790.64 | 0 | 2024-03-06 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -124940.84 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 4th Fl-Lobby Floor -Skirting Work | 200.048 | 18 | 0 | 3600.864 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -132130.616 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 7th Fl-Lobby Flooring Work | 599.48 | 16 | 0 | 9591.68 | 0 | 2024-03-06 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -126139.8 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 2nd Fl-Lobby Floor -Skirting Work | 200.048 | 18 | 0 | 3600.864 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -132130.616 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 7th Fl-Lobby Floor -Skirting Work | 200.048 | 20 | 0 | 4000.96 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -131730.52 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 9th Fl-Lobby Floor -Skirting Work | 200.048 | 20 | 0 | 4000.96 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -131730.52 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 3rd Fl-Lobby Floor -Skirting Work | 200.048 | 18 | 0 | 3600.864 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -132130.616 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 5th Fl-Lobby Floor -Skirting Work | 200.048 | 20 | 0 | 4000.96 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -131730.52 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 6th Fl-Lobby Floor -Skirting Work | 200.048 | 20 | 0 | 4000.96 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -131730.52 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 8th Fl-Lobby Flooring Work | 599.48 | 16 | 0 | 9591.68 | 0 | 2024-03-06 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -126139.8 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 12th Fl-Lobby Flooring Work | 599.48 | 18 | 0 | 10790.64 | 0 | 2024-03-06 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -124940.84 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 9th Fl-Lobby Flooring Work | 599.48 | 16 | 0 | 9591.68 | 0 | 2024-03-06 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -126139.8 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 12th Fl-Lobby Floor -Skirting Work | 200.048 | 22 | 0 | 4401.056 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -131330.424 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 20th Fl-Lobby Floor -Skirting Work | 200.048 | 29.25 | 0 | 5851.404 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -129880.076 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 11th Fl-Lobby Flooring Work | 599.48 | 18 | 0 | 10790.64 | 0 | 2024-03-06 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -124940.84 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 6th Fl-Lobby Flooring Work | 599.48 | 16 | 0 | 9591.68 | 0 | 2024-03-06 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -126139.8 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 8th Fl-Lobby Floor -Skirting Work | 200.048 | 20 | 0 | 4000.96 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -131730.52 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 20th Fl-Lobby Flooring Work | 599.48 | 25.24 | 0 | 15130.8752 | 0 | 2024-03-06 | Labour charges for Flooring fixing and Floor Guard Laying work for D-Building Common Lobby. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -120600.6048 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | R.M.Marbles | 519 | 2022-08-24 | 10th Fl-Lobby Floor -Skirting Work | 200.048 | 22 | 0 | 4401.056 | 0 | 2024-03-06 | Labour charges for Skirting Fixing work for D-Building Common Lobby Flooring work. | 100 |  | 105871 | 2024-03-11 | 135731.48 | 2024-03-20 15:38 | -131330.424 | PAPPU BAGELA
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 522 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4313559.322 | 0 | 1941101.6949 | 349398.3 | 2024-07-08 | After Material Receipt at site | 45 | 08/07/2024 Received | 109105 | 2024-07-15 | 1941101.69 | 1900-01-01 | 0.0049 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 522 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4313559.322 | 0.31 | 1941101.6949 | 349398.36 | 2024-02-06 | After Material Receipt at site | 45 | Invoice No- 8150268924 Item No-L-A1,PWU1525-19 31STOPS | 105130 | 2024-02-06 | 1941102 | 2024-02-08 18:12 | -0.3051 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 522 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4313559.322 | 0.17 | 1078389.8305 | 194110.2 | 2024-02-08 | Material Intimation | 25 | For 3rd Lift | 105315 | 2024-06-13 | 1078390 | 2024-06-13 12:36 | -0.1695 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 522 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4313559.322 | 0.03 | 215677.9661 | 38822.04 | 2023-02-20 | Advance Along with Workorder | 5 | Item=L-A2,PWU15/25-19 31 STOPS Invoice No-8150223940 | 98552 | 2023-03-08 | 215678 | 2023-03-08 12:27 | -0.0339 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 522 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4313559.322 | 0.03 | 215677.9661 | 38822.04 | 2023-02-20 | Advance Along with Workorder | 5 | Item= L-A1,PWU15/25-19 31STOPS Invoice No-8150223939 | 98283 | 2023-02-21 | 215678 | 2023-02-28 14:23 | -0.0339 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 522 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4313559.322 | 0.17 | 1078389.8305 | 194110.2 | 2023-11-28 | Material Intimation | 25 | Item- L-A1,PWU15/25-19 31STOPS Invoice No- 8150260257 | 103627 | 2023-12-04 | 1078390 | 2023-12-09 12:24 | -0.1695 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 523 | 2022-08-29 | Supply & Installation of Lifts - E Bldg. | 1 | 4313559.322 | 0.03 | 215677.9661 | 38822.04 | 2023-02-20 | Advance Along with Workorder | 5 | Item=L-C1,PWU15/25-19 31 STOPS Invoice No-8150223942 | 98553 | 2023-03-08 | 215678 | 2023-03-08 12:27 | -0.0339 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 523 | 2022-08-29 | Supply & Installation of Lifts - E Bldg. | 1 | 4313559.322 | 0 | 215677.9661 | 38822.04 | 2023-02-20 | Advance Along with Workorder | 5 | Item= L-C2,PWU15/25-19 31 STOPS Invoice No- 8150223944 | 98554 | 2023-03-08 | 215677.97 | 2023-03-08 12:27 | -0.0039 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 523 | 2022-08-29 | Supply & Installation of Lifts - E Bldg. | 1 | 4313559.322 | 0 | 1078389.8305 | 194110.16 | 2024-07-17 | Material Intimation | 25 | Invoice No-8150296742 DT 09.07.2024 Item- L-C1,PWU15/25-19 31STOPS | 109285 | 2024-07-23 | 1078389.83 | 1900-01-01 | 0.0005 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 524 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4152542.37 | 0 | 622881.3555 | 112118.64 | 2024-05-06 | After Installation | 15 | Invoice No-8150286281 , Equipment No-L-B1,PWU08/25-19 31stops | 107722 | 2024-05-20 | 622881.36 | 2024-07-13 14:45 | -0.0045 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 524 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4152542.37 | 0 | 415254.237 | 74745.76 | 2024-05-06 | Handover with Trial Testing | 10 | Invoice No-8150286281 , Equipment No-L-B1,PWU08/25-19 31stops | 107723 | 2024-05-20 | 415254.24 | 2024-07-13 14:45 | -0.003 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 524 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4152542.37 | -0.07 | 1868644.0665 | 336355.92 | 2024-02-06 | After Material Receipt at site | 45 | Invoice No- 8150268307 Item-L-B1,PWU08/25-19 31STOPS | 105131 | 2024-02-06 | 1868644 | 2024-02-08 18:11 | 0.0665 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 524 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4152542.37 | -0.12 | 207627.1185 | 37372.86 | 2023-02-20 | Advance Along with Workorder | 5 | Item=L-B1,PWU08/25-19 31 STOPS Invoice No-8150223941 | 98284 | 2023-02-21 | 207627 | 2023-02-28 14:23 | 0.1185 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 524 | 2022-08-29 | Supply & Installation of Lifts - D Bldg. | 1 | 4152542.37 | 0.41 | 1038135.5925 | 186864.48 | 2023-11-28 | Material Intimation | 25 | Item-L-B1,PWU08/25 - 19 31STOPS Invoice No- 8150260258 | 103628 | 2023-12-04 | 1038136 | 2023-12-09 12:25 | -0.4075 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 525 | 2022-08-29 | Supply & Installation of Lifts - E Bldg. | 1 | 4152542.37 | 0 | 207627.1185 | 37372.88 | 2023-02-20 | Advance Along with Workorder | 5 | Item= L-D1,PWU08/25-19 31 STOPS Invoice No- 8150223944 | 98285 | 2023-02-21 | 207627.12 | 2023-02-28 14:24 | -0.0015 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 526 | 2022-08-29 | Supply & Installation of Lifts - F Bldg. | 1 | 1398305.084 | 0 | 69915.2542 | 12584.74 | 2023-02-20 | Advance Along with Workorder | 5 | Item=L-E1,PWU15/10-19 5 STOPS Invoice No- 8150223945 | 98286 | 2023-02-21 | 69915.25 | 2023-02-28 14:25 | 0.0042 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 526 | 2022-08-29 | Supply & Installation of Lifts - F Bldg. | 1 | 1398305.084 | 0 | 69915.2542 | 12584.74 | 2023-02-20 | Advance Along with Workorder | 5 | Item= L-F1,PWI15 /10-19 5STOPS Invoice No- 8150223946 | 98287 | 2023-02-21 | 69915.25 | 2023-02-28 14:25 | 0.0042 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 526 | 2022-08-29 | Supply & Installation of Lifts - F Bldg. | 1 | 1398305.084 | 0 | 349576.271 | 62923.72 | 2023-02-20 | Material Intimation | 25 | Item=L-F1,PWI15/10-19 5STOPS Invoice No-8150226193 | 98288 | 2023-02-21 | 349576.27 | 2023-02-28 14:26 | 0.001 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 526 | 2022-08-29 | Supply & Installation of Lifts - F Bldg. | 1 | 1398305.084 | 0 | 349576.271 | 62923.72 | 2023-02-20 | Material Intimation | 25 | Item=L-E1,PWI15/10-19 5 STOPS Invoice no- 8150226279 | 98289 | 2023-02-21 | 349576.27 | 2023-02-28 14:26 | 0.001 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 526 | 2022-08-29 | Supply & Installation of Lifts - F Bldg. | 1 | 1398305.084 | 0.24 | 209745.7626 | 37754.28 | 2023-08-02 | After Installation | 15 | Invoice No- 8150249006 Item-L-E1, PWI 15 /10-19 5 STOPS | 101330 | 2023-08-19 | 209746 | 2023-09-04 19:05 | -0.2374 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 526 | 2022-08-29 | Supply & Installation of Lifts - F Bldg. | 1 | 1398305.084 | -0.29 | 629237.2878 | 113262.66 | 2023-08-25 | After Material Receipt at site | 45 | Item= L-F1,PWI15/10-19 5 STOPS Invoice No- 8150236165 | 101441 | 2023-08-25 | 629237 | 2023-08-31 14:08 | 0.2878 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 526 | 2022-08-29 | Supply & Installation of Lifts - F Bldg. | 1 | 1398305.084 | -0.29 | 629237.2878 | 113262.66 | 2023-08-25 | After Material Receipt at site | 45 | Item=L-E1,PWI15/10-19 5 STOPS Invoice No- 8150236164 | 101442 | 2023-08-25 | 629237 | 2023-08-31 14:08 | 0.2878 | Kone Elevator (I) Pvt. Ltd
Lift Supply & Installaion BC | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 526 | 2022-08-29 | Supply & Installation of Lifts - F Bldg. | 1 | 1398305.084 | 0.49 | 139830.5084 | 25169.58 | 2023-10-11 | Handover with Trial Testing | 10 | L-E1,PWI15/10-19 5STOPS Invoice No-8150256909 | 102541 | 2023-10-12 | 139831 | 2023-10-31 14:57 | -0.4916 | Kone Elevator (I) Pvt. Ltd
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 21st Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg LG Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -79977.65 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg Ground Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P2 Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 12th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg Ground Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -79977.65 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P1 Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 10th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 11th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 24th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 22nd Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 23rd Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 1st Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 2nd Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 16th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 17th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P5 Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -79977.65 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P5 Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 15th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 4th Fl-Lobby Lift Cladding Work | 41.46 | 10 | 0 | 414.6 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82815.2 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 6th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 3rd Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg Stilt Fl Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 14th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 14th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 7th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 2nd Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 6th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 12th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 19th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 1st Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 22nd Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 10th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P1 Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -79977.65 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 13th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 20th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 13th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 18th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 4th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 5th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 7th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 8th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 5th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 11th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 20th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P3 Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 23rd Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 24th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 8th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 9th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 9th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg LG Floor Lift Cladding Work | 82.93 | 10 | 0 | 829.3 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82400.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 21st Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 16th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 19th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 15th Fl-Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg Stilt Fl Lobby Lift Cladding Work | 34.46 | 55 | 0 | 1895.3 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -81334.5 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 17th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 18th Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 3rd Fl-Lobby Lift Cladding Work | 45.6 | 10 | 0 | 456 | 0 | 2024-07-25 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -82773.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P2 Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -79977.65 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg P3 Floor Lift Cladding Work | 59.13 | 55 | 0 | 3252.15 | 0 | 2024-07-25 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 109402 | 2024-07-29 | 83229.8 | 2024-08-05 14:01 | -79977.65 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 13th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 20th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 10th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 22nd Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 15th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg Stilt Fl Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 16th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 19th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 14th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg Stilt Fl Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 12th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 19th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 1st Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 12th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 17th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 18th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 3rd Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 24th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 21st Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 6th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 24th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 10th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 11th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 16th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 9th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 8th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 9th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 17th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 1st Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 2nd Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 2nd Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 14th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 7th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 21st Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 23rd Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 5th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 7th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 8th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 22nd Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 23rd Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 13th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 18th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 4th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 11th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 20th Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 5th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 3rd Fl-Lobby Lift Cladding Work | 24.66 | 55 | 0 | 1356.3 | 0 | 2024-04-13 | Labour Charges for- Granite Cutting and fixing work for lift cladding of D Building with proper joint filling,right angle and plumb.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -41833.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 15th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 4th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Granite edge polish -BRE | N/C | N/C | R.M.Marbles | 527 | 2022-08-29 | D-Bldg 6th Fl-Lobby Lift Cladding Work | 37.13 | 10 | 0 | 371.3 | 0 | 2024-04-13 | Labour Charges for- Granite Edge polish work for lift cladding of D Building.Transportation of raw material from store to required working place to be done by contractor. | 100 |  | 106789 | 2024-04-15 | 43190 | 2024-04-30 15:23 | -42818.7 | PAPPU BAGELA
Event Sponsorship | N/C | N/C | LOKMAT MEDIA PVT. LTD. | 528 | 2022-08-29 | BRANDING Branding | 1 | 2500000 | 0 | 2500000 | 450000 | 2022-08-30 | EVENT SPONCERSHIP- LOKMAT GROUP + GOEL GANAG GROUP AT HOTEL CONROD, PUNE (LIVE INTERACTION WITH SADGURU - SAVE SOIL 2022) VENUE BRANCDING, ONLINE- DIGITAL PROMOTION ETC | 100 |  | 96076 | 2022-08-31 | 2500000 | 2022-11-05 16:24 | 0 | LOKMAT MEDIA PVT. LTD.
Sorting & Shifting Work | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Shifting mockup,checking & rework - 8691.19 Sq.Ft | 6518.3925 | 75 | 0 | 488879.4375 | 87998.3 | 2022-09-10 | Charges for- Sorting & Shifting ,Mockup, Checking and Rework (1st Floor) | 100 |  | 96203 | 2022-09-10 | 1010350.24 | 2022-09-15 16:44 | -521470.8025 | HIGHRISE CONSTRUCTION COMPANY
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Bldg-7th Slab RCC Buit-Up Area | 4345.59 | 120 | 0 | 521470.8 | 93864.74 | 2022-09-10 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 96203 | 2022-09-10 | 1010350.24 | 2022-09-15 16:44 | -488879.44 | HIGHRISE CONSTRUCTION COMPANY
Sorting & Shifting Work | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Shifting mockup,checking & rework - 8691.19 Sq.Ft | 2172.7867 | 75 | 0 | 162959.0025 | 29332.62 | 2022-09-26 | Charges for- Sorting & Shifting ,Mockup, Checking and Rework (1st Floor) | 100 |  | 96374 | 2022-09-27 | 684431 | 2022-10-04 11:59 | -521471.9975 | HIGHRISE CONSTRUCTION COMPANY
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Bldg-7th Slab RCC Buit-Up Area | 4345.6 | 120 | 0 | 521472 | 93864.96 | 2022-09-26 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 96374 | 2022-09-27 | 684431 | 2022-10-04 11:59 | -162959 | HIGHRISE CONSTRUCTION COMPANY
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Bldg-8th Refuge Slab RCC Buit-Up Area | 614.4362 | 120 | 0 | 73732.344 | 13271.82 | 2022-10-04 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | For Flat 103 | 96557 | 2022-10-05 | 73732.34 | 2022-10-15 11:52 | 0.004 | HIGHRISE CONSTRUCTION COMPANY
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Bldg-8th Refuge Slab RCC Buit-Up Area | 3773.5667 | 120 | 0 | 452828.004 | 81509.04 | 2022-10-20 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 96829 | 2022-10-20 | 768840 | 2022-11-08 10:45 | -316011.996 | HIGHRISE CONSTRUCTION COMPANY
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Bldg-8th Refuge Slab RCC Buit-Up Area | 2633.4333 | 120 | 0 | 316011.996 | 56882.16 | 2022-10-20 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 96829 | 2022-10-20 | 768840 | 2022-11-08 10:45 | -452828.004 | HIGHRISE CONSTRUCTION COMPANY
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 600 | 10 | 0 | 6000 | 0 | 2023-04-07 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 99059 | 2023-04-08 | 6000 | 2023-04-24 10:55 | 0 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 1891 | 10 | 0 | 18910 | 0 | 2023-04-08 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 99060 | 2023-04-08 | 18910 | 2023-04-24 10:55 | 0 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 2193 | 10 | 0 | 21930 | 0 | 2023-02-23 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 98315 | 2023-02-24 | 21930 | 2023-03-14 18:19 | 0 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 500 | 10 | 0 | 5000 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 99557 | 2023-05-09 | 5000 | 2023-05-29 13:07 | 0 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F- Bldg Stilt Floor Gypsum On Wall | 964.2 | 10 | 0 | 9642 | 0 | 2022-10-06 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 96598 | 2022-10-07 | 9642 | 2022-11-17 12:57 | 0 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F- Bldg Stilt Floor Gypsum On Wall | 1264 | 10 | 0 | 12640 | 2275.2 | 2024-04-07 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 106650 | 2024-04-08 | 17640 | 1900-01-01 | -5000 | SHREE RAM INTERIOR & DECORATORS
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 500 | 10 | 0 | 5000 | 900 | 2024-04-07 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 106650 | 2024-04-08 | 17640 | 1900-01-01 | -12640 | SHREE RAM INTERIOR & DECORATORS
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 367 | 10 | 0 | 3670 | 660.6 | 2024-02-10 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 105230 | 2024-02-12 | 3670 | 2024-03-18 12:02 | 0 | SHREE RAM INTERIOR & DECORATORS
Gypsum on Wall Rate Diff (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 11529 | 1 | 0 | 11529 | 0 | 2023-11-03 | Labour charges and Rate Diff. for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal part. | 100 |  | 103232 | 2023-11-03 | 15529 | 2023-11-23 11:38 | -4000 | SHAHID RAJA KHAN
Gypsum on Wall Rate Diff (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 4000 | 1 | 0 | 4000 | 0 | 2023-11-03 | Labour charges and Rate Diff. for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal part. | 100 |  | 103232 | 2023-11-03 | 15529 | 2023-11-23 11:38 | -11529 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F- Bldg Stilt Floor Gypsum On Wall | 300 | 10 | 0 | 3000 | 0 | 2023-08-12 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 101219 | 2023-08-12 | 3000 | 2023-08-12 14:27 | 0 | PAWAR SHIVAPPA TARANAIK
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 1135.6 | 10 | 0 | 11356 | 2044.08 | 2023-10-27 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 103042 | 2023-10-27 | 11356 | 2023-11-07 13:58 | 0 | ANIL MAHTO ENTERPRISES
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 2000 | 10 | 0 | 20000 | 3600 | 2024-01-23 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 104745 | 2024-01-23 | 20000 | 2024-02-19 15:18 | 0 | SHREE RAM INTERIOR & DECORATORS
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 4042.7 | 10 | 0 | 40427 | 7276.86 | 2023-03-04 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 98513 | 2023-03-06 | 40427 | 2023-03-29 11:19 | 0 | A K INTERIOR CONTRACTOR
Gypsum on Wall Rate Diff (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 6000 | 1 | 0 | 6000 | 1080 | 2023-09-20 | Labour charges and Rate Diff. for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal part. | 100 |  | 102010 | 2023-09-21 | 46895 | 2023-10-11 11:10 | -40895 | A K INTERIOR CONTRACTOR
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 3rd Floor Gypsum On Wall | 2689.5 | 10 | 0 | 26895 | 4841.1 | 2023-09-20 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 102010 | 2023-09-21 | 46895 | 2023-10-11 11:10 | -20000 | A K INTERIOR CONTRACTOR
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 532 | 2022-09-05 | F-Bldg 3rd Floor Gypsum On Wall | 1400 | 10 | 0 | 14000 | 2520 | 2023-09-21 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 102010 | 2023-09-21 | 46895 | 2023-10-11 11:10 | -32895 | A K INTERIOR CONTRACTOR
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 3428.52 | 3 | 0 | 10285.56 | 514.28 | 2023-10-17 | Rate differance charges for Material Supply for F Building gypsum work. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102740 | 2023-10-18 | 34841.88 | 2024-01-31 17:43 | -24556.32 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 3rd Floor Gypsum On Wall | 1142.84 | 3 | 0 | 3428.52 | 171.42 | 2023-10-17 | Rate differance charges for Material Supply for F Building gypsum work. | 100 | Invoice No-LSF/826/2023-24 | 102740 | 2023-10-18 | 34841.88 | 2024-01-31 17:43 | -31413.36 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 4285.6 | 3 | 0 | 12856.8 | 642.84 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg 1st Floor. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102740 | 2023-10-18 | 34841.88 | 2024-01-31 17:43 | -21985.08 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 2757 | 3 | 0 | 8271 | 413.56 | 2023-10-17 | Material Supply and Rate Diff. charges for gypsum on wall (Tikki Dhada) work for F-Bldg 1st Floor Internal Part. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102740 | 2023-10-18 | 34841.88 | 2024-01-31 17:43 | -26570.88 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 4857.07 | 10 | 0 | 48570.7 | 2428.54 | 2023-02-11 | Material Supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 98258 | 2023-02-18 | 48570.7 | 2023-03-17 15:02 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 1714.26 | 10 | 0 | 17142.6 | 857.14 | 2023-02-11 | Material Supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 | Invoice No-1720 | 98259 | 2023-02-18 | 17142.6 | 2023-03-31 13:16 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 4857.07 | 10 | 0 | 48570.7 | 2428.54 | 2023-02-11 | Material Supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 | INVOICE NO-1714 | 98260 | 2023-02-18 | 48570.7 | 2023-03-17 15:01 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 3rd Floor Gypsum On Wall | 2857.1 | 10 | 0 | 28571 | 1428.56 | 2023-02-11 | Material Supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 98261 | 2023-02-18 | 28571 | 2023-03-17 15:03 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 4285.6 | 10 | 0 | 42856 | 2142.8 | 2023-03-19 | Material Supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 | Invoice no 1326 date 25/2/23 | 98829 | 2023-03-20 | 42856 | 2023-03-31 13:18 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 2757 | 10 | 0 | 27570 | 1378.5 | 2023-03-19 | Material Supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 | invoice no 1373, date -8/3/23 | 98830 | 2023-03-20 | 27570 | 2023-03-31 13:18 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 1714.26 | 10 | 0 | 17142.6 | 857.14 | 2023-02-15 | Material Supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 | Invoice No-1720 | 98206 | 2023-02-15 | 17142.6 | 2023-03-31 13:17 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 3rd Floor Gypsum On Wall | 1142.84 | 10 | 0 | 11428.4 | 571.42 | 2023-02-13 | Material Supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 | Invoice No-1525 | 98207 | 2023-02-15 | 11428.4 | 2023-03-31 13:17 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F- Bldg Stilt Floor Gypsum On Wall | 3428.5 | 10 | 0 | 34285 | 1714.26 | 2022-11-16 | Material Supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 97055 | 2022-11-17 | 34285 | 2022-12-06 12:37 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 3428.5 | 10 | 0 | 34285 | 1714.26 | 2022-11-25 | Material Supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 97136 | 2022-11-26 | 34285 | 2022-12-06 12:37 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 533 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 1685.7 | 10 | 0 | 16857 | 842.86 | 2022-11-25 | Material Supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Internal Part. | 100 |  | 97138 | 2022-11-26 | 16857 | 2022-12-06 12:37 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg LG Floor-Parking Gypsum On Wall | 2110.3 | 10 | 0 | 21103 | 3798.54 | 2023-05-05 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Parking area Common Lobby. | 100 |  | 99460 | 2023-05-06 | 21103 | 2023-05-29 12:43 | 0 | A K INTERIOR CONTRACTOR
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 1st Floor Com. Staircase Gypsum on Wall - 506.9 Sq | 290.072 | 10 | 0 | 2900.72 | 0 | 2023-01-18 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 |  | 97846 | 2023-01-18 | 25644.32 | 2023-01-24 19:42 | -22743.6 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 1st Floor Fire Staircase Gypsum on Ceiling | 266.88 | 5 | 0 | 1334.4 | 0 | 2023-01-18 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Fire Staircase. | 100 |  | 97846 | 2023-01-18 | 25644.32 | 2023-01-24 19:42 | -24309.92 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 2nd Floor Com. Staircase Gypsum on Wall - 506.9 Sq | 290.072 | 10 | 0 | 2900.72 | 0 | 2023-01-18 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 |  | 97846 | 2023-01-18 | 25644.32 | 2023-01-24 19:42 | -22743.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg Stilt Floor Fire Staircase Gypsum on Wall | 529 | 10 | 0 | 5290 | 0 | 2023-01-18 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 |  | 97846 | 2023-01-18 | 25644.32 | 2023-01-24 19:42 | -20354.32 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 2nd Floor Com. Staircase Gypsum on Ceiling - 163.01 | 130.408 | 5 | 0 | 652.04 | 0 | 2023-01-18 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 |  | 97846 | 2023-01-18 | 25644.32 | 2023-01-24 19:42 | -24992.28 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 1st Floor Fire Staircase Gypsum on Wall | 529 | 10 | 0 | 5290 | 0 | 2023-01-18 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 |  | 97846 | 2023-01-18 | 25644.32 | 2023-01-24 19:42 | -20354.32 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 2nd Floor Fire Staircase Gypsum on Wall | 529 | 10 | 0 | 5290 | 0 | 2023-01-18 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 |  | 97846 | 2023-01-18 | 25644.32 | 2023-01-24 19:42 | -20354.32 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 2nd Floor Fire Staircase Gypsum on Ceiling | 266.968 | 5 | 0 | 1334.84 | 0 | 2023-01-18 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Fire Staircase. | 100 |  | 97846 | 2023-01-18 | 25644.32 | 2023-01-24 19:42 | -24309.48 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 3rd Floor Com. Staircase Gypsum on Ceiling - 162.9 | 130.32 | 5 | 0 | 651.6 | 0 | 2023-01-18 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 |  | 97846 | 2023-01-18 | 25644.32 | 2023-01-24 19:42 | -24992.72 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 123.776 | 10 | 0 | 1237.76 | 0 | 2023-04-07 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 |  | 99058 | 2023-04-08 | 4924.64 | 2023-04-24 10:54 | -3686.88 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg Terrace Floor Gypsum On Ceiling | 228.112 | 5 | 0 | 1140.56 | 0 | 2023-04-07 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Lobby. | 100 |  | 99058 | 2023-04-08 | 4924.64 | 2023-04-24 10:54 | -3784.08 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 3rd Floor Gypsum On Wall | 130.968 | 10 | 0 | 1309.68 | 0 | 2023-04-07 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 |  | 99058 | 2023-04-08 | 4924.64 | 2023-04-24 10:54 | -3614.96 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 123.664 | 10 | 0 | 1236.64 | 0 | 2023-04-07 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 |  | 99058 | 2023-04-08 | 4924.64 | 2023-04-24 10:54 | -3688 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg LG Floor Fire Staircase Gypsum on Wall | 748.792 | 10 | 0 | 7487.92 | 0 | 2023-03-15 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -20613.46 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 1st Floor Fire Staircase Gypsum on Ceiling | 33 | 5 | 0 | 165 | 0 | 2023-03-15 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Fire Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -27936.38 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg LG Floor Com.Staircase Gypsum on Ceiling | 162.496 | 5 | 0 | 812.48 | 0 | 2023-03-15 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -27288.9 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg Stilt Floor Com. Staircase Gypsum on Wall - 544.39 | 313.24 | 10 | 0 | 3132.4 | 0 | 2023-03-15 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -24968.98 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg LG Floor Fire Staircase Gypsum on Ceiling | 198.693 | 5 | 0 | 993.465 | 0 | 2023-03-15 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Fire Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -27107.915 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg LG Floor Fire Staircase Gypsum on Ceiling | 22.077 | 5 | 0 | 110.385 | 0 | 2023-03-15 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Fire Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -27990.995 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 2nd Floor Com. Staircase Gypsum on Ceiling - 163.01 | 16.301 | 5 | 0 | 81.505 | 0 | 2023-03-15 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -28019.875 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg Stilt Floor Fire Staircase Gypsum on Wall | 66.125 | 10 | 0 | 661.25 | 0 | 2023-03-15 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -27440.13 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg Terrace Floor Gypsum On Wall | 422.568 | 10 | 0 | 4225.68 | 0 | 2023-03-15 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -23875.7 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 1st Floor Com. Staircase Gypsum on Ceiling - 162.9 | 146.61 | 5 | 0 | 733.05 | 0 | 2023-03-15 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -27368.33 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg LG Floor Com. Staircase Gypsum on Wall - 751.57 Sq | 446.744 | 10 | 0 | 4467.44 | 0 | 2023-03-15 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -23633.94 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 3rd Floor Com. Staircase Gypsum on Ceiling - 162.9 | 16.29 | 5 | 0 | 81.45 | 0 | 2023-03-15 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -28019.93 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 2nd Floor Fire Staircase Gypsum on Ceiling | 33.371 | 5 | 0 | 166.855 | 0 | 2023-03-15 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Fire Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -27934.525 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg Stilt Floor Fire Staircase Gypsum on Ceiling | 280.552 | 5 | 0 | 1402.76 | 0 | 2023-03-15 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Fire Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -26698.62 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg Stilt Floor Com. Staircase Gypsum on Ceiling - 169. | 135.8 | 5 | 0 | 679 | 0 | 2023-03-15 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -27422.38 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 3rd Floor Com. Staircase Gypsum on Wall - 506.9 Sq | 290.072 | 10 | 0 | 2900.72 | 0 | 2023-03-15 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 |  | 98740 | 2023-03-16 | 28101.38 | 2023-03-30 12:45 | -25200.66 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg LG Floor Fire Staircase Gypsum on Wall | 187.198 | 10 | 0 | 1871.98 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -20063.62 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 3rd Floor Gypsum On Wall | 32.742 | 10 | 0 | 327.42 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -21608.18 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg LG Floor-Parking Gypsum on Ceiling | 574 | 5 | 0 | 2870 | 0 | 2023-05-09 | Labour charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Parking Common Lobby. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -19065.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 1st Floor Com. Staircase Gypsum on Wall - 506.9 Sq | 72.518 | 10 | 0 | 725.18 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -21210.42 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg Stilt Floor Gypsum On Wall | 163.71 | 10 | 0 | 1637.1 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -20298.5 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 30.916 | 10 | 0 | 309.16 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -21626.44 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 2nd Floor Com. Staircase Gypsum on Wall - 506.9 Sq | 72.518 | 10 | 0 | 725.18 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -21210.42 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg Stilt Floor Com. Staircase Gypsum on Wall - 544.39 | 78.31 | 10 | 0 | 783.1 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -21152.5 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg LG Floor Gypsum On Wall | 789 | 10 | 0 | 7890 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -14045.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg LG Floor Com. Staircase Gypsum on Wall - 751.57 Sq | 111.686 | 10 | 0 | 1116.86 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -20818.74 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 30.944 | 10 | 0 | 309.44 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -21626.16 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 3rd Floor Com. Staircase Gypsum on Wall - 506.9 Sq | 72.518 | 10 | 0 | 725.18 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -21210.42 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 1st Floor Fire Staircase Gypsum on Wall | 132.25 | 10 | 0 | 1322.5 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -20613.1 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | YUGESH KUMAR | 534 | 2022-09-05 | F-Bldg 2nd Floor Fire Staircase Gypsum on Wall | 132.25 | 10 | 0 | 1322.5 | 0 | 2023-05-09 | Labour charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 |  | 99550 | 2023-05-09 | 21935.6 | 2023-06-10 10:33 | -20613.1 | SHAHID RAJA KHAN
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Stilt Floor Com. Staircase Gypsum on Wall - 544.39 | 185 | 10 | 0 | 1850 | 92.5 | 2023-10-17 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70032.69 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 154.72 | 3 | 0 | 464.16 | 23.2 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg Common Lobby, Common Staircase & Fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71418.53 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 3rd Floor Com. Staircase Gypsum on Ceiling - 162.9 | 162.9 | 3.28 | 0 | 534.312 | 26.72 | 2023-10-17 | Material Supply charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71348.378 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Stilt Floor Fire Staircase Gypsum on Ceiling | 350.69 | 3.28 | 0 | 1150.2632 | 57.52 | 2023-10-17 | Material Supply charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Fire Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70732.4268 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor-Parking Gypsum On Wall | 2857.1 | 1.4 | 0 | 3999.94 | 200 | 2023-10-17 | Material Supply charges and Rate Diff. for Tikki Dhada work (Gypsum on wall) for F-Bldg Parking common lobby. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -67882.75 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 1st Floor Fire Staircase Gypsum on Ceiling | 333.6 | 3.28 | 0 | 1094.208 | 54.72 | 2023-10-17 | Material Supply charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Fire Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70788.482 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 2nd Floor Com. Staircase Gypsum on Ceiling - 163.01 | 163.01 | 3.28 | 0 | 534.6728 | 26.74 | 2023-10-17 | Material Supply charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 |  | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71348.0172 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor Fire Staircase Gypsum on Ceiling | 220.77 | 3.28 | 0 | 724.1256 | 36.2 | 2023-10-17 | Material Supply charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Fire Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71158.5644 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 154.58 | 3 | 0 | 463.74 | 23.18 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg Common Lobby, Common Staircase & Fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71418.95 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Stilt Floor Fire Staircase Gypsum on Wall | 152.84 | 10 | 0 | 1528.4 | 76.42 | 2023-10-17 | Material Supply charges for Quantity differance of Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70354.29 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor Com.Staircase Gypsum on Ceiling | 203.12 | 3.28 | 0 | 666.2336 | 33.32 | 2023-10-17 | Material Supply charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71216.4564 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor-Parking Gypsum On Wall | 2857.1 | 1.4 | 0 | 3999.94 | 200 | 2023-10-17 | Rate Differance Charges for Supply of Material for Tikki dhada (Gypsum on wall) for F Building parking common lobby area. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -67882.75 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Stilt Floor Com. Staircase Gypsum on Ceiling - 169. | 169.75 | 3.28 | 0 | 556.78 | 27.84 | 2023-10-17 | Material Supply charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71325.91 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 3rd Floor Gypsum On Wall | 163.71 | 3 | 0 | 491.13 | 24.56 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg Common Lobby, Common Staircase & Fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71391.56 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Stilt Floor Com. Staircase Gypsum on Wall - 544.39 | 152.84 | 10 | 0 | 1528.4 | 76.42 | 2023-10-17 | Material Supply charges for Quantity differance of Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70354.29 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Stilt Floor Gypsum On Wall | 163.71 | 3 | 0 | 491.13 | 24.56 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg Common Lobby, Common Staircase & Fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71391.56 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 2nd Floor Fire Staircase Gypsum on Ceiling | 333.71 | 3.28 | 0 | 1094.5688 | 54.72 | 2023-10-17 | Material Supply charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Fire Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70788.1212 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor Fire Staircase Gypsum on Wall | 935.99 | 3 | 0 | 2807.97 | 140.4 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg Common Lobby, Common Staircase & Fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -69074.72 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Stilt Floor Fire Staircase Gypsum on Wall | 661.25 | 3 | 0 | 1983.75 | 99.18 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg stilt Floor fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -69898.94 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 2nd Floor Fire Staircase Gypsum on Wall | 661.25 | 3 | 0 | 1983.75 | 99.18 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg 2nd Floor fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -69898.94 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 1st Floor Com. Staircase Gypsum on Ceiling - 162.9 | 162.9 | 3.28 | 0 | 534.312 | 26.72 | 2023-10-17 | Material Supply charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71348.378 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor Com. Staircase Gypsum on Wall - 751.57 Sq | 558.43 | 3 | 0 | 1675.29 | 83.76 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg Common Lobby, Common Staircase & Fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70207.4 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor-Parking Gypsum On Wall | 1042 | 10 | 0 | 10420 | 521 | 2023-10-17 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Parking Common Lobby. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -61462.69 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor-Parking Gypsum on Ceiling | 4593.81 | 3.28 | 0 | 15067.6968 | 753.38 | 2023-10-17 | Material Supply charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Parking Common Lobby. | 100 |  | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -56814.9932 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 2nd Floor Com. Staircase Gypsum on Wall - 506.9 Sq | 362.59 | 3 | 0 | 1087.77 | 54.38 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg Common Lobby, Common Staircase & Fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70794.92 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 3rd Floor Com. Staircase Gypsum on Wall - 506.9 Sq | 362.59 | 3 | 0 | 1087.77 | 54.38 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg Common Lobby, Common Staircase & Fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70794.92 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 3rd Floor Fire Staircase Gypsum on Ceiling | 320.77 | 3.28 | 0 | 1052.1256 | 52.6 | 2023-10-17 | Material Supply Charges for Quantity differance of Patra punning work (Gypsum on Ceiling) for F Building Fire Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70830.5644 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Terrace Floor Gypsum On Ceiling | 285.14 | 3.28 | 0 | 935.2592 | 46.76 | 2023-10-17 | Material Supply charges for Patra Punning work (Gypsum on Ceiling) for F-Bldg Common Lobby. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70947.4308 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor Com. Staircase Gypsum on Wall - 751.57 Sq | 193.14 | 10 | 0 | 1931.4 | 96.58 | 2023-10-17 | Material Supply charges for Quantity differance of Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -69951.29 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor Fire Staircase Gypsum on Wall | 120.42 | 10 | 0 | 1204.2 | 60.22 | 2023-10-17 | Material Supply charges for Quantity differance of Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70678.49 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Ceiling (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor Fire Staircase Gypsum on Ceiling | 124.32 | 3.28 | 0 | 407.7696 | 20.38 | 2023-10-17 | Material Supply Charges for Quantity differance of Patra punning work (Gypsum on Ceiling) for F Building Fire Staircase. | 100 | Invoice No- LSF/826/2023-24 (480 Bags) DT 13/10/2023 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71474.9204 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Stilt Floor Com. Staircase Gypsum on Wall - 544.39 | 206 | 3 | 0 | 618 | 30.9 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg stilt Floor fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -71264.69 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 1st Floor Com. Staircase Gypsum on Wall - 506.9 Sq | 362.59 | 10 | 0 | 3625.9 | 181.3 | 2023-10-17 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -68256.79 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Terrace Floor Gypsum On Wall | 511.9 | 3 | 0 | 1535.7 | 76.78 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg Common Lobby, Common Staircase & Fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -70346.99 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall Rate Diff. (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor Gypsum On Wall | 917.34 | 3 | 0 | 2752.02 | 137.6 | 2023-10-17 | Material Supply charges and Rate Diff. for (Tikki Dhada) work gypsum on wall for F-Bldg Common Lobby, Common Staircase & Fire staircase. | 100 | Invoice No-LSF/826/2023-24 | 102741 | 2023-10-18 | 71882.69 | 2024-01-31 17:43 | -69130.67 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor-Parking Gypsum On Wall | 2857.1 | 10 | 0 | 28571 | 1428.56 | 2023-07-12 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Parking Common Lobby. | 100 | Invoice No-LSF/311/2023-24 | 100662 | 2023-07-13 | 28571 | 2023-08-14 14:34 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor-Parking Gypsum On Wall | 2857.1 | 10 | 0 | 28571 | 1428.56 | 2023-07-12 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Parking Common Lobby. | 100 | Invoice No-LSF/280/2023-24 | 100663 | 2023-07-13 | 28571 | 2023-08-14 14:33 | 0 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Stilt Floor Com. Staircase Gypsum on Wall - 544.39 | 206 | 10 | 0 | 2060 | 103 | 2023-03-19 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 | invoice no 1373, date -8/3/23 | 98831 | 2023-03-20 | 15280 | 2023-03-31 13:19 | -13220 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Stilt Floor Fire Staircase Gypsum on Wall | 661 | 10 | 0 | 6610 | 330.5 | 2023-03-19 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 | invoice no 1373, date -8/3/23 | 98831 | 2023-03-20 | 15280 | 2023-03-31 13:19 | -8670 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 2nd Floor Fire Staircase Gypsum on Wall | 661 | 10 | 0 | 6610 | 330.5 | 2023-03-19 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 | invoice no 1373, date -8/3/23 | 98831 | 2023-03-20 | 15280 | 2023-03-31 13:19 | -8670 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor Com. Staircase Gypsum on Wall - 751.57 Sq | 558.43 | 10 | 0 | 5584.3 | 279.22 | 2023-03-22 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 | Invoice No- LSF/1419/2022-2023 | 98881 | 2023-03-23 | 42855.6 | 2023-03-31 13:18 | -37271.3 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 2nd Floor Com. Staircase Gypsum on Wall - 506.9 Sq | 362.59 | 10 | 0 | 3625.9 | 181.3 | 2023-03-22 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 | Invoice No- LSF/1419/2022-2023 | 98881 | 2023-03-23 | 42855.6 | 2023-03-31 13:18 | -39229.7 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor Gypsum On Wall | 917.34 | 10 | 0 | 9173.4 | 458.68 | 2023-03-22 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 |  | 98881 | 2023-03-23 | 42855.6 | 2023-03-31 13:18 | -33682.2 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Terrace Floor Gypsum On Wall | 511.9 | 10 | 0 | 5119 | 255.96 | 2023-03-22 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 | Invoice No- LSF/1419/2022-2023 | 98881 | 2023-03-23 | 42855.6 | 2023-03-31 13:18 | -37736.6 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 2nd Floor Gypsum On Wall | 154.72 | 10 | 0 | 1547.2 | 77.36 | 2023-03-22 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 | Invoice No- LSF/1419/2022-2023 | 98881 | 2023-03-23 | 42855.6 | 2023-03-31 13:18 | -41308.4 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 3rd Floor Gypsum On Wall | 163.71 | 10 | 0 | 1637.1 | 81.86 | 2023-03-22 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 | Invoice No- LSF/1419/2022-2023 | 98881 | 2023-03-23 | 42855.6 | 2023-03-31 13:18 | -41218.5 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg LG Floor Fire Staircase Gypsum on Wall | 935.99 | 10 | 0 | 9359.9 | 468 | 2023-03-22 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Fire Staircase. | 100 | Invoice No- LSF/1419/2022-2023 | 98881 | 2023-03-23 | 42855.6 | 2023-03-31 13:18 | -33495.7 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg Stilt Floor Gypsum On Wall | 163.71 | 10 | 0 | 1637.1 | 81.86 | 2023-03-22 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 | Invoice No- LSF/1419/2022-2023 | 98881 | 2023-03-23 | 42855.6 | 2023-03-31 13:18 | -41218.5 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 3rd Floor Com. Staircase Gypsum on Wall - 506.9 Sq | 362.59 | 10 | 0 | 3625.9 | 181.3 | 2023-03-22 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Staircase. | 100 | Invoice No- LSF/1419/2022-2023 | 98881 | 2023-03-23 | 42855.6 | 2023-03-31 13:18 | -39229.7 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | YUGESH KUMAR | 535 | 2022-09-05 | F-Bldg 1st Floor Gypsum On Wall | 154.58 | 10 | 0 | 1545.8 | 77.3 | 2023-03-22 | Material supply charges for Tikki Dhada work (Gypsum on wall) for F-Bldg Common Lobby. | 100 | Invoice No- LSF/1419/2022-2023 | 98881 | 2023-03-23 | 42855.6 | 2023-03-31 13:18 | -41309.8 | LAXMI STRUCTURES & FIXTURES LLP
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Common lobby flooring work | 185.36 | 23 | 0 | 4263.28 | 0 | 2023-09-21 13:17 | Labour charges for Flooring work (1200 x 600 mm) for F-Building Common Lobby. | 100 |  | 102040 | 2023-09-22 | 57291.29 | 2023-09-30 12:15 | -53028.01 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Common lobby flooring work | 251.36 | 23 | 0 | 5781.28 | 0 | 2023-09-21 15:24 | Labour charges for Flooring work (1200 x 600 mm) for F-Building Common Lobby. | 100 |  | 102040 | 2023-09-22 | 57291.29 | 2023-09-30 12:15 | -51510.01 | PAPPU BAGELA
Granite Flooring | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Common lobby flooring work | 149.47 | 45 | 0 | 6726.15 | 0 | 2023-09-21 15:24 | Labour charges for Granite Flooring Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 102040 | 2023-09-22 | 57291.29 | 2023-09-30 12:15 | -50565.14 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Common lobby flooring work | 187.0435 | 23 | 0 | 4302.0005 | 0 | 2023-09-21 13:17 | Labour charges for Flooring work (1200 x 600 mm) for F-Building Common Lobby. | 100 |  | 102040 | 2023-09-22 | 57291.29 | 2023-09-30 12:15 | -52989.2895 | PAPPU BAGELA
Granite Flooring | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Common lobby flooring work | 55.25 | 45 | 0 | 2486.25 | 0 | 2023-09-21 15:24 | Labour charges for Granite Flooring Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 102040 | 2023-09-22 | 57291.29 | 2023-09-30 12:15 | -54805.04 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Common lobby flooring work | 1430.76 | 23 | 0 | 32907.48 | 0 | 2023-09-21 13:17 | Labour charges for Flooring work (1200 x 600 mm) for F-Building Common Lobby. | 100 |  | 102040 | 2023-09-22 | 57291.29 | 2023-09-30 12:15 | -24383.81 | PAPPU BAGELA
Granite Flooring | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F- Bldg Stilt Floor Common lobby flooring work | 18.33 | 45 | 0 | 824.85 | 0 | 2023-09-21 15:24 | Labour charges for Granite Flooring Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 | for LG floor | 102040 | 2023-09-22 | 57291.29 | 2023-09-30 12:15 | -56466.44 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Common lobby flooring work | 251.9565 | 23 | 0 | 5794.9995 | 0 | 2023-08-26 | Labour charges for Flooring work (1200 x 600 mm) for F-Building Common Lobby. | 100 |  | 101493 | 2023-08-28 | 38815 | 2023-09-04 11:46 | -33020.0005 | PAPPU BAGELA
Granite Flooring | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Common lobby flooring work | 70 | 45 | 0 | 3150 | 0 | 2023-08-26 | Labour charges for Granite Flooring Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 101493 | 2023-08-28 | 38815 | 2023-09-04 11:46 | -35665 | PAPPU BAGELA
Granite Flooring | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F- Bldg Stilt Floor Common lobby flooring work | 54.3111 | 45 | 0 | 2443.9995 | 0 | 2023-08-26 | Labour charges for Granite Flooring Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 101493 | 2023-08-28 | 38815 | 2023-09-04 11:46 | -36371.0005 | PAPPU BAGELA
Granite Flooring | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Common lobby flooring work | 70 | 45 | 0 | 3150 | 0 | 2023-08-26 | Labour charges for Granite Flooring Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 101493 | 2023-08-28 | 38815 | 2023-09-04 11:46 | -35665 | PAPPU BAGELA
Granite Skirting | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F- Bldg Stilt Floor Common lobby flooring work | 27.7111 | 45 | 0 | 1246.9995 | 0 | 2023-08-26 | Labour charges for Granite Skirting Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 101493 | 2023-08-28 | 38815 | 2023-09-04 11:46 | -37568.0005 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Common lobby flooring work | 251.9565 | 23 | 0 | 5794.9995 | 0 | 2023-08-26 | Labour charges for Flooring work (1200 x 600 mm) for F-Building Common Lobby. | 100 |  | 101493 | 2023-08-28 | 38815 | 2023-09-04 11:46 | -33020.0005 | PAPPU BAGELA
Granite Skirting | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Common lobby flooring work | 27.7111 | 45 | 0 | 1246.9995 | 0 | 2023-08-26 | Labour charges for Granite Skirting Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 101493 | 2023-08-28 | 38815 | 2023-09-04 11:46 | -37568.0005 | PAPPU BAGELA
Granite Skirting | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Common lobby flooring work | 27.7111 | 45 | 0 | 1246.9995 | 0 | 2023-08-26 | Labour charges for Granite Skirting Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 101493 | 2023-08-28 | 38815 | 2023-09-04 11:46 | -37568.0005 | PAPPU BAGELA
Granite Flooring | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Common lobby flooring work | 70 | 45 | 0 | 3150 | 0 | 2023-08-26 | Labour charges for Granite Flooring Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 101493 | 2023-08-28 | 38815 | 2023-09-04 11:46 | -35665 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F- Bldg Stilt Floor Common lobby flooring work | 251.9565 | 23 | 0 | 5794.9995 | 0 | 2023-08-26 | Labour charges for Flooring work (1200 x 600 mm) for F-Building Common Lobby. | 100 |  | 101493 | 2023-08-28 | 38815 | 2023-09-04 11:46 | -33020.0005 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Common lobby flooring work | 251.9565 | 23 | 0 | 5794.9995 | 0 | 2023-08-26 | Labour charges for Flooring work (1200 x 600 mm) for F-Building Common Lobby. | 100 |  | 101493 | 2023-08-28 | 38815 | 2023-09-04 11:46 | -33020.0005 | PAPPU BAGELA
Granite Flooring | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Common lobby flooring work | 25.88 | 45 | 0 | 1164.6 | 0 | 2024-04-22 15:58 | Labour charges for Granite Flooring Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 107110 | 2024-04-25 | 23091.32 | 2024-05-15 14:39 | -21926.72 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Common lobby flooring work | 331.7135 | 23 | 0 | 7629.4105 | 0 | 2024-04-22 15:58 | Labour charges for Flooring work (1200 x 600 mm) for F-Building Common Lobby. | 100 |  | 107110 | 2024-04-25 | 23091.32 | 2024-05-15 14:39 | -15461.9095 | PAPPU BAGELA
Granite Flooring | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Terrace Floor Common lobby flooring work | 36.16 | 45 | 0 | 1627.2 | 0 | 2024-04-22 15:58 | Labour charges for Granite Flooring Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 107110 | 2024-04-25 | 23091.32 | 2024-05-15 14:39 | -21464.12 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Common lobby flooring work | 146.95 | 23 | 0 | 3379.85 | 0 | 2024-04-22 15:58 | Labour charges for Flooring work (1200 x 600 mm) for F-Building Common Lobby. | 100 |  | 107110 | 2024-04-25 | 23091.32 | 2024-05-15 14:39 | -19711.47 | PAPPU BAGELA
Granite Flooring | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F- Bldg Stilt Floor Common lobby flooring work | 16.8589 | 45 | 0 | 758.6505 | 0 | 2024-04-22 15:58 | Labour charges for Granite Flooring Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 107110 | 2024-04-25 | 23091.32 | 2024-05-15 14:39 | -22332.6695 | PAPPU BAGELA
Granite Flooring | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Common lobby flooring work | 11.13 | 45 | 0 | 500.85 | 0 | 2024-04-22 15:58 | Labour charges for Granite Flooring Fixing work (Roylite Brown Granite) for F-Building Common Lobby. | 100 |  | 107110 | 2024-04-25 | 23091.32 | 2024-05-15 14:39 | -22590.47 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Common lobby flooring work | 349.1635 | 23 | 0 | 8030.7605 | 0 | 2024-04-22 15:58 | Labour charges for Flooring work (1200 x 600 mm) for F-Building Common Lobby. | 100 |  | 107110 | 2024-04-25 | 23091.32 | 2024-05-15 14:39 | -15060.5595 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Toilet Door Frame | 204 | 10 | 0 | 2040 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -37585 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Common area Window Sill | 31 | 45 | 0 | 1395 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38230 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Toilet Door Frame | 102 | 10 | 0 | 1020 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38605 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Ledge Wall Top (Common Toilet) | 4 | 10 | 0 | 40 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39585 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Ledge Wall Top (Common Toilet) | 2 | 10 | 0 | 20 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39605 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Common area Window Sill | 31 | 10 | 0 | 310 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39315 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Umbra Patti | 28 | 45 | 0 | 1260 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38365 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Umbra Patti | 28 | 45 | 0 | 1260 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38365 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Ledge Wall Top (Common Toilet) | 4 | 45 | 0 | 180 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39445 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Terrace Floor Umbra Patti | 7 | 10 | 0 | 70 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39555 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Toilet Ventilator (Common Toilet) | 19 | 45 | 0 | 855 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38770 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Common area Window Sill | 31 | 45 | 0 | 1395 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38230 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Umbra Patti | 19 | 45 | 0 | 855 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38770 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Common area Window Sill | 31 | 10 | 0 | 310 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39315 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Toilet Door Frame | 68 | 45 | 0 | 3060 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -36565 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Ledge Wall Top (Common Toilet) | 4 | 10 | 0 | 40 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39585 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Common area Window Sill | 31 | 10 | 0 | 310 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39315 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Umbra Patti | 28 | 45 | 0 | 1260 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38365 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Ledge Wall Top (Common Toilet) | 2 | 45 | 0 | 90 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39535 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Ledge Wall Top (Common Toilet) | 4 | 45 | 0 | 180 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ledge Wall Top. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39445 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Toilet Ventilator (Common Toilet) | 10 | 45 | 0 | 450 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39175 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Stilt Floor Umbra Patti | 23 | 10 | 0 | 230 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39395 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Toilet Ventilator (Common Toilet) | 19 | 45 | 0 | 855 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38770 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Toilet Door Frame | 136 | 45 | 0 | 6120 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -33505 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Terrace Floor Umbra Patti | 7 | 45 | 0 | 315 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39310 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Toilet Ventilator (Common Toilet) | 19 | 10 | 0 | 190 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39435 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Common area Window Sill | 16 | 10 | 0 | 160 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39465 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Umbra Patti | 37 | 10 | 0 | 370 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39255 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Toilet Ventilator (Common Toilet) | 10 | 10 | 0 | 100 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39525 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Toilet Ventilator (Common Toilet) | 19 | 10 | 0 | 190 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Ventilator Frame.. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39435 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Stilt Floor Umbra Patti | 14 | 45 | 0 | 630 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38995 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 1st Floor Umbra Patti | 64 | 10 | 0 | 640 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38985 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg LG Floor Common area Window Sill | 16 | 45 | 0 | 720 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38905 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Toilet Door Frame | 204 | 10 | 0 | 2040 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -37585 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Umbra Patti | 64 | 10 | 0 | 640 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38985 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 3rd Floor Umbra Patti | 64 | 10 | 0 | 640 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Umbra Patti for Lift Door Single Patti, Toilet Door Double Patti and Folding Door at Entrance Single Patti. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38985 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Stilt Floor Common area Window Sill | 34 | 10 | 0 | 340 | 0 | 2024-07-24 15:52 | Labour charges for Granite Edge Polish work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -39285 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Common area Window Sill | 31 | 45 | 0 | 1395 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38230 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg 2nd Floor Toilet Door Frame | 136 | 45 | 0 | 6120 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Toilet Door Frame. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -33505 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 536 | 2022-09-15 | F-Bldg Stilt Floor Common area Window Sill | 34 | 45 | 0 | 1530 | 0 | 2024-07-24 15:52 | Labour charges for Granite Cutting and Fixing work for F-Bldg Common Area Window Sill. | 100 |  | 109400 | 2024-07-29 | 39625 | 1900-01-01 | -38095 | PAPPU BAGELA
Brickbat W/P | N/C | N/C | AJAY KUMAR GUPTA | 538 | 2022-09-16 | F-Bldg LG Floor Toilet Waterproofing Work | 38.21 | 18 | 0 | 687.78 | 123.8 | 2023-06-27 12:25 | Labour charges for Brickbat Waterproofing work for F-Bldg Toilet Waterproofing work for LG Floor. | 100 |  | 100301 | 2023-06-27 | 5883.64 | 2023-06-28 11:57 | -5195.86 | GANGAPRASAD K VARMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AJAY KUMAR GUPTA | 538 | 2022-09-16 | F-Bldg 1st Floor Toilet Waterproofing Work | 23.26 | 22 | 0 | 511.72 | 92.1 | 2023-06-27 12:25 | Labour and Material Charges for Chemical Waterproofing work for 1st Floor Toilet Waterproofing work. | 100 |  | 100301 | 2023-06-27 | 5883.64 | 2023-06-28 11:57 | -5371.92 | GANGAPRASAD K VARMA
Brickbat W/P | N/C | N/C | AJAY KUMAR GUPTA | 538 | 2022-09-16 | F-Bldg 1st Floor Toilet Waterproofing Work | 260.23 | 18 | 0 | 4684.14 | 843.14 | 2023-06-27 12:25 | Labour charges for Brickbat Waterproofing work for F-Bldg Toilet Waterproofing work for 1st Floor. | 100 |  | 100301 | 2023-06-27 | 5883.64 | 2023-06-28 11:57 | -1199.5 | GANGAPRASAD K VARMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 538 | 2022-09-16 | F-Bldg 3rd Floor Toilet Waterproofing Work | 102.9 | 22 | 0 | 2263.8 | 0 | 2024-07-12 16:01 | Labour and Material Charges for Chemical Waterproofing work for 3rd Floor Toilet Waterproofing work. | 100 |  | 109090 | 2024-07-15 | 4116 | 1900-01-01 | -1852.2 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | AJAY KUMAR GUPTA | 538 | 2022-09-16 | F-Bldg 3rd Floor Toilet Waterproofing Work | 102.9 | 18 | 0 | 1852.2 | 0 | 2024-07-12 16:01 | Labour charges for Brickbat Waterproofing work for 3rd Floor Toilet area F-Bldg | 100 |  | 109090 | 2024-07-15 | 4116 | 1900-01-01 | -2263.8 | PRABHURAM VERMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AJAY KUMAR GUPTA | 538 | 2022-09-16 | F-Bldg LG Floor Toilet Waterproofing Work | 38.21 | 22 | 0 | 840.62 | 0 | 2023-10-07 09:31 | Labour and Material Charges for Chemical Waterproofing work for LG Floor Floor Toilet W/P work. | 100 |  | 102435 | 2023-10-09 | 840.62 | 2023-10-28 11:57 | 0 | PRABHURAM VERMA
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Lift Duct Cement paint | 671.64 | 1 | 0 | 671.64 | 120.9 | 2024-06-18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 108504 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -1646.98 | TEJASHREE ENTERPRISES
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 64.4 | 2024-06-18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 108504 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -1960.825 | TEJASHREE ENTERPRISES
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F- Bldg Stilt Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 64.4 | 2024-06-18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 108504 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -1960.825 | TEJASHREE ENTERPRISES
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 64.4 | 2024-06-18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 108504 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -1960.825 | TEJASHREE ENTERPRISES
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 64.4 | 2024-06-18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 108504 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -1960.825 | TEJASHREE ENTERPRISES
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Lift Duct Cement paint | 215.78 | 1 | 0 | 215.78 | 38.84 | 2024-06-18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 108504 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -2102.84 | TEJASHREE ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Southside Acrylic Texture Paint | 80 | 1.5 | 0 | 120 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 108013 | 2024-06-03 | 120 | 1900-01-01 | 0 | YUGESH KUMAR
1st Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F- Bldg Stilt Floor Lift Duct Cement paint | 715.59 | 1 | 0 | 715.59 | 0 | 2023-06-28 10:18 | Labour charges for Applying 1st Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6240.23 | YUGESH KUMAR
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Lift Duct Cement paint | 671.64 | 1 | 0 | 671.64 | 0 | 2023-06-28 10:18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6284.18 | YUGESH KUMAR
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Lift Duct Cement paint | 215.78 | 1 | 0 | 215.78 | 0 | 2023-06-28 10:18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6740.04 | YUGESH KUMAR
1st Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Lift Duct Cement paint | 715.59 | 1 | 0 | 715.59 | 0 | 2023-06-28 10:18 | Labour charges for Applying 1st Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6240.23 | YUGESH KUMAR
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 0 | 2023-06-28 10:18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6598.025 | YUGESH KUMAR
1st Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Lift Duct Cement paint | 431.56 | 1 | 0 | 431.56 | 0 | 2023-06-28 10:18 | Labour charges for Applying 1st Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6524.26 | YUGESH KUMAR
1st Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Lift Duct Cement paint | 1343.28 | 1 | 0 | 1343.28 | 0 | 2023-06-28 10:18 | Labour charges for Applying 1st Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -5612.54 | YUGESH KUMAR
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F- Bldg Stilt Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 0 | 2023-06-28 10:18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6598.025 | YUGESH KUMAR
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 0 | 2023-06-28 10:18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6598.025 | YUGESH KUMAR
2nd Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 0 | 2023-06-28 10:18 | Labour charges for 2nd Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6598.025 | YUGESH KUMAR
1st Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Lift Duct Cement paint | 715.59 | 1 | 0 | 715.59 | 0 | 2023-06-28 10:18 | Labour charges for Applying 1st Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6240.23 | YUGESH KUMAR
1st Coat Cement Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Lift Duct Cement paint | 715.59 | 1 | 0 | 715.59 | 0 | 2023-06-28 10:18 | Labour charges for Applying 1st Coat Cement Paint for F-Bldg Lift Duct. | 100 |  | 100328 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6240.23 | YUGESH KUMAR
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Eastside Acrylic Texture Paint | 1009 | 7.25 | 0 | 7315.25 | 0 | 2024-06-02 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -13680.5 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Southside Acrylic Texture Paint | 87 | 1.5 | 0 | 130.5 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20865.25 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Northside Acrylic Texture Paint-(Floor) | 92 | 1.5 | 0 | 138 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20857.75 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Stilt Floor Eastside Acrylic Texture Paint | 823 | 1 | 0 | 823 | 0 | 2024-06-02 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20172.75 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Eastside Acrylic Texture Paint | 60 | 1.5 | 0 | 90 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20905.75 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Acrylic Texture Paint | 800 | 7.25 | 0 | 5800 | 0 | 2024-06-02 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -15195.75 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Northside Acrylic Texture Paint | 90 | 1.5 | 0 | 135 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20860.75 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Acrylic Texture Paint | 3000 | 1.5 | 0 | 4500 | 0 | 2024-06-02 | Labour charges for Applying 2nd Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -16495.75 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Acrylic Texture Paint | 400 | 1.5 | 0 | 600 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20395.75 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Northside Acrylic Texture Paint | 50 | 1.5 | 0 | 75 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20920.75 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Northside Acrylic Texture Paint | 40 | 1.5 | 0 | 60 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20935.75 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Southside Acrylic Texture Paint | 80 | 1 | 0 | 80 | 0 | 2024-06-02 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20915.75 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Eastside Acrylic Texture Paint | 62 | 1.5 | 0 | 93 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20902.75 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Eastside Acrylic Texture Paint | 100 | 1.5 | 0 | 150 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20845.75 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Southside Acrylic Texture Paint | 85 | 1.5 | 0 | 127.5 | 0 | 2024-06-02 | Labour charges for Applying 2nd Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20868.25 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Southside Acrylic Texture Paint | 88 | 1 | 0 | 88 | 0 | 2024-06-02 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20907.75 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Stilt Floor Eastside Acrylic Texture Paint | 80 | 1.5 | 0 | 120 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20875.75 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Southside Acrylic Texture Paint | 85 | 1.5 | 0 | 127.5 | 0 | 2024-06-02 | Labour charges for Applying 2nd Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20868.25 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Southside Acrylic Texture Paint | 88 | 1.5 | 0 | 132 | 0 | 2024-06-02 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20863.75 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Acrylic Texture Paint | 411 | 1 | 0 | 411 | 0 | 2024-06-02 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 107938 | 2024-06-03 | 20995.75 | 2024-06-15 17:59 | -20584.75 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Northside Acylic Texture Paint | 900 | 7.25 | 0 | 6525 | 1174.5 | 2023-09-13 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101856 | 2023-09-15 | 17969.4 | 2023-09-30 11:50 | -11444.4 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Stilt Floor Eastside Acrylic Texture Paint | 741.132 | 1.5 | 0 | 1111.698 | 200.1 | 2023-09-14 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101856 | 2023-09-15 | 17969.4 | 2023-09-30 11:50 | -16857.702 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Eastside Acrylic Texture Paint | 570.303 | 1.5 | 0 | 855.4545 | 153.98 | 2023-09-14 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101856 | 2023-09-15 | 17969.4 | 2023-09-30 11:50 | -17113.9455 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Eastside Acrylic Texture Paint | 972.99 | 1.5 | 0 | 1459.485 | 262.7 | 2023-09-14 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101856 | 2023-09-15 | 17969.4 | 2023-09-30 11:50 | -16509.915 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F- Bldg Stilt Floor Northside Acrylic Texture Paint | 837.063 | 1.5 | 0 | 1255.5945 | 226 | 2023-09-14 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101856 | 2023-09-15 | 17969.4 | 2023-09-30 11:50 | -16713.8055 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Eastside Acrylic Texture Paint | 572.652 | 1.5 | 0 | 858.978 | 154.62 | 2023-09-14 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101856 | 2023-09-15 | 17969.4 | 2023-09-30 11:50 | -17110.422 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Eastside Acrylic Texture Paint | 572.652 | 1.5 | 0 | 858.978 | 154.62 | 2023-09-14 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101856 | 2023-09-15 | 17969.4 | 2023-09-30 11:50 | -17110.422 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Northside Acrylic Texture Paint-(Floor) | 837.063 | 1.5 | 0 | 1255.5945 | 226 | 2023-09-14 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101856 | 2023-09-15 | 17969.4 | 2023-09-30 11:50 | -16713.8055 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Northside Acrylic Texture Paint | 837.063 | 1.5 | 0 | 1255.5945 | 226 | 2023-09-14 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101856 | 2023-09-15 | 17969.4 | 2023-09-30 11:50 | -16713.8055 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Northside Acrylic Texture Paint | 837.063 | 1.5 | 0 | 1255.5945 | 226 | 2023-09-14 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101856 | 2023-09-15 | 17969.4 | 2023-09-30 11:50 | -16713.8055 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Northside Acylic Texture Paint | 851.625 | 1.5 | 0 | 1277.4375 | 229.94 | 2023-09-14 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101856 | 2023-09-15 | 17969.4 | 2023-09-30 11:50 | -16691.9625 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Southside Acrylic Texture Paint | 792.513 | 1.5 | 0 | 1188.7695 | 213.98 | 2023-08-16 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101286 | 2023-08-17 | 9586.91 | 2023-09-01 11:43 | -8398.1405 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Southside Acrylic Texture Paint | 802.107 | 1.5 | 0 | 1203.1605 | 216.56 | 2023-08-16 | Labour charges for Applying 2nd Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101286 | 2023-08-17 | 9586.91 | 2023-09-01 11:43 | -8383.7495 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Southside Acrylic Texture Paint | 802.107 | 1.5 | 0 | 1203.1605 | 216.56 | 2023-08-16 | Labour charges for Applying 2nd Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101286 | 2023-08-17 | 9586.91 | 2023-09-01 11:43 | -8383.7495 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Southside Acrylic Texture Paint | 802.107 | 1.5 | 0 | 1203.1605 | 216.56 | 2023-08-16 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101286 | 2023-08-17 | 9586.91 | 2023-09-01 11:43 | -8383.7495 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Southside Acrylic Texture Paint | 792.513 | 1 | 0 | 792.513 | 142.66 | 2023-08-16 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101286 | 2023-08-17 | 9586.91 | 2023-09-01 11:43 | -8794.397 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Southside Acrylic Texture Paint | 802.107 | 1 | 0 | 802.107 | 144.38 | 2023-08-16 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101286 | 2023-08-17 | 9586.91 | 2023-09-01 11:43 | -8784.803 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Southside Acrylic Texture Paint | 792.513 | 1.5 | 0 | 1188.7695 | 213.98 | 2023-08-16 | Labour charges for Applying 2nd Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101286 | 2023-08-17 | 9586.91 | 2023-09-01 11:43 | -8398.1405 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Southside Acrylic Texture Paint | 802.107 | 1 | 0 | 802.107 | 144.38 | 2023-08-16 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101286 | 2023-08-17 | 9586.91 | 2023-09-01 11:43 | -8784.803 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Southside Acrylic Texture Paint | 802.107 | 1.5 | 0 | 1203.1605 | 216.56 | 2023-08-16 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101286 | 2023-08-17 | 9586.91 | 2023-09-01 11:43 | -8383.7495 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Eastside Acrylic Texture Paint | 540.55 | 3.5 | 0 | 1891.925 | 340.54 | 2024-01-19 16:22 | Labour charges for Scaffolding Fixing and Removing work for F-Bldg External Texture paint. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -81246.765 | MANSI ENTERPRISES.
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F- Bldg Stilt Floor Northside Acrylic Texture Paint | 465.035 | 3.5 | 0 | 1627.6225 | 292.98 | 2024-01-19 16:22 | Labour charges for Scaffolding Fixing and Removing work for F-Bldg External Texture paint. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -81511.0675 | MANSI ENTERPRISES.
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Eastside Acrylic Texture Paint | 318.14 | 3.5 | 0 | 1113.49 | 200.42 | 2024-01-19 16:22 | Labour charges for Scaffolding Fixing and Removing work for F-Bldg External Texture paint. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -82025.2 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Eastside Acrylic Texture Paint | 633.67 | 7.25 | 0 | 4594.1075 | 826.94 | 2024-01-19 17:03 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -78544.5825 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Eastside Acrylic Texture Paint | 636.28 | 7.25 | 0 | 4613.03 | 830.34 | 2024-01-19 17:03 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -78525.66 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F- Bldg Stilt Floor Northside Acrylic Texture Paint | 930.07 | 7.25 | 0 | 6743.0075 | 1213.74 | 2024-01-19 16:58 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -76395.6825 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Acrylic Texture Paint | 2924.91 | 7.25 | 0 | 21205.5975 | 3817 | 2024-01-19 17:18 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -61933.0925 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Northside Acrylic Texture Paint | 930.07 | 7.25 | 0 | 6743.0075 | 1213.74 | 2024-01-19 16:58 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -76395.6825 | MANSI ENTERPRISES.
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Northside Acrylic Texture Paint-(Floor) | 465.035 | 3.5 | 0 | 1627.6225 | 292.98 | 2024-01-19 16:22 | Labour charges for Scaffolding Fixing and Removing work for F-Bldg External Texture paint. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -81511.0675 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Northside Acrylic Texture Paint-(Floor) | 930.07 | 7.25 | 0 | 6743.0075 | 1213.74 | 2024-01-19 16:58 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -76395.6825 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Stilt Floor Eastside Acrylic Texture Paint | 823.48 | 7.25 | 0 | 5970.23 | 1074.64 | 2024-01-19 17:03 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -77168.46 | MANSI ENTERPRISES.
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Eastside Acrylic Texture Paint | 318.14 | 3.5 | 0 | 1113.49 | 200.42 | 2024-01-19 16:22 | Labour charges for Scaffolding Fixing and Removing work for F-Bldg External Texture paint. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -82025.2 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Northside Acrylic Texture Paint | 930.07 | 7.25 | 0 | 6743.0075 | 1213.74 | 2024-01-19 16:58 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -76395.6825 | MANSI ENTERPRISES.
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Eastside Acrylic Texture Paint | 316.835 | 3.5 | 0 | 1108.9225 | 199.6 | 2024-01-19 16:22 | Labour charges for Scaffolding Fixing and Removing work for F-Bldg External Texture paint. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -82029.7675 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Eastside Acrylic Texture Paint | 636.28 | 7.25 | 0 | 4613.03 | 830.34 | 2024-01-19 17:03 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -78525.66 | MANSI ENTERPRISES.
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Northside Acylic Texture Paint | 473.125 | 3.5 | 0 | 1655.9375 | 298.06 | 2024-01-19 16:22 | Labour charges for Scaffolding Fixing and Removing work for F-Bldg External Texture paint. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -81482.7525 | MANSI ENTERPRISES.
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Northside Acrylic Texture Paint | 465.035 | 3.5 | 0 | 1627.6225 | 292.98 | 2024-01-19 16:22 | Labour charges for Scaffolding Fixing and Removing work for F-Bldg External Texture paint. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -81511.0675 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Northside Acylic Texture Paint | 46.25 | 7.25 | 0 | 335.3125 | 60.36 | 2024-01-19 16:58 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -82803.3775 | MANSI ENTERPRISES.
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Northside Acrylic Texture Paint | 465.035 | 3.5 | 0 | 1627.6225 | 292.98 | 2024-01-19 16:22 | Labour charges for Scaffolding Fixing and Removing work for F-Bldg External Texture paint. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -81511.0675 | MANSI ENTERPRISES.
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Stilt Floor Eastside Acrylic Texture Paint | 411.74 | 3.5 | 0 | 1441.09 | 259.4 | 2024-01-19 16:22 | Labour charges for Scaffolding Fixing and Removing work for F-Bldg External Texture paint. | 100 |  | 104639 | 2024-01-19 | 83138.69 | 2024-02-02 14:25 | -81697.6 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Eastside Acrylic Texture Paint | 72 | 7.25 | 0 | 522 | 93.96 | 2024-01-23 | Labour charges for Applying Texture Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 104742 | 2024-01-23 | 522 | 1900-01-01 | 0 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Northside Acylic Texture Paint | 851.625 | 1 | 0 | 851.625 | 153.3 | 2023-09-20 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101983 | 2023-09-20 | 15313.98 | 2023-10-11 11:11 | -14462.355 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Acrylic Texture Paint | 3705.03 | 1 | 0 | 3705.03 | 666.9 | 2023-09-20 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101983 | 2023-09-20 | 15313.98 | 2023-10-11 11:11 | -11608.95 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Acrylic Texture Paint | 3705.03 | 1.5 | 0 | 5557.545 | 1000.36 | 2023-09-20 | Labour charges for Applying 1st Coat Acrylic Paint for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101983 | 2023-09-20 | 15313.98 | 2023-10-11 11:11 | -9756.435 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Eastside Acrylic Texture Paint | 572.652 | 1 | 0 | 572.652 | 103.08 | 2023-09-20 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101983 | 2023-09-20 | 15313.98 | 2023-10-11 11:11 | -14741.328 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Northside Acrylic Texture Paint | 837.063 | 1 | 0 | 837.063 | 150.68 | 2023-09-20 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101983 | 2023-09-20 | 15313.98 | 2023-10-11 11:11 | -14476.917 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Northside Acrylic Texture Paint | 837.063 | 1 | 0 | 837.063 | 150.68 | 2023-09-20 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101983 | 2023-09-20 | 15313.98 | 2023-10-11 11:11 | -14476.917 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Northside Acrylic Texture Paint-(Floor) | 837.063 | 1 | 0 | 837.063 | 150.68 | 2023-09-20 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101983 | 2023-09-20 | 15313.98 | 2023-10-11 11:11 | -14476.917 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Eastside Acrylic Texture Paint | 570.303 | 1 | 0 | 570.303 | 102.66 | 2023-09-20 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101983 | 2023-09-20 | 15313.98 | 2023-10-11 11:11 | -14743.677 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Eastside Acrylic Texture Paint | 572.652 | 1 | 0 | 572.652 | 103.08 | 2023-09-20 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101983 | 2023-09-20 | 15313.98 | 2023-10-11 11:11 | -14741.328 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Eastside Acrylic Texture Paint | 972.99 | 1 | 0 | 972.99 | 175.14 | 2023-09-20 | Labour charges for Applying 1 Coat Water base primer for F Building external side.Transortation of raw material from store to required place to be done by contractor. | 100 |  | 101983 | 2023-09-20 | 15313.98 | 2023-10-11 11:11 | -14340.99 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Duct- Semi Acrylic Paint | 2299.302 | 1 | 0 | 2299.302 | 413.88 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine. | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -28111.388 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F- Bldg Stilt Floor Duct- Semi Acrylic Paint | 3617.532 | 1.5 | 0 | 5426.298 | 976.74 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -24984.392 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Duct- Semi Acrylic Paint | 2326.329 | 1.5 | 0 | 3489.4935 | 628.1 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -26921.1965 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Duct- Semi Acrylic Paint | 2326.329 | 1 | 0 | 2326.329 | 418.74 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine. | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -28084.361 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 2nd Floor Duct- Semi Acrylic Paint | 2326.329 | 1.5 | 0 | 3489.4935 | 628.1 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -26921.1965 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Duct- Semi Acrylic Paint | 753.309 | 1.5 | 0 | 1129.9635 | 203.4 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -29280.7265 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 3rd Floor Duct- Semi Acrylic Paint | 2326.329 | 1 | 0 | 2326.329 | 418.74 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine. | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -28084.361 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg 1st Floor Duct- Semi Acrylic Paint | 2299.302 | 1.5 | 0 | 3448.953 | 620.82 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -26961.737 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F- Bldg Stilt Floor Duct- Semi Acrylic Paint | 3617.532 | 1 | 0 | 3617.532 | 651.16 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine. | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -26793.158 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Duct- Semi Acrylic Paint | 841.482 | 1.5 | 0 | 1262.223 | 227.2 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -29148.467 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg LG Floor Duct- Semi Acrylic Paint | 753.309 | 1 | 0 | 753.309 | 135.6 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine. | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -29657.381 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | YUGESH KUMAR | 539 | 2022-09-16 | F-Bldg Terrace Floor Duct- Semi Acrylic Paint | 841.482 | 1 | 0 | 841.482 | 151.46 | 2023-09-21 | Labour charges for Applying one Coat Water Base Primer for F-Building Duct Paint. Material to be shifted by contractor from site store to required place by own labour/ machine. | 100 |  | 102003 | 2023-09-21 | 30410.69 | 2023-10-11 11:12 | -29569.208 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F- Bldg Stilt Floor Duct- Semi Acrylic Paint | 4019.48 | 1.5 | 0 | 6029.22 | 1085.26 | 2023-09-21 | Material Supply of 1st Coat Semi Acrylic Paint for Duct.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -27760.47 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Duct- Semi Acrylic Paint | 2554.78 | 1.5 | 0 | 3832.17 | 689.8 | 2023-09-21 | Material Supply of 1st Coat Semi Acrylic Paint for Duct.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -29957.52 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Duct- Semi Acrylic Paint | 2584.81 | 1.5 | 0 | 3877.215 | 697.9 | 2023-09-21 | Material Supply of 1st Coat Semi Acrylic Paint for Duct.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -29912.475 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Duct- Semi Acrylic Paint | 837.01 | 1.5 | 0 | 1255.515 | 226 | 2023-09-21 | Material Supply of 1st Coat Semi Acrylic Paint for Duct.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -32534.175 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Duct- Semi Acrylic Paint | 2584.81 | 1 | 0 | 2584.81 | 465.26 | 2023-09-21 | Material supply of 1 coat Water Base Primer for F-Building Duct Paint.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -31204.88 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Northside Acrylic Texture Paint-(Floor) | 930.07 | 1 | 0 | 930.07 | 167.42 | 2023-09-20 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101984 | 2023-09-20 | 10428.82 | 1900-01-01 | -9498.75 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Northside Acrylic Texture Paint | 930.07 | 1 | 0 | 930.07 | 167.42 | 2023-09-20 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101984 | 2023-09-20 | 10428.82 | 1900-01-01 | -9498.75 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Northside Acylic Texture Paint | 946.25 | 1 | 0 | 946.25 | 170.32 | 2023-09-20 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101984 | 2023-09-20 | 10428.82 | 1900-01-01 | -9482.57 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg Terrace Floor Acrylic Texture Paint | 3705.03 | 1 | 0 | 3705.03 | 666.9 | 2023-09-20 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101984 | 2023-09-20 | 10428.82 | 1900-01-01 | -6723.79 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Eastside Acrylic Texture Paint | 570.303 | 1 | 0 | 570.303 | 102.66 | 2023-09-20 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101984 | 2023-09-20 | 10428.82 | 1900-01-01 | -9858.517 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Northside Acrylic Texture Paint | 930.07 | 1 | 0 | 930.07 | 167.42 | 2023-09-20 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101984 | 2023-09-20 | 10428.82 | 1900-01-01 | -9498.75 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Eastside Acrylic Texture Paint | 636.28 | 1 | 0 | 636.28 | 114.54 | 2023-09-20 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101984 | 2023-09-20 | 10428.82 | 1900-01-01 | -9792.54 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Eastside Acrylic Texture Paint | 636.28 | 1 | 0 | 636.28 | 114.54 | 2023-09-20 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101984 | 2023-09-20 | 10428.82 | 1900-01-01 | -9792.54 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Eastside Acrylic Texture Paint | 63.367 | 1 | 0 | 63.367 | 11.4 | 2023-09-20 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101984 | 2023-09-20 | 10428.82 | 1900-01-01 | -10365.453 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Eastside Acrylic Texture Paint | 1081.1 | 1 | 0 | 1081.1 | 194.6 | 2023-09-20 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101984 | 2023-09-20 | 10428.82 | 1900-01-01 | -9347.72 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Eastside Acrylic Texture Paint | 633.67 | 7.25 | 0 | 4594.1075 | 826.94 | 2023-09-18 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 101945 | 2023-09-20 | 11542.14 | 1900-01-01 | -6948.0325 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Eastside Acrylic Texture Paint | 200 | 7.25 | 0 | 1450 | 261 | 2023-09-18 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 101945 | 2023-09-20 | 11542.14 | 1900-01-01 | -10092.14 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Eastside Acrylic Texture Paint | 636.28 | 7.25 | 0 | 4613.03 | 830.34 | 2023-09-18 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 101945 | 2023-09-20 | 11542.14 | 1900-01-01 | -6929.11 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Southside Acrylic Texture Paint | 122.069 | 7.25 | 0 | 885.0003 | 159.3 | 2023-09-18 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 101945 | 2023-09-20 | 11542.14 | 1900-01-01 | -10657.1398 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Eastside Acrylic Texture Paint | 636.28 | 2 | 0 | 1272.56 | 229.06 | 2023-09-14 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101896 | 2023-09-15 | 23293.67 | 2023-09-30 11:54 | -22021.11 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Northside Acrylic Texture Paint-(Floor) | 837.063 | 2 | 0 | 1674.126 | 301.34 | 2023-09-14 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101896 | 2023-09-15 | 23293.67 | 2023-09-30 11:54 | -21619.544 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Northside Acrylic Texture Paint | 930.07 | 2 | 0 | 1860.14 | 334.82 | 2023-09-14 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101896 | 2023-09-15 | 23293.67 | 2023-09-30 11:54 | -21433.53 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Northside Acylic Texture Paint | 946.25 | 2 | 0 | 1892.5 | 340.66 | 2023-09-14 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101896 | 2023-09-15 | 23293.67 | 2023-09-30 11:54 | -21401.17 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Northside Acylic Texture Paint | 900 | 7.25 | 0 | 6525 | 1174.5 | 2023-09-13 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 101896 | 2023-09-15 | 23293.67 | 2023-09-30 11:54 | -16768.67 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Eastside Acrylic Texture Paint | 1081.1 | 2 | 0 | 2162.2 | 389.2 | 2023-09-14 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101896 | 2023-09-15 | 23293.67 | 2023-09-30 11:54 | -21131.47 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg Stilt Floor Eastside Acrylic Texture Paint | 823.48 | 2 | 0 | 1646.96 | 296.46 | 2023-09-14 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101896 | 2023-09-15 | 23293.67 | 2023-09-30 11:54 | -21646.71 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Eastside Acrylic Texture Paint | 633.67 | 2 | 0 | 1267.34 | 228.12 | 2023-09-15 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101896 | 2023-09-15 | 23293.67 | 2023-09-30 11:54 | -22026.33 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Northside Acrylic Texture Paint | 930.07 | 2 | 0 | 1860.14 | 334.82 | 2023-09-14 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101896 | 2023-09-15 | 23293.67 | 2023-09-30 11:54 | -21433.53 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F- Bldg Stilt Floor Northside Acrylic Texture Paint | 930.07 | 2 | 0 | 1860.14 | 334.82 | 2023-09-14 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101896 | 2023-09-15 | 23293.67 | 2023-09-30 11:54 | -21433.53 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Eastside Acrylic Texture Paint | 636.28 | 2 | 0 | 1272.56 | 229.06 | 2023-09-14 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101896 | 2023-09-15 | 23293.67 | 2023-09-30 11:54 | -22021.11 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg Terrace Floor Duct- Semi Acrylic Paint | 934.98 | 1 | 0 | 934.98 | 168.3 | 2023-09-21 | Material supply of 1 coat Water Base Primer for F-Building Duct Paint.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -32854.71 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F- Bldg Stilt Floor Duct- Semi Acrylic Paint | 4019.48 | 1 | 0 | 4019.48 | 723.5 | 2023-09-21 | Material supply of 1 coat Water Base Primer for F-Building Duct Paint.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -29770.21 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Duct- Semi Acrylic Paint | 837.01 | 1 | 0 | 837.01 | 150.66 | 2023-09-21 | Material supply of 1 coat Water Base Primer for F-Building Duct Paint.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -32952.68 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Duct- Semi Acrylic Paint | 2554.78 | 1 | 0 | 2554.78 | 459.86 | 2023-09-21 | Material supply of 1 coat Water Base Primer for F-Building Duct Paint.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -31234.91 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Duct- Semi Acrylic Paint | 2584.81 | 1.5 | 0 | 3877.215 | 697.9 | 2023-09-21 | Material Supply of 1st Coat Semi Acrylic Paint for Duct.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -29912.475 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Duct- Semi Acrylic Paint | 2584.81 | 1 | 0 | 2584.81 | 465.26 | 2023-09-21 | Material supply of 1 coat Water Base Primer for F-Building Duct Paint.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -31204.88 | VEER BHADRA ENTERPRISES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg Terrace Floor Duct- Semi Acrylic Paint | 934.98 | 1.5 | 0 | 1402.47 | 252.44 | 2023-09-21 | Material Supply of 1st Coat Semi Acrylic Paint for Duct.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 102004 | 2023-09-21 | 33789.69 | 2023-09-30 12:15 | -32387.22 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Eastside Acrylic Texture Paint | 72 | 7.25 | 0 | 522 | 93.96 | 2024-01-23 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 104743 | 2024-01-23 | 522 | 1900-01-01 | 0 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg Terrace Floor Acrylic Texture Paint | 2000 | 2 | 0 | 4000 | 720 | 2024-04-07 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 106653 | 2024-04-08 | 7625 | 1900-01-01 | -3625 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Eastside Acrylic Texture Paint | 500 | 7.25 | 0 | 3625 | 652.5 | 2024-04-07 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 106653 | 2024-04-08 | 7625 | 1900-01-01 | -4000 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Eastside Acrylic Texture Paint | 436.28 | 7.25 | 0 | 3163.03 | 569.34 | 2024-01-19 17:09 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 104640 | 2024-01-19 | 68303.35 | 2024-02-02 14:24 | -65140.32 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F- Bldg Stilt Floor Northside Acrylic Texture Paint | 930.07 | 7.25 | 0 | 6743.0075 | 1213.74 | 2024-01-19 17:00 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 104640 | 2024-01-19 | 68303.35 | 2024-02-02 14:24 | -61560.3425 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Northside Acrylic Texture Paint-(Floor) | 930.07 | 7.25 | 0 | 6743.0075 | 1213.74 | 2024-01-19 17:00 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 104640 | 2024-01-19 | 68303.35 | 2024-02-02 14:24 | -61560.3425 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Southside Acrylic Texture Paint | 758.501 | 7.25 | 0 | 5499.1322 | 989.84 | 2024-01-19 17:12 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 104640 | 2024-01-19 | 68303.35 | 2024-02-02 14:24 | -62804.2178 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Southside Acrylic Texture Paint | 711.45 | 7.25 | 0 | 5158.0125 | 928.44 | 2024-01-19 17:12 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 104640 | 2024-01-19 | 68303.35 | 2024-02-02 14:24 | -63145.3375 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Northside Acrylic Texture Paint | 930.07 | 7.25 | 0 | 6743.0075 | 1213.74 | 2024-01-19 17:00 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 104640 | 2024-01-19 | 68303.35 | 2024-02-02 14:24 | -61560.3425 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg Stilt Floor Eastside Acrylic Texture Paint | 823.48 | 7.25 | 0 | 5970.23 | 1074.64 | 2024-01-19 17:09 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 104640 | 2024-01-19 | 68303.35 | 2024-02-02 14:24 | -62333.12 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg Terrace Floor Acrylic Texture Paint | 2924.91 | 7.25 | 0 | 21205.5975 | 3817 | 2024-01-19 17:17 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 104640 | 2024-01-19 | 68303.35 | 2024-02-02 14:24 | -47097.7525 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Northside Acrylic Texture Paint | 930.07 | 7.25 | 0 | 6743.0075 | 1213.74 | 2024-01-19 17:00 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 104640 | 2024-01-19 | 68303.35 | 2024-02-02 14:24 | -61560.3425 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Northside Acylic Texture Paint | 46.25 | 7.25 | 0 | 335.3125 | 60.36 | 2024-01-19 17:00 | Material Supply charges for Texture Paint for F Building external Side | 100 |  | 104640 | 2024-01-19 | 68303.35 | 2024-02-02 14:24 | -67968.0375 | MANSI ENTERPRISES.
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Southside Acrylic Texture Paint | 891.23 | 1 | 0 | 891.23 | 160.42 | 2023-08-16 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101285 | 2023-08-17 | 14646.68 | 2023-09-01 11:43 | -13755.45 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Southside Acrylic Texture Paint | 880.57 | 2.5 | 0 | 2201.425 | 396.26 | 2023-08-16 | Material Supply Charges for 2nd Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101285 | 2023-08-17 | 14646.68 | 2023-09-01 11:43 | -12445.255 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Southside Acrylic Texture Paint | 880.57 | 2 | 0 | 1761.14 | 317 | 2023-08-16 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101285 | 2023-08-17 | 14646.68 | 2023-09-01 11:43 | -12885.54 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Southside Acrylic Texture Paint | 891.23 | 2.5 | 0 | 2228.075 | 401.06 | 2023-08-16 | Material Supply Charges for 2nd Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101285 | 2023-08-17 | 14646.68 | 2023-09-01 11:43 | -12418.605 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Southside Acrylic Texture Paint | 891.23 | 2 | 0 | 1782.46 | 320.84 | 2023-08-16 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101285 | 2023-08-17 | 14646.68 | 2023-09-01 11:43 | -12864.22 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Southside Acrylic Texture Paint | 891.23 | 2.5 | 0 | 2228.075 | 401.06 | 2023-08-16 | Material Supply Charges for 2nd Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101285 | 2023-08-17 | 14646.68 | 2023-09-01 11:43 | -12418.605 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Southside Acrylic Texture Paint | 880.57 | 1 | 0 | 880.57 | 158.5 | 2023-08-16 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101285 | 2023-08-17 | 14646.68 | 2023-09-01 11:43 | -13766.11 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Southside Acrylic Texture Paint | 891.23 | 1 | 0 | 891.23 | 160.42 | 2023-08-16 | Material Supply charges for 1 Coat Water base primer for F Building external texture paint. | 100 |  | 101285 | 2023-08-17 | 14646.68 | 2023-09-01 11:43 | -13755.45 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Southside Acrylic Texture Paint | 891.23 | 2 | 0 | 1782.46 | 320.84 | 2023-08-16 | Material Supply Charges for 1st Coat Acrylic Paint for F Building external texture paint. | 100 |  | 101285 | 2023-08-17 | 14646.68 | 2023-09-01 11:43 | -12864.22 | VEER BHADRA ENTERPRISES
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 0 | 2023-06-28 10:35 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6598.025 | YUGESH KUMAR
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg Terrace Floor Lift Duct Cement paint | 215.78 | 1 | 0 | 215.78 | 0 | 2023-06-28 10:35 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6740.04 | YUGESH KUMAR
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 0 | 2023-06-28 10:35 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6598.025 | YUGESH KUMAR
1st Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F- Bldg Stilt Floor Lift Duct Cement paint | 715.59 | 1 | 0 | 715.59 | 0 | 2023-06-28 10:35 | Material Supply charges for 1st coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6240.23 | YUGESH KUMAR
1st Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Lift Duct Cement paint | 715.59 | 1 | 0 | 715.59 | 0 | 2023-06-28 10:35 | Material Supply charges for 1st coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6240.23 | YUGESH KUMAR
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 0 | 2023-06-28 10:35 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6598.025 | YUGESH KUMAR
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F- Bldg Stilt Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 0 | 2023-06-28 10:35 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6598.025 | YUGESH KUMAR
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Lift Duct Cement paint | 671.64 | 1 | 0 | 671.64 | 0 | 2023-06-28 10:35 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6284.18 | YUGESH KUMAR
1st Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg Terrace Floor Lift Duct Cement paint | 431.56 | 1 | 0 | 431.56 | 0 | 2023-06-28 10:35 | Material Supply charges for 1st coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6524.26 | YUGESH KUMAR
1st Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Lift Duct Cement paint | 715.59 | 1 | 0 | 715.59 | 0 | 2023-06-28 10:35 | Material Supply charges for 1st coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6240.23 | YUGESH KUMAR
1st Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Lift Duct Cement paint | 1343.28 | 1 | 0 | 1343.28 | 0 | 2023-06-28 10:35 | Material Supply charges for 1st coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -5612.54 | YUGESH KUMAR
1st Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Lift Duct Cement paint | 715.59 | 1 | 0 | 715.59 | 0 | 2023-06-28 10:35 | Material Supply charges for 1st coat cement paint for F-Bldg Lift Duct. | 100 |  | 100329 | 2023-06-28 | 6955.82 | 2023-07-29 10:56 | -6240.23 | YUGESH KUMAR
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg LG Floor Lift Duct Cement paint | 671.64 | 1 | 0 | 671.64 | 120.9 | 2024-06-18 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 108558 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -1646.98 | TEJASHREE ENTERPRISES
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 3rd Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 64.4 | 2024-06-18 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 108558 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -1960.825 | TEJASHREE ENTERPRISES
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg Terrace Floor Lift Duct Cement paint | 215.78 | 1 | 0 | 215.78 | 38.84 | 2024-06-18 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 108558 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -2102.84 | TEJASHREE ENTERPRISES
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 2nd Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 64.4 | 2024-06-18 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 108558 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -1960.825 | TEJASHREE ENTERPRISES
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F-Bldg 1st Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 64.4 | 2024-06-18 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 108558 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -1960.825 | TEJASHREE ENTERPRISES
2nd Coat Cement Paint (M) | N/C | N/C | YUGESH KUMAR | 540 | 2022-09-16 | F- Bldg Stilt Floor Lift Duct Cement paint | 357.795 | 1 | 0 | 357.795 | 64.4 | 2024-06-18 | Material Supply charges for 2nd coat cement paint for F-Bldg Lift Duct. | 100 |  | 108558 | 2024-06-24 | 2318.62 | 2024-07-15 15:16 | -1960.825 | TEJASHREE ENTERPRISES
Leased Line - | N/C | N/C | LIMERICK TECHNOLOGIES PRIVATE LIMITED | 543 | 2022-09-29 | Fixed Assets EDP & IT Expenses | 1 | 67500 | 0 | 67500 | 12150 | 2022-11-05 | Charges for Leased line for Head office for 1 Year at speed of 50 MBPS (1:1) | 100 |  | 96935 | 2022-11-05 | 72500 | 2022-11-22 11:18 | -5000 | LIMERICK TECHNOLOGIES PRIVATE LIMITED
Installation Leased Line | N/C | N/C | LIMERICK TECHNOLOGIES PRIVATE LIMITED | 543 | 2022-09-29 | Fixed Assets EDP & IT Expenses | 1 | 5000 | 0 | 5000 | 900 | 2022-11-05 | Charges for Installation of Leased line for Head office | 100 |  | 96935 | 2022-11-05 | 72500 | 2022-11-22 11:18 | -67500 | LIMERICK TECHNOLOGIES PRIVATE LIMITED
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 547 | 2022-10-01 | F-Bldg 1st Floor Ceiling Paint | 5946.87 | 0.75 | 0 | 4460.1525 | 0 | 2023-10-06 | Labour charges for Applying Water Base Primer on Ceiling for F-Building Internal part Painting work. | 100 |  | 102393 | 2023-10-07 | 8675.75 | 1900-01-01 | -4215.5975 | YUGESH KUMAR
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 547 | 2022-10-01 | F-Bldg 2nd Floor Ceiling Paint Work | 5620.8 | 0.75 | 0 | 4215.6 | 0 | 2023-10-06 | Labour charges for Applying Water Base Primer on Ceiling for F-Building Internal part Painting work. | 100 |  | 102393 | 2023-10-07 | 8675.75 | 1900-01-01 | -4460.15 | YUGESH KUMAR
2nd Coat OBD (L) | N/C | N/C | YUGESH KUMAR | 547 | 2022-10-01 | F-Bldg 1st Floor Wall Paint | 8377.528 | 1.25 | 0 | 10471.91 | 0 | 2024-04-13 | Labour charges for Applying 2nd Coat OBD Paint on wall for F-Building Internal part Painting work. | 100 |  | 106764 | 2024-04-15 | 26400.03 | 2024-04-30 15:24 | -15928.12 | BHARAT KASHINATH KARCHE
2nd Coat OBD (L) | N/C | N/C | YUGESH KUMAR | 547 | 2022-10-01 | F-Bldg 1st Floor Ceiling Paint | 4757.496 | 1.25 | 0 | 5946.87 | 0 | 2024-04-13 | Labour charges for Applying 2nd Coat OBD Paint on Ceiling for F-Building Internal part Painting work. | 100 |  | 106764 | 2024-04-15 | 26400.03 | 2024-04-30 15:24 | -20453.16 | BHARAT KASHINATH KARCHE
1st Coat OBD (L) | N/C | N/C | YUGESH KUMAR | 547 | 2022-10-01 | F-Bldg 1st Floor Ceiling Paint | 3966 | 1 | 0 | 3966 | 0 | 2024-04-10 | Labour charges for Applying 1st Coat OBD Paint on Ceiling for F-Building Internal part Painting work. | 100 |  | 106764 | 2024-04-15 | 26400.03 | 2024-04-30 15:24 | -22434.03 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 547 | 2022-10-01 | F-Bldg 1st Floor Wall Paint | 1047 | 0.75 | 0 | 785.25 | 0 | 2024-04-10 | Labour charges for Applying Water Base Primer on wall for F-Building Internal part Painting work. | 100 |  | 106764 | 2024-04-15 | 26400.03 | 2024-04-30 15:24 | -25614.78 | BHARAT KASHINATH KARCHE
1st Coat OBD (L) | N/C | N/C | YUGESH KUMAR | 547 | 2022-10-01 | F-Bldg 1st Floor Wall Paint | 5230 | 1 | 0 | 5230 | 0 | 2024-04-10 | Labour charges for Applying 1st Coat OBD Paint on wall for F-Building Internal part Painting work. | 100 |  | 106764 | 2024-04-15 | 26400.03 | 2024-04-30 15:24 | -21170.03 | BHARAT KASHINATH KARCHE
1st Coat OBD (L) | N/C | N/C | YUGESH KUMAR | 547 | 2022-10-01 | F-Bldg 1st Floor Wall Paint | 5235.955 | 1 | 0 | 5235.955 | 0 | 2024-04-07 | Labour charges for Applying 1st Coat OBD Paint on wall for F-Building Internal part Painting work. | 100 |  | 106643 | 2024-04-08 | 14284.5 | 2024-04-30 15:24 | -9048.545 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 547 | 2022-10-01 | F-Bldg 1st Floor Wall Paint | 9424.719 | 0.75 | 0 | 7068.5392 | 0 | 2024-04-07 | Labour charges for Applying Water Base Primer on wall for F-Building Internal part Painting work. | 100 |  | 106643 | 2024-04-08 | 14284.5 | 2024-04-30 15:24 | -7215.9608 | BHARAT KASHINATH KARCHE
1st Coat OBD (L) | N/C | N/C | YUGESH KUMAR | 547 | 2022-10-01 | F-Bldg 1st Floor Ceiling Paint | 1980 | 1 | 0 | 1980 | 0 | 2024-04-07 | Labour charges for Applying 1st Coat OBD Paint on Ceiling for F-Building Internal part Painting work. | 100 |  | 106643 | 2024-04-08 | 14284.5 | 2024-04-30 15:24 | -12304.5 | BHARAT KASHINATH KARCHE
Departmental Labour - SO | N/C | N/C | KANU KALIPADA BALA | 548 | 2022-10-01 | Demolition of Old Structure & Material shifting work | 25 | 500 | 0 | 12500 | 0 | 2024-07-17 | Departmental labour charges for-Demolition old structure material Shifting work in four stock rooms. | 100 |  | 109237 | 2024-07-22 | 22500 | 1900-01-01 | -10000 | PRAKASH SAHU
Departmental Labour - SO | N/C | N/C | KANU KALIPADA BALA | 548 | 2022-10-01 | Demolition of Old Structure & Material shifting work | 20 | 500 | 0 | 10000 | 0 | 2024-07-17 | Departmental labour charges for- Transformer room structure demolition sheet removing work. | 100 |  | 109237 | 2024-07-22 | 22500 | 1900-01-01 | -12500 | PRAKASH SAHU
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 552 | 2022-10-11 | Gypsum work for flat no. 104 | 1353 | 5 | 0 | 6765 | 0 | 2022-11-11 | Labour charges for Flat No. 104 Gypsum Punning work on wall. | 100 |  | 97025 | 2022-11-12 | 6765 | 2022-11-17 12:57 | 0 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 552 | 2022-10-11 | Gypsum work for flat no. 104 | 519.3 | 5 | 0 | 2596.5 | 0 | 2023-03-15 | Labour charges for Flat No. 104 Gypsum Punning work on Ceiling. | 100 |  | 98742 | 2023-03-16 | 2596.5 | 2023-03-29 11:17 | 0 | SHAHID RAJA KHAN
H-Frame (M+L) | N/C | N/C | R.T.S. STEEL SERVICES | 554 | 2022-10-12 | F-Bldg H-Frame Scaffolding Fabrication | 100 | 4200 | 0 | 420000 | 75600 | 2022-11-10 | Labour and Material supply charges for H- Frame Scaffolding with Gauge Medium 2.5mm thick including Blue Colour for F-Bldg External Plaster work. | 100 |  | 97003 | 2022-11-10 | 420000 | 2022-12-23 11:43 | 0 | R.T.S. STEEL SERVICES
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP-Top Slab Chemical W/P + Screeding work (L) | 427 | 22 | 0 | 9394 | 0 | 2023-09-25 | Material & Labour charges for Chemical Waterproofing work for STP Top Slab and Pump room top. | 100 |  | 103062 | 2023-10-30 | 9394 | 2023-10-30 10:57 | 0 | PRABHURAM VERMA
Membrane Horizontal Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP External Waterproofing Work | 593.26 | 13 | 0 | 7712.38 | 1388.22 | 2024-02-17 17:52 | Labour charges for STP Horizontal Waterproofing,Cleaning 120GSM fleeces as cushion on entire pcc area 250 GSM Rigidex-F Membrane over fleece just 300mm,make Rigidex-F Membrane joint waterproof,After joint treatment lay 120GSM Clothes to protect Rigidex-F. | 100 |  | 105402 | 2024-06-28 | 11090.98 | 2024-07-05 11:30 | -3378.6 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | Between D&E-Bldg Parking Ret Wall Ext.Waterproofing Work | 225.24 | 15 | 0 | 3378.6 | 608.14 | 2024-02-17 17:52 | Charges for Vertical Membrane W/P work for Retaining wall, remove all binding wire & nails from wall,cleaning,open all cold joint in V shape,honeycomb & Tie rod repairing treat by perma polycare+SBR Bond.Apply Neoproof RC 202+50 GSM coating. | 100 |  | 105402 | 2024-06-28 | 11090.98 | 2024-07-05 11:30 | -7712.38 | AQUARIUS WATERPROOFING
Cement Ghotai Plaster | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP-Int Chemical Waterproofing+Ghotai Plaster | 1888.784 | 15 | 0 | 28331.76 | 5099.72 | 2023-07-14 | Labour charges for Cement Ghotai Plaster work for STP- Internal RCC Pardi- Screen Chamber, O & G Tank, Equilization Tank, Anoxic Tank, aeration Tank, Tube Settler, Intermediates storage tank, Sludge Tank & Treated Water Storage Tank. | 100 |  | 100759 | 2023-07-19 | 62723.76 | 2023-07-29 10:56 | -34392 | GANGAPRASAD K VARMA
Cement Ghotai Plaster | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | F-Bldg ETP-Int Chemical Waterproofing+Ghotai Plaster | 1910.4 | 15 | 0 | 28656 | 5158.08 | 2023-07-14 | Labour charges for Cement Ghotai Plaster work for ETP-15 KLD Internal RCC Pardi-Screen Chamber, O & G Tank, Neutralization Tank,Collection cum settling tank, Aeration Tank,Tube Settler, Intermediates storage tank & Treated Water Storage tank. | 100 |  | 100759 | 2023-07-19 | 62723.76 | 2023-07-29 10:56 | -34067.76 | GANGAPRASAD K VARMA
Screeding W/P-BCo | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | F-Bldg ETP-Int Chemical Waterproofing+Ghotai Plaster | 382.4 | 15 | 0 | 5736 | 1032.48 | 2023-07-14 | Labour charges for Screeding work for ETP-15 KLD Internal RCC Pardi-Screen Chamber, O & G Tank, Neutralization Tank,Collection cum settling tank, Aeration Tank,Tube Settler, Intermediates storage tank & Treated Water Storage tank. | 100 |  | 100759 | 2023-07-19 | 62723.76 | 2023-07-29 10:56 | -56987.76 | GANGAPRASAD K VARMA
Screeding W/P-BCo | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP-Int Chemical Waterproofing+Ghotai Plaster | 302.4 | 15 | 0 | 4536 | 816.48 | 2023-07-14 | Labour charges for Screeding work for STP- Internal waterproofing Screen Chamber, O & G Tank, Equilization Tank, Anoxic Tank, aeration Tank, Tube Settler, Intermediates storage tank, Sludge Tank & Treated Water Storage Tank. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | GANGAPRASAD K VARMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP-Int Chemical Waterproofing+Ghotai Plaster | 2191.184 | 22 | 0 | 48206.048 | 8677.08 | 2023-07-14 | material & Labour charges for Chemical waterproofing work for STP- Internal RCC Pardi & Bottom for Screen Chamber,O & G Tank,Equilization Tank, Anoxic Tank, aeration Tank, Tube Settler, Intermediates storage tank, Sludge Tank & Treated Water Storage Tank. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | GANGAPRASAD K VARMA
Membrane Horizontal Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | Between D&E-Bldg Parking Ret Wall Ext.Waterproofing Work | 248 | 13 | 0 | 3224 | 580.32 | 2024-04-30 15:37 | Charges for Horizontal Membrane W/P on Retaining wall,Cleaning 120GSM fleeces as cushion on entire area 250 GSM Rigidex-F Membrane over fleece just 300mm,make Rigidex-F Membrane joint waterproof,After treatment lay 120GSM Clothes to protect Rigidex-F | 100 |  | 107371 | 2024-05-07 | 8702.9 | 2024-07-05 11:30 | -5478.9 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | Between D&E-Bldg Parking Ret Wall Ext.Waterproofing Work | 365.26 | 15 | 0 | 5478.9 | 986.2 | 2024-04-30 15:37 | Charges for Vertical Membrane W/P work for Retaining wall, remove all binding wire & nails from wall,cleaning,open all cold joint in V shape,honeycomb & Tie rod repairing treat by perma polycare+SBR Bond.Apply Neoproof RC 202+50 GSM coating. | 100 |  | 107371 | 2024-05-07 | 8702.9 | 2024-07-05 11:30 | -3224 | AQUARIUS WATERPROOFING
Chemical W/P-DLd | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | F-Bldg Top Slab Chemical W/P + Screeding Work | 135 | 22 | 0 | 2970 | 0 | 2023-10-09 11:50 | Material & Labour Charges for Chemical waterproofing work of ETP top Slab & Pumproom. | 100 |  | 102489 | 2023-10-11 | 9564 | 2023-11-03 15:40 | -6594 | PRABHURAM VERMA
Screeding W/P-BCo | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | F-Bldg Top Slab Chemical W/P + Screeding Work | 246 | 15 | 0 | 3690 | 0 | 2023-10-09 11:50 | Labour Charges for Screeding work of ETP top Slab & Pumproom top | 100 |  | 102489 | 2023-10-11 | 9564 | 2023-11-03 15:40 | -5874 | PRABHURAM VERMA
Screeding W/P-BCo | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP-Top Slab Chemical W/P + Screeding work (L) | 193.6 | 15 | 0 | 2904 | 0 | 2023-10-09 11:50 | Labour charges for Screeding work for STP Top Slab and Pump room top. | 100 |  | 102489 | 2023-10-11 | 9564 | 2023-11-03 15:40 | -6660 | PRABHURAM VERMA
Membrane Vertical Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP External Waterproofing Work | 726.4 | 15 | 0 | 10896 | 1961.28 | 2023-05-10 | Labour charges for STP Vertical RCC Retaining wall waterproofing work remove all binding wire & nails from wall,cleaning,open all cold joint in v shape,honeycomb & Tie rod repairing treat by perma polycare+SBR Bond. Apply Neoproof RC 202+50 GSM coating. | 100 |  | 99585 | 2023-05-11 | 24048 | 2023-06-28 11:56 | -13152 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | F-Bldg ETP Ext Waterproofing Work | 876.8 | 15 | 0 | 13152 | 2367.36 | 2023-05-10 | Labour charges for ETP Vertical RCC Retaining wall waterproofing work remove all binding wire & nails from wall,cleaning,open all cold joint in V shape,honeycomb & Tie rod repairing treat by perma polycare+SBR Bond.Apply Neoproof RC 202+50 GSM coating. | 100 |  | 99585 | 2023-05-11 | 24048 | 2023-06-28 11:56 | -10896 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 556 | 2022-10-13 | F-Bldg ETP Ext Waterproofing Work | 876.8 | 40 | 0 | 35072 | 6312.96 | 2023-05-10 | Material Supply for ETP-15 KLD Vertical RCC Pardi waterproofing treatment. | 100 |  | 99584 | 2023-05-11 | 64128 | 2023-06-28 11:58 | -29056 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 556 | 2022-10-13 | STP External Waterproofing Work | 726.4 | 40 | 0 | 29056 | 5230.08 | 2023-05-10 | Material Supply for STP Vertical RCC Pardi waterproofing treatment. | 100 |  | 99584 | 2023-05-11 | 64128 | 2023-06-28 11:58 | -35072 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 556 | 2022-10-13 | Between D&E-Bldg Parking Ret Wall Ext.Waterproofing Work | 590.55 | 40 | 0 | 23622 | 4251.96 | 2024-04-30 15:41 | Material supply for Membrane Vertical waterproofing treatment for Retaining wall between D & E front side. | 100 |  | 107372 | 2024-05-07 | 32055.02 | 2024-06-24 12:27 | -8433.02 | AQUARIUS WATERPROOFING
Membrane Horizontal Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 556 | 2022-10-13 | Between D&E-Bldg Parking Ret Wall Ext.Waterproofing Work | 248.03 | 34 | 0 | 8433.02 | 1517.94 | 2024-04-30 15:41 | Material supply for Membrane Horizontal waterproofing with Rigidex-F Membrane for Retaining wall between D & E front side. | 100 |  | 107372 | 2024-05-07 | 32055.02 | 2024-06-24 12:27 | -23622 | AQUARIUS WATERPROOFING
Event Sponsorship | N/C | N/C | KOTHARI ADVERTISING AGENCY | 557 | 2022-10-18 | BRANDING Branding | 1 | 200000 | 0 | 200000 | 10000 | 2023-01-09 | LOKSATTA DIWALI SANDHYA OCT. 2022 DTD. 20TH OCT. 2022 AT TILAK SMARAK MANDIR (ASSOCIATE PARTNER - LOGO & CREDIT IN THE ADS PROMOTING THE LOKSATTA DIWALI SANDHYA, 2) ASSOCIATE PARTNER MENTION IN THE EDITORIAL ARTICLES, 3) ASSOCIATES PARTNER LOGO/ CREDIT TH | 100 |  | 97709 | 2023-01-09 | 200000 | 2023-01-09 18:11 | 0 | KOTHARI ADVERTISING AGENCY
Total Statiotn Survey | N/C | N/C | VECTOR SURVEYORS | 558 | 2022-10-19 | Amenity Plot- Surveying Work by Total Station | 1 | 4500 | 0 | 4500 | 0 | 2022-11-12 | Charges for Total station survey work for amenity plot area. | 100 |  | 97039 | 2022-11-14 | 4500 | 2022-12-03 10:53 | 0 | VECTOR SURVEYORS
Total Statiotn Survey | N/C | N/C | VECTOR SURVEYORS | 559 | 2022-10-19 | UGWT- Surveying Work by total station | 1 | 4500 | 0 | 4500 | 0 | 2022-11-12 | Charges for D & E Building Survey point work for UGWT Fire tank , UGWT Pump room & UGWT Domestic tank. | 100 |  | 97040 | 2022-11-14 | 4500 | 2022-12-03 10:54 | 0 | VECTOR SURVEYORS
Total Statiotn Survey | N/C | N/C | VECTOR SURVEYORS | 559 | 2022-10-19 | Club House-Survey work by Total Station | 3 | 4500 | 0 | 13500 | 0 | 2024-02-18 12:31 | Charges for Club -house Surveying work by Total Station for Pile Cap Foundation & Plinth Foundation Pile cap work. | 100 |  | 105375 | 2024-02-19 | 13500 | 2024-03-23 12:17 | 0 | VECTOR SURVEYORS
Deep Cleaning work | N/C | N/C | MARSH HOUSEKEEPING SOLUTIONS | 560 | 2022-10-27 | F-Bldg 1st Floor Int Part Deep Cleaning Work | 4035.21 | 4 | 0 | 16140.84 | 0 | 2024-04-14 | Labour charges for Deep Cleaning work for F-Building 1st Floor (OPD + Rooms). | 100 |  | 106793 | 2024-04-15 | 16140.84 | 2024-04-30 15:24 | 0 | A R CLEANING SERVICS
Deep Cleaning work | N/C | N/C | MARSH HOUSEKEEPING SOLUTIONS | 560 | 2022-10-27 | F-Bldg 1st Floor Common Lobby Deep Cleaning Work | 2251.35 | 3 | 0 | 6754.05 | 0 | 2024-04-15 | Labour charges for Deep Cleaning work for F-Building Common Lobby Tile Flooring and Granite Flooring. | 100 |  | 106984 | 2024-04-22 | 7886.61 | 2024-07-26 12:21 | -1132.56 | A R CLEANING SERVICS
Deep Cleaning work | N/C | N/C | MARSH HOUSEKEEPING SOLUTIONS | 560 | 2022-10-27 | F-Bldg 1st Floor Int Part Deep Cleaning Work | 283.14 | 4 | 0 | 1132.56 | 0 | 2024-04-15 | Labour charges for Deep Cleaning work for F-Building all Toilets. | 100 |  | 106984 | 2024-04-22 | 7886.61 | 2024-07-26 12:21 | -6754.05 | A R CLEANING SERVICS
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.992 | 360 | 2024-01-24 | JUNE-2023 | 8.3333 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.988 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.992 | 360 | 2024-01-24 | JULY-2023 | 8.3333 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.988 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.992 | 360 | 2024-01-24 | AUG-2023 | 8.3333 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.988 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.992 | 360 | 2024-01-24 | SEP-2023 | 8.3333 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.988 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.992 | 360 | 2024-01-24 | OCT-2023 | 8.3333 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.988 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 2000.088 | 360.02 | 2024-01-24 | NOV-2023 | 8.3337 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.892 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
Stamping Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 20000 | 0 | 20000 | 3600 | 2024-01-24 | Stamping charges for the Year 2022-2023. | 100 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -23999.98 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.992 | 360 | 2024-01-24 | DEC-2022 | 8.3333 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.988 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.992 | 360 | 2024-01-24 | JAN-2023 | 8.3333 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.988 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.992 | 360 | 2024-01-24 | FEB-2023 | 8.3333 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.988 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.992 | 360 | 2024-01-24 | MAR-2023 | 8.3333 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.988 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.992 | 360 | 2024-01-24 | APR-2023 | 8.3333 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.988 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.992 | 360 | 2024-01-24 | MAY-2023 | 8.3333 |  | 104748 | 2024-01-24 | 43999.98 | 2024-01-24 12:29 | -41999.988 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
Load Cells (M+L) | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge New Load Cell Charges | 1 | 24500 | 0 | 24500 | 4410 | 2023-12-07 | Material Charges and Installation Charges of New Load Cells Cup Ball Type for Weighbridge | 100 | INvoice No-523 DT 07/09/2023 | 103799 | 2023-12-11 | 24500 | 1900-01-01 | 0 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
Stamping Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 20000 | 0 | 20000 | 3600 | 2024-01-24 | Stamping Charges for the year of 2023-2024 | 100 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -24000 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.92 | 359.98 | 2024-01-24 | JUNE 2024 | 8.333 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -42000.08 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.92 | 359.98 | 2024-01-24 | JULY 2024 | 8.333 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -42000.08 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.92 | 359.98 | 2024-01-24 | AUG 2024 | 8.333 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -42000.08 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.92 | 359.98 | 2024-01-24 | SEP 2024 | 8.333 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -42000.08 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.92 | 359.98 | 2024-01-24 | OCT 2024 | 8.333 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -42000.08 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 2000.88 | 360.16 | 2024-01-24 | NOV 2024 | 8.337 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -41999.12 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.92 | 359.98 | 2024-01-24 | DEC 2023 | 8.333 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -42000.08 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.92 | 359.98 | 2024-01-24 | JAN 2024 | 8.333 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -42000.08 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.92 | 359.98 | 2024-01-24 | FEB 2024 | 8.333 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -42000.08 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.92 | 359.98 | 2024-01-24 | MARCH 2024 | 8.333 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -42000.08 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.92 | 359.98 | 2024-01-24 | APRIL 2024 | 8.333 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -42000.08 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
AMC Charges | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 24000 | 0 | 1999.92 | 359.98 | 2024-01-24 | MAY 2024 | 8.333 |  | 107014 | 2024-04-22 | 44000 | 2024-05-21 18:46 | -42000.08 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
Miscellaneous Expenses | N/C | N/C | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | 566 | 2022-10-29 | Weigh Bridge AMC Charges + Stamping Charges | 1 | 2000 | 0 | 2000 | 360 | 2024-04-22 | Late Fees Charges for Stamping work. | 100 |  | 107015 | 2024-04-22 | 2000 | 2024-05-03 13:23 | 0 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2022-11-03 | APRIL 2022 | 8.3333 |  | 96908 | 2022-11-03 | 39999.84 | 2022-11-03 20:07 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2022-11-03 | MAY 2022 | 8.3333 |  | 96909 | 2022-11-03 | 39999.84 | 2022-11-03 20:07 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2022-11-03 | JUNE 2022 | 8.3333 |  | 96910 | 2022-11-03 | 39999.84 | 2022-11-03 20:07 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2022-11-03 | JULY 2022 | 8.3333 |  | 96911 | 2022-11-03 | 39999.84 | 2022-11-03 20:07 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2022-11-03 | AUGUST 2022 | 8.3333 |  | 96912 | 2022-11-03 | 39999.84 | 2022-11-03 20:07 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2022-11-03 | SEPT. 2022 | 8.3333 |  | 96913 | 2022-11-03 | 39999.84 | 2022-11-03 20:07 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2022-11-03 | OCT. 2022 | 8.3333 |  | 96914 | 2022-11-03 | 39999.84 | 2022-11-03 20:07 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-03-26 | FEB. 2023 | 8.3333 |  | 100003 | 2023-03-26 | 39999.84 | 2023-06-08 18:10 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-03-26 | DEC. 2022 | 8.3333 |  | 100004 | 2023-03-26 | 39999.84 | 2023-06-08 18:10 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-03-26 | JAN. 2023 | 8.3333 |  | 100005 | 2023-03-26 | 39999.84 | 2023-06-08 18:10 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 40001.76 | 7200.32 | 2023-03-26 | MARCH 2023 | 8.3337 |  | 100006 | 2023-03-26 | 40001.76 | 2023-06-08 18:10 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 567 | 2022-11-03 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-03-26 | NOV. 2022 | 8.3333 |  | 100007 | 2023-03-26 | 39999.84 | 2023-06-08 18:10 | 0 | GOOD OLD DELIGHT
Wet Mix Macadam (L) | N/C | N/C | AMAN ASSOCIATES | 568 | 2022-11-07 | F-Bldg Side Road Work -PQC Road | 1200.9785 | 5.11 | 0 | 6137.0001 | 1104.66 | 2023-11-02 | Labour Charges for Wet Mix Macadam of 150mm for Road work near F Building. | 100 |  | 103209 | 2023-11-02 | 45399 | 1900-01-01 | -39261.9999 | AMAN ASSOCIATES
GSB 1st Layer (L) | N/C | N/C | AMAN ASSOCIATES | 568 | 2022-11-07 | F-Bldg Side Road Work -PQC Road | 2761.0568 | 5.11 | 0 | 14109.0002 | 2539.62 | 2023-11-02 | Labour Charges for 1st Layer of Granular Sub base of 125mm for Road work near F Building. | 100 |  | 103209 | 2023-11-02 | 45399 | 1900-01-01 | -31289.9998 | AMAN ASSOCIATES
GSB 2nd Layer (L) | N/C | N/C | AMAN ASSOCIATES | 568 | 2022-11-07 | F-Bldg Side Road Work -PQC Road | 2761.0568 | 5.11 | 0 | 14109.0002 | 2539.62 | 2023-11-02 | Labour Charges for 2nd Layer of Granular Sub base of 125mm for Road work near F Building. | 100 |  | 103209 | 2023-11-02 | 45399 | 1900-01-01 | -31289.9998 | AMAN ASSOCIATES
Rolling,Compaction,Levelling | N/C | N/C | AMAN ASSOCIATES | 568 | 2022-11-07 | F-Bldg Side Road Work -PQC Road | 2761 | 4 | 0 | 11044 | 1987.92 | 2023-11-02 | Labour Charges for Rolling,Compaction and levelling work for road work near F Building. | 100 |  | 103209 | 2023-11-02 | 45399 | 1900-01-01 | -34355 | AMAN ASSOCIATES
Rate Difference | N/C | N/C | AMAN ASSOCIATES | 568 | 2022-11-07 | Kharadi DP Road Work Rate Difference | 1 | 2644988 | 0 | 2644988 | 476097.84 | 2022-11-07 | Charges for Rate Difference of Kharadi DP Road Work | 100 |  | 96956 | 2022-11-07 | 2644988 | 2022-11-08 13:02 | 0 | AMAN ASSOCIATES
Lift Scaffolding Work BC | N/C | N/C | UMESH M PATIL | 569 | 2022-11-08 | F-Bldg Lift Scaffolding Work | 1 | 11000 | 0 | 11000 | 0 | 2024-02-23 17:52 | Labour Charges for F-Bldg Stretcher Lift Scaffolding work. | 100 |  | 105558 | 2024-02-26 | 11000 | 2024-03-16 10:32 | 0 | UMESH M PATIL
Lift Scaffolding Work BC | N/C | N/C | UMESH M PATIL | 569 | 2022-11-08 | F-Bldg Lift Scaffolding Work | 1 | 11000 | 0 | 11000 | 0 | 2023-02-21 | Material and Labour charges for Lift scaffolding work including Khyata, Bamboo, Transport, loading, unloading, fixing, removing & Climbing pools fixing for F-Bldg Stretcher Lift- 01. | 100 |  | 98280 | 2023-02-21 | 22000 | 2023-02-28 14:32 | -11000 | UMESH M PATIL
Lift Scaffolding Work BC | N/C | N/C | UMESH M PATIL | 569 | 2022-11-08 | F-Bldg Lift Scaffolding Work | 1 | 11000 | 0 | 11000 | 0 | 2023-02-21 | Material and Labour charges for Lift scaffolding work including Khyata, Bamboo, Transport, loading, unloading, fixing, removing & Climbing pools fixing for F-Bldg Stretcher Lift- 02. | 100 |  | 98280 | 2023-02-21 | 22000 | 2023-02-28 14:32 | -11000 | UMESH M PATIL
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg LG.Fl Int side External Plaster Work | 256.914 | 25 | 0 | 6422.85 | 0 | 2023-06-19 | Labour charges for Single coat External Plaster work for LG Floor Columns. | 100 |  | 100214 | 2023-06-20 | 79094.45 | 2023-07-11 13:10 | -72671.6 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg LG.Fl Int side External Plaster Work | 3633.58 | 20 | 0 | 72671.6 | 0 | 2023-06-19 | Labour charges for Single coat External Plaster work for LG Floor Common Lobby Wall. | 100 |  | 100214 | 2023-06-20 | 79094.45 | 2023-07-11 13:10 | -6422.85 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg Southside External Plaster Work | 3313.7143 | 35 | 0 | 115980.0005 | 0 | 2023-05-13 | Labour charges for External wall Dabba Double Coat Plaster in cement, crush sand & Natural sand mortar with specified proportion & proper joint preparation between RCC (Column beam) & Blockwork using chiken mesh,nails & washer with line,level & Plumb etc. | 100 |  | 99649 | 2023-05-16 | 115980 | 2023-06-10 10:38 | 0.0005 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg Eastside External Plaster Work | 19.5 | 28 | 0 | 546 | 98.28 | 2023-09-20 | Labour charges for External wall Dabba Single Coat Plaster in cement, crush sand & Natural sand mortar with specified proportion & proper joint preparation between RCC (Column beam) & Blockwork using chiken mesh,nails & washer with line,level & Plumb etc. | 100 |  | 102007 | 2023-09-21 | 48831.35 | 2023-09-30 12:14 | -48285.35 | JAI SEVALAL CONSTRUCTION
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg LG.Fl Int side External Plaster Work | 45.32 | 25 | 0 | 1133 | 203.94 | 2023-09-20 | Labour charges for Single coat External Plaster work for LG Floor Columns. | 100 |  | 102007 | 2023-09-21 | 48831.35 | 2023-09-30 12:14 | -47698.35 | JAI SEVALAL CONSTRUCTION
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg Westside External Plaster Work | 1226.21 | 35 | 0 | 42917.35 | 7725.12 | 2023-09-20 | Labour charges for External wall Dabba Double Coat Plaster in cement, crush sand & Natural sand mortar with specified proportion & proper joint preparation between RCC (Column beam) & Blockwork using chiken mesh,nails & washer with line,level & Plumb etc. | 100 |  | 102007 | 2023-09-21 | 48831.35 | 2023-09-30 12:14 | -5914 | JAI SEVALAL CONSTRUCTION
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg Northside External Plaster Work | 151.25 | 28 | 0 | 4235 | 762.3 | 2023-09-20 | Labour charges for External wall Dabba Single Coat Plaster in cement, crush sand & Natural sand mortar with specified proportion & proper joint preparation between RCC (Column beam) & Blockwork using chiken mesh,nails & washer with line,level & Plumb etc. | 100 |  | 102007 | 2023-09-21 | 48831.35 | 2023-09-30 12:14 | -44596.35 | JAI SEVALAL CONSTRUCTION
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg Eastside External Plaster Work | 466.745 | 28 | 0 | 13068.86 | 2352.4 | 2024-02-12 | Labour charges for External wall Dabba Single Coat Plaster in cement, crush sand & Natural sand mortar with specified proportion & proper joint preparation between RCC (Column beam) & Blockwork using chiken mesh,nails & washer with line,level & Plumb etc. | 100 |  | 105290 | 2024-02-12 | 13068.86 | 2024-03-01 11:45 | 0 | JAI SEVALAL CONSTRUCTION
Rough Plaster | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | LG Toilet Internal Rough Coat (tar) Plaster | 385.479 | 20 | 0 | 7709.58 | 0 | 2023-03-18 | Labour charges for Tar Plaster work for F-Bldg LG Floor Common Toilet. | 100 |  | 98821 | 2023-03-20 | 18137.88 | 2023-03-30 12:49 | -10428.3 | K RAMU RATHOD
Rough Plaster | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | First Floor Toilet Internal Rough Coat (tar) Plaster | 521.415 | 20 | 0 | 10428.3 | 0 | 2023-03-18 | Labour charges for Tar Plaster work for F-Bldg First Floor Common Toilet. | 100 |  | 98821 | 2023-03-20 | 18137.88 | 2023-03-30 12:49 | -7709.58 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg Northside External Plaster Work | 3905 | 28 | 0 | 109340 | 0 | 2023-03-06 | Labour charges for External wall Dabba Single Coat Plaster in cement, crush sand & Natural sand mortar with specified proportion & proper joint preparation between RCC (Column beam) & Blockwork using chiken mesh,nails & washer with line,level & Plumb etc. | 100 |  | 98545 | 2023-03-08 | 109340 | 2023-03-24 11:22 | 0 | K RAMU RATHOD
Rough Plaster | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | First Floor Toilet Internal Rough Coat (tar) Plaster | 1637.41 | 20 | 0 | 32748.2 | 0 | 2023-01-18 | Labour charges for Tar Plaster work for F-Bldg First Floor Internal Part Toilet. | 100 |  | 97855 | 2023-01-19 | 32748.2 | 2023-01-31 10:24 | 0 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg Southside External Plaster Work | 2520 | 35 | 0 | 88200 | 0 | 2023-01-02 | Labour charges for External wall Dabba Double Coat Plaster in cement, crush sand & Natural sand mortar with specified proportion & proper joint preparation between RCC (Column beam) & Blockwork using chiken mesh,nails & washer with line,level & Plumb etc. | 100 |  | 97591 | 2023-01-03 | 88200 | 2023-01-23 18:38 | 0 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg Westside External Plaster Work | 2618.575 | 35 | 0 | 91650.125 | 0 | 2022-12-09 | Labour charges for External wall Dabba Double Coat Plaster in cement, crush sand & Natural sand mortar with specified proportion & proper joint preparation between RCC (Column beam) & Blockwork using chiken mesh,nails & washer with line,level & Plumb etc. | 100 |  | 97324 | 2022-12-10 | 145001.47 | 2022-12-23 11:28 | -53351.345 | K RAMU RATHOD
External Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 570 | 2022-11-08 | F-Bldg Eastside External Plaster Work | 1905.405 | 28 | 0 | 53351.34 | 0 | 2022-12-09 | Labour charges for External wall Dabba Single Coat Plaster in cement, crush sand & Natural sand mortar with specified proportion & proper joint preparation between RCC (Column beam) & Blockwork using chiken mesh,nails & washer with line,level & Plumb etc. | 100 |  | 97324 | 2022-12-10 | 145001.47 | 2022-12-23 11:28 | -91650.13 | K RAMU RATHOD
Lift AMC | N/C | N/C | PURVA ENTERPRISES | 573 | 2022-11-19 | Spartan Material lift- Annual Maintenance Work | 1 | 6000 | 0 | 6000 | 1080 | 2023-10-16 | Charges for Annal Maintenance of Spartan P/M Lift. | 100 | Lift AMC Dated On 24/08/2023 Report No-1859 | 102683 | 2023-10-17 | 6000 | 2023-12-22 11:34 | 0 | PURVA ENTERPRISES
Lift AMC | N/C | N/C | PURVA ENTERPRISES | 573 | 2022-11-19 | Spartan Material lift- Annual Maintenance Work | 1 | 6000 | 0 | 6000 | 1080 | 2023-06-15 | Charges for Annal Maintenance of Spartan P/M Lift. | 100 | For Spartan Lift Amc ( 31/05/2023)Report No- 1821 | 100178 | 2023-06-16 | 6000 | 1900-01-01 | 0 | PURVA ENTERPRISES
Lift AMC | N/C | N/C | PURVA ENTERPRISES | 573 | 2022-11-19 | Spartan Material lift- Annual Maintenance Work | 1 | 6000 | 0 | 6000 | 1080 | 2023-04-24 | Charges for Annal Maintenance of Spartan P/M Lift. | 100 | For Spartan Lift AMC (17/01/2023) Report No-1746 | 99283 | 2023-04-25 | 24000 | 2023-05-16 12:31 | -18000 | PURVA ENTERPRISES
Lift AMC | N/C | N/C | PURVA ENTERPRISES | 573 | 2022-11-19 | Spartan Material lift- Annual Maintenance Work | 1 | 6000 | 0 | 6000 | 1080 | 2023-04-24 | Charges for Annal Maintenance of Spartan P/M Lift. | 100 | For Spartan Lift AMC (06/04/2023) Report No-1689 | 99283 | 2023-04-25 | 24000 | 2023-05-16 12:31 | -18000 | PURVA ENTERPRISES
Lift AMC | N/C | N/C | PURVA ENTERPRISES | 573 | 2022-11-19 | Spartan Material lift- Annual Maintenance Work | 1 | 6000 | 0 | 6000 | 1080 | 2023-04-24 | Charges for Annal Maintenance of Spartan P/M Lift. | 100 | For Spartan Lift AMC (10/09/2022) Report No-1631 | 99283 | 2023-04-25 | 24000 | 2023-05-16 12:31 | -18000 | PURVA ENTERPRISES
Lift AMC | N/C | N/C | PURVA ENTERPRISES | 573 | 2022-11-19 | Spartan Material lift- Annual Maintenance Work | 1 | 6000 | 0 | 6000 | 1080 | 2023-04-24 | Charges for Annal Maintenance of Spartan P/M Lift. | 100 | For Spartan Lift AMC (05/12/2022) Report No-1715 | 99283 | 2023-04-25 | 24000 | 2023-05-16 12:31 | -18000 | PURVA ENTERPRISES
Removing Work DCH | N/C | N/C | PURVA ENTERPRISES | 573 | 2022-11-19 | Tower Crane D Bldg.-Tower Crane Hoisting Rope | 1 | 5000 | 0 | 5000 | 900 | 2024-03-01 | Charges for Tower Crane Hoisting rope Removing & Fitting work Total- 420 meter. | 100 | Report No-1858 | 107257 | 2024-05-02 | 5000 | 2024-05-06 12:05 | 0 | PURVA ENTERPRISES
Lumpsum work- DCW | N/C | N/C | VEDANT CONSTRUCTION | 574 | 2022-11-25 | STP - 265 KLD Slab Cutting work | 1 | 65000 | 0 | 65000 | 11700 | 2023-01-10 | Lumpsum Charges for - Slab Cutting work of STP 265 KLD | 100 |  | 97734 | 2023-01-10 | 65000 | 2023-01-23 18:47 | 0 | VEDANT CONSTRUCTION
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 11 | 900 | 0 | 9900 | 1782 | 2022-12-21 | Labour charges for Pile Drilling/ Boring work 500 mm dia. forTransformer Room. | 100 |  | 97475 | 2022-12-21 | 44900 | 2022-12-23 11:24 | -35000 | MASKE PILE FOUNDATION
Mobilisation - DEn | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 1 | 35000 | 0 | 35000 | 6300 | 2022-12-21 | Charges for one time Transportation including crane for Transformer Room. | 100 |  | 97475 | 2022-12-21 | 44900 | 2022-12-23 11:24 | -9900 | MASKE PILE FOUNDATION
Pile Concreting Work | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Near Well Pile Work-Near Well (L) - 1 No. | 27.88 | 100 | 0 | 2788 | 0 | 2023-06-22 | Labour Charges for Concreting of 600mm dia pile work for UGWT Pile near well. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -153449 | MASKE PILE FOUNDATION
Transport Charges | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Near Well Pile Work-Near Well (L) - 1 No. | 1 | 35000 | 0 | 35000 | 0 | 2023-06-22 | Transport Charges for 600mm Dia pile work for UGWT (Only one time transport Charges) | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -121237 | MASKE PILE FOUNDATION
Pile Concreting Work | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 12.25 | 100 | 0 | 1225 | 0 | 2023-06-22 | Labour charges for Pile Concreting work 500 mm dia. for Transformer Room. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -155012 | MASKE PILE FOUNDATION
Chiseling work for Piling - DEn | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Near Well Pile Work-Near Well (L) - 1 No. | 40 | 500 | 0 | 20000 | 0 | 2023-06-22 | Labour Charges for Chiseling work of 600mm dia pile for UGWT Pile near well. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -136237 | MASKE PILE FOUNDATION
Reinforcement for Piling-BC | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Near Well Pile Work-Near Well (L) - 1 No. | 71.64 | 100 | 0 | 7164 | 0 | 2023-06-22 | Labour Charges for Reinforcement of 600mm dia pile work for UGWT Pile near well. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -149073 | MASKE PILE FOUNDATION
Reinforcement for Piling-BC | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 57.97 | 100 | 0 | 5797 | 0 | 2023-06-22 | Labour charges for Reinforcement Cutting, Bending and Fixing for Piling work Transformer Room. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -150440 | MASKE PILE FOUNDATION
Piling work 600 mm. dia.(Machine Pile) | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Near Well Pile Work-Near Well (L) - 1 No. | 54.95 | 1000 | 0 | 54950 | 0 | 2023-06-22 | Charges for Drilling/Boring of 600mm Dia pile work for UGWT near well E Building podium | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -101287 | MASKE PILE FOUNDATION
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 32.57 | 900 | 0 | 29313 | 0 | 2023-06-22 | Labour charges for Pile Drilling/ Boring work 500 mm dia. forTransformer Room. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -126924 | MASKE PILE FOUNDATION
Reinforcement for Piling-BC | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 11.55 | 100 | 0 | 1155 | 207.9 | 2024-02-02 15:59 | Labour charges for Reinforcement Cutting,Bending & Fixing for Piling work Transformer Room. | 100 |  | 104926 | 2024-02-02 | 351973 | 2024-02-19 15:28 | -350818 | MASKE PILE FOUNDATION
Pile Concreting Work | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 57.2 | 100 | 0 | 5720 | 1029.6 | 2024-02-02 15:59 | Labour charges for Pile Concreting work 500 mm dia. for Transformer Room. | 100 |  | 104926 | 2024-02-02 | 351973 | 2024-02-19 15:28 | -346253 | MASKE PILE FOUNDATION
Mobilisation - DEn | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 2 | 35000 | 0 | 70000 | 12600 | 2024-02-02 15:59 | Charges for one time Transportation including crane for Transformer room. | 100 |  | 104926 | 2024-02-02 | 351973 | 2024-02-19 15:28 | -281973 | MASKE PILE FOUNDATION
Piling Work 500mm dia rate diff. | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 10 | 26079 | 0 | 260790 | 46942.2 | 2024-02-02 15:59 | Labour charges and Rate Diff. for pile Drilling / Boring work 500mm dia. for Transformer Room. | 100 |  | 104926 | 2024-02-02 | 351973 | 2024-02-19 15:28 | -91183 | MASKE PILE FOUNDATION
Chiseling work for Piling - DEn | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 35.77 | 400 | 0 | 14308 | 2575.44 | 2024-02-02 15:59 | Labour charges for Chiselling work for piling work for Transformer Room. | 100 |  | 104926 | 2024-02-02 | 351973 | 2024-02-19 15:28 | -337665 | MASKE PILE FOUNDATION
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-23rd Refuge Slab RCC Buit-Up Area | 3511.068 | 152 | 0 | 533682.336 | 96062.82 | 2023-10-16 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 102658 | 2023-10-16 | 533682.34 | 2023-10-23 12:32 | -0.004 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-23rd Refuge Slab RCC Buit-Up Area | 3511.068 | 152 | 0 | 533682.336 | 96062.82 | 2023-10-23 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 102919 | 2023-10-23 | 788334.22 | 2023-11-03 15:42 | -254651.884 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-14th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 145 | 0 | 63011.1275 | 11342 | 2023-10-23 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | 10 % against internal handingover | 102919 | 2023-10-23 | 788334.22 | 2023-11-03 15:42 | -725323.0925 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-14th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 145 | 0 | 63011.1275 | 11342 | 2023-10-23 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | 10 % against internal handingover | 102919 | 2023-10-23 | 788334.22 | 2023-11-03 15:42 | -725323.0925 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-15th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 148 | 0 | 64314.806 | 11576.66 | 2023-10-23 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | 10 % against internal handingover | 102919 | 2023-10-23 | 788334.22 | 2023-11-03 15:42 | -724019.414 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-15th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 148 | 0 | 64314.806 | 11576.66 | 2023-10-23 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | 10 % against internal handingover | 102919 | 2023-10-23 | 788334.22 | 2023-11-03 15:42 | -724019.414 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-16th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 148 | 0 | 64314.806 | 11576.66 | 2023-10-23 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | 10% released for internal handingover | 102924 | 2023-10-23 | 257259.24 | 2023-11-03 15:41 | -192944.434 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-16th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 148 | 0 | 64314.806 | 11576.66 | 2023-10-23 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | 10% released for internal handingover | 102924 | 2023-10-23 | 257259.24 | 2023-11-03 15:41 | -192944.434 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-17th Slab RCC Buit-Up Area | 434.5595 | 148 | 0 | 64314.806 | 11576.66 | 2023-10-23 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | 10% released for internal handingover | 102924 | 2023-10-23 | 257259.24 | 2023-11-03 15:41 | -192944.434 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-17th Slab RCC Buit-Up Area | 434.5595 | 148 | 0 | 64314.806 | 11576.66 | 2023-10-23 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | 10% released for internal handingover | 102924 | 2023-10-23 | 257259.24 | 2023-11-03 15:41 | -192944.434 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-24th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 152 | 0 | 528424.352 | 95116.38 | 2023-11-02 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 103202 | 2023-11-02 | 528424.35 | 2023-11-25 11:31 | 0.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-24th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 152 | 0 | 528424.352 | 95116.38 | 2023-11-03 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 103252 | 2023-11-04 | 528424.35 | 2023-11-23 11:40 | 0.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-18th Refuge Slab RCC Buit-Up Area | 438.8835 | 148 | 0 | 64954.758 | 11691.86 | 2023-11-10 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 103435 | 2023-11-11 | 258539.14 | 2023-11-22 11:29 | -193584.382 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-18th Refuge Slab RCC Buit-Up Area | 438.8835 | 148 | 0 | 64954.758 | 11691.86 | 2023-11-10 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 103435 | 2023-11-11 | 258539.14 | 2023-11-22 11:29 | -193584.382 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-19th Slab RCC Buit-Up Area | 434.5595 | 148 | 0 | 64314.806 | 11576.66 | 2023-11-10 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 103435 | 2023-11-11 | 258539.14 | 2023-11-22 11:29 | -194224.334 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-19th Slab RCC Buit-Up Area | 434.5595 | 148 | 0 | 64314.806 | 11576.66 | 2023-11-10 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 103435 | 2023-11-11 | 258539.14 | 2023-11-22 11:29 | -194224.334 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-25th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 152 | 0 | 528424.352 | 95116.38 | 2023-11-24 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 103493 | 2023-11-25 | 1056848.7 | 2023-12-11 14:12 | -528424.348 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-25th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 152 | 0 | 528424.352 | 95116.38 | 2023-11-24 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 103493 | 2023-11-25 | 1056848.7 | 2023-12-11 14:12 | -528424.348 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-17th Slab RCC Buit-Up Area | 3476.476 | 148 | 0 | 514518.448 | 92613.32 | 2023-07-15 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 100717 | 2023-07-17 | 514518.45 | 2023-07-26 11:42 | -0.002 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-15th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-07-27 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 100860 | 2023-07-27 | 86911.9 | 2023-08-09 12:18 | 0 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-17th Slab RCC Buit-Up Area | 3476.476 | 148 | 0 | 514518.448 | 92613.32 | 2023-07-25 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 100862 | 2023-07-27 | 514518.45 | 2023-08-09 12:18 | -0.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-9th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 15.48 | 145 | 0 | 2244.6 | 404.02 | 2023-07-25 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101141 | 2023-08-09 | 386883.2 | 2023-08-23 18:32 | -384638.6 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-11th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.55 | 145 | 0 | 63009.75 | 11341.76 | 2023-08-09 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101141 | 2023-08-09 | 386883.2 | 2023-08-23 18:32 | -323873.45 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-10th Slab RCC Buit-Up Area | 434.55 | 145 | 0 | 63009.75 | 11341.76 | 2023-07-25 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101141 | 2023-08-09 | 386883.2 | 2023-08-23 18:32 | -323873.45 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-10th Slab RCC Buit-Up Area | 434.55 | 145 | 0 | 63009.75 | 11341.76 | 2023-07-25 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101141 | 2023-08-09 | 386883.2 | 2023-08-23 18:32 | -323873.45 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-11th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.55 | 145 | 0 | 63009.75 | 11341.76 | 2023-08-09 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101141 | 2023-08-09 | 386883.2 | 2023-08-23 18:32 | -323873.45 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-9th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 914.48 | 145 | 0 | 132599.6 | 23867.92 | 2023-07-25 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101141 | 2023-08-09 | 386883.2 | 2023-08-23 18:32 | -254283.6 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-18th Refuge Slab RCC Buit-Up Area | 3511.068 | 148 | 0 | 519638.064 | 93534.86 | 2023-08-09 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101142 | 2023-08-09 | 519638.06 | 2023-08-14 14:33 | 0.004 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-16th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 148 | 0 | 514518.448 | 92613.32 | 2023-06-27 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 100300 | 2023-06-27 | 514518.45 | 2023-07-11 13:11 | -0.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-18th Refuge Slab RCC Buit-Up Area | 3511.068 | 148 | 0 | 519638.064 | 93534.86 | 2023-08-14 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101255 | 2023-08-14 | 519638.06 | 2023-08-23 18:31 | 0.004 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-19th Slab RCC Buit-Up Area | 3476.476 | 148 | 0 | 514518.448 | 92613.32 | 2023-08-28 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101501 | 2023-08-29 | 514518.45 | 2023-09-12 12:50 | -0.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-19th Slab RCC Buit-Up Area | 3476.476 | 148 | 0 | 514518.448 | 92613.32 | 2023-08-28 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101502 | 2023-08-29 | 514518.45 | 2023-09-12 12:47 | -0.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-26th Slab Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 152 | 0 | 66053.044 | 11889.54 | 2024-08-05 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 109614 | 2024-08-05 | 668832.46 | 1900-01-01 | -602779.416 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-27th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 156 | 0 | 67791.282 | 12202.44 | 2024-08-05 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 109614 | 2024-08-05 | 668832.46 | 1900-01-01 | -601041.178 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-25th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 152 | 0 | 66053.044 | 11889.54 | 2024-08-05 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 109614 | 2024-08-05 | 668832.46 | 1900-01-01 | -602779.416 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-24th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 152 | 0 | 66053.044 | 11889.54 | 2024-08-05 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 109614 | 2024-08-05 | 668832.46 | 1900-01-01 | -602779.416 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-24th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 152 | 0 | 66053.044 | 11889.54 | 2024-08-05 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 109614 | 2024-08-05 | 668832.46 | 1900-01-01 | -602779.416 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-26th Slab Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 152 | 0 | 66053.044 | 11889.54 | 2024-08-05 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 109614 | 2024-08-05 | 668832.46 | 1900-01-01 | -602779.416 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-28th Refuge Slab RCC Buit-Up Area | 438.8835 | 156 | 0 | 68465.826 | 12323.84 | 2024-08-05 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 109614 | 2024-08-05 | 668832.46 | 1900-01-01 | -600366.634 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-27th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 156 | 0 | 67791.282 | 12202.44 | 2024-08-05 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 109614 | 2024-08-05 | 668832.46 | 1900-01-01 | -601041.178 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-28th Refuge Slab RCC Buit-Up Area | 438.8835 | 156 | 0 | 68465.826 | 12323.84 | 2024-08-05 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 109614 | 2024-08-05 | 668832.46 | 1900-01-01 | -600366.634 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-25th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 152 | 0 | 66053.044 | 11889.54 | 2024-08-05 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 109614 | 2024-08-05 | 668832.46 | 1900-01-01 | -602779.416 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-29th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 156 | 0 | 542330.256 | 97619.44 | 2024-02-06 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 105218 | 2024-02-12 | 1084660.52 | 2024-03-02 12:03 | -542330.264 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-29th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 156 | 0 | 542330.256 | 97619.44 | 2024-02-06 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 105218 | 2024-02-12 | 1084660.52 | 2024-03-02 12:03 | -542330.264 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-28th Refuge Slab RCC Buit-Up Area | 3511.068 | 156 | 0 | 547726.608 | 98590.78 | 2024-01-15 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 104666 | 2024-01-22 | 1637783.48 | 2024-02-05 11:48 | -1090056.872 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-28th Refuge Slab RCC Buit-Up Area | 3511.068 | 156 | 0 | 547726.608 | 98590.78 | 2024-01-15 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 104666 | 2024-01-22 | 1637783.48 | 2024-02-05 11:48 | -1090056.872 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-27th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 156 | 0 | 542330.256 | 97619.44 | 2024-01-15 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 104666 | 2024-01-22 | 1637783.48 | 2024-02-05 11:48 | -1095453.224 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-26th Slab Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 152 | 0 | 528424.352 | 95116.38 | 2024-01-22 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 104754 | 2024-01-24 | 1056848.7 | 2024-01-31 15:46 | -528424.348 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-26th Slab Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 152 | 0 | 528424.352 | 95116.38 | 2024-01-22 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 104754 | 2024-01-24 | 1056848.7 | 2024-01-31 15:46 | -528424.348 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-21st Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 152 | 0 | 66053.044 | 11889.54 | 2024-01-01 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 104294 | 2024-01-01 | 1238490.26 | 2024-01-23 14:17 | -1172437.216 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-27th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 156 | 0 | 542330.256 | 97619.44 | 2024-01-01 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 104294 | 2024-01-01 | 1238490.26 | 2024-01-23 14:17 | -696160.004 | VINAYAKA ASSOCIATE
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-26th Slab Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2024-01-01 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 104294 | 2024-01-01 | 1238490.26 | 2024-01-23 14:17 | -1151578.36 | VINAYAKA ASSOCIATE
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-27th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2024-01-01 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 104294 | 2024-01-01 | 1238490.26 | 2024-01-23 14:17 | -1151578.36 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-21st Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 152 | 0 | 66053.044 | 11889.54 | 2024-01-01 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 104294 | 2024-01-01 | 1238490.26 | 2024-01-23 14:17 | -1172437.216 | VINAYAKA ASSOCIATE
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-24th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2024-01-01 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 104294 | 2024-01-01 | 1238490.26 | 2024-01-23 14:17 | -1151578.36 | VINAYAKA ASSOCIATE
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-25th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2024-01-01 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 104294 | 2024-01-01 | 1238490.26 | 2024-01-23 14:17 | -1151578.36 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-20th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 148 | 0 | 64314.806 | 11576.66 | 2024-01-01 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 104294 | 2024-01-01 | 1238490.26 | 2024-01-23 14:17 | -1174175.454 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-20th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 148 | 0 | 64314.806 | 11576.66 | 2024-01-01 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 104294 | 2024-01-01 | 1238490.26 | 2024-01-23 14:17 | -1174175.454 | VINAYAKA ASSOCIATE
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-23rd Refuge Slab RCC Buit-Up Area | 8777.67 | 10 | 0 | 87776.7 | 15799.8 | 2024-01-01 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 104294 | 2024-01-01 | 1238490.26 | 2024-01-23 14:17 | -1150713.56 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-31st Slab RCC Buit-Up Area - 8290.23 Sq.Ft | 3155.708 | 156 | 0 | 492290.448 | 88612.28 | 2024-04-28 15:27 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 107146 | 2024-04-29 | 1000725.06 | 2024-07-11 10:27 | -508434.612 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-31st Slab RCC Buit-Up Area - 8290.23 Sq.Ft | 3259.1962 | 156 | 0 | 508434.6072 | 91518.22 | 2024-04-28 15:42 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 107146 | 2024-04-29 | 1000725.06 | 2024-07-11 10:27 | -492290.4528 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-23rd Refuge Slab RCC Buit-Up Area | 438.8835 | 152 | 0 | 66710.292 | 12007.86 | 2024-03-04 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | Against Handingover | 105749 | 2024-03-04 | 807856.92 | 1900-01-01 | -741146.628 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-22nd Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 152 | 0 | 66053.044 | 11889.54 | 2024-03-04 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | Against Handingover | 105749 | 2024-03-04 | 807856.92 | 1900-01-01 | -741803.876 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-22nd Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 152 | 0 | 66053.044 | 11889.54 | 2024-03-04 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | Against Handingover | 105749 | 2024-03-04 | 807856.92 | 1900-01-01 | -741803.876 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-30th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 156 | 0 | 542330.256 | 97619.44 | 2024-03-04 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 105749 | 2024-03-04 | 807856.92 | 1900-01-01 | -265526.664 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-23rd Refuge Slab RCC Buit-Up Area | 438.8835 | 152 | 0 | 66710.292 | 12007.86 | 2024-03-04 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | Against Handingover | 105749 | 2024-03-04 | 807856.92 | 1900-01-01 | -741146.628 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-30th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 156 | 0 | 542330.256 | 97619.44 | 2024-03-16 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 106102 | 2024-03-18 | 717018.86 | 2024-03-23 12:17 | -174688.604 | VINAYAKA ASSOCIATE
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-28th Refuge Slab RCC Buit-Up Area | 8777.67 | 10 | 0 | 87776.7 | 15799.8 | 2024-03-16 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 106102 | 2024-03-18 | 717018.86 | 2024-03-23 12:17 | -629242.16 | VINAYAKA ASSOCIATE
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-29th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2024-03-16 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 106102 | 2024-03-18 | 717018.86 | 2024-03-23 12:17 | -630106.96 | VINAYAKA ASSOCIATE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-9th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 899 | 145 | 0 | 130355 | 23463.9 | 2023-02-14 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | For only shear wall reinforcement only (15Rs.) | 98194 | 2023-02-15 | 130355 | 2023-02-24 11:39 | 0 | HIGHRISE CONSTRUCTION COMPANY
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-20th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 148 | 0 | 514518.448 | 92613.32 | 2023-09-11 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101802 | 2023-09-11 | 514518.45 | 2023-09-20 12:02 | -0.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-20th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 148 | 0 | 514518.448 | 92613.32 | 2023-09-16 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101923 | 2023-09-18 | 514518.45 | 2023-09-30 11:24 | -0.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-12th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 145 | 0 | 63011.1275 | 11342 | 2023-09-18 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101942 | 2023-09-18 | 126649.24 | 2023-09-30 11:24 | -63638.1125 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-13th Refuge Slab RCC Buit-Up Area | 438.8835 | 145 | 0 | 63638.1075 | 11454.86 | 2023-09-18 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101942 | 2023-09-18 | 126649.24 | 2023-09-30 11:24 | -63011.1325 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-12th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 434.5595 | 145 | 0 | 63011.1275 | 11342 | 2023-09-20 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101988 | 2023-09-20 | 126649.24 | 2023-09-30 12:13 | -63638.1125 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-13th Refuge Slab RCC Buit-Up Area | 438.8835 | 145 | 0 | 63638.1075 | 11454.86 | 2023-09-20 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 101988 | 2023-09-20 | 126649.24 | 2023-09-30 12:13 | -63011.1325 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-21st Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 152 | 0 | 528424.352 | 95116.38 | 2023-09-26 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 102110 | 2023-09-27 | 1056848.7 | 2023-10-11 11:17 | -528424.348 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-21st Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 152 | 0 | 528424.352 | 95116.38 | 2023-09-26 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 102110 | 2023-09-27 | 1056848.7 | 2023-10-11 11:17 | -528424.348 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-22nd Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 152 | 0 | 528424.352 | 95116.38 | 2023-10-02 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 102165 | 2023-10-02 | 528424.35 | 2023-10-11 11:16 | 0.002 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-21st Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-10-02 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 102191 | 2023-10-03 | 609248.1 | 2023-10-11 11:18 | -522336.2 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-16th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-10-02 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 102191 | 2023-10-03 | 609248.1 | 2023-10-11 11:18 | -522336.2 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-18th Refuge Slab RCC Buit-Up Area | 8777.67 | 10 | 0 | 87776.7 | 15799.8 | 2023-10-02 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 102191 | 2023-10-03 | 609248.1 | 2023-10-11 11:18 | -521471.4 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-17th Slab RCC Buit-Up Area | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-10-02 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 102191 | 2023-10-03 | 609248.1 | 2023-10-11 11:18 | -522336.2 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-20th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-10-02 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 102191 | 2023-10-03 | 609248.1 | 2023-10-11 11:18 | -522336.2 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-19th Slab RCC Buit-Up Area | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-10-02 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 102191 | 2023-10-03 | 609248.1 | 2023-10-11 11:18 | -522336.2 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-22nd Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-10-02 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 102191 | 2023-10-03 | 609248.1 | 2023-10-11 11:18 | -522336.2 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-22nd Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 152 | 0 | 528424.352 | 95116.38 | 2023-10-10 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 102490 | 2023-10-11 | 528424.35 | 2023-10-23 12:32 | 0.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-16th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 80 | 148 | 0 | 11840 | 2131.2 | 2023-06-20 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | for Part 1 | 100215 | 2023-06-20 | 514518.45 | 2023-06-28 12:58 | -502678.45 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-14th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 145 | 0 | 504089.02 | 90736.02 | 2023-05-04 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 99426 | 2023-05-05 | 504089.02 | 2023-05-23 12:58 | 0 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-15th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 148 | 0 | 514518.448 | 92613.32 | 2023-05-17 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | 1st part 80% released | 99694 | 2023-05-18 | 514518.45 | 2023-06-08 18:07 | -0.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-15th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 148 | 0 | 514518.448 | 92613.32 | 2023-05-20 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | 2nd part 80% | 99737 | 2023-05-22 | 514518.45 | 2023-06-06 14:24 | -0.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-12th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 145 | 0 | 504089.02 | 90736.02 | 2023-03-10 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 98618 | 2023-03-11 | 504089.02 | 2023-03-29 11:36 | 0 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-16th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3396.476 | 148 | 0 | 502678.448 | 90482.12 | 2023-06-20 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | For part 1 | 100215 | 2023-06-20 | 514518.45 | 2023-06-28 12:58 | -11840.002 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-10th Slab RCC Buit-Up Area | 3476.476 | 145 | 0 | 504089.02 | 90736.02 | 2023-02-08 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 98103 | 2023-02-09 | 504089.02 | 2023-02-20 15:35 | 0 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-11th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 145 | 0 | 504089.02 | 90736.02 | 2023-02-14 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | for part -1 | 98193 | 2023-02-15 | 504089.02 | 2023-02-20 15:35 | 0 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-11th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 145 | 0 | 504089.02 | 90736.02 | 2023-02-27 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 98374 | 2023-02-27 | 504089.02 | 2023-03-14 18:59 | 0 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-13th Refuge Slab RCC Buit-Up Area | 3511.068 | 145 | 0 | 509104.86 | 91638.88 | 2023-04-12 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 99128 | 2023-04-12 | 509104.86 | 2023-04-13 12:05 | 0 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-14th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 145 | 0 | 504089.02 | 90736.02 | 2023-04-12 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 99130 | 2023-04-12 | 504089.02 | 2023-04-13 12:05 | 0 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-9th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-05-22 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 99748 | 2023-05-23 | 522336.2 | 2023-06-10 10:36 | -435424.3 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-10th Slab RCC Buit-Up Area | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-05-22 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 99748 | 2023-05-23 | 522336.2 | 2023-06-10 10:36 | -435424.3 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-12th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-05-22 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 99748 | 2023-05-23 | 522336.2 | 2023-06-10 10:36 | -435424.3 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-14th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-05-22 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 99748 | 2023-05-23 | 522336.2 | 2023-06-10 10:36 | -435424.3 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-13th Refuge Slab RCC Buit-Up Area | 8777.67 | 10 | 0 | 87776.7 | 15799.8 | 2023-05-22 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 99748 | 2023-05-23 | 522336.2 | 2023-06-10 10:36 | -434559.5 | KSHITEEJ ENTERPRISES
Schedule & Quality | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-11th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 8691.19 | 10 | 0 | 86911.9 | 15644.14 | 2023-05-22 | Scheduling and Quality for Aluform Shuttering,Reinforcement,Concreting for Slab,Beam,Staircase and Shear walls. | 100 |  | 99748 | 2023-05-23 | 522336.2 | 2023-06-10 10:36 | -435424.3 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-13th Refuge Slab RCC Buit-Up Area | 3511.068 | 145 | 0 | 509104.86 | 91638.88 | 2023-04-08 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 99052 | 2023-04-08 | 509104.86 | 2023-04-11 17:45 | 0 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-12th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 3476.476 | 145 | 0 | 504089.02 | 90736.02 | 2023-04-08 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 99053 | 2023-04-08 | 504089.02 | 2023-04-11 17:45 | 0 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-9th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 2996.5517 | 145 | 0 | 434499.9965 | 78210 | 2023-01-10 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 97750 | 2023-01-11 | 869000 | 2023-01-25 09:47 | -434500.0035 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-9th Slab RCC Buit-Up Area - 8691.19 Sq.Ft | 2996.5517 | 145 | 0 | 434499.9965 | 78210 | 2023-01-10 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 97750 | 2023-01-11 | 869000 | 2023-01-25 09:47 | -434500.0035 | KSHITEEJ ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KSHITEEJ ENTERPRISES | 576 | 2022-12-05 | E-Bldg-10th Slab RCC Buit-Up Area | 3476.476 | 145 | 0 | 504089.02 | 90736.02 | 2023-01-24 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 97928 | 2023-01-25 | 504089.02 | 2023-02-08 12:26 | 0 | KSHITEEJ ENTERPRISES
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 10th Floor Eastside Acrylic Texture Paint | 98.546 | 7.5 | 0 | 739.095 | 0 | 2024-01-05 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 104358 | 2024-01-08 | 3048.07 | 2024-03-23 12:23 | -2308.975 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 10th Floor Southside Acrylic Texture Paint | 53.3 | 7.5 | 0 | 399.75 | 0 | 2024-01-05 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 104358 | 2024-01-08 | 3048.07 | 2024-03-23 12:23 | -2648.32 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 11th Floor Westside Acrylic Texture Paint | 50.89 | 7.5 | 0 | 381.675 | 0 | 2024-01-05 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 104358 | 2024-01-08 | 3048.07 | 2024-03-23 12:23 | -2666.395 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 11th Floor Eastside Acrylic Texture Paint | 47.65 | 7.5 | 0 | 357.375 | 0 | 2024-01-05 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 104358 | 2024-01-08 | 3048.07 | 2024-03-23 12:23 | -2690.695 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 10th Floor Northside Acrylic Texture Paint | 53.3 | 7.5 | 0 | 399.75 | 0 | 2024-01-05 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 104358 | 2024-01-08 | 3048.07 | 2024-03-23 12:23 | -2648.32 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 10th Floor Westside Acrylic Texture Paint | 50.59 | 7.5 | 0 | 379.425 | 0 | 2024-01-05 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 104358 | 2024-01-08 | 3048.07 | 2024-03-23 12:23 | -2668.645 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 12th Floor Southside Acrylic Texture Paint | 52.13 | 7.5 | 0 | 390.975 | 0 | 2024-01-05 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 104358 | 2024-01-08 | 3048.07 | 2024-03-23 12:23 | -2657.095 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 7th Floor Southside Acrylic Texture Paint | 21.6 | 7.5 | 0 | 162 | 29.16 | 2024-01-04 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35931.65 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Eastside Acrylic Texture Paint | 174.89 | 7.5 | 0 | 1311.675 | 236.1 | 2024-01-04 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34781.975 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 8th Floor Westside Acrylic Texture Paint | 148.62 | 7.5 | 0 | 1114.65 | 200.64 | 2024-01-04 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34979 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 9th Floor Northside Acrylic Texture Paint | 91.32 | 7.5 | 0 | 684.9 | 123.28 | 2024-01-04 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35408.75 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Northside Acrylic Texture Paint | 162.31 | 7.5 | 0 | 1217.325 | 219.12 | 2024-01-04 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34876.325 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 1st Floor Southside Acrylic Texture Paint | 31.67 | 7.5 | 0 | 237.525 | 42.76 | 2024-01-04 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35856.125 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 8th Floor Southside Acrylic Texture Paint | 140.57 | 7.5 | 0 | 1054.275 | 189.78 | 2024-01-04 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35039.375 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Eastside Acrylic Texture Paint | 174.89 | 7.5 | 0 | 1311.675 | 236.1 | 2024-01-04 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34781.975 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Southside Acrylic Texture Paint | 148.92 | 7.5 | 0 | 1116.9 | 201.04 | 2024-01-04 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34976.75 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Northside Acrylic Texture Paint | 155.86 | 7.5 | 0 | 1168.95 | 210.42 | 2024-01-04 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34924.7 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 9th Floor Southside Acrylic Texture Paint | 143.45 | 7.5 | 0 | 1075.875 | 193.66 | 2024-01-04 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35017.775 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Southside Acrylic Texture Paint | 148.92 | 7.5 | 0 | 1116.9 | 201.04 | 2024-01-04 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34976.75 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Westside Acrylic Texture Paint | 163.05 | 7.5 | 0 | 1222.875 | 220.12 | 2024-01-04 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34870.775 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Northside Acrylic Texture Paint | 205.96 | 7.5 | 0 | 1544.7 | 278.04 | 2024-01-04 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34548.95 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Eastside Acrylic Texture Paint | 174.89 | 7.5 | 0 | 1311.675 | 236.1 | 2024-01-04 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34781.975 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Southside Acrylic Texture Paint | 146.88 | 7.5 | 0 | 1101.6 | 198.28 | 2024-01-04 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34992.05 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 7th Floor Northside Acrylic Texture Paint | 95.21 | 7.5 | 0 | 714.075 | 128.54 | 2024-01-04 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35379.575 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Southside Acrylic Texture Paint | 90.23 | 7.5 | 0 | 676.725 | 121.82 | 2024-01-04 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35416.925 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Westside Acrylic Texture Paint | 163.05 | 7.5 | 0 | 1222.875 | 220.12 | 2024-01-04 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34870.775 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 7th Floor Westside Acrylic Texture Paint | 47.81 | 7.5 | 0 | 358.575 | 64.54 | 2024-01-04 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35735.075 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 9th Floor Westside Acrylic Texture Paint | 143.2 | 7.5 | 0 | 1074 | 193.32 | 2024-01-04 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35019.65 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Westside Acrylic Texture Paint | 133.058 | 7.5 | 0 | 997.935 | 179.62 | 2024-01-04 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35095.715 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 7th Floor Eastside Acrylic Texture Paint | 50.85 | 7.5 | 0 | 381.375 | 68.64 | 2024-01-04 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35712.275 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 1st Floor Westside Acrylic Texture Paint | 96.86 | 7.5 | 0 | 726.45 | 130.76 | 2024-01-04 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35367.2 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Northside Acrylic Texture Paint | 205.97 | 7.5 | 0 | 1544.775 | 278.06 | 2024-01-04 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34548.875 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 8th Floor Eastside Acrylic Texture Paint | 70.91 | 7.5 | 0 | 531.825 | 95.72 | 2024-01-04 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35561.825 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 9th Floor Eastside Acrylic Texture Paint | 70.91 | 7.5 | 0 | 531.825 | 95.72 | 2024-01-04 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35561.825 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Northside Acrylic Texture Paint | 150.28 | 7.5 | 0 | 1127.1 | 202.88 | 2024-01-04 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34966.55 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Eastside Acrylic Texture Paint | 154.84 | 7.5 | 0 | 1161.3 | 209.04 | 2024-01-04 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34932.35 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Southside Acrylic Texture Paint | 148.92 | 7.5 | 0 | 1116.9 | 201.04 | 2024-01-04 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34976.75 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 1st Floor Northside Acrylic Texture Paint | 181.45 | 7.5 | 0 | 1360.875 | 244.96 | 2024-01-04 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34732.775 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 1st Floor Eastside Acrylic Texture Paint | 174.89 | 7.5 | 0 | 1311.675 | 236.1 | 2024-01-04 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34781.975 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Westside Acrylic Texture Paint | 163.05 | 7.5 | 0 | 1222.875 | 220.12 | 2024-01-04 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34870.775 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Eastside Acrylic Texture Paint | 174.89 | 7.5 | 0 | 1311.675 | 236.1 | 2024-01-04 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34781.975 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 8th Floor Northside Acrylic Texture Paint | 99.064 | 7.5 | 0 | 742.98 | 133.74 | 2024-01-04 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -35350.67 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Westside Acrylic Texture Paint | 163.23 | 7.5 | 0 | 1224.225 | 220.36 | 2024-01-04 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 104357 | 2024-01-08 | 36093.65 | 2024-02-02 14:25 | -34869.425 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 1st Floor Southside Acrylic Texture Paint | 126 | 7.5 | 0 | 945 | 170.1 | 2023-06-21 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -77030.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Eastside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 9th Floor Southside Acrylic Texture Paint | 417.07 | 7.5 | 0 | 3128.025 | 563.04 | 2023-06-21 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -74847.805 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Northside Acrylic Texture Paint | 417.07 | 7.5 | 0 | 3128.025 | 563.04 | 2023-06-21 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -74847.805 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 9th Floor Westside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Southside Acrylic Texture Paint | 208 | 7.5 | 0 | 1560 | 280.8 | 2023-06-21 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -76415.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Eastside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Southside Acrylic Texture Paint | 417.07 | 7.5 | 0 | 3128.025 | 563.04 | 2023-06-21 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -74847.805 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Northside Acrylic Texture Paint | 417.07 | 7.5 | 0 | 3128.025 | 563.04 | 2023-06-21 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -74847.805 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 8th Floor Southside Acrylic Texture Paint | 417.07 | 7.5 | 0 | 3128.025 | 563.04 | 2023-06-21 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -74847.805 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Eastside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Southside Acrylic Texture Paint | 417.07 | 7.5 | 0 | 3128.025 | 563.04 | 2023-06-21 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -74847.805 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Westside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Southside Acrylic Texture Paint | 417.07 | 7.5 | 0 | 3128.025 | 563.04 | 2023-06-21 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -74847.805 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Westside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 1st Floor Northside Acrylic Texture Paint | 335.07 | 7.5 | 0 | 2513.025 | 452.34 | 2023-06-21 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75462.805 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Northside Acrylic Texture Paint | 417 | 7.5 | 0 | 3127.5 | 562.96 | 2023-06-21 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -74848.33 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Eastside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Westside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Northside Acrylic Texture Paint | 335.07 | 7.5 | 0 | 2513.025 | 452.34 | 2023-06-21 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75462.805 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 1st Floor Westside Acrylic Texture Paint | 100 | 7.5 | 0 | 750 | 135 | 2023-06-21 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -77225.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Westside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Westside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Northside Acrylic Texture Paint | 417.07 | 7.5 | 0 | 3128.025 | 563.04 | 2023-06-21 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -74847.805 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Eastside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Southside Acrylic Texture Paint | 417.07 | 7.5 | 0 | 3128.025 | 563.04 | 2023-06-21 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -74847.805 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 1st Floor Eastside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 8th Floor Westside Acrylic Texture Paint | 394 | 7.5 | 0 | 2955 | 531.9 | 2023-06-21 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100232 | 2023-06-21 | 77975.83 | 2023-06-28 12:02 | -75020.83 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 8th Floor Westside Acrylic Texture Paint | 200 | 7.5 | 0 | 1500 | 270 | 2023-06-22 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66156.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 1st Floor Eastside Acrylic Texture Paint | 305.07 | 7.5 | 0 | 2288.025 | 411.84 | 2023-06-22 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65368.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Westside Acrylic Texture Paint | 258 | 7.5 | 0 | 1935 | 348.3 | 2023-06-22 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65721.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Westside Acrylic Texture Paint | 138 | 7.5 | 0 | 1035 | 186.3 | 2023-06-22 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66621.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 7th Floor Eastside Acrylic Texture Paint | 203.07 | 7.5 | 0 | 1523.025 | 274.14 | 2023-06-22 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66133.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Northside Acrylic Texture Paint | 393.07 | 7.5 | 0 | 2948.025 | 530.64 | 2023-06-22 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -64708.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Northside Acrylic Texture Paint | 406 | 7.5 | 0 | 3045 | 548.1 | 2023-06-22 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -64611.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Eastside Acrylic Texture Paint | 305.07 | 7.5 | 0 | 2288.025 | 411.84 | 2023-06-22 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65368.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Southside Acrylic Texture Paint | 178 | 7.5 | 0 | 1335 | 240.3 | 2023-06-22 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66321.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 7th Floor Northside Acrylic Texture Paint | 380 | 7.5 | 0 | 2850 | 513 | 2023-06-22 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -64806.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 1st Floor Northside Acrylic Texture Paint | 390 | 7.5 | 0 | 2925 | 526.5 | 2023-06-22 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -64731.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Northside Acrylic Texture Paint | 406 | 7.5 | 0 | 3045 | 548.1 | 2023-06-22 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -64611.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 9th Floor Eastside Acrylic Texture Paint | 283.07 | 7.5 | 0 | 2123.025 | 382.14 | 2023-06-22 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65533.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 8th Floor Eastside Acrylic Texture Paint | 283.07 | 7.5 | 0 | 2123.025 | 382.14 | 2023-06-22 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65533.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Northside Acrylic Texture Paint | 265.07 | 7.5 | 0 | 1988.025 | 357.84 | 2023-06-22 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65668.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Westside Acrylic Texture Paint | 258 | 7.5 | 0 | 1935 | 348.3 | 2023-06-22 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65721.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Eastside Acrylic Texture Paint | 305.07 | 7.5 | 0 | 2288.025 | 411.84 | 2023-06-22 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65368.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 8th Floor Northside Acrylic Texture Paint | 396 | 7.5 | 0 | 2970 | 534.6 | 2023-06-22 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -64686.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 1st Floor Westside Acrylic Texture Paint | 286 | 7.5 | 0 | 2145 | 386.1 | 2023-06-22 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65511.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 7th Floor Southside Acrylic Texture Paint | 86 | 7.5 | 0 | 645 | 116.1 | 2023-06-22 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -67011.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Southside Acrylic Texture Paint | 170 | 7.5 | 0 | 1275 | 229.5 | 2023-06-22 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66381.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Westside Acrylic Texture Paint | 258 | 7.5 | 0 | 1935 | 348.3 | 2023-06-22 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65721.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Eastside Acrylic Texture Paint | 225.07 | 7.5 | 0 | 1688.025 | 303.84 | 2023-06-22 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65968.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Southside Acrylic Texture Paint | 178 | 7.5 | 0 | 1335 | 240.3 | 2023-06-22 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66321.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 2nd Floor Southside Acrylic Texture Paint | 152 | 7.5 | 0 | 1140 | 205.2 | 2023-06-22 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66516.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 6th Floor Westside Acrylic Texture Paint | 258 | 7.5 | 0 | 1935 | 348.3 | 2023-06-22 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65721.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 8th Floor Southside Acrylic Texture Paint | 145 | 7.5 | 0 | 1087.5 | 195.76 | 2023-06-22 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66569.39 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Eastside Acrylic Texture Paint | 305.07 | 7.5 | 0 | 2288.025 | 411.84 | 2023-06-22 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65368.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 5th Floor Southside Acrylic Texture Paint | 178 | 7.5 | 0 | 1335 | 240.3 | 2023-06-22 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66321.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 3rd Floor Eastside Acrylic Texture Paint | 305.07 | 7.5 | 0 | 2288.025 | 411.84 | 2023-06-22 | Material Supply Charges for External Texture Painting work for East Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65368.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 7th Floor Westside Acrylic Texture Paint | 191.07 | 7.5 | 0 | 1433.025 | 257.94 | 2023-06-22 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66223.865 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 9th Floor Westside Acrylic Texture Paint | 178 | 7.5 | 0 | 1335 | 240.3 | 2023-06-22 | Material Supply Charges for External Texture Painting work for West Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66321.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 4th Floor Northside Acrylic Texture Paint | 232 | 7.5 | 0 | 1740 | 313.2 | 2023-06-22 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -65916.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 9th Floor Southside Acrylic Texture Paint | 156 | 7.5 | 0 | 1170 | 210.6 | 2023-06-22 | Material Supply Charges for External Texture Painting work for South Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -66486.89 | MANSI ENTERPRISES.
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 577 | 2022-12-05 | D-Bldg 9th Floor Northside Acrylic Texture Paint | 365.07 | 7.5 | 0 | 2738.025 | 492.84 | 2023-06-22 | Material Supply Charges for External Texture Painting work for North Side D-Bldg. | 100 |  | 100233 | 2023-06-22 | 67656.89 | 2023-06-28 12:02 | -64918.865 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Eastside Acrylic Texture Paint | 304.97 | 7.25 | 0 | 2211.0325 | 397.98 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63190.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 7th Floor Northside Acrylic Texture Paint | 380 | 7.25 | 0 | 2755 | 495.9 | 2023-06-19 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -62646.33 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 9th Floor Southside Acrylic Texture Paint | 156 | 7.25 | 0 | 1131 | 203.58 | 2023-06-19 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -64270.33 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Eastside Acrylic Texture Paint | 304.97 | 7.25 | 0 | 2211.0325 | 397.98 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63190.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Northside Acrylic Texture Paint | 406.07 | 7.25 | 0 | 2944.0075 | 529.92 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -62457.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Southside Acrylic Texture Paint | 178.07 | 7.25 | 0 | 1291.0075 | 232.38 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -64110.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Southside Acrylic Texture Paint | 170.07 | 7.25 | 0 | 1233.0075 | 221.94 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -64168.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 9th Floor Westside Acrylic Texture Paint | 178.07 | 7.25 | 0 | 1291.0075 | 232.38 | 2023-06-22 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -64110.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 7th Floor Eastside Acrylic Texture Paint | 203.03 | 7.25 | 0 | 1471.9675 | 264.96 | 2023-06-19 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63929.3625 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Northside Acrylic Texture Paint | 406.07 | 7.25 | 0 | 2944.0075 | 529.92 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -62457.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 8th Floor Northside Acrylic Texture Paint | 396 | 7.25 | 0 | 2871 | 516.78 | 2023-06-19 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -62530.33 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 8th Floor Southside Acrylic Texture Paint | 144.97 | 7.25 | 0 | 1051.0325 | 189.18 | 2023-06-19 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -64350.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 1st Floor Northside Acrylic Texture Paint | 390.07 | 7.25 | 0 | 2828.0075 | 509.04 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -62573.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Westside Acrylic Texture Paint | 258.07 | 7.25 | 0 | 1871.0075 | 336.78 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63530.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 9th Floor Northside Acrylic Texture Paint | 364.97 | 7.25 | 0 | 2646.0325 | 476.28 | 2023-06-19 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -62755.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Westside Acrylic Texture Paint | 258.07 | 7.25 | 0 | 1871.0075 | 336.78 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63530.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 8th Floor Westside Acrylic Texture Paint | 200 | 7.25 | 0 | 1450 | 261 | 2023-06-19 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63951.33 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Westside Acrylic Texture Paint | 258.07 | 7.25 | 0 | 1871.0075 | 336.78 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63530.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 1st Floor Eastside Acrylic Texture Paint | 304.97 | 7.25 | 0 | 2211.0325 | 397.98 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63190.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 1st Floor Westside Acrylic Texture Paint | 286.07 | 7.25 | 0 | 2074.0075 | 373.32 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63327.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Northside Acrylic Texture Paint | 232 | 7.25 | 0 | 1682 | 302.76 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63719.33 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Northside Acrylic Texture Paint | 392.97 | 7.25 | 0 | 2849.0325 | 512.82 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -62552.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 8th Floor Eastside Acrylic Texture Paint | 283.03 | 7.25 | 0 | 2051.9675 | 369.36 | 2023-06-19 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63349.3625 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Westside Acrylic Texture Paint | 258.07 | 7.25 | 0 | 1871.0075 | 336.78 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63530.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Eastside Acrylic Texture Paint | 224.97 | 7.25 | 0 | 1631.0325 | 293.58 | 2023-06-22 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63770.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 9th Floor Eastside Acrylic Texture Paint | 283.03 | 7.25 | 0 | 2051.9675 | 369.36 | 2023-06-19 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63349.3625 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 7th Floor Southside Acrylic Texture Paint | 86.07 | 7.25 | 0 | 624.0075 | 112.32 | 2023-06-19 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -64777.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 7th Floor Westside Acrylic Texture Paint | 191.03 | 7.25 | 0 | 1384.9675 | 249.3 | 2023-06-19 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -64016.3625 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Southside Acrylic Texture Paint | 152 | 7.25 | 0 | 1102 | 198.36 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -64299.33 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Westside Acrylic Texture Paint | 138.07 | 7.25 | 0 | 1001.0075 | 180.18 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -64400.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Southside Acrylic Texture Paint | 178.07 | 7.25 | 0 | 1291.0075 | 232.38 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -64110.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Southside Acrylic Texture Paint | 178.07 | 7.25 | 0 | 1291.0075 | 232.38 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -64110.3225 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Eastside Acrylic Texture Paint | 304.97 | 7.25 | 0 | 2211.0325 | 397.98 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63190.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Eastside Acrylic Texture Paint | 304.97 | 7.25 | 0 | 2211.0325 | 397.98 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63190.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Northside Acrylic Texture Paint | 264.97 | 7.25 | 0 | 1921.0325 | 345.78 | 2023-06-20 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100238 | 2023-06-22 | 65401.33 | 2023-06-28 12:01 | -63480.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Westside Acrylic Texture Paint | 133.058 | 7.25 | 0 | 964.6705 | 173.64 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33925.7395 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 7th Floor Eastside Acrylic Texture Paint | 50.85 | 7.25 | 0 | 368.6625 | 66.36 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -34521.7475 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 9th Floor Westside Acrylic Texture Paint | 143.2 | 7.25 | 0 | 1038.2 | 186.88 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33852.21 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Southside Acrylic Texture Paint | 148.92 | 7.25 | 0 | 1079.67 | 194.34 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33810.74 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Northside Acrylic Texture Paint | 162.31 | 7.25 | 0 | 1176.7475 | 211.82 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33713.6625 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Northside Acrylic Texture Paint | 155.86 | 7.25 | 0 | 1129.985 | 203.4 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33760.425 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 7th Floor Southside Acrylic Texture Paint | 21.6 | 7.25 | 0 | 156.6 | 28.18 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -34733.81 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 7th Floor Westside Acrylic Texture Paint | 47.81 | 7.25 | 0 | 346.6225 | 62.4 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -34543.7875 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 9th Floor Eastside Acrylic Texture Paint | 70.91 | 7.25 | 0 | 514.0975 | 92.54 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -34376.3125 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Westside Acrylic Texture Paint | 163.05 | 7.25 | 0 | 1182.1125 | 212.78 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33708.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Eastside Acrylic Texture Paint | 174.89 | 7.25 | 0 | 1267.9525 | 228.24 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33622.4575 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Northside Acrylic Texture Paint | 150.28 | 7.25 | 0 | 1089.53 | 196.12 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33800.88 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Northside Acrylic Texture Paint | 205.96 | 7.25 | 0 | 1493.21 | 268.78 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33397.2 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Westside Acrylic Texture Paint | 163.23 | 7.25 | 0 | 1183.4175 | 213.02 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33706.9925 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Northside Acrylic Texture Paint | 205.97 | 7.25 | 0 | 1493.2825 | 268.8 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33397.1275 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 7th Floor Northside Acrylic Texture Paint | 95.21 | 7.25 | 0 | 690.2725 | 124.24 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -34200.1375 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 9th Floor Southside Acrylic Texture Paint | 143.45 | 7.25 | 0 | 1040.0125 | 187.2 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33850.3975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Eastside Acrylic Texture Paint | 174.89 | 7.25 | 0 | 1267.9525 | 228.24 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33622.4575 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Eastside Acrylic Texture Paint | 174.89 | 7.25 | 0 | 1267.9525 | 228.24 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33622.4575 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 8th Floor Northside Acrylic Texture Paint | 99.064 | 7.25 | 0 | 718.214 | 129.28 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -34172.196 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 8th Floor Southside Acrylic Texture Paint | 140.57 | 7.25 | 0 | 1019.1325 | 183.44 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33871.2775 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 1st Floor Northside Acrylic Texture Paint | 181.45 | 7.25 | 0 | 1315.5125 | 236.8 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33574.8975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Westside Acrylic Texture Paint | 163.05 | 7.25 | 0 | 1182.1125 | 212.78 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33708.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Eastside Acrylic Texture Paint | 174.89 | 7.25 | 0 | 1267.9525 | 228.24 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33622.4575 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Southside Acrylic Texture Paint | 416.97 | 7.25 | 0 | 3023.0325 | 544.14 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72353.3475 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Eastside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Southside Acrylic Texture Paint | 416.97 | 7.25 | 0 | 3023.0325 | 544.14 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72353.3475 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Northside Acrylic Texture Paint | 335.03 | 7.25 | 0 | 2428.9675 | 437.22 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72947.4125 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Northside Acrylic Texture Paint | 416.97 | 7.25 | 0 | 3023.0325 | 544.14 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72353.3475 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Westside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 1st Floor Southside Acrylic Texture Paint | 126.07 | 7.25 | 0 | 914.0075 | 164.52 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -74462.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Northside Acrylic Texture Paint | 416.97 | 7.25 | 0 | 3023.0325 | 544.14 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72353.3475 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Northside Acrylic Texture Paint | 416.97 | 7.25 | 0 | 3023.0325 | 544.14 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72353.3475 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 1st Floor Eastside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 1st Floor Westside Acrylic Texture Paint | 100 | 7.25 | 0 | 725 | 130.5 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -74651.38 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 8th Floor Westside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Westside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Westside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Westside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 1st Floor Northside Acrylic Texture Paint | 335.03 | 7.25 | 0 | 2428.9675 | 437.22 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72947.4125 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 8th Floor Southside Acrylic Texture Paint | 416.97 | 7.25 | 0 | 3023.0325 | 544.14 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72353.3475 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Westside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 9th Floor Westside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Eastside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Southside Acrylic Texture Paint | 416.97 | 7.25 | 0 | 3023.0325 | 544.14 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72353.3475 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Southside Acrylic Texture Paint | 416.97 | 7.25 | 0 | 3023.0325 | 544.14 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72353.3475 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Southside Acrylic Texture Paint | 208 | 7.25 | 0 | 1508 | 271.44 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -73868.38 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Northside Acrylic Texture Paint | 416.97 | 7.25 | 0 | 3023.0325 | 544.14 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72353.3475 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 9th Floor Southside Acrylic Texture Paint | 416.97 | 7.25 | 0 | 3023.0325 | 544.14 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72353.3475 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Eastside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Eastside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Eastside Acrylic Texture Paint | 394.07 | 7.25 | 0 | 2857.0075 | 514.26 | 2023-06-17 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 100193 | 2023-06-17 | 75376.38 | 2023-06-28 12:01 | -72519.3725 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 1st Floor Eastside Acrylic Texture Paint | 174.89 | 7.25 | 0 | 1267.9525 | 228.24 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33622.4575 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 1st Floor Westside Acrylic Texture Paint | 96.86 | 7.25 | 0 | 702.235 | 126.4 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -34188.175 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 8th Floor Westside Acrylic Texture Paint | 148.62 | 7.25 | 0 | 1077.495 | 193.96 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33812.915 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 3rd Floor Southside Acrylic Texture Paint | 148.92 | 7.25 | 0 | 1079.67 | 194.34 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33810.74 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 4th Floor Eastside Acrylic Texture Paint | 154.84 | 7.25 | 0 | 1122.59 | 202.06 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33767.82 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 1st Floor Southside Acrylic Texture Paint | 31.67 | 7.25 | 0 | 229.6075 | 41.32 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -34660.8025 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Westside Acrylic Texture Paint | 163.05 | 7.25 | 0 | 1182.1125 | 212.78 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33708.2975 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 5th Floor Southside Acrylic Texture Paint | 148.92 | 7.25 | 0 | 1079.67 | 194.34 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33810.74 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 6th Floor Southside Acrylic Texture Paint | 146.88 | 7.25 | 0 | 1064.88 | 191.68 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -33825.53 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 8th Floor Eastside Acrylic Texture Paint | 70.91 | 7.25 | 0 | 514.0975 | 92.54 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -34376.3125 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 9th Floor Northside Acrylic Texture Paint | 91.32 | 7.25 | 0 | 662.07 | 119.18 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -34228.34 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 2nd Floor Southside Acrylic Texture Paint | 90.23 | 7.25 | 0 | 654.1675 | 117.76 | 2024-01-04 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 104360 | 2024-01-08 | 34890.41 | 2024-02-02 14:25 | -34236.2425 | MANSI ENTERPRISES.
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 10th Floor Southside Acrylic Texture Paint | 53.3 | 7.25 | 0 | 386.425 | 0 | 2024-01-05 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 104359 | 2024-01-08 | 2946.41 | 2024-03-23 12:22 | -2559.985 | K RAMESH KUMAR
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 10th Floor Eastside Acrylic Texture Paint | 98.54 | 7.25 | 0 | 714.415 | 0 | 2024-01-05 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 104359 | 2024-01-08 | 2946.41 | 2024-03-23 12:22 | -2231.995 | K RAMESH KUMAR
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 10th Floor Westside Acrylic Texture Paint | 50.59 | 7.25 | 0 | 366.7775 | 0 | 2024-01-05 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 104359 | 2024-01-08 | 2946.41 | 2024-03-23 12:22 | -2579.6325 | K RAMESH KUMAR
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 11th Floor Westside Acrylic Texture Paint | 50.89 | 7.25 | 0 | 368.9525 | 0 | 2024-01-05 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for West side External Painting work. | 100 |  | 104359 | 2024-01-08 | 2946.41 | 2024-03-23 12:22 | -2577.4575 | K RAMESH KUMAR
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 12th Floor Southside Acrylic Texture Paint | 52.13 | 7.25 | 0 | 377.9425 | 0 | 2024-01-05 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for South side External Painting work. | 100 |  | 104359 | 2024-01-08 | 2946.41 | 2024-03-23 12:22 | -2568.4675 | K RAMESH KUMAR
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 10th Floor Northside Acrylic Texture Paint | 53.3 | 7.25 | 0 | 386.425 | 0 | 2024-01-05 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for North side External Painting work. | 100 |  | 104359 | 2024-01-08 | 2946.41 | 2024-03-23 12:22 | -2559.985 | K RAMESH KUMAR
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 578 | 2022-12-06 | D-Bldg 11th Floor Eastside Acrylic Texture Paint | 47.65 | 7.25 | 0 | 345.4625 | 0 | 2024-01-05 | Labour charges for Applying Texture Paint including Joint Putty, Grinding & Touch up for Eest side External Painting work. | 100 |  | 104359 | 2024-01-08 | 2946.41 | 2024-03-23 12:22 | -2600.9475 | K RAMESH KUMAR
Organic Waste Composter Machine (M+L) | N/C | N/C | GREEN PLANET SOLUTION | 579 | 2022-12-08 | Organic Waste Composter | 1 | 835000 | 0 | 83500 | 10020 | 2023-10-12 | Advance along with Work order | 10 |  | 102941 | 2023-10-24 | 668000 | 2023-11-03 15:43 | -584500 | GREEN PLANET SOLUTION
Organic Waste Composter Machine (M+L) | N/C | N/C | GREEN PLANET SOLUTION | 579 | 2022-12-08 | Organic Waste Composter | 1 | 835000 | 0 | 584500 | 70140 | 2023-10-13 | Before Dispatch of Material at Site | 70 |  | 102941 | 2023-10-24 | 668000 | 2023-11-03 15:43 | -83500 | GREEN PLANET SOLUTION
Toilet False Ceiling (L) BC | N/C | N/C | A K INTERIOR CONTRACTOR | 580 | 2022-12-09 | F-Bldg 3rd Floor Toilet False Ceiling Work | 64 | 15 | 0 | 960 | 172.8 | 2024-04-07 | Labour Charges for F Buiding 3rd floor Toilet False Ceiling work.Transportation of material from store to required working place to be done Contractor. | 100 |  | 106646 | 2024-04-08 | 4800 | 2024-05-03 13:14 | -3840 | A K INTERIOR CONTRACTOR
Toilet False Ceiling (M) - BC | N/C | N/C | A K INTERIOR CONTRACTOR | 580 | 2022-12-09 | F-Bldg 3rd Floor Toilet False Ceiling Work | 64 | 60 | 0 | 3840 | 691.2 | 2024-04-07 | Material Supply Charges for F Buiding 3rd floor Toilet False Ceiling work.Transportation of material from store to required working place to be done Contractor. | 100 |  | 106646 | 2024-04-08 | 4800 | 2024-05-03 13:14 | -960 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 580 | 2022-12-09 | F-Bldg LG Floor- Parking Area False Ceiling Work | 955.408 | 15 | 0 | 14331.12 | 2579.6 | 2023-08-19 | Labour charges for False Ceiling work for F-Building LG Floor Parking area. | 100 |  | 101333 | 2023-08-19 | 14331.12 | 2023-09-01 11:40 | 0 | A K INTERIOR CONTRACTOR
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 581 | 2022-12-09 | F-Bldg LG Floor- Parking Area False Ceiling Work | 1194.26 | 60 | 0 | 71655.6 | 12898 | 2023-08-19 | Material Supply charges for False Ceiling work F-Building Parking area. | 100 |  | 101334 | 2023-08-19 | 71655.6 | 2023-09-01 11:46 | 0 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 1st Floor Common Lobby False Ceiling Work | 183 | 15 | 0 | 2745 | 494.1 | 2024-01-18 17:36 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 104680 | 2024-01-22 | 14729.7 | 2024-02-09 11:05 | -11984.7 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 2nd Floor Common Lobby False Ceiling Work | 15 | 15 | 0 | 225 | 40.5 | 2024-01-18 17:36 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 104680 | 2024-01-22 | 14729.7 | 2024-02-09 11:05 | -14504.7 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 3rd Floor Common Lobby False Ceiling Work | 27 | 15 | 0 | 405 | 72.9 | 2024-01-18 17:36 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 104680 | 2024-01-22 | 14729.7 | 2024-02-09 11:05 | -14324.7 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg Stilt Floor Common Lobby False Ceiling Work | 289 | 15 | 0 | 4335 | 780.3 | 2024-01-18 17:36 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 104680 | 2024-01-22 | 14729.7 | 2024-02-09 11:05 | -10394.7 | A K INTERIOR CONTRACTOR
Gypsum False Ceiling Patta (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | 1st Floor- Waiting Area False Ceiling Work | 467.98 | 15 | 0 | 7019.7 | 1263.54 | 2024-01-18 17:36 | Labour charges for Fixing of Gypsum False Ceiling Patta work for 1st Floor Waiting Area F-Bldg | 100 |  | 104680 | 2024-01-22 | 14729.7 | 2024-02-09 11:05 | -7710 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 2nd Floor Common Lobby False Ceiling Work | 135 | 15 | 0 | 2025 | 364.5 | 2023-12-15 15:54 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 104033 | 2023-12-18 | 16200 | 2024-01-08 16:12 | -14175 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 1st Floor Common Lobby False Ceiling Work | 945 | 15 | 0 | 14175 | 2551.5 | 2023-12-15 15:54 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 104033 | 2023-12-18 | 16200 | 2024-01-08 16:12 | -2025 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 3rd Floor Common Lobby False Ceiling Work | 150 | 15 | 0 | 2250 | 405 | 2023-08-24 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101430 | 2023-08-25 | 20354.78 | 2023-09-04 11:39 | -18104.78 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg LG Floor Common Lobby False Ceiling Work | 150 | 15 | 0 | 2250 | 405 | 2023-08-24 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101430 | 2023-08-25 | 20354.78 | 2023-09-04 11:39 | -18104.78 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 2nd Floor Common Lobby False Ceiling Work | 150 | 15 | 0 | 2250 | 405 | 2023-08-24 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101430 | 2023-08-25 | 20354.78 | 2023-09-04 11:39 | -18104.78 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg Stilt Floor Common Lobby False Ceiling Work | 289 | 15 | 0 | 4335 | 780.3 | 2023-08-24 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101430 | 2023-08-25 | 20354.78 | 2023-09-04 11:39 | -16019.78 | A K INTERIOR CONTRACTOR
Gypsum False Ceiling Patta (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | 1st Floor- Waiting Area False Ceiling Work | 467.985 | 15 | 0 | 7019.775 | 1263.56 | 2023-08-24 | Labour charges for Fixing of Gypsum False Ceiling Patta work for 1st Floor Waiting Area F-Bldg | 100 |  | 101430 | 2023-08-25 | 20354.78 | 2023-09-04 11:39 | -13335.005 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 1st Floor Common Lobby False Ceiling Work | 150 | 15 | 0 | 2250 | 405 | 2023-08-24 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101430 | 2023-08-25 | 20354.78 | 2023-09-04 11:39 | -18104.78 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 1st Floor Common Lobby False Ceiling Work | 900 | 15 | 0 | 13500 | 2430 | 2023-08-26 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101477 | 2023-08-26 | 16500 | 1900-01-01 | -3000 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg LG Floor Common Lobby False Ceiling Work | 200 | 15 | 0 | 3000 | 540 | 2023-08-26 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101477 | 2023-08-26 | 16500 | 1900-01-01 | -13500 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | 1st Floor- Waiting Area False Ceiling Work | 628.425 | 15 | 0 | 9426.375 | 1696.74 | 2023-08-18 | Labour charges for Fixing of Gypsum False Ceiling work for 1st Floor waiting area F-Bldg | 100 |  | 101331 | 2023-08-19 | 9426.38 | 2023-09-04 11:41 | -0.005 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 3rd Floor Common Lobby False Ceiling Work | 123 | 15 | 0 | 1845 | 332.1 | 2023-09-20 | Labour Charges for False Ceiling work for F Building Common lobby area | 100 |  | 102009 | 2023-09-21 | 1845 | 2023-10-17 12:56 | 0 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg LG Floor Common Lobby False Ceiling Work | 1990.58 | 15 | 0 | 29858.7 | 5374.56 | 2024-04-08 16:20 | Labour charges & Qty Diff. for False ceiling work for F-Bldg Common Lobby area. | 100 |  | 106683 | 2024-04-08 | 35000.7 | 2024-05-06 13:01 | -5142 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 3rd Floor Common Lobby False Ceiling Work | 171.4 | 15 | 0 | 2571 | 462.78 | 2024-04-08 16:20 | Labour charges & Qty Diff. for False ceiling work for F-Bldg Common Lobby area. | 100 |  | 106683 | 2024-04-08 | 35000.7 | 2024-05-06 13:01 | -32429.7 | A K INTERIOR CONTRACTOR
False Ceiling Work (L) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR | 582 | 2022-12-09 | F-Bldg 2nd Floor Common Lobby False Ceiling Work | 171.4 | 15 | 0 | 2571 | 462.78 | 2024-04-08 16:20 | Labour charges & Qty Diff. for False ceiling work for F-Bldg Common Lobby area. | 100 |  | 106683 | 2024-04-08 | 35000.7 | 2024-05-06 13:01 | -32429.7 | A K INTERIOR CONTRACTOR
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg 1st Floor Common Lobby False Ceiling Work | 878.4 | 60 | 0 | 52704 | 9486.72 | 2023-12-15 16:20 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 104034 | 2023-12-18 | 58464 | 2023-12-25 15:40 | -5760 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg 2nd Floor Common Lobby False Ceiling Work | 96 | 60 | 0 | 5760 | 1036.8 | 2023-12-15 16:20 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 104034 | 2023-12-18 | 58464 | 2023-12-25 15:40 | -52704 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg LG Floor Common Lobby False Ceiling Work | 1990.58 | 60 | 0 | 119434.8 | 21498.26 | 2024-04-08 16:07 | Material supply charges for False ceiling work for F-Bldg Common Lobby area. | 100 |  | 106681 | 2024-04-08 | 140002.8 | 2024-05-06 13:02 | -20568 | A K INTERIOR CONTRACTOR
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg 2nd Floor Common Lobby False Ceiling Work | 171.4 | 60 | 0 | 10284 | 1851.12 | 2024-04-08 16:07 | Material supply charges for False ceiling work for F-Bldg Common Lobby area. | 100 |  | 106681 | 2024-04-08 | 140002.8 | 2024-05-06 13:02 | -129718.8 | A K INTERIOR CONTRACTOR
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg 3rd Floor Common Lobby False Ceiling Work | 171.4 | 60 | 0 | 10284 | 1851.12 | 2024-04-08 16:07 | Material supply charges for False ceiling work for F-Bldg Common Lobby area. | 100 |  | 106681 | 2024-04-08 | 140002.8 | 2024-05-06 13:02 | -129718.8 | A K INTERIOR CONTRACTOR
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | 1st Floor- Waiting Area False Ceiling Work | 500 | 60 | 0 | 30000 | 5400 | 2024-01-18 17:42 | Material Supply charges of Gypsum False Ceiling work for 1st Floor Waiting area F-Bldg. | 100 |  | 104682 | 2024-01-22 | 90900 | 2024-02-09 11:06 | -60900 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg Stilt Floor Common Lobby False Ceiling Work | 398 | 60 | 0 | 23880 | 4298.4 | 2024-01-18 17:42 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 104682 | 2024-01-22 | 90900 | 2024-02-09 11:06 | -67020 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg 2nd Floor Common Lobby False Ceiling Work | 24 | 60 | 0 | 1440 | 259.2 | 2024-01-18 17:42 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 104682 | 2024-01-22 | 90900 | 2024-02-09 11:06 | -89460 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg 1st Floor Common Lobby False Ceiling Work | 219 | 60 | 0 | 13140 | 2365.2 | 2024-01-18 17:42 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 104682 | 2024-01-22 | 90900 | 2024-02-09 11:06 | -77760 | A K INTERIOR CONTRACTOR (MATERIAL)
Gypsum False Ceiling Patta (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | 1st Floor- Waiting Area False Ceiling Work | 374 | 60 | 0 | 22440 | 4039.2 | 2024-01-18 17:42 | Material Supply charges of Gypsum False Ceiling Patta work for 1st Floor Waiting area F-Bldg. | 100 |  | 104682 | 2024-01-22 | 90900 | 2024-02-09 11:06 | -68460 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg 3rd Floor Common Lobby False Ceiling Work | 120 | 60 | 0 | 7200 | 1296 | 2023-09-21 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 102018 | 2023-09-21 | 7200 | 2023-10-11 11:11 | 0 | A K INTERIOR CONTRACTOR
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg 1st Floor Common Lobby False Ceiling Work | 900 | 60 | 0 | 54000 | 9720 | 2023-08-26 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101476 | 2023-08-26 | 75000 | 2023-09-04 11:40 | -21000 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg LG Floor Common Lobby False Ceiling Work | 350 | 60 | 0 | 21000 | 3780 | 2023-08-26 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101476 | 2023-08-26 | 75000 | 2023-09-04 11:40 | -54000 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | 1st Floor- Waiting Area False Ceiling Work | 628.425 | 60 | 0 | 37705.5 | 6787 | 2023-08-18 | Material Supply charges of Gypsum False Ceiling work for 1st Floor Waiting area F-Bldg. | 100 |  | 101325 | 2023-08-19 | 37705.5 | 2023-09-12 12:49 | 0 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg 1st Floor Common Lobby False Ceiling Work | 180 | 60 | 0 | 10800 | 1944 | 2023-08-24 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101429 | 2023-08-25 | 84436.02 | 2023-09-12 12:49 | -73636.02 | A K INTERIOR CONTRACTOR (MATERIAL)
Gypsum False Ceiling Patta (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | 1st Floor- Waiting Area False Ceiling Work | 93.597 | 60 | 0 | 5615.82 | 1010.84 | 2023-08-24 | Material Supply charges of Gypsum False Ceiling Patta work for 1st Floor Waiting area F-Bldg. | 100 |  | 101429 | 2023-08-25 | 84436.02 | 2023-09-12 12:49 | -78820.2 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg 2nd Floor Common Lobby False Ceiling Work | 180 | 60 | 0 | 10800 | 1944 | 2023-08-24 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101429 | 2023-08-25 | 84436.02 | 2023-09-12 12:49 | -73636.02 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg Stilt Floor Common Lobby False Ceiling Work | 180 | 60 | 0 | 10800 | 1944 | 2023-08-24 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101429 | 2023-08-25 | 84436.02 | 2023-09-12 12:49 | -73636.02 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | F-Bldg 3rd Floor Common Lobby False Ceiling Work | 180 | 60 | 0 | 10800 | 1944 | 2023-08-24 | Material Supply Charges for False Ceiling work for F Building Common lobby area | 100 |  | 101429 | 2023-08-25 | 84436.02 | 2023-09-12 12:49 | -73636.02 | A K INTERIOR CONTRACTOR (MATERIAL)
False Ceiling Work (M) - DCH | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | 1st Floor- Waiting Area False Ceiling Work | 125.685 | 60 | 0 | 7541.1 | 1357.4 | 2023-08-24 | Material Supply charges of Gypsum False Ceiling work for 1st Floor Waiting area F-Bldg. | 100 |  | 101429 | 2023-08-25 | 84436.02 | 2023-09-12 12:49 | -76894.92 | A K INTERIOR CONTRACTOR (MATERIAL)
Gypsum False Ceiling Patta (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 583 | 2022-12-09 | 1st Floor- Waiting Area False Ceiling Work | 467.985 | 60 | 0 | 28079.1 | 5054.24 | 2023-08-24 | Material Supply charges of Gypsum False Ceiling Patta work for 1st Floor Waiting area F-Bldg. | 100 |  | 101429 | 2023-08-25 | 84436.02 | 2023-09-12 12:49 | -56356.92 | A K INTERIOR CONTRACTOR (MATERIAL)
Excavation Manually | N/C | N/C | SHIVAM ENTERPRISES | 584 | 2022-12-10 | LG Floor- Excavation Work for Service line | 64.6 | 180 | 0 | 11628 | 0 | 2023-01-31 | Labour charges for Manually Excavation work for electrical Line, Storm water Line & Fire Line for LG Floor D,E,F- Bldg. | 100 |  | 97971 | 2023-01-31 | 11628 | 2023-02-23 15:29 | 0 | SHIVAM ENTERPRISES
Backfilling - UDR | N/C | N/C | SHIVAM ENTERPRISES | 584 | 2022-12-10 | LG Floor- Excavation Work for Service line | 4285.7143 | 3.5 | 0 | 15000.0001 | 0 | 2023-10-18 | Labour charges for Manually Backfilling work for Electrical Line, Storm water Line and Fire Line for LG Floor D,E,F- Bldg. | 100 |  | 102790 | 2023-10-19 | 47000 | 2023-11-06 16:14 | -32000 | SHIVAM ENTERPRISES
Excavation Manually | N/C | N/C | SHIVAM ENTERPRISES | 584 | 2022-12-10 | LG Floor- Excavation Work for Service line | 177.7778 | 180 | 0 | 32000.004 | 0 | 2023-10-18 | Labour charges for Manually Excavation work for electrical Line, Storm water Line & Fire Line for LG Floor D,E,F- Bldg. | 100 |  | 102790 | 2023-10-19 | 47000 | 2023-11-06 16:14 | -14999.996 | SHIVAM ENTERPRISES
Backfilling - UDR | N/C | N/C | SHIVAM ENTERPRISES | 584 | 2022-12-10 | LG Floor- Excavation Work for Service line | 2822 | 3.5 | 0 | 9877 | 0 | 2023-04-13 | Labour charges for Manually Backfilling work for Electrical Line, Storm water Line and Fire Line for LG Floor D,E,F- Bldg. | 100 |  | 99171 | 2023-04-14 | 9877 | 2023-04-24 10:52 | 0 | SHIVAM ENTERPRISES
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2023-10-05 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of SEPT-2023. | 100 |  | 102311 | 2023-10-05 | 15000 | 2023-10-21 18:15 | -7500 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2023-10-05 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of AUG-2023. | 100 |  | 102311 | 2023-10-05 | 15000 | 2023-10-21 18:15 | -7500 | DURGARAM CHANDURAM BHATEE
Chamber Cleaning Work | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | Drainage Chamber Cleaning Work | 14 | 100 | 0 | 1400 | 0 | 2023-03-13 | Labour charges for Drainage Line Chamber Cleaning work. | 100 |  | 98648 | 2023-03-14 | 1400 | 1900-01-01 | 0 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2023-07-12 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of JUNE-2023. | 100 |  | 100661 | 2023-07-13 | 15000 | 2023-07-26 12:28 | -7500 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2023-07-12 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of MAY-2023. | 100 |  | 100661 | 2023-07-13 | 15000 | 2023-07-26 12:28 | -7500 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2023-03-02 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of FEB-2023. | 100 |  | 98460 | 2023-03-03 | 15000 | 2023-03-29 11:16 | -7500 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2023-03-02 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of JAN-2023. | 100 |  | 98460 | 2023-03-03 | 15000 | 2023-03-29 11:16 | -7500 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2023-05-10 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of APR-2023. | 100 |  | 99579 | 2023-05-10 | 15000 | 2023-05-29 13:11 | -7500 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2023-05-10 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of MAR-2023. | 100 |  | 99579 | 2023-05-10 | 15000 | 2023-05-29 13:11 | -7500 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2023-08-10 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of JULY-2023. | 100 |  | 101165 | 2023-08-10 | 7500 | 2023-08-23 18:30 | 0 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2023-11-06 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of OCT-2023. | 100 |  | 103346 | 2023-11-07 | 7500 | 2023-11-08 16:32 | 0 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 8000 | 0 | 8000 | 0 | 2024-02-12 | Labour Charges for Housekeeping work (Female Coolie-1) for the month of JANUARY-2024. | 100 |  | 105285 | 2024-02-12 | 8000 | 2024-03-23 12:19 | 0 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 8000 | 0 | 8000 | 0 | 2024-03-11 | Labour Charges for Housekeeping work (Female Coolie-1) for the month of FEBRUARY-2024 | 100 |  | 106028 | 2024-03-12 | 8000 | 2024-03-23 12:17 | 0 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 8000 | 0 | 8000 | 0 | 2024-07-01 | Labour Charges for Housekeeping work (Female Coolie-1) for the month of JUNE-2024 | 100 |  | 108689 | 2024-07-01 | 16000 | 2024-07-05 11:38 | -8000 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 8000 | 0 | 8000 | 0 | 2024-07-01 | Labour Charges for Housekeeping work (Female Coolie-1) for the month of MAY-2024 | 100 |  | 108689 | 2024-07-01 | 16000 | 2024-07-05 11:38 | -8000 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 8000 | 0 | 8000 | 0 | 2024-05-06 | Labour Charges for Housekeeping work (Female Coolie-1) for the month of MARCH-2024 | 100 |  | 107397 | 2024-05-07 | 16000 | 2024-06-06 12:27 | -8000 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 8000 | 0 | 8000 | 0 | 2024-05-06 | Labour Charges for Housekeeping work (Female Coolie-1) for the month of APRIL-2024 | 100 |  | 107397 | 2024-05-07 | 16000 | 2024-06-06 12:27 | -8000 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2024-01-08 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of DEC-2023. | 100 |  | 104503 | 2024-01-08 | 15000 | 2024-01-16 14:57 | -7500 | DURGARAM CHANDURAM BHATEE
Female Coolie | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | D&E Parking housekeeping work | 1 | 7500 | 0 | 7500 | 0 | 2024-01-08 | Labour charges for Housekeeping work (Female Coolie-1) for the Month of NOV-2023. | 100 |  | 104503 | 2024-01-08 | 15000 | 2024-01-16 14:57 | -7500 | DURGARAM CHANDURAM BHATEE
Sleeve Fixing UWT | N/C | N/C | K B N FABRICATION | 586 | 2022-12-12 | UGWT- MS Sleeves Work | 9 | 400 | 0 | 3600 | 0 | 2023-02-24 | Labour charges for G.I sleeve Fixing work for D and E Building UGWT Domestic Tank Side Sleeves and Fire Tank Side Sleeves. | 100 |  | 98325 | 2023-02-24 | 3600 | 2023-03-14 18:54 | 0 | IZHAR MANSOOR SHAIKH
Sleeve Fixing UWT | N/C | N/C | K B N FABRICATION | 586 | 2022-12-12 | UGWT- MS Sleeves Work | 21 | 400 | 0 | 8400 | 0 | 2022-12-30 | Labour charges for G.I sleeve Fixing work for D and E Building UGWT Domestic Tank Side Sleeves and Fire Tank Side Sleeves. | 100 |  | 97569 | 2022-12-31 | 8400 | 2023-01-31 11:44 | 0 | IZHAR MANSOOR SHAIKH
Excavation by Bucket | N/C | N/C | SHIVAM ENTERPRISES | 587 | 2022-12-12 | F Bldg.-Road Excavation Work | 647.79 | 60 | 0 | 38867.4 | 0 | 2023-12-13 | Charges for Excavation work by Bucket for road near F-Bldg on North Side & East Side. | 100 |  | 103990 | 2023-12-18 | 51823.2 | 2023-12-25 15:37 | -12955.8 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SHIVAM ENTERPRISES | 587 | 2022-12-12 | F Bldg.-Road Excavation Work | 647.79 | 20 | 0 | 12955.8 | 0 | 2023-12-13 | Charges for Spreading & Levelling work for Road near F-Bldg on North Side & East Side. | 100 |  | 103990 | 2023-12-18 | 51823.2 | 2023-12-25 15:37 | -38867.4 | SHIVAM ENTERPRISES
JCB Charges | N/C | N/C | SHIVAM ENTERPRISES | 587 | 2022-12-12 | Filling & Leveling for STP Access road | 16 | 850 | 0 | 13600 | 0 | 2023-01-27 | JCB Charges for Levelling and Filling work for Access Road for STP. | 100 |  | 97946 | 2023-01-28 | 13600 | 2023-02-23 15:29 | 0 | SHIVAM ENTERPRISES
Welding work- DEn | N/C | N/C | PARTH ENTERPRISES | 588 | 2022-12-13 | Tower Crane Support Welding | 1 | 1300 | 0 | 1300 | 0 | 2023-03-02 | Labour Charges for Tower Crane Pocket Support ( I Section) Welding and cuttting work | 100 |  | 98447 | 2023-03-02 | 1300 | 2023-03-16 11:39 | 0 | IZHAR MANSOOR SHAIKH
Double Hydrant Valve (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Internal Hydrant System | 25 | 33000 | 0 | 577500 | 103950 | 2024-07-07 | Against Material Supply | 70 | Challan No-18537 DT03.07.24 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -289290.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Strainer "Y" (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Pump Room Equipment | 1 | 7263 | 0 | 5084.1 | 915.14 | 2024-07-07 | Against Material Supply | 70 | Challan No-18493 DT 12.06.2024 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -861706.3 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Vane Type Water Flow (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 25 | 7500 | 0 | 131250 | 23625 | 2024-07-07 | Against Material Supply | 70 | Challan No-18598 DT 27.06.2024 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -735540.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Orifice Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Internal Hydrant System | 25 | 1400 | 0 | 24500 | 4410 | 2024-07-07 | Against Material Supply | 70 | Challan No-18537 DT-03.07.2024 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -842290.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Orifice Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 8 | 1100 | 0 | 6160 | 1108.8 | 2024-07-15 | Against Material Supply | 70 | Challan No-18537 DT 03.07.2024 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -860630.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Bucket Stand (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Extinguishers - 1 No. | 1 | 639 | 0 | 447.3 | 80.52 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -866343.1 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Hydrant Valve 63mm (M). | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 8 | 18500 | 0 | 103600 | 18648 | 2024-07-07 | Against Material Supply | 70 | Challan No-18537 DT 03.07.2024 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -763190.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Bucket (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Extinguishers - 1 No. | 4 | 3000 | 0 | 8400 | 1512 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -858390.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher ABC 6Kg (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Extinguisher & Signages | 7 | 2010 | 0 | 9849 | 1772.82 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109133 | 2024-07-16 | 866790.4 | 1900-01-01 | -856941.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8 | 1850 | 0 | 10360 | 1864.8 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1352740 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 100 | 350 | 0 | 24500 | 4410 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1338600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 300 | 350 | 0 | 73500 | 13230 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1289600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 128 | 500 | 0 | 44800 | 8064 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1318300 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 298 | 450 | 0 | 93870 | 16896.6 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1269230 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 350 | 0 | 14700 | 2646 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -239470 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 500 | 380 | 0 | 133000 | 23940 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -121170 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 338 | 450 | 0 | 106470 | 19164.6 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -147700 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 62 | 800 | 0 | 34720 | 6249.6 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1328380 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 436 | 380 | 0 | 115976 | 20875.68 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1247124 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8 | 2100 | 0 | 11760 | 2116.8 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1351340 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 60 | 450 | 0 | 18900 | 3402 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1344200 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 546.9005 | 1450 | -0.01 | 555104.0075 | 99918.72 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -807995.9925 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 971 | 350 | 0 | 237895 | 42821.1 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1125205 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 32mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 21 | 1450 | 0 | 21315 | 3836.7 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1341785 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 100 | 340 | 0 | 23800 | 4284 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1339300 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 120 | 650 | 0 | 54600 | 9828 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1308500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 60 | 1000 | 0 | 42000 | 7560 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1321100 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher ABC 6Kg (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Extinguisher & Signages | 18 | 2010 | 0 | 25326 | 4558.68 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT-27/06/2024 | 108665 | 2024-07-01 | 30366 | 2024-07-15 15:03 | -5040 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Fire Pump Room Equipment | 2 | 3600 | 0 | 5040 | 907.2 | 2024-06-26 | Against Material Supply | 70 | Challan No-18403 DT 18403 | 108665 | 2024-07-01 | 30366 | 2024-07-15 15:03 | -25326 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 9 | 1200 | 0 | 7560 | 1360.8 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-10/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1883210 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 1020 | 350 | 0 | 249900 | 44982 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1640870 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 300 | 1450 | 0 | 304500 | 54810 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1586270 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 9 | 1000 | 0 | 6300 | 1134 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-10/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1884470 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 40 | 1000 | 0 | 28000 | 5040 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-10/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1862770 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 300 | 650 | 0 | 136500 | 24570 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT5/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1754270 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 73 | 1000 | 0 | 51100 | 9198 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-10/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1839670 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 750 | 450 | 0 | 236250 | 42525 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1654520 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 498 | 2100 | 0 | 732060 | 131770.8 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1158710 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 300 | 500 | 0 | 105000 | 18900 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1785770 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 60 | 800 | 0 | 33600 | 6048 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1857170 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 650 | 350 | 0 | 159250 | 28665 | 2023-12-11 | Against Material Supply | 70 |  | 103842 | 2023-12-11 | 172102 | 2023-12-25 15:44 | -12852 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 54 | 340 | 0 | 12852 | 2313.36 | 2023-12-11 | Against Material Supply | 70 |  | 103842 | 2023-12-11 | 172102 | 2023-12-25 15:44 | -159250 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 30 | 1000 | 0 | 21000 | 3780 | 2023-12-31 | Against Material Supply | 70 | Challan No- 17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -705530 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 96 | 650 | 0 | 43680 | 7862.4 | 2024-01-01 | Against Material Supply | 70 |  | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -682850 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 100 | 340 | 0 | 23800 | 4284 | 2024-01-01 | Against Material Supply | 70 | Challan No-17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -702730 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 100 | 340 | 0 | 23800 | 4284 | 2024-01-01 | Against Material Supply | 70 | Challan No-17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -702730 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 1450 | 0 | 60900 | 10962 | 2023-12-31 | Against Material Supply | 70 | Challan No- 17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -665630 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 500 | 0 | 21000 | 3780 | 2024-01-01 | Against Material Supply | 70 | Challan No-17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -705530 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 10 | 2100 | 0 | 14700 | 2646 | 2024-01-01 | Against Material Supply | 70 | Challan No-17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -711830 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 290 | 2550 | 0 | 517650 | 93177 | 2024-01-01 | Against Material Supply | 70 | Challan No-17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -208880 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Pump Room Equipment | 2 | 3600 | 0 | 5040 | 907.2 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -364490 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 50 | 2100 | 0 | 73500 | 13230 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -296030 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Drain Valve 25 mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 25 | 4500 | 0 | 78750 | 14175 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -290780 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Pump Room Equipment | 1 | 3200 | 0 | 2240 | 403.2 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -367290 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 100 | 2100 | 0 | 147000 | 26460 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -222530 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 25 | 3600 | 0 | 63000 | 11340 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -306530 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 32mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 20 | 1450 | 0 | 1450 | 261 | 2024-02-12 | Before Submission of Noc File | 5 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325016.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 222.4 | 1450 | 0 | 80620 | 14511.6 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -245846.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 41 | 1000 | 0 | 10250 | 1845 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -316216.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 41 | 1000 | 0 | 2050 | 369 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -324416.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 54.56 | 450 | 0 | 6138 | 1104.84 | 2024-02-12 | After Installation & Pressure Testing | 25 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -320328.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 54.5778 | 450 | 0 | 1228.0005 | 221.04 | 2024-02-12 | Before Submission of Noc File | 5 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325238.0095 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 83.701 | 2100 | -0.02 | 43943.025 | 7909.74 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -282522.985 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 195.6 | 450 | 0 | 22005 | 3960.9 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -304461.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 195.6 | 450 | 0 | 4401 | 792.18 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -322065.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 100 | 350 | 0 | 24500 | 4410 | 2024-01-12 | Against Material Supply | 70 | challan no-17351 | 104547 | 2024-01-15 | 49000 | 2024-02-08 11:57 | -24500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 100 | 350 | 0 | 24500 | 4410 | 2024-01-12 | Against Material Supply | 70 | challan no-17351 | 104547 | 2024-01-15 | 49000 | 2024-02-08 11:57 | -24500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 768 | 500 | 0 | 268800 | 48384 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -891345 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 357 | 450 | 0 | 112455 | 20241.9 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -1047690 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 180 | 1450 | 0 | 182700 | 32886 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -977445 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 102 | 650 | 0 | 46410 | 8353.8 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -1113735 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 1020 | 350 | 0 | 249900 | 44982 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -910245 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 204 | 2100 | 0 | 299880 | 53978.4 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -860265 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 102 | 380 | 0 | 9690 | 1744.2 | 2024-02-12 | After Installation & Pressure Testing | 25 | For Shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -316776.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 102 | 380 | 0 | 1938 | 348.84 | 2024-02-12 | Before Submission of Noc File | 5 | For Shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -324528.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 29.4 | 800 | 0 | 1176 | 211.68 | 2024-02-12 | Before Submission of Noc File | 5 |  | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325290.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 12 | 450 | 0 | 1350 | 243 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325116.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 12 | 450 | 0 | 270 | 48.6 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -326196.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 29.4 | 800 | 0 | 5880 | 1058.4 | 2024-02-12 | After Installation & Pressure Testing | 25 |  | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -320586.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 83.7048 | 2100 | 0 | 8789.004 | 1582.02 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -317677.006 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 283.4286 | 350 | 0 | 24800.0025 | 4464 | 2024-02-12 | After Installation & Pressure Testing | 25 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -301666.0075 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 7.0011 | 1850 | -0.01 | 3238.0087 | 582.84 | 2024-02-12 | After Installation & Pressure Testing | 25 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -323228.0012 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 7.0054 | 1850 | 0 | 647.9995 | 116.64 | 2024-02-12 | Before Submission of Noc File | 5 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325818.0105 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8.352 | 500 | 0 | 1044 | 187.92 | 2024-02-12 | After Installation & Pressure Testing | 25 |  | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325422.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8.36 | 500 | 0 | 209 | 37.62 | 2024-02-12 | Before Submission of Noc File | 5 | For Shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -326257.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 71.704 | 500 | 0 | 8963 | 1613.34 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -317503.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 71.72 | 500 | 0 | 1793 | 322.74 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -324673.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 49.4031 | 650 | 0 | 8028.0037 | 1445.04 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -318438.0062 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 49.4154 | 650 | 0 | 1606.0005 | 289.08 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -324860.0095 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 222.4 | 1450 | 0 | 16124 | 2902.32 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -310342.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 444.0457 | 350 | 0 | 38853.9987 | 6993.72 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -287612.0112 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 444.0571 | 350 | 0 | 7770.9992 | 1398.78 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -318695.0108 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 283.4286 | 350 | 0 | 4960.0005 | 892.8 | 2024-02-12 | Before Submission of Noc File | 5 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -321506.0095 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 32mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 20 | 1450 | 0 | 7250 | 1305 | 2024-02-12 | After Installation & Pressure Testing | 25 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -319216.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 300 | 450 | 0 | 94500 | 17010 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -958934 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 68.9005 | 1450 | -0.01 | 69934.0075 | 12588.12 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -983499.9925 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 120 | 1000 | 0 | 84000 | 15120 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -969434 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 30 | 800 | 0 | 16800 | 3024 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -1036634 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 310 | 1450 | 0 | 314650 | 56637 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -738784 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 300 | 350 | 0 | 73500 | 13230 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -979934 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 300 | 500 | 0 | 105000 | 18900 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -948434 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 150 | 2550 | 0 | 267750 | 48195 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -785684 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 60 | 650 | 0 | 27300 | 4914 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -1026134 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 650 | 0 | 27300 | 4914 | 2023-09-16 | Against Material Supply | 70 | Challan No- 16574 | 101921 | 2023-09-18 | 450135 | 2023-10-23 12:37 | -422835 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 600 | 350 | 0 | 147000 | 26460 | 2023-09-16 | Against Material Supply | 70 | Challan No- 16574 | 101921 | 2023-09-18 | 450135 | 2023-10-23 12:37 | -303135 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 600 | 500 | 0 | 210000 | 37800 | 2023-09-16 | Against Material Supply | 70 | Challan No- 16574 | 101921 | 2023-09-18 | 450135 | 2023-10-23 12:37 | -240135 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 9 | 450 | 0 | 2835 | 510.3 | 2023-09-16 | Against Material Supply | 70 | Remaining Qty from Previous Challan . | 101921 | 2023-09-18 | 450135 | 2023-10-23 12:37 | -447300 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 90 | 1000 | 0 | 63000 | 11340 | 2023-09-16 | Against Material Supply | 70 | Challan No- 16574 | 101921 | 2023-09-18 | 450135 | 2023-10-23 12:37 | -387135 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 294.901 | 750 | -0.02 | 154823.025 | 27868.14 | 2023-08-22 | After Installation & Pressure Testing | 70 |  | 101390 | 2023-08-23 | 154823.01 | 2023-09-20 11:58 | 0.015 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 195.6 | 250 | 0 | 12225 | 2200.5 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -367082 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 54.56 | 250 | 0 | 9548 | 1718.64 | 2024-02-12 | After Installation & Pressure Testing | 70 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -369759 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 54.56 | 250 | 0 | 3410 | 613.8 | 2024-02-12 | After Final Noc | 25 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -375897 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 195.6 | 250 | 0 | 34230 | 6161.4 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -345077 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 102 | 200 | 0 | 14280 | 2570.4 | 2024-02-12 | After Installation & Pressure Testing | 70 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -365027 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 102 | 200 | 0 | 5100 | 918 | 2024-02-12 | After Final Noc | 25 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -374207 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 32mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 20 | 200 | 0 | 1000 | 180 | 2024-02-12 | After Final Noc | 25 | for shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -378307 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 32mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 20 | 200 | 0 | 2800 | 504 | 2024-02-12 | After Installation & Pressure Testing | 70 | for shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -376507 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8.3524 | 300 | 0 | 1754.004 | 315.72 | 2024-02-12 | After Installation & Pressure Testing | 70 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -377552.996 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8.3467 | 300 | 0 | 626.0025 | 112.68 | 2024-02-12 | After Final Noc | 25 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -378680.9975 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 83.7 | 600 | 0 | 35154 | 6327.72 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -344153 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 83.7 | 600 | 0 | 12555 | 2259.9 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -366752 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 71.7 | 300 | 0 | 15057 | 2710.26 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -364250 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 49.4 | 400 | 0 | 13832 | 2489.76 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -365475 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 49.4 | 400 | 0 | 4940 | 889.2 | 2024-02-12 | After Final Noc | 25 |  | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -374367 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 71.7067 | 300 | 0 | 5378.0025 | 968.04 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -373928.9975 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 12 | 350 | 0 | 2940 | 529.2 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -376367 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 12 | 350 | 0 | 1050 | 189 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -378257 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 41 | 500 | 0 | 14350 | 2583 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -364957 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 41 | 500 | 0 | 5125 | 922.5 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -374182 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 283.4 | 200 | 0 | 14170 | 2550.6 | 2024-02-12 | After Final Noc | 25 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -365137 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 283.4286 | 200 | 0 | 39680.004 | 7142.4 | 2024-02-12 | After Installation & Pressure Testing | 70 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -339626.996 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 222.4 | 550 | 0 | 85624 | 15412.32 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -293683 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 222.4 | 550 | 0 | 30580 | 5504.4 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -348727 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 29.4 | 450 | 0 | 9261 | 1666.98 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -370046 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 29.4044 | 450 | 0 | 3307.995 | 595.44 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -375999.005 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 40mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 7 | 200 | 0 | 980 | 176.4 | 2024-02-12 | After Installation & Pressure Testing | 70 | for shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -378327 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 40mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 7 | 200 | 0 | 350 | 63 | 2024-02-12 | After Final Noc | 25 | for shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -378957 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 138 | 750 | 0 | 72450 | 13041 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106228 | 2024-03-18 | 74634 | 2024-03-28 12:36 | -2184 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 5.2 | 600 | 0 | 2184 | 393.12 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106228 | 2024-03-18 | 74634 | 2024-03-28 12:36 | -72450 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 550 | 0 | 23100 | 4158 | 2024-03-18 | After Installation & Pressure Testing | 70 | Hydrant Riser Lower | 106230 | 2024-03-18 | 174300 | 2024-03-30 12:28 | -151200 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 180 | 600 | 0 | 75600 | 13608 | 2024-03-18 | After Installation & Pressure Testing | 70 | Hydrant Riser Lower + Upper | 106230 | 2024-03-18 | 174300 | 2024-03-30 12:28 | -98700 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 180 | 600 | 0 | 75600 | 13608 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106230 | 2024-03-18 | 174300 | 2024-03-30 12:28 | -98700 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 28 | 450 | 0 | 8820 | 1587.6 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1155385 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 1350 | 300 | 0 | 283500 | 51030 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -880705 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 357 | 250 | 0 | 62475 | 11245.5 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1101730 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Drain Valve 25 mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 23 | 350 | 0 | 5635 | 1014.3 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1158570 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 711 | 550 | 0 | 273735 | 49272.3 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -890470 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 205 | 400 | 0 | 57400 | 10332 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1106805 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 19 | 250 | 0 | 3325 | 598.5 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1160880 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 1432 | 200 | 0 | 200480 | 36086.4 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -963725 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 184 | 200 | 0 | 25760 | 4636.8 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1138445 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 23 | 350 | 0 | 5635 | 1014.3 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1158570 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 196 | 500 | 0 | 68600 | 12348 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1095605 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 1206 | 200 | 0 | 168840 | 30391.2 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -995365 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 97 | 400 | 0 | 27160 | 4888.8 | 2024-03-20 | After Installation & Pressure Testing | 70 |  | 106286 | 2024-03-20 | 41160 | 2024-03-30 12:28 | -14000 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 18 | 600 | 0 | 7560 | 1360.8 | 2024-03-20 | After Installation & Pressure Testing | 70 |  | 106286 | 2024-03-20 | 41160 | 2024-03-30 12:28 | -33600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 23 | 400 | 0 | 6440 | 1159.2 | 2024-03-20 | After Installation & Pressure Testing | 70 |  | 106286 | 2024-03-20 | 41160 | 2024-03-30 12:28 | -34720 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 6.5455 | 550 | -0.02 | 2520.0175 | 0 | 2023-10-11 | After Installation & Pressure Testing | 70 | Debit for Shivappa Pawar (Housekeeping ) | 102552 | 2023-10-12 | 2520 | 2023-11-06 16:16 | 0.0175 | PAWAR SHIVAPPA TARANAIK
Yellow Box Marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 594 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 200 | 580 | 0 | 116000 | 20880 | 2023-03-06 14:51 | Providing and Applying Charges for Yellow Box making work with Thermoplastic material and machine of Yellow colour 2.3 or 2.5mm thickness. | 100 |  | 98537 | 2023-03-06 | 362007 | 2023-03-20 11:53 | -246007 | AVS TRAFEIC SYSTEMS
Zebra Crossing marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 594 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 104 | 580 | 0 | 60320 | 10857.6 | 2023-03-06 14:51 | Providing and Applying Charges for Zebra Crossing making work with Thermoplastic material and machine of White colour 2.3 or 2.5mm thickness.Road width side 52 meter of all roads of same junction x 4 meter long x 0.5 | 100 |  | 98537 | 2023-03-06 | 362007 | 2023-03-20 11:53 | -301687 | AVS TRAFEIC SYSTEMS
Yellow Box Marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 594 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 167 | 580 | 0 | 96860 | 17434.8 | 2023-03-06 14:51 | Charges for Qty Diff. for Providing and Applying Charges for Yellow Box making work with Thermoplastic material and machine of Yellow colour 2.3 or 2.5mm thickness. | 100 |  | 98537 | 2023-03-06 | 362007 | 2023-03-20 11:53 | -265147 | AVS TRAFEIC SYSTEMS
Zebra Crossing marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 594 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 153.15 | 580 | 0 | 88827 | 15988.86 | 2023-03-06 14:51 | Charges for Qty Diff. of Providing and Applying Charges for Zebra Crossing making work with Thermoplastic material and machine of White colour 2.3 or 2.5mm thickness.Road width side 52 meter of all roads of same junction x 4 meter long x 0.5 | 100 |  | 98537 | 2023-03-06 | 362007 | 2023-03-20 11:53 | -273180 | AVS TRAFEIC SYSTEMS
Zebra Crossing marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 595 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 26.57 | 580 | 0 | 15410.6 | 2773.9 | 2023-03-06 13:54 | Providing and Applying Charges for Zebra Crossing making work with Thermoplastic material and machine of White colour 2.3 or 2.5mm thickness.Road width side 58 meter of all roads of same junction x 4 meter long x 0.5 | 100 |  | 98538 | 2023-03-06 | 149390.6 | 2023-03-20 11:53 | -133980 | AVS TRAFEIC SYSTEMS
Yellow Box Marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 595 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 231 | 580 | 0 | 133980 | 24116.4 | 2023-03-06 13:54 | Providing and Applying Charges for Yellow Box making work with Thermoplastic material and machine of Yellow colour 2.3 or 2.5mm thickness. | 100 |  | 98538 | 2023-03-06 | 149390.6 | 2023-03-20 11:53 | -15410.6 | AVS TRAFEIC SYSTEMS
Tractor Trip - DCW | N/C | N/C | PRAKASH CONTRACTOR | 596 | 2022-12-19 | Road Beautification - Civil work | 9.2 | 1000 | 0 | 9200 | 0 | 2023-01-23 | Tractor Trip Charges for Road Beautification Civil work at Vadgaon Chowk.Excavation,Poyata Soil Filling Shrub Plantation work and other misc work. | 100 |  | 97899 | 2023-01-23 | 9200 | 2023-02-27 15:43 | 0 | NAMANNA RATHOD
Labour Lumpsum | N/C | N/C | PRAKASH CONTRACTOR | 596 | 2022-12-19 | Road Beautification - Civil work | 0.7709 | 55000 | 0 | 42399.5 | 0 | 2023-01-05 17:22 | Labour Charges for Excavation for Shrub bed,Poyata Soil filling in Shrub bed,Shrubs Plantation work and Misc. work with required labour and machinery. | 100 |  | 97650 | 2023-01-05 | 42399.5 | 2023-01-23 18:36 | 0 | PRAKASH CONTRACTOR
Labour Lumpsum | N/C | N/C | PRAKASH CONTRACTOR | 596 | 2022-12-19 | Road Beautification - Civil work | 0.0982 | 55000 | 0 | 5401 | 0 | 2023-02-01 16:40 | Labour Charges for Excavation for Shrub bed,Poyata Soil filling in Shrub bed,Shrubs Plantation work and Misc. work with required labour and machinery. | 100 |  | 97979 | 2023-02-02 | 5401 | 2023-02-23 14:59 | 0 | PRAKASH CONTRACTOR
4C 6 sqmm Alu. Cable (L) | N/C | N/C | LAXMI ELECTRICALS | 597 | 2022-12-19 | Street Light Pole fixing work | 20 | 40 | 0 | 800 | 0 | 2023-01-05 18:49 | Labour Charges for 4 Core 6 Sq.mm Cable for Street light pole. Safety of all workers, public & Vehicles is of contractors responsbility. At P.L.Deshapande Garden Beautification. | 100 |  | 97663 | 2023-01-06 | 18300 | 2023-01-31 11:54 | -17500 | LAXMI ELECTRICALS
Street Light Foundation Work - DSL | N/C | N/C | LAXMI ELECTRICALS | 597 | 2022-12-19 | Street Light Pole fixing work | 7 | 1500 | 0 | 10500 | 0 | 2023-01-05 18:49 | Labour and Material Supply Charges for Street light pole foundation Concreting work. Safety of all workers, public & Vehicles is of contractors responsbility.At P.L.Deshapande Garden Beautification. | 100 |  | 97663 | 2023-01-06 | 18300 | 2023-01-31 11:54 | -7800 | LAXMI ELECTRICALS
Street Light Pole fixing (L) | N/C | N/C | LAXMI ELECTRICALS | 597 | 2022-12-19 | Street Light Pole fixing work | 7 | 1000 | 0 | 7000 | 0 | 2023-01-05 18:49 | Charges for 10 Feet Street Light pole Fixing work including excavation of pit,Pole Grouting with concreting etc. At P.L.Deshapande Garden Beautification. | 100 |  | 97663 | 2023-01-06 | 18300 | 2023-01-31 11:54 | -11300 | LAXMI ELECTRICALS
Installation Charges | N/C | N/C | ABHISHREE LOGISTICS & SERVICES | 598 | 2022-12-19 | Vertical Artificial Green Wall Work | 1 | 40000 | 0 | 40000 | 7200 | 2023-01-06 16:51 | Installation charges for artificial Green Wall/Column. | 100 |  | 98377 | 2023-02-27 | 512965.7 | 2023-02-27 19:29 | -472965.7 | ABHISHREE LOGISTICS & SERVICES
Supply Vertical Green Wall | N/C | N/C | ABHISHREE LOGISTICS & SERVICES | 598 | 2022-12-19 | Vertical Artificial Green Wall Work | 2012.62 | 235 | 0 | 472965.7 | 85133.82 | 2023-01-06 16:51 | Material Charges for Artificial Green wall clading on bridge column as per drawing at Veer pasalkar chowk Vadgaon Flayover.Hilton sheet Adhesive,all scaffolding & other required stagging work to be done by contractor. | 100 |  | 98377 | 2023-02-27 | 512965.7 | 2023-02-27 19:29 | -40000 | ABHISHREE LOGISTICS & SERVICES
Incentive | N/C | N/C | SWAPNIL SUBHASH ERANDE | 600 | 2022-12-21 | Staff Insentive | 1 | 61500 | 0 | 61500 | 0 | 2022-12-21 | Staff incentive for Ganga Altus D Bldg Standard work order.(Dushant-12500/-,Aditya-10500,Riya -15000,Swapnil-23500) | 100 |  | 97476 | 2022-12-21 | 61500 | 2022-12-23 17:30 | 0 | SWAPNIL SUBHASH ERANDE
Insurance Renewal | N/C | N/C | ICICI LOMBARD GIC LTD | 601 | 2022-12-22 | Vehicle Insurance Renewal | 1 | 37209 | 0 | 37209 | 6697.62 | 2022-12-23 | Charges for Insurance renewal work for Camry Hybrid -MH 12 NP-5342 For the year of 2022 to 2023 (28th Dec 2022 to 27th Dec 2023). | 100 |  | 97492 | 2022-12-23 | 37209 | 2022-12-23 13:12 | 0 | ICICI LOMBARD GIC LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2024-06-05 | Photocopy Machine Rental Charges for month of APR-2024 | 100 |  | 108063 | 2024-06-05 | 36000 | 2024-06-08 15:50 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2024-06-05 | Photocopy Machine Rental Charges for Month of MAY-2024 | 100 |  | 108063 | 2024-06-05 | 36000 | 2024-06-08 15:50 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 10116.129 | 0.31 | 0 | 3136 | 564.48 | 2023-08-04 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 101020 | 2023-08-04 | 21136 | 2023-08-07 12:27 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-08-04 | Photocopy Machine Rental Charges for the month of JULY-2023 | 100 |  | 101020 | 2023-08-04 | 21136 | 2023-08-07 12:27 | -3136 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 2735.4839 | 0.31 | 0 | 848 | 152.64 | 2023-06-05 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 99907 | 2023-06-05 | 18848 | 2023-06-06 14:19 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-06-05 | Photocopy Machine Rental Charges for the month of MAY-2023 | 100 |  | 99907 | 2023-06-05 | 18848 | 2023-06-06 14:19 | -848 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 20583.871 | 0.31 | 0 | 6381 | 1148.58 | 2023-09-13 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 101830 | 2023-09-13 | 24381 | 2023-09-13 17:14 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-09-13 | Photocopy Machine Rental Charges for the month of MARCH-2023 | 100 |  | 101830 | 2023-09-13 | 24381 | 2023-09-13 17:14 | -6381 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-09-04 | Photocopy Machine rental charges for the month of AUG-2023 | 100 |  | 101631 | 2023-09-04 | 18165 | 2023-09-12 12:49 | -165 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 532.2581 | 0.31 | 0 | 165 | 29.7 | 2023-09-04 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 101631 | 2023-09-04 | 18165 | 2023-09-12 12:49 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-07-05 | Photocopy Machine Rental Charges for the month of JUNE-2023 | 100 |  | 100503 | 2023-07-05 | 18000 | 2023-07-11 12:48 | 0 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2024-01-05 | Photocopy Machine Rental Charges for month of DEC-2023 | 100 |  | 104345 | 2024-01-05 | 18000 | 2024-01-10 12:26 | 0 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-11-29 | Photocopy Machine Rental Charges for month of OCT-2023 | 100 |  | 103524 | 2023-11-29 | 18000 | 2023-12-19 10:49 | 0 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 535.4839 | 0.31 | 0 | 166 | 29.88 | 2023-12-04 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 103677 | 2023-12-04 | 18166 | 2023-12-08 10:56 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-12-04 | Photocopy Machine Rental Charges for month of NOV-2023 | 100 |  | 103677 | 2023-12-04 | 18166 | 2023-12-08 10:56 | -166 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 17967.7419 | 0.31 | 0 | 5570 | 1002.6 | 2024-02-07 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 105137 | 2024-02-07 | 23570 | 2024-02-07 19:03 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2024-02-07 | Photocopy Machine Rental Charges for month of JAN-2024 | 100 |  | 105137 | 2024-02-07 | 23570 | 2024-02-07 19:03 | -5570 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-10-20 | Photocopy Machine rental charges for the month of SEP-2023 | 100 |  | 102867 | 2023-10-20 | 19870 | 2023-11-06 16:14 | -1870 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 6032.2581 | 0.31 | 0 | 1870 | 336.6 | 2023-10-20 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 102867 | 2023-10-20 | 19870 | 2023-11-06 16:14 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2024-03-05 | Photocopy Machine Rental Charges for month of FEB-2024 | 100 | FOR THE MONTH OF FEB 2024 | 105775 | 2024-03-05 | 19530 | 2024-03-05 18:04 | -1530 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 0.085 | 18000 | 0 | 1530 | 275.4 | 2024-03-05 | Photocopy Machine Rental Charges for month of MAR-2024 | 100 | FOR THE MONTH OF MARCH 2024 | 105775 | 2024-03-05 | 19530 | 2024-03-05 18:04 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 0.915 | 18000 | 0 | 16470 | 2964.6 | 2024-04-04 | Photocopy Machine Rental Charges for month of MAR-2024 | 100 |  | 106466 | 2024-04-04 | 19096 | 2024-04-04 16:31 | -2626 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 8470.9677 | 0.31 | 0 | 2626 | 472.68 | 2024-04-04 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 106466 | 2024-04-04 | 19096 | 2024-04-04 16:31 | -16470 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2024-07-04 | Photocopy Machine Rental Charges for Month of JUNE-2024 | 100 |  | 108793 | 2024-07-04 | 25119 | 2024-07-15 15:06 | -7119 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 22964.5161 | 0.31 | 0 | 7119 | 1281.42 | 2024-07-04 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 108793 | 2024-07-04 | 25119 | 2024-07-15 15:06 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2024-08-05 | Photocopy Machine Rental Charges for Month of JULY-2024 | 100 |  | 109536 | 2024-08-05 | 22750 | 2024-08-05 17:37 | -4750 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 0.2639 | 18000 | -0.2 | 4750.2 | 855 | 2024-08-05 |  | 100 |  | 109536 | 2024-08-05 | 22750 | 2024-08-05 17:37 | -17999.8 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-02-06 | Photocopy Machine Rental Charges for the month of JAN-2023 | 100 |  | 98074 | 2023-02-06 | 18000 | 2023-02-09 11:33 | 0 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-01-17 | Photocopy Machine Rental Charges for the month of OCT-2022 | 100 |  | 97822 | 2023-01-17 | 18122 | 2023-01-17 12:51 | -122 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 393.5484 | 0.31 | 0 | 122 | 21.96 | 2023-01-17 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 97822 | 2023-01-17 | 18122 | 2023-01-17 12:51 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-01-17 | Photocopy Machine Rental Charges for the month of DEC-2022 | 100 |  | 97824 | 2023-01-17 | 18000 | 2023-01-17 12:51 | 0 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-01-17 | Photocopy Machine Rental Charges for the month of NOV-2022 | 100 |  | 97825 | 2023-01-17 | 19552 | 2023-01-17 12:52 | -1552 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 5006.4516 | 0.31 | 0 | 1552 | 279.36 | 2023-01-17 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 97825 | 2023-01-17 | 19552 | 2023-01-17 12:52 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-03-03 | Photocopy Machine Rental Charges for the month of FEB-2023 | 100 |  | 98473 | 2023-03-03 | 18000 | 2023-03-03 16:53 | 0 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Rental Charges. | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 1 | 18000 | 0 | 18000 | 3240 | 2023-05-03 | Photocopy Machine Rental Charges for the month of APRIL-2023 | 100 |  | 99395 | 2023-05-03 | 24761 | 2023-05-10 13:13 | -6761 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
Xerox Printout | N/C | N/C | SHARP BUSINESS SYSTEMS INDIA PVT LTD | 602 | 2022-12-22 | Photocopy-Xerox Machine Rental Charges. | 21809.6774 | 0.31 | 0 | 6761 | 1216.98 | 2023-05-03 | Chasrges to Extra Photocopy print above 40000 Nos. From Oct-2022 to Sep-2023 (Per Month 10000 Print Avarage) | 100 |  | 99395 | 2023-05-03 | 24761 | 2023-05-10 13:13 | -18000 | SHARP BUSINESS SYSTEMS INDIA PVT LTD
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 0.3661 | 500000 | -3 | 36610 | 6589.26 | 2023-05-09 | FEB 2023 | 20 |  | 99546 | 2023-05-09 | 36607 | 2023-05-10 12:16 | 3 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 1.0989 | 500000 | 0 | 109890 | 19780.2 | 2023-05-09 | JAN 2023 | 20 |  | 99574 | 2023-05-10 | 180620 | 2023-05-10 12:16 | -70730 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 0.6051 | 500000 | 0 | 60510 | 10891.8 | 2023-05-09 | FEB 2023 | 20 |  | 99574 | 2023-05-10 | 180620 | 2023-05-10 12:16 | -120110 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 0.1022 | 500000 | 0 | 10220 | 1839.6 | 2023-05-09 | DEC 2022 | 20 |  | 99574 | 2023-05-10 | 180620 | 2023-05-10 12:16 | -170400 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 4.0288 | 500000 | 1 | 402880 | 72518.58 | 2023-05-09 | FEB 2023 | 20 |  | 99575 | 2023-05-10 | 402881 | 2023-05-10 12:16 | -1 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 0.2475 | 500000 | -2 | 24750 | 4454.64 | 2023-04-29 | MARCH 2023 | 20 |  | 99336 | 2023-04-29 | 24748 | 2023-04-29 11:38 | 2 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 1.0026 | 500000 | -1 | 100260 | 18046.62 | 2023-04-29 | MARCH 2023 | 20 |  | 99337 | 2023-04-29 | 100259 | 2023-04-29 11:38 | 1 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 1.1792 | 500000 | 0 | 117920 | 21225.6 | 2023-03-24 | MARCH 2023 | 20 | BILL NO. 4700217256 | 98992 | 2023-03-24 | 117920 | 2023-04-05 19:43 | 0 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 0.9824 | 500000 | 0 | 98240 | 17683.2 | 2023-03-24 | MARCH 2023 | 20 | BILL PERIOD 03/01/2023- 04/02/2023 | 98993 | 2023-03-24 | 98240 | 2023-04-05 19:43 | 0 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 1.2875 | 500000 | 0 | 128750 | 23175 | 2023-03-24 | MARCH 2023 | 20 | BILL PERIOD 02/01/2023-03/02/2023 | 98994 | 2023-03-24 | 128750 | 2023-04-05 19:43 | 0 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 0.2587 | 500000 | 0 | 25870 | 4656.6 | 2023-03-24 | MARCH 2023 | 20 |  | 98995 | 2023-03-24 | 25870 | 2023-04-05 19:43 | 0 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 603 | 2022-12-22 | ONLINE / DIGITAL Social / Digital Activity | 3.9011 | 500000 | -3 | 390110 | 70219.26 | 2023-02-09 | JAN 2023 | 20 |  | 98111 | 2023-02-09 | 390107 | 2023-02-10 15:22 | 3 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
Advertisement in Magazine | N/C | N/C | ERA FAME MEDIA GROUP | 605 | 2023-01-02 | ADVERTISEMENT Advt Release | 1 | 52000 | 0 | 52000 | 2600 | 2023-01-10 | CONSTRUCTION TIMES 4 PAGES ADVERTORIAL WITH ATUL SIR PHOO ON COVER PAGE TOPIC ON REAL RICH COST RS. 52000 + 5% TAX | 100 |  | 97740 | 2023-01-10 | 52000 | 2023-01-11 10:38 | 0 | ERA FAME MEDIA GROUP
Advertisement Release- | N/C | N/C | SAKAL MEDIA PRIVATE LIMITED | 607 | 2023-01-03 | ADVERTISEMENT Advt Release | 1 | 350000 | 0 | 350000 | 17500 | 2023-03-25 | SAKAL MEDIA GROUP- 91ST ANNIVERSARY CELEBRATING. DISPLAY COLOUR ADVT.IN sakal property today - back page - pune + pcmc edition half page cost rs. 350000/- + 5% gst publish date as 07th jan. 2023 | 100 |  | 99166 | 2023-03-25 | 350000 | 2023-04-13 17:00 | 0 | SAKAL MEDIA PRIVATE LIMITED
Advertisement Release- | N/C | N/C | SHREE AMBIKA PRINTERS & PUBLICATIONS | 608 | 2023-01-03 | ADVERTISEMENT Advt Release | 1 | 90000 | 0 | 90000 | 4500 | 2023-03-11 | PUNYANAGARI GROUP- PUBLICATION ANNIVERSARY WITH SILVER JUBILEE CELEBRATING DISPLAY COLOUR ADVERTIEMENT FULL PAGE PUNE EDITION COST RS. 90000/-+ 5% TAX | 100 | publish dtd. 14/01/2023 | 98632 | 2023-03-11 | 90000 | 2023-03-11 18:58 | 0 | SHREE AMBIKA PRINTERS & PUBLICATIONS
Waterproofing work. | N/C | N/C | AQUARIUS WATERPROOFING | 610 | 2023-01-05 | HO Window Frame Joint W/P | 1 | 12000 | 0 | 12000 | 2160 | 2023-01-27 | Charges for Window frame joint treatment by using Neoproof rubber + GT Tape and Window sill level wall top treatment by neoproof roof coat + 50gsm Cloth. | 100 |  | 97944 | 2023-01-28 | 12000 | 2023-03-30 12:41 | 0 | AQUARIUS WATERPROOFING
Advertisement Release- | N/C | N/C | POOJA COMMUNICATIONS (INDIA) PVT LTD | 611 | 2023-01-05 | ADVERTISEMENT Advt Release | 1 | 114400 | 0 | 114400 | 5720 | 2023-01-17 | MAHARASHTRA TIMES ANNIVERSARY ISSUE - MT PUNE ANY RHP FULL PAGE COLOUR DISPLAY ADVT. SIZE AS 32.9 SQ CM. (W X 52.5 SQ CM.COST RS. 130000/- + TAX (60 DAYS CREDIT PERIOD AS FROM PUBLISH ADVERTIEMENT IN NEWS PAPER) | 100 | maharashtra times full page colour dtd. 07/01/2023 | 97836 | 2023-01-17 | 114400 | 2023-01-21 10:38 | 0 | POOJA COMMUNICATIONS (INDIA) PVT LTD
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-704-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-706-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-105-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-106-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-307-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-601-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-803-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1001-3BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-904-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-303-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-806-3BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-207-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-607-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-205-3BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-405-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-605-3BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-304-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-403-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-506-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-603-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-807-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-906-3BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1007-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-401-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-708-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-802-3BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-908-2BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1003-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-104-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-107-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-308-2BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-208-2BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-408-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-502-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1102-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1301-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1303-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1304-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1307-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1401-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1408-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1207-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1305-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1406-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1201-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1402-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1203-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1204-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1403-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1405-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1202-2BHK(Near Refuse Area) Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1206-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1208-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1302-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1404-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1205-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1306-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1407-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1308-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2024-06-14 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 108374 | 2024-06-17 | 19200 | 1900-01-01 | -18400 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-102-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-406-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-703-2BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-804-2BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1004-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-606-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-504-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1005-3BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1106-3BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1108-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-206-3BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-901-3BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-903-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1103-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-108-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-306-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-508-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-608-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-902-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1101-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-602-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-801-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1002-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-402-3BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-404-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-907-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1006-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-604-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-705-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-707-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-905-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1008-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-407-2BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-702-2BHK(Near Refuse Area) Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-1104-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-204-2BHK Toilet Ventilator | 0.8 | 500 | 0 | 400 | 72 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -57200 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-503-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-201-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-305-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-101-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-202-2BHK(Near Refuse Area) Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-203-2BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-805-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-301-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-501-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 612 | 2023-01-21 | D-701-3BHK Toilet Ventilator | 1.6 | 500 | 0 | 800 | 144 | 2023-12-08 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103807 | 2023-12-11 | 57600 | 2024-01-02 11:44 | -56800 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-901-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1003-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-201-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-502-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-603-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-605-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-904-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-206-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-406-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-405-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-701-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-902-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1206-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1205-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1405-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1204-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1203-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1307-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1208-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1304-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1402-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1201-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1202-2BHK(Near Refuse Area) Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1303-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1305-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1407-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1203-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1208-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1301-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1302-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1306-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1204-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1305-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1307-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1401-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1404-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1403-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1408-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1207-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1308-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1402-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1407-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1206-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1408-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1401-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1403-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1404-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1308-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1405-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1205-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1207-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1406-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1406-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1304-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1306-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1302-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1301-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1303-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2024-06-14 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -125600 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1201-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1202-2BHK(Near Refuse Area) Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2024-06-14 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 108373 | 2024-06-17 | 129600 | 1900-01-01 | -128200 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-906-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1004-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-301-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-505-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-804-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-803-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-205-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-208-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-501-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-106-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-107-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-708-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-305-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-306-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-507-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-908-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-202-2BHK(Near Refuse Area) Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-303-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-404-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-604-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-703-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-401-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-704-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1001-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-105-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1005-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-203-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-302-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-304-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-403-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-504-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1002-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-508-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-801-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-802-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-608-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-807-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-808-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-101-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-602-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-806-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-905-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-407-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-606-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-907-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-104-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-308-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-506-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-601-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-307-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-707-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1006-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-108-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-204-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-402-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-503-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-705-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-903-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1007-2BHK Toilet Ventilator | 1 | 700 | 0 | 700 | 126 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -106400 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-207-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-408-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-607-2BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-702-2BHK(Near Refuse Area) Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-805-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-706-3BHK Toilet Ventilator | 2 | 700 | 0 | 1400 | 252 | 2023-12-12 | Material supply charges and Rate Diff. for Toilet Ventilator work for D-Bldg Specification-3.5mm clear glass,Ivory Powder coating,Std SS Finish hardware,10mm square bar & GI Sheet-Door frame 18 SWG (1.2mm) thick & shutter frame 20 SWG 1mm thick. | 100 |  | 104018 | 2023-12-18 | 107100 | 2024-01-02 11:45 | -105700 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-706-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-906-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-607-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-806-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-707-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-801-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-802-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1001-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1002-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1003-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-708-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-606-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-905-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-907-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1004-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-705-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-903-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-805-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-807-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1006-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-908-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-803-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-904-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-608-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-603-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-605-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-704-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1005-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-1007-2BHK Toilet Ventilator | 1 | 2000 | 0 | 2000 | 360 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -144000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-901-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-902-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-804-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-604-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-703-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-701-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-702-2BHK(Near Refuse Area) Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-808-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-20 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102917 | 2023-10-23 | 146000 | 2023-11-07 13:58 | -142000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-306-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-601-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-207-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-208-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-301-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-406-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-501-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-101-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-202-2BHK(Near Refuse Area) Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-303-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-308-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-508-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-602-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-506-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-401-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-408-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-104-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-201-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-405-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-203-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-403-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-502-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-504-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-205-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-503-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-302-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-305-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-404-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-407-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-304-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-204-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-402-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-505-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-206-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-307-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-507-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-107-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-105-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-106-3BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 613 | 2023-01-21 | D-108-2BHK Toilet Ventilator | 2 | 2000 | 0 | 4000 | 720 | 2023-10-10 | Material Supply charges for Toilet Ventilator work for D-Building. | 100 |  | 102492 | 2023-10-11 | 160000 | 2023-11-01 14:25 | -156000 | SAI ENGINEERING WORKS
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1205 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.403 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.605 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.805 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.803 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.908 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1001 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1002 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.206 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.407 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.408 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.701 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.808 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.301 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.608 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1101 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.806 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.905 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1006 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.306 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1004 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.405 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.706 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.904 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.906 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1203 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.303 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.406 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.705 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1206 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.207 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.208 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.901 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.902 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.903 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1007 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.604 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.606 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1008 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1107 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1208 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.401 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1201 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1202 Chemical Waterproofing Before Brickbat | 27.472 | 22 | 0 | 604.384 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24987.756 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1602 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -23984.204 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1604 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24279.356 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1605 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -23984.204 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.708 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24279.356 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1102 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -23984.204 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1608 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24279.356 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1003 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24279.356 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1603 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24279.356 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1601 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -23984.204 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1005 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -23984.204 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.704 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24279.356 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1103 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24279.356 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.707 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24279.356 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1106 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -23984.204 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1607 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24279.356 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.302 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -23984.204 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.703 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24279.356 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.702 Chemical Waterproofing Before Brickbat | 27.472 | 22 | 0 | 604.384 | 0 | 2023-10-16 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102685 | 2023-10-17 | 25592.14 | 2023-11-06 16:12 | -24987.756 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.103 Chemical Waterproofing Before Brickbat | 57.2727 | 22 | 0 | 1259.9994 | 0 | 2023-10-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102551 | 2023-10-12 | 2520 | 2023-11-24 10:35 | -1260.0006 | PAWAR SHIVAPPA TARANAIK
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.102 Chemical Waterproofing Before Brickbat | 57.2727 | 22 | 0 | 1259.9994 | 0 | 2023-10-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102551 | 2023-10-12 | 2520 | 2023-11-24 10:35 | -1260.0006 | PAWAR SHIVAPPA TARANAIK
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2104 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2101 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30224.824 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2103 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2204 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2201 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30224.824 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2306 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30224.824 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2307 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2304 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2205 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30224.824 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2208 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2203 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2207 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2302 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30224.824 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2105 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30224.824 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2106 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30224.824 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2301 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30224.824 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2108 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2303 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2305 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30224.824 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2308 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2206 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30224.824 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2107 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-04-27 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 107139 | 2024-04-29 | 31832.76 | 2024-06-03 12:42 | -30519.976 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1706 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-08 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 106713 | 2024-04-08 | 3215.88 | 2024-05-21 12:29 | -1607.944 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1606 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-04-08 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 106713 | 2024-04-08 | 3215.88 | 2024-05-21 12:29 | -1607.944 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1404 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27599.256 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1308 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27599.256 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1505 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27304.104 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1307 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27599.256 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1507 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27599.256 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1303 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27599.256 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1503 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27599.256 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1504 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27599.256 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1506 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27304.104 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1406 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27304.104 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1402 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27304.104 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1301 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27304.104 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1302 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27304.104 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1401 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27304.104 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1408 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27599.256 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1403 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27599.256 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1407 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27599.256 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1501 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27304.104 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1508 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27599.256 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1502 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-08-03 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101000 | 2023-08-04 | 28912.04 | 2023-09-04 11:40 | -27304.104 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1803 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-11-07 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 103386 | 2023-11-08 | 10370.1 | 2023-12-02 12:18 | -9057.316 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1805 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-11-07 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 103386 | 2023-11-08 | 10370.1 | 2023-12-02 12:18 | -8762.164 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1808 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-11-07 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 103386 | 2023-11-08 | 10370.1 | 2023-12-02 12:18 | -9057.316 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1802 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-11-07 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 103386 | 2023-11-08 | 10370.1 | 2023-12-02 12:18 | -8762.164 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1806 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-11-07 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 103386 | 2023-11-08 | 10370.1 | 2023-12-02 12:18 | -8762.164 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1807 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-11-07 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 103386 | 2023-11-08 | 10370.1 | 2023-12-02 12:18 | -9057.316 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1801 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-11-07 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 103386 | 2023-11-08 | 10370.1 | 2023-12-02 12:18 | -8762.164 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1906 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-05 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104366 | 2024-01-08 | 15524.78 | 2024-01-23 14:22 | -13916.844 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.004 Chemical Waterproofing Before Brickbat | 114.96 | 22 | 0 | 2529.12 | 0 | 2024-01-05 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104366 | 2024-01-08 | 15524.78 | 2024-01-23 14:22 | -12995.66 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1902 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-05 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104366 | 2024-01-08 | 15524.78 | 2024-01-23 14:22 | -13916.844 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1903 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-05 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104366 | 2024-01-08 | 15524.78 | 2024-01-23 14:22 | -14211.996 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1905 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-05 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104366 | 2024-01-08 | 15524.78 | 2024-01-23 14:22 | -13916.844 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1907 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-05 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104366 | 2024-01-08 | 15524.78 | 2024-01-23 14:22 | -14211.996 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1804 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-05 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104366 | 2024-01-08 | 15524.78 | 2024-01-23 14:22 | -14211.996 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1901 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-05 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104366 | 2024-01-08 | 15524.78 | 2024-01-23 14:22 | -13916.844 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1908 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-05 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104366 | 2024-01-08 | 15524.78 | 2024-01-23 14:22 | -14211.996 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1904 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-05 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104366 | 2024-01-08 | 15524.78 | 2024-01-23 14:22 | -14211.996 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1306 Chemical Waterproofing Before Brickbat | 45.68 | 22 | 0 | 1004.96 | 0 | 2023-08-31 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101535 | 2023-08-31 | 5000.37 | 2023-09-01 10:58 | -3995.41 | PAWAR SHIVAPPA TARANAIK
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1405 Chemical Waterproofing Before Brickbat | 45.68 | 22 | 0 | 1004.96 | 0 | 2023-08-31 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101535 | 2023-08-31 | 5000.37 | 2023-09-01 10:58 | -3995.41 | PAWAR SHIVAPPA TARANAIK
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1301 Chemical Waterproofing Before Brickbat | 18.1818 | 22 | 0 | 399.9996 | 0 | 2023-08-31 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101535 | 2023-08-31 | 5000.37 | 2023-09-01 10:58 | -4600.3704 | PAWAR SHIVAPPA TARANAIK
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1302 Chemical Waterproofing Before Brickbat | 18.1818 | 22 | 0 | 399.9996 | 0 | 2023-08-31 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101535 | 2023-08-31 | 5000.37 | 2023-09-01 10:58 | -4600.3704 | PAWAR SHIVAPPA TARANAIK
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1304 Chemical Waterproofing Before Brickbat | 37.295 | 22 | 0 | 820.49 | 0 | 2023-08-31 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101535 | 2023-08-31 | 5000.37 | 2023-09-01 10:58 | -4179.88 | PAWAR SHIVAPPA TARANAIK
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1406 Chemical Waterproofing Before Brickbat | 16.5909 | 22 | 0 | 364.9998 | 0 | 2023-08-31 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101535 | 2023-08-31 | 5000.37 | 2023-09-01 10:58 | -4635.3702 | PAWAR SHIVAPPA TARANAIK
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1305 Chemical Waterproofing Before Brickbat | 45.68 | 22 | 0 | 1004.96 | 0 | 2023-08-31 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 101535 | 2023-08-31 | 5000.37 | 2023-09-01 10:58 | -3995.41 | PAWAR SHIVAPPA TARANAIK
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.003 Chemical Waterproofing Before Brickbat | 114.96 | 22 | 0 | 2529.12 | 0 | 2023-09-23 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102064 | 2023-09-25 | 19111.84 | 2023-11-01 14:25 | -16582.72 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.001 Chemical Waterproofing Before Brickbat | 130.96 | 22 | 0 | 2881.12 | 0 | 2023-09-23 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102064 | 2023-09-25 | 19111.84 | 2023-11-01 14:25 | -16230.72 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.006 Chemical Waterproofing Before Brickbat | 130.96 | 22 | 0 | 2881.12 | 0 | 2023-09-23 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102064 | 2023-09-25 | 19111.84 | 2023-11-01 14:25 | -16230.72 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.007 Chemical Waterproofing Before Brickbat | 114.96 | 22 | 0 | 2529.12 | 0 | 2023-09-23 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102064 | 2023-09-25 | 19111.84 | 2023-11-01 14:25 | -16582.72 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.002 Chemical Waterproofing Before Brickbat | 130.96 | 22 | 0 | 2881.12 | 0 | 2023-09-23 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102064 | 2023-09-25 | 19111.84 | 2023-11-01 14:25 | -16230.72 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.008 Chemical Waterproofing Before Brickbat | 114.96 | 22 | 0 | 2529.12 | 0 | 2023-09-23 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102064 | 2023-09-25 | 19111.84 | 2023-11-01 14:25 | -16582.72 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.005 Chemical Waterproofing Before Brickbat | 130.96 | 22 | 0 | 2881.12 | 0 | 2023-09-23 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 102064 | 2023-09-25 | 19111.84 | 2023-11-01 14:25 | -16230.72 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1705 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16520.764 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2005 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16520.764 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2001 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16520.764 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2003 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16815.916 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1105 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16520.764 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1707 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16815.916 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2002 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16520.764 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.2004 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16815.916 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1703 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16815.916 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1704 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16815.916 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1702 Chemical Waterproofing Before Brickbat | 27.472 | 22 | 0 | 604.384 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -17524.316 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1701 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16520.764 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1708 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-12-15 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 104043 | 2023-12-18 | 18128.7 | 2024-01-16 14:56 | -16815.916 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.106 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.107 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.108 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.307 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.507 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.508 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.802 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1204 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.501 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.607 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.204 Chemical Waterproofing Before Brickbat | 53.7048 | 22 | 0 | 1181.5056 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113744.2044 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.305 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.804 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.104 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.404 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.907 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.801 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.402 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.503 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.505 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.201 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.601 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.602 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.205 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.304 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.506 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.603 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.807 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1108 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1207 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.105 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.308 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.502 Chemical Waterproofing Before Brickbat | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113317.774 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.1104 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.204 Chemical Waterproofing Before Brickbat | 5.9672 | 22 | 0 | 131.2784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -114794.4316 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.203 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | AJAY KUMAR GUPTA | 614 | 2023-01-24 | D-Flat.No.504 Chemical Waterproofing Before Brickbat | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-05-11 | Material and Labour charges for Chemical Waterproofing work Before Brickbat for D-Bldg Flats. | 100 |  | 99605 | 2023-05-12 | 114925.71 | 2023-05-29 13:09 | -113612.926 | AJAY KUMAR GUPTA
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 615 | 2023-02-06 | LG Floor Toilet Ventilator Work | 1 | 2000 | 0 | 2000 | 360 | 2024-01-15 17:00 | Material Supply Charges for Toilet Ventilator for F Building | 100 |  | 104674 | 2024-01-22 | 16000 | 2024-02-19 15:21 | -14000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 615 | 2023-02-06 | 2nd Floor Toilet Ventilator Work | 7 | 2000 | 0 | 14000 | 2520 | 2024-01-15 17:00 | Material Supply Charges for Toilet Ventilator for F Building | 100 |  | 104674 | 2024-01-22 | 16000 | 2024-02-19 15:21 | -2000 | SAI ENGINEERING WORKS
Toilet Ventilator (M) | N/C | N/C | SAI ENGINEERING WORKS | 615 | 2023-02-06 | 1st Floor Toilet Ventilator Work | 11 | 2000 | 0 | 22000 | 3960 | 2023-12-05 10:50 | Material Supply Charges for Toilet Ventilator for F Building | 100 |  | 103797 | 2023-12-11 | 22000 | 2024-02-28 11:08 | 0 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 616 | 2023-02-06 | 1st Floor Toilet Ventilator Work | 9 | 500 | 0 | 4500 | 810 | 2023-12-05 10:50 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 103798 | 2023-12-11 | 4500 | 2024-02-28 11:08 | 0 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 616 | 2023-02-06 | LG Floor Toilet Ventilator Work | 1 | 500 | 0 | 500 | 90 | 2024-01-15 17:03 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 104675 | 2024-01-22 | 4000 | 2024-02-20 12:21 | -3500 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 616 | 2023-02-06 | 1st Floor Toilet Ventilator Work | 2 | 500 | 0 | 1000 | 180 | 2024-01-15 17:03 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 104675 | 2024-01-22 | 4000 | 2024-02-20 12:21 | -3000 | SAI ENGINEERING WORKS
Toilet Ventilator (L) | N/C | N/C | SAI ENGINEERING WORKS | 616 | 2023-02-06 | 2nd Floor Toilet Ventilator Work | 5 | 500 | 0 | 2500 | 450 | 2024-01-15 17:03 | Labour charges for fixing of Toilet Ventilator with Window Frame with shutter up one side fan and Glass, all glass lower work will be done on site, Rate includes Transport,fitting,loading,unloading. | 100 |  | 104675 | 2024-01-22 | 4000 | 2024-02-20 12:21 | -1500 | SAI ENGINEERING WORKS
M.S. Jali- DPo | N/C | N/C | IZHAR MANSOOR SHAIKH | 618 | 2023-02-06 | Safety Jali making for D, E & F Bldgs. | 145.81 | 10 | 0 | 1458.1 | 0 | 2024-08-02 | Labour Charges for MS Jali (40 inch x 75 inch) Making work for F-Bldg. | 100 |  | 109584 | 2024-08-05 | 1458.1 | 1900-01-01 | 0 | SURESH RANGNATH SHITOLE
M.S. Jali- DPo | N/C | N/C | IZHAR MANSOOR SHAIKH | 618 | 2023-02-06 | Safety Jali making for D, E & F Bldgs. | 833.2 | 10 | 0 | 8332 | 0 | 2023-03-06 | Labour Charges for MS Jali (40 inch x 75 inch) Making work for D-Bldg. | 100 |  | 98542 | 2023-03-06 | 15200 | 2023-03-16 11:39 | -6868 | IZHAR MANSOOR SHAIKH
M.S. Jali- DPo | N/C | N/C | IZHAR MANSOOR SHAIKH | 618 | 2023-02-06 | Safety Jali making for D, E & F Bldgs. | 686.8 | 10 | 0 | 6868 | 0 | 2023-03-06 | Labour Charges for MS Jali (40 inch x 75 inch) Making work for E-Bldg. | 100 |  | 98542 | 2023-03-06 | 15200 | 2023-03-16 11:39 | -8332 | IZHAR MANSOOR SHAIKH
M.S. Jali- DPo | N/C | N/C | IZHAR MANSOOR SHAIKH | 618 | 2023-02-06 | Safety Jali making for D, E & F Bldgs. | 766 | 10 | 0 | 7660 | 0 | 2023-10-06 | Labour Charges for MS Jali (40 inch x 75 inch) Making work for E-Bldg. | 100 |  | 102403 | 2023-10-07 | 7660 | 2023-10-28 11:56 | 0 | SURESH RANGNATH SHITOLE
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1103-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-202-2BHK(Near Refuse Area) Alu Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-205-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2202-2BHK(Near Refuse Area) Alu Sliding Window | 17.768 | 74 | 0 | 1314.832 | 236.66 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1138620.808 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2305-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2402-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-504-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-706-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-805-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-906-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-908-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1002-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-106-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1204-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1205-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1403-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1406-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1605-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1606-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1807-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-003-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-101-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-103-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1206-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1208-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1307-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1307-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1502-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1601-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2005-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2008-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-202-2BHK(Near Refuse Area) Alu Sliding Window | 17.768 | 74 | 0 | 1314.832 | 236.66 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1138620.808 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2208-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2407-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2408-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-602-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-802-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1006-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1006-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1105-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1107-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-001-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1005-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1007-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1803-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2001-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-204-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2102-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2201-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2304-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-507-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-705-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-804-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-808-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-907-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1001-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1002-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1003-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-105-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1203-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1404-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1404-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1603-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1604-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1503-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1506-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1703-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-404-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-506-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-506-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-605-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-704-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-706-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-805-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1001-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1004-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1005-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-108-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1202-2BHK(Near Refuse Area) Alu Sliding Window | 17.768 | 74 | 0 | 1314.832 | 236.66 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1138620.808 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1205-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1403-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1405-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-608-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-002-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1008-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1408-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1902-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1406-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1805-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1807-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1808-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2004-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2006-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2007-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2008-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2206-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2206-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2406-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1904-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2205-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2302-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2304-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-305-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-403-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-507-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-707-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-806-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1902-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2001-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2003-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2403-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2405-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-302-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-303-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-404-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-406-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-503-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-505-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1201-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1206-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1208-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1401-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1502-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1507-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1702-2BHK(Near Refuse Area) Alu Sliding Window | 17.768 | 74 | 0 | 1314.832 | 236.66 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1138620.808 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1801-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-203-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2104-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2203-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1707-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1907-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-208-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2107-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2306-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2308-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2401-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-301-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-407-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-501-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-502-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-503-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-701-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-901-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-105-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1401-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1601-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1603-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1608-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1702-2BHK(Near Refuse Area) Alu Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-604-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-606-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-606-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-905-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-907-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1101-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1105-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2203-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2302-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2405-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-705-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-806-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-905-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-001-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1008-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1102-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1305-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1503-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1505-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1705-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1705-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1906-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1906-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-104-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1107-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1201-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1302-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1408-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1507-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1608-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1801-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1803-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1808-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2003-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1908-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2106-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-501-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-701-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-703-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-703-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-902-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1004-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-107-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-201-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-206-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2102-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2104-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2403-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-304-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-405-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-505-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-604-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-707-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-808-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2408-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-307-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-308-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-406-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-508-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-801-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1202-2BHK(Near Refuse Area) Alu Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1204-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1605-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1607-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1804-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1805-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1806-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2007-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2205-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2301-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-308-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-002-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-101-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1308-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1602-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1701-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1701-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-401-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-603-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-708-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-802-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-803-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-804-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1106-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1207-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1501-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1901-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2101-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2204-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2402-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-407-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-607-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-807-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-005-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-006-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-007-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-008-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1302-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1303-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1305-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1504-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1504-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1708-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1908-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2002-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-203-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2101-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2103-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2301-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-304-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-306-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-402-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1003-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-107-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2202-2BHK(Near Refuse Area) Alu Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2303-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2305-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2404-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-303-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-605-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2005-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2006-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-201-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2208-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2406-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-306-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-307-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-401-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-508-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-603-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-801-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2401-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-408-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-502-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-702-2BHK(Near Refuse Area) Alu Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-704-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-902-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-903-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-904-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-108-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1203-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1402-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1405-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1604-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1606-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1804-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1806-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2207-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2207-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2407-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-402-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-403-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-601-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-601-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-602-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-803-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-003-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-008-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-104-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1101-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1108-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1301-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1308-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1402-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1602-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1903-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1706-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1707-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1907-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-205-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2105-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2105-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2306-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2308-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-106-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-903-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-904-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-207-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2106-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2108-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2108-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2307-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2307-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-301-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-302-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-408-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-702-2BHK(Near Refuse Area) Alu Sliding Window | 17.768 | 74 | 0 | 1314.832 | 236.66 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1138620.808 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-901-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1505-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1704-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-005-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-006-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1104-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1104-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1303-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1306-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1506-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1904-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1905-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-207-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1007-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-103-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1108-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1207-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1306-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1407-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1508-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1607-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1708-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1802-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1802-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2002-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2004-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-204-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2103-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2303-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2404-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-305-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-405-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-504-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-607-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-708-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-004-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1106-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1301-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1407-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1501-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1508-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1703-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1901-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1903-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1103-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1304-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1304-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1704-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1706-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1905-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-206-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1133679.272 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-208-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2107-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-2201-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-608-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-807-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-906-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-908-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-004-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-007-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D Building Bed room | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1135764.728 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 619 | 2023-02-09 | D-1102-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-28 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for D-Building Kitchen Window. | 100 |  | 108677 | 2024-07-01 | 1139935.64 | 2024-08-05 13:59 | -1139433.624 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2408-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1704-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1408-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-202-2BHK(Near Refuse Area) Alu Sliding Window | 17.768 | 294 | 0 | 5223.792 | 940.28 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1230974.418 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2301-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2302-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1901-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1901-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1902-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2007-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2101-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2207-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2301-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-001-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-002-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1404-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1606-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1502-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1702-2BHK(Near Refuse Area) Alu Sliding Window | 17.768 | 294 | 0 | 5223.792 | 940.28 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1230974.418 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2105-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2107-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2304-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2306-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2405-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2407-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-007-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1306-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1307-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1505-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-004-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1402-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1501-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1701-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1202-2BHK(Near Refuse Area) Alu Sliding Window | 17.768 | 294 | 0 | 5223.792 | 940.28 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1230974.418 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1301-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1308-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1602-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1604-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1906-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2003-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2108-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2202-2BHK(Near Refuse Area) Alu Sliding Window | 17.768 | 294 | 0 | 5223.792 | 940.28 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1230974.418 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2404-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1304-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1507-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1508-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1907-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1908-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1703-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1903-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1707-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1801-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2002-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2203-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2403-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-702-2BHK(Near Refuse Area) Alu Sliding Window | 17.768 | 294 | 0 | 5223.792 | 940.28 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1230974.418 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-003-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1601-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1902-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1907-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-006-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1503-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1705-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1904-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2004-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2005-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2105-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2204-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2303-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2404-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-704-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1407-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1605-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1807-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1401-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1302-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1504-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1805-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1905-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2003-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2004-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2406-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2106-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-008-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1305-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2001-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2107-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2202-2BHK(Near Refuse Area) Alu Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2401-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2402-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2403-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2006-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2104-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2203-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2206-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2208-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2307-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2002-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2007-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2207-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2307-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2308-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2405-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2406-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1405-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1903-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2101-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2102-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1406-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1607-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1806-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2008-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2302-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1908-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2201-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2402-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1506-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1706-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1708-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1303-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2104-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2205-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2305-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2407-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1608-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1808-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2008-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2102-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2303-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2304-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-005-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1403-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1603-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1803-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1802-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1804-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2006-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2106-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2306-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2103-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2208-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2408-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1904-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2005-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2205-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2305-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1905-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1906-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2103-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2108-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2206-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2001-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2201-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1211082.066 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2204-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1219454.114 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2308-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-2401-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-28 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 108678 | 2024-07-01 | 1236198.21 | 1900-01-01 | -1234203.714 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1806-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-305-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-505-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1007-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1101-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1302-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1405-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1401-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1506-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1507-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1602-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1707-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-304-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-503-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-504-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-905-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1002-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1108-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1403-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1605-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1706-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1805-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-207-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-306-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1601-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1708-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1802-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-301-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-104-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-105-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-905-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-803-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-902-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1003-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-201-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-401-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-801-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-607-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-103-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-303-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-305-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-704-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-707-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-504-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-506-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1005-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1205-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1206-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-606-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-804-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-001-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-002-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-003-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1006-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1008-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1207-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-404-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-605-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1007-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-202-2BHK(Near Refuse Area) Alu Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-203-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-403-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-406-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1208-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-204-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-205-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-402-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-604-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-602-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-605-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-802-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1204-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1207-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1406-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1407-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-203-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-401-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-402-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-804-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-308-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-508-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-607-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-708-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-807-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-903-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-407-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-506-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-701-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-706-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-908-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-302-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-501-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-507-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-608-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-902-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1404-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1804-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-208-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1003-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1701-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-803-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1301-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-307-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-408-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1304-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1502-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1201-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1203-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1305-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1004-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1608-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1807-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1808-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-404-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-603-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-604-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-805-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1103-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1801-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-705-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-106-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1603-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-901-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-104-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1704-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1001-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1505-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1604-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1606-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-303-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-105-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1208-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1005-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1205-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1408-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1006-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1206-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1501-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-108-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-101-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1107-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1306-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1307-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1308-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1508-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-502-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-703-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1104-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1105-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1106-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1008-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-107-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1102-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1303-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1402-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1703-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1503-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1705-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-204-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-206-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-601-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-801-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-907-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1607-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1702-2BHK(Near Refuse Area) Alu Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1159034.616 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-201-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-806-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-904-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-906-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-606-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-707-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-808-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1504-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1803-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1167406.664 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-205-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-405-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-406-3BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-403-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2023-11-02 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Kitchen Window. | 100 |  | 103259 | 2023-11-04 | 1184150.76 | 1900-01-01 | -1182156.264 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1103-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-306-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-407-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-005-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1001-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-107-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1102-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-004-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1002-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1004-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-501-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-508-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-701-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-703-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1106-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-302-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-006-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-106-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1101-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1202-2BHK(Near Refuse Area) Alu Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1204-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-207-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-308-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-008-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-101-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1105-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1108-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-304-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-503-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-706-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-907-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1104-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-206-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-208-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-408-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-601-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-702-2BHK(Near Refuse Area) Alu Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-108-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-301-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-602-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-908-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-307-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-502-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-507-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-007-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1201-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-808-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1107-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-505-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-705-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-904-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-906-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-806-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-708-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-802-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-1203-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-608-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-405-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-603-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-805-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-807-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-901-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2126500.196 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 620 | 2023-02-09 | D-903-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2023-09-25 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for D-Bldg Bed room Window. | 100 |  | 102096 | 2023-09-26 | 2151616.34 | 2023-10-20 10:57 | -2134872.244 | K K POWER CONTROL WIRES PVT LTD
Fabrication work lumpsum -SOSB | N/C | N/C | R.T.S. STEEL SERVICES | 621 | 2023-02-16 | Labour Camp (One Boat Club Balance work) | 1 | 75000 | 0 | 75000 | 13500 | 2023-03-05 18:38 | Charges for Ganga Altus Labour Rooms MS Structure (12 rooms) removing & Loading in vehicle Wt.- 5390 kg, & Ganga Bhagyoday MS Material collection from all over site and cutting as per vehicle size loading in vehicle and unloading at One Boat club site. | 100 |  | 99419 | 2023-05-04 | 75000 | 2023-05-04 16:34 | 0 | R.T.S. STEEL SERVICES
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-203-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-505-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-607-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1001-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1002-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1008-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-506-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-603-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-604-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1308-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1901-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-108-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1103-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1306-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1307-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2104-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-206-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-903-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-605-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-707-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1402-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1805-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1902-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2203-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2204-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-105-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-202-2BHK(Near Refuse Area) FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1003-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-502-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-601-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-608-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1004-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1101-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1301-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1305-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2001-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-504-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-606-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-308-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-403-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-404-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-706-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-801-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-804-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-304-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-503-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-703-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-901-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-904-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-905-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2205-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2304-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157488.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-602-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-702-2BHK(Near Refuse Area) FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-704-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-806-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2305-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157286.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-505-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-607-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2102-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2006-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -158152.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-305-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1106-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1201-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1207-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1602-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1603-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1604-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1705-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2201-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-605-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-707-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1007-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-106-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1406-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1708-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-207-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2207-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2306-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157286.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-906-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1105-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1304-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1401-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1502-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-201-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2005-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2103-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2005-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -158152.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-307-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-405-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-902-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-007-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2007-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2105-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2007-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -158231.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-302-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-202-2BHK(Near Refuse Area) FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2203-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2204-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2301-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157286.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-401-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-407-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-708-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-802-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-805-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-004-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1607-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1701-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2003-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2006-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1206-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1908-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2004-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2101-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2004-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -158231.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-408-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-705-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-803-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-807-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-204-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-506-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-603-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-604-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-907-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1102-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1303-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1702-2BHK(Near Refuse Area) FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1906-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2206-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2303-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157488.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-402-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-701-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-808-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-908-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-001-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-005-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-108-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1103-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1306-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1307-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2008-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2104-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2008-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -158231.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1108-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1707-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1802-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1904-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1905-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-003-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-008-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1202-2BHK(Near Refuse Area) FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1205-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1203-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1204-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1605-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1606-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1608-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-306-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-103-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-107-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1503-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2106-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2107-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1006-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1107-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1601-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1704-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-104-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1302-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1907-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-205-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2108-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-301-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-406-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-507-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1008-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-501-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-504-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-606-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1101-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-402-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-106-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-906-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1007-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1406-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1708-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-207-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2207-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-208-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1106-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1201-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1207-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1602-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1603-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1604-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1907-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2108-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-304-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-503-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-703-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1006-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1107-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1601-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1704-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1705-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2201-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-901-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-904-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-905-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1408-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1504-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1505-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1508-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1801-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1903-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2002-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-408-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-705-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-803-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-306-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-401-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-407-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-708-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-802-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-805-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1203-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-307-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2406-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2023-10-03 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 102213 | 2023-10-04 | 10530 | 2023-11-06 16:13 | -9112.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2403-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2023-10-03 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 102213 | 2023-10-04 | 10530 | 2023-11-06 16:13 | -9315 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2408-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2023-10-03 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 102213 | 2023-10-04 | 10530 | 2023-11-06 16:13 | -9315 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2402-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2023-10-03 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 102213 | 2023-10-04 | 10530 | 2023-11-06 16:13 | -9112.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2404-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2023-10-03 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 102213 | 2023-10-04 | 10530 | 2023-11-06 16:13 | -9315 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2407-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2023-10-03 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 102213 | 2023-10-04 | 10530 | 2023-11-06 16:13 | -9315 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2401-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2023-10-03 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 102213 | 2023-10-04 | 10530 | 2023-11-06 16:13 | -9112.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2405-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2023-10-03 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 102213 | 2023-10-04 | 10530 | 2023-11-06 16:13 | -9112.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1403-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1405-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1407-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1501-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1803-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1804-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1806-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1807-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-203-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1104-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1208-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1506-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1507-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1703-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1706-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1808-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-206-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2202-2BHK(Near Refuse Area) FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-903-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1408-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1504-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1505-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1508-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1801-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1903-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2002-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-208-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2307-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157488.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2308-2BHK FAS Conduit Work | 0.9 | 1350 | 0 | 1215 | 218.7 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157488.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-303-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-508-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1003-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-105-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1402-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1805-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1902-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-006-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-101-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-102-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1308-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1901-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1004-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1005-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1404-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2208-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2302-3BHK FAS Conduit Work | 0.9 | 1575 | 0 | 1417.5 | 255.16 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157286.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-601-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-608-2BHK FAS Conduit Work | 0.55 | 1350 | 0 | 742.5 | 133.66 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157961.25 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-002-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1001-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1002-3BHK FAS Conduit Work | 0.55 | 1575 | 0 | 866.25 | 155.92 | 2023-07-29 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100894 | 2023-07-29 | 158703.75 | 2023-08-09 12:25 | -157837.5 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-405-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-902-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1108-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-103-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-107-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-303-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-508-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1503-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2106-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2107-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1204-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1605-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1606-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1608-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-102-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-101-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-204-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-807-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1202-2BHK(Near Refuse Area) FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1205-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1206-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1908-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2101-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1707-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1802-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1904-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1905-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2103-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-201-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-602-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-702-2BHK(Near Refuse Area) FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-704-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-806-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-701-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-808-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-908-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1102-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1303-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1702-2BHK(Near Refuse Area) FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1906-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2206-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-305-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1607-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1701-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2003-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2102-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-302-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-308-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-403-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-404-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-706-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-801-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-804-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2105-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1105-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1304-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1401-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1502-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2205-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1301-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1305-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2001-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-104-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-205-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-301-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-406-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-507-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1302-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1403-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1405-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1407-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1501-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1803-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1804-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1806-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1807-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-907-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1104-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1208-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1506-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1507-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1703-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1706-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1808-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2202-2BHK(Near Refuse Area) FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1005-3BHK FAS Conduit Work | 0.35 | 1575 | 0 | 551.25 | 99.22 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 3 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-4(Living-1,Guest Bedroom-1,Common bedroom-1,Master Bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86625 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-1404-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
FAS Conduit & Cable Laying | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 622 | 2023-02-18 | D-2208-2BHK FAS Conduit Work | 0.35 | 1350 | 0 | 472.5 | 85.06 | 2023-07-27 | Labour Charges for FAS Conduit & Cabel laying work.D Building Intrenal 2 BHK flat (H.D Heat Detector-1 in kitchen,SD Smoke Detector-3(Living-1,Guest Bedroom-1,Common bedroom-1),Hooter-1 in Kitchen & Gas detector-1in Kitchen) | 100 |  | 100877 | 2023-07-28 | 87176.25 | 2023-08-09 12:25 | -86703.75 | HARISH CHANDRA JADHAV ELECTRICALS
RCC Work ETP | N/C | N/C | RITU ENTERPRISES | 625 | 2023-02-24 | ETP RCC Work (L) | 116136 | 4 | 0 | 185817.6 | 33447.16 | 2023-09-13 | RCC Work for all Pardi | 40 |  | 101827 | 2023-09-13 | 185817.6 | 2023-09-20 12:01 | 0 | RITU ENTERPRISES
RCC Work ETP | N/C | N/C | RITU ENTERPRISES | 625 | 2023-02-24 | ETP RCC Work (L) | 92908.8 | 4 | 0 | 74327.04 | 13378.86 | 2023-05-26 | Upto Raft including all work | 20 |  | 99808 | 2023-05-27 | 74327.04 | 2023-06-10 10:33 | 0 | RITU ENTERPRISES
SURVEY / ANALYSIS / SERVICE REPORT | N/C | N/C | ZOHO CORPORATION PRIVATE LIMITED | 626 | 2023-03-01 | ONLINE / DIGITAL Social / Digital Activity | 1 | 52200 | 0 | 52200 | 9396 | 2023-03-17 | ONLINE SURVEY BUILDER FEATURES - ZOHO SURVEY SOFTWARE SERVICES PURCHSED FOR 1 YEAR AS ON 05/03/2023 TO TILL 04/03/2024. 100% ADVANCE WITH TAX AMOUNT | 100 |  | 98783 | 2023-03-17 | 52200 | 2023-03-17 17:29 | 0 | ZOHO CORPORATION PRIVATE LIMITED
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1607-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1506-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1508-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1601-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1301-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1604-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1401-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1602-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-502-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-803-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-303-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-602-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-802-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-702-2BHK(Near Refuse Area) Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1001-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1002-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1004-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-404-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-801-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1201-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-301-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-603-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-904-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-504-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-902-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-804-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1204-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-104-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-304-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-701-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-901-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1202-2BHK(Near Refuse Area) Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-203-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-204-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-601-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-202-2BHK(Near Refuse Area) Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-403-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1101-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1104-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-903-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-201-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2202-2BHK(Near Refuse Area) Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-01-27 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104864 | 2024-01-29 | 9500 | 2024-02-21 11:27 | -8500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2205-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-01-27 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104864 | 2024-01-29 | 9500 | 2024-02-21 11:27 | -8000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2201-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-01-27 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104864 | 2024-01-29 | 9500 | 2024-02-21 11:27 | -8000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2207-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-01-27 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104864 | 2024-01-29 | 9500 | 2024-02-21 11:27 | -8500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2203-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-01-27 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104864 | 2024-01-29 | 9500 | 2024-02-21 11:27 | -8500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2208-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-01-27 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104864 | 2024-01-29 | 9500 | 2024-02-21 11:27 | -8500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2206-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-01-27 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104864 | 2024-01-29 | 9500 | 2024-02-21 11:27 | -8000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2204-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-01-27 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104864 | 2024-01-29 | 9500 | 2024-02-21 11:27 | -8500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2304-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-04-13 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 106787 | 2024-04-15 | 5000 | 2024-05-07 12:48 | -4000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2303-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-04-13 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 106787 | 2024-04-15 | 5000 | 2024-05-07 12:48 | -4000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2305-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-04-13 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 106787 | 2024-04-15 | 5000 | 2024-05-07 12:48 | -3500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2302-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-04-13 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 106787 | 2024-04-15 | 5000 | 2024-05-07 12:48 | -3500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-606-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-806-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-906-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-307-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-206-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-508-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-708-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-207-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-408-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-805-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-208-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-101-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-205-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-406-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-707-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-107-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-705-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-907-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1108-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-305-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-306-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-706-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1205-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1008-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1603-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1504-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1505-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1302-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1402-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1404-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1308-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1408-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1502-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1608-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1507-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1501-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1503-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1307-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1605-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1407-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1303-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1403-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-09-18 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 101948 | 2023-09-20 | 25200 | 2023-09-30 11:39 | -24400 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-001-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-10-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 102279 | 2023-10-05 | 8400 | 2023-10-28 11:37 | -7200 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-005-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-10-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 102279 | 2023-10-05 | 8400 | 2023-10-28 11:37 | -7200 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-002-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-10-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 102279 | 2023-10-05 | 8400 | 2023-10-28 11:37 | -7200 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1005-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-10-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 102279 | 2023-10-05 | 8400 | 2023-10-28 11:37 | -7200 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-007-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-10-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 102279 | 2023-10-05 | 8400 | 2023-10-28 11:37 | -7600 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-008-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-10-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 102279 | 2023-10-05 | 8400 | 2023-10-28 11:37 | -7600 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-006-3BHK Toilet Ledge Wall Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-10-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 102279 | 2023-10-05 | 8400 | 2023-10-28 11:37 | -7200 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-003-2BHK Toilet Ledge Wall Work | 0.8 | 1000 | 0 | 800 | 144 | 2023-10-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 102279 | 2023-10-05 | 8400 | 2023-10-28 11:37 | -7600 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1702-2BHK(Near Refuse Area) Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1707-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-703-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1703-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1803-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1807-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1808-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1106-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1705-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1805-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1103-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1003-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2308-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-06-21 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 108520 | 2024-06-24 | 10500 | 2024-07-05 11:47 | -9500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2405-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-06-21 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 108520 | 2024-06-24 | 10500 | 2024-07-05 11:47 | -9000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2406-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-06-21 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 108520 | 2024-06-24 | 10500 | 2024-07-05 11:47 | -9000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2404-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-06-21 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 108520 | 2024-06-24 | 10500 | 2024-07-05 11:47 | -9500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2408-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-06-21 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 108520 | 2024-06-24 | 10500 | 2024-07-05 11:47 | -9500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2401-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-06-21 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 108520 | 2024-06-24 | 10500 | 2024-07-05 11:47 | -9000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2307-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-06-21 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 108520 | 2024-06-24 | 10500 | 2024-07-05 11:47 | -9500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2403-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-06-21 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 108520 | 2024-06-24 | 10500 | 2024-07-05 11:47 | -9500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2407-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-06-21 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 108520 | 2024-06-24 | 10500 | 2024-07-05 11:47 | -9500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-308-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-905-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-908-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-108-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-605-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1107-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-507-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-106-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-505-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-607-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-608-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1006-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-405-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-807-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-808-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1206-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1207-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-506-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54000 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1007-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-407-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1208-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-02 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99386 | 2023-05-03 | 55500 | 2023-05-29 12:54 | -54500 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2101-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1804-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1105-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2104-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2108-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2103-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2105-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1902-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2106-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1706-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2107-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1606-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-01-13 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104557 | 2024-01-15 | 15500 | 2024-02-02 14:27 | -14000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2306-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2024-06-21 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 108522 | 2024-06-24 | 1500 | 1900-01-01 | 0 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-501-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-105-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-604-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-401-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-402-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -47500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-503-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1203-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-05-16 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 99673 | 2023-05-17 | 49000 | 2023-05-29 12:52 | -48000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1802-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1806-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1701-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-302-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-704-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1102-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1704-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1708-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1801-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-11-04 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 103290 | 2023-11-06 | 25500 | 2023-11-22 11:30 | -24000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2007-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1906-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1907-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2006-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2008-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1405-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1901-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1905-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1305-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2005-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2001-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1304-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1904-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1306-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2002-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1908-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2003-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-004-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-2004-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25500 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1406-3BHK Toilet Ledge Wall Work | 1 | 1500 | 0 | 1500 | 270 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 3 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25000 | SAI PLUMBING WORKS
Ledge Wall - BC | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 628 | 2023-03-02 | D-1903-2BHK Toilet Ledge Wall Work | 1 | 1000 | 0 | 1000 | 180 | 2023-12-15 | Labour charges for Ledge wall Making and Plaster work for 2 BHK Flats D-Bldg. | 100 |  | 104025 | 2023-12-18 | 26500 | 2023-12-25 15:37 | -25500 | SAI PLUMBING WORKS
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-10 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-12 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-13 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Vertical Core Cut 50mm | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-16 | 1 | 175 | 0 | 175 | 0 | 2023-12-12 | Labour Charges for 2 inch Vertical Core Cutting work in slab for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6880 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-2 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-21 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Vertical Core Cut 50mm | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-22 | 1 | 175 | 0 | 175 | 0 | 2023-12-12 | Labour Charges for 2 inch Vertical Core Cutting work in slab for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6880 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-14 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-11 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-15 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-6 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Vertical Core Cut 50mm | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-17 | 1 | 175 | 0 | 175 | 0 | 2023-12-12 | Labour Charges for 2 inch Vertical Core Cutting work in slab for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6880 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-4 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-5 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-1 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-17 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-8 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-9 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Vertical Core Cut 50mm | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-18 | 1 | 175 | 0 | 175 | 0 | 2023-12-12 | Labour Charges for 2 inch Vertical Core Cutting work in slab for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6880 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-16 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-7 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Vertical Core Cut 50mm | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-20 | 1 | 175 | 0 | 175 | 0 | 2023-12-12 | Labour Charges for 2 inch Vertical Core Cutting work in slab for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6880 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-18 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-20 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-3 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-19 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Vertical Core Cut 50mm | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-21 | 1 | 175 | 0 | 175 | 0 | 2023-12-12 | Labour Charges for 2 inch Vertical Core Cutting work in slab for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6880 | AJAY KUMAR GUPTA
Horizontal Core Cut 2'' | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-22 | 1 | 265 | 0 | 265 | 0 | 2023-12-12 | Labour Charges for 2 inch Horizontal Core Cutting work for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6790 | AJAY KUMAR GUPTA
Vertical Core Cut 50mm | N/C | N/C | AJAY KUMAR GUPTA | 629 | 2023-03-02 | Core Cutting Work Shop No-19 | 1 | 175 | 0 | 175 | 0 | 2023-12-12 | Labour Charges for 2 inch Vertical Core Cutting work in slab for Fire fighting work. | 100 |  | 104019 | 2023-12-18 | 7055 | 2024-01-16 14:59 | -6880 | AJAY KUMAR GUPTA
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 582 | 20 | 0 | 11640 | 0 | 2024-03-15 | Labour charges for Spreading and Levelling work for UGWT D & E Fire tank, pump room, Domestic tank,raft toe. | 100 |  | 106095 | 2024-03-18 | 11640 | 1900-01-01 | 0 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 134.111 | 60 | 0 | 8046.66 | 0 | 2024-05-13 12:40 | Labour charges for Backfilling work for Domestic tank side column & Domestic tank footings for E-Bldg side ramp. | 100 |  | 107566 | 2024-05-13 | 73018.56 | 2024-06-26 11:45 | -64971.9 | SHIVAM ENTERPRISES
Excavation in Hard Rock | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 309.39 | 210 | 0 | 64971.9 | 0 | 2024-05-13 12:25 | Labour charges for Hard Rock Excavation work for UGWT D & E Ramp column footing. | 100 |  | 107566 | 2024-05-13 | 73018.56 | 2024-06-26 11:45 | -8046.66 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 289.04 | 60 | 0 | 17342.4 | 0 | 2023-04-13 | Labour charges for Back filling work for D-Bldg Fire Tank side column & Fire Tank side footings. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -46880 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 210 | 20 | 0 | 4200 | 0 | 2023-04-13 | Labour charges for Spreading & Levelling work for Domestic tank side column & Domestic tank footings for E-Bldg side ramp. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -60022.4 | SHIVAM ENTERPRISES
Excavation in Soil- UST | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 200 | 60 | 0 | 12000 | 0 | 2023-04-13 | Labour charges for Excavation work in Soft soil for E-Bldg Domestic tank side column footings. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -52222.4 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 176 | 60 | 0 | 10560 | 0 | 2023-04-13 | Labour charges for Backfilling work for UGWT D & E Fire tank, pump room, Domestic tank,raft toe. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -53662.4 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 210 | 60 | 0 | 12600 | 0 | 2023-04-13 | Labour charges for Backfilling work for Domestic tank side column & Domestic tank footings for E-Bldg side ramp. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -51622.4 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 176 | 20 | 0 | 3520 | 0 | 2023-04-13 | Labour charges for Spreading and Levelling work for UGWT D & E Fire tank, pump room, Domestic tank,raft toe. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -60702.4 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 200 | 20 | 0 | 4000 | 0 | 2023-04-13 | Labour charges for Spreading and levelling work for domestic tank side column footings E-Bldg. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -60222.4 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 582 | 60 | 0 | 34920 | 0 | 2023-07-05 | Labour charges for Backfilling work for UGWT D & E Fire tank, pump room, Domestic tank,raft toe. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -44395.8 | SHIVAM ENTERPRISES
Excavation in Soil- UST | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 346.75 | 60 | 0 | 20805 | 0 | 2023-07-05 | Labour charges for Excavation work in Soft soil for E-Bldg Domestic tank side column footings. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -58510.8 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 309 | 15 | 0 | 4635 | 0 | 2023-07-05 | Labour charges for Spreading and Levelling work for UGWT D & E Ramp column footings. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -74680.8 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 312 | 20 | 0 | 6240 | 0 | 2023-07-05 | Labour charges for Spreading & Levelling work for Domestic tank side column & Domestic tank footings for E-Bldg side ramp. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -73075.8 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 289.04 | 20 | 0 | 5780.8 | 0 | 2023-07-05 | Labour charges for Spreading & Levelling work for D-Bldg Fire Tank side column & Fire Tank side footings. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -73535 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 346.75 | 20 | 0 | 6935 | 0 | 2023-07-05 | Labour charges for Spreading and levelling work for domestic tank side column footings E-Bldg. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -72380.8 | SHIVAM ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 408.29 | 255.454 | 0 | 104299.3137 | 18773.88 | 2023-10-11 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 102505 | 2023-10-11 | 253716.36 | 1900-01-01 | -149417.0463 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 179.86 | 155 | 0 | 27878.3 | 5018.1 | 2023-10-11 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 102505 | 2023-10-11 | 253716.36 | 1900-01-01 | -225838.06 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 456 | 140 | 0 | 63840 | 11491.2 | 2023-10-11 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 102505 | 2023-10-11 | 253716.36 | 1900-01-01 | -189876.36 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 179.86 | 155 | 0 | 27878.3 | 5018.1 | 2023-10-11 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 102505 | 2023-10-11 | 253716.36 | 1900-01-01 | -225838.06 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 180.73 | 165 | 0 | 29820.45 | 5367.68 | 2023-10-11 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 102505 | 2023-10-11 | 253716.36 | 1900-01-01 | -223895.91 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 297 | 140 | 0 | 41580 | 7484.4 | 2023-10-05 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 | Challan No 22 12 mm-50 Nos,16mm-1 Nos. Callan No- 138 12mm-89 Nos,16mm - 2 Nos. Ch No-131 - 12mm - 36 Nos. | 102321 | 2023-10-05 | 41580 | 1900-01-01 | 0 | AVCON TECHNICS PVT LTD
Fire Bucket Stand (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 2500 | 0 | 1750 | 315 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT 27/06/2024 | 108670 | 2024-07-01 | 95900 | 2024-07-15 15:03 | -94150 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Bucket (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 4 | 1000 | 0 | 2800 | 504 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT 27/06/2024 | 108670 | 2024-07-01 | 95900 | 2024-07-15 15:03 | -93100 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler Alarm Valve 150mm dia (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 43500 | 0 | 91350 | 16443 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT-27/06/2024 | 108670 | 2024-07-01 | 95900 | 2024-07-15 15:03 | -4550 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 14 | 1000 | 0 | 9800 | 1764 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108232 | 2024-06-10 | 78820 | 2024-06-15 16:30 | -69020 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 200mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 29 | 3400 | 0 | 69020 | 12423.6 | 2024-06-10 | Against Material Supply | 70 | DT5/06/2024 1 Mtr Balance Due to less quantity in WO | 108232 | 2024-06-10 | 78820 | 2024-06-15 16:30 | -9800 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC Jockey Pump (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 205000 | 0 | 287000 | 51660 | 2024-01-24 | Against Material Supply | 70 | Challan No- 17569 | 104856 | 2024-01-29 | 2212000 | 2024-02-08 11:56 | -1925000 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Motor Driven Pump (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 1375000 | 0 | 1925000 | 346500 | 2024-01-24 | Against Material Supply | 70 | Challan No- 17569 | 104856 | 2024-01-29 | 2212000 | 2024-02-08 11:56 | -287000 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pressure Guage 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 8 | 3200 | 0 | 17920 | 3225.6 | 2024-07-29 | Against Material Supply | 70 | Challan No-18613 DT 18/07/2024 | 109433 | 2024-07-29 | 20300 | 1900-01-01 | -2380 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 200mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 3400 | 0 | 2380 | 428.4 | 2024-07-29 | Against Material Supply | 70 | Total Challan Qty-30 Mtrs. RA Bill Released Qty-29 Mtrs(RA-108232 Challan No-18352 (Amendment Qty 1 Mtrs released from this Completion) | 109433 | 2024-07-29 | 20300 | 1900-01-01 | -17920 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Diesel Engine Driven Pump (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 1717410 | 0 | 1202187 | 216393.66 | 2024-04-08 | Against Material Supply | 70 |  | 106672 | 2024-04-08 | 1202187 | 2024-04-10 17:55 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 150mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 10000 | 0 | 21000 | 3780 | 2024-07-16 | Against Material Supply | 70 | Challan No-18548 DT 04.07.2024 | 109155 | 2024-07-18 | 35770 | 1900-01-01 | -14770 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 6700 | 0 | 4690 | 844.2 | 2024-07-16 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109155 | 2024-07-18 | 35770 | 1900-01-01 | -31080 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
4 Way 63mm,Fire Service inlet (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 7200 | 0 | 10080 | 1814.4 | 2024-07-16 | Against Material Supply | 70 | Challan No-18537 DT 03.07.2024 | 109155 | 2024-07-18 | 35770 | 1900-01-01 | -25690 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 6500 | 0 | 4550 | 819 | 2023-04-10 | Against Material Supply | 70 |  | 99105 | 2023-04-11 | 9450 | 2023-04-15 16:20 | -4900 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 80mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 7000 | 0 | 4900 | 882 | 2023-04-10 | Against Material Supply | 70 |  | 99105 | 2023-04-11 | 9450 | 2023-04-15 16:20 | -4550 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 7500 | 0 | 31500 | 5670 | 2023-04-18 | Against Material Supply | 70 |  | 99228 | 2023-04-18 | 31500 | 2023-07-19 11:38 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pressure Guage 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 3200 | 0 | 13440 | 2419.2 | 2024-07-15 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -403340 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 150mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 10000 | 0 | 21000 | 3780 | 2024-07-14 | Against Material Supply | 70 | Challan No-18548 DT 4/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -395780 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI Pipe C Class 250mm dia-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 4400 | 0 | 6160 | 1108.8 | 2024-07-15 | Against Material Supply | 70 | Challan No-18542 DT 03.07.2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -410620 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pressure Switch (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 10 | 2350 | 0 | 16450 | 2961 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT03.07.24 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -400330 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI Pipe C Class 250mm dia-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 10 | 4400 | 0 | 30800 | 5544 | 2024-07-07 | Against Material Supply | 70 | Challan No-18542 DT-03.07.2024 Received - 12 mtrs. (2 Mtrs Balance) | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -385980 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 14 | 12000 | 0 | 117600 | 21168 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 4/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -299180 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 4 | 7500 | 0 | 21000 | 3780 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -395780 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Foot Valve 150 mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 17500 | 0 | 12250 | 2205 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT04.07.24 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -404530 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 200mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 25500 | 0 | 35700 | 6426 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 4/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -381080 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC Air Vessel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 27000 | 0 | 37800 | 6804 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT03.07.24 (2 balance =Received -4 Nos.) | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -378980 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Strainer "Y" (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 5900 | 0 | 8260 | 1486.8 | 2024-07-10 | Against Material Supply | 70 | Challan No-18546 DT 04.07.24 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -408520 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
CI Strainer 150 mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 8900 | 0 | 18690 | 3364.2 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -398090 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 200mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 16500 | 0 | 23100 | 4158 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -393680 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
C.I.Basket Strainer 200mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 29200 | 0 | 40880 | 7358.4 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -375900 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 6500 | 0 | 13650 | 2457 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 1900-01-01 | -403130 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 80mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 7000 | 0 | 1750 | 315 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105278 | 2024-02-12 | 17200 | 2024-02-27 10:43 | -15450 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 7500 | 0 | 11250 | 2025 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105278 | 2024-02-12 | 17200 | 2024-02-27 10:43 | -5950 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 7500 | 0 | 2250 | 405 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105278 | 2024-02-12 | 17200 | 2024-02-27 10:43 | -14950 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 6500 | 0 | 1625 | 292.5 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105278 | 2024-02-12 | 17200 | 2024-02-27 10:43 | -15575 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 6500 | 0 | 325 | 58.5 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105278 | 2024-02-12 | 17200 | 2024-02-27 10:43 | -16875 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 250 | 0 | 175 | 31.5 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -1726 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 250 | 0 | 1050 | 189 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -851 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 250 | 0 | 375 | 67.5 | 2024-02-12 | After Final Noc | 25 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -1526 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 80mm-(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 250 | 0 | 175 | 31.5 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -1726 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 80mm-(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1.008 | 250 | 0 | 63 | 11.34 | 2024-02-12 | After Final Noc | 25 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -1838 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1.008 | 250 | 0 | 63 | 11.34 | 2024-02-12 | After Final Noc | 25 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -1838 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-04-12 | Charges for Garden Maintenance and Watering work for Month FEB-2023. | 100 |  | 99135 | 2023-04-12 | 8800 | 2023-05-04 14:17 | -4400 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-04-12 | Charges for Garden Maintenance and Watering work for Month MAR-2023. | 100 |  | 99135 | 2023-04-12 | 8800 | 2023-05-04 14:17 | -4400 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-07-03 | Charges for Garden Maintenance and Watering work for Month APR-2023. | 100 |  | 100442 | 2023-07-04 | 13200 | 2023-08-14 14:34 | -8800 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-07-03 | Charges for Garden Maintenance and Watering work for Month MAY-2023. | 100 |  | 100442 | 2023-07-04 | 13200 | 2023-08-14 14:34 | -8800 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-07-03 | Charges for Garden Maintenance and Watering work for Month JUNE-2023. | 100 |  | 100442 | 2023-07-04 | 13200 | 2023-08-14 14:34 | -8800 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-11-04 | Charges for Garden Maintenance and Watering work for Month SEPT-2023. | 100 |  | 103266 | 2023-11-04 | 8800 | 2023-11-18 14:35 | -4400 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-11-04 | Charges for Garden Maintenance and Watering work for Month OCT-2023. | 100 |  | 103266 | 2023-11-04 | 8800 | 2023-11-18 14:35 | -4400 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-09-18 15:51 | Charges for Garden Maintenance and Watering work for Month JULY-2023. | 100 |  | 101949 | 2023-09-20 | 8800 | 2023-10-30 15:49 | -4400 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-09-18 15:51 | Charges for Garden Maintenance and Watering work for Month AUG-2023. | 100 |  | 101949 | 2023-09-20 | 8800 | 2023-10-30 15:49 | -4400 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2024-02-14 | Charges for Garden Maintenance and Watering work for Month JAN-2024. | 100 |  | 105371 | 2024-02-19 | 13200 | 2024-03-12 14:17 | -8800 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2024-02-14 | Charges for Garden Maintenance and Watering work for Month NOV-2023. | 100 |  | 105371 | 2024-02-19 | 13200 | 2024-03-12 14:17 | -8800 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2024-02-14 | Charges for Garden Maintenance and Watering work for Month DEC-2023. | 100 |  | 105371 | 2024-02-19 | 13200 | 2024-03-12 14:17 | -8800 | SITARAM GANGADHAR AUTI
RCC Substructure Labour (B-up area)- BC | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 539.47 | 100 | 0 | 53947 | 0 | 2023-09-13 | Labour charges for RCC Work for Substructure including PCC Below Footing,soling,Footing RCC Work,pile breaking,pile cap casting,plinth beam,plinth filling, PCC at plinth with steel work for Transformer room. | 100 |  | 101847 | 2023-09-15 | 53947 | 1900-01-01 | 0 | VIJAY MOHITE
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 653.72 | 290 | 0 | 189578.8 | 0 | 2023-10-20 15:06 | Labour charges for RCC Work for Super-structure including columns above plinth beam, Beams and slabs for Transformer Room. | 100 |  | 102866 | 2023-10-20 | 201003.8 | 2023-11-01 14:27 | -11425 | VIJAY MOHITE
RCC Substructure Labour (B-up area)- BC | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 114.25 | 100 | 0 | 11425 | 0 | 2023-10-20 15:06 | Labour charges for RCC Work for Substructure including PCC Below Footing,soling,Footing RCC Work,pile breaking,pile cap casting,plinth beam,plinth filling, PCC at plinth with steel work for Transformer room. | 100 |  | 102866 | 2023-10-20 | 201003.8 | 2023-11-01 14:27 | -189578.8 | VIJAY MOHITE
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 115.913 | 290 | 0 | 33614.77 | 6050.66 | 2024-07-13 18:54 | Labour charges for RCC Work for Super-structure including columns above plinth beam, Beams and slabs for Transformer Room. | 100 |  | 109094 | 2024-07-15 | 33614.77 | 2024-07-26 12:27 | 0 | ROHIT CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 219.7855 | 290 | 0 | 63737.795 | 0 | 2024-06-17 20:05 | Labour charges for RCC Work for Super-structure including columns above plinth beam, Beams and slabs for Transformer Room. | 100 | Final Bill For Remaining 20% | 108503 | 2024-06-24 | 63737.8 | 2024-07-05 11:37 | -0.005 | VIJAY MOHITE
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 817.15 | 145 | 0 | 118486.75 | 0 | 2024-06-16 12:27 | Labour charges for RCC Work for Superstructure due to increase in height more than 5 Meter. | 100 |  | 108392 | 2024-06-17 | 164343.75 | 2024-06-26 11:41 | -45857 | VIJAY MOHITE
RCC Substructure Labour (B-up area)- BC | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 408.57 | 100 | 0 | 40857 | 0 | 2024-06-16 12:33 | Labour charges for RCC Work for Substructure including PCC Below Footing,soling,Footing RCC Work,pile breaking,pile cap casting,plinth beam,plinth filling, PCC at plinth with steel work for Transformer room. | 100 |  | 108392 | 2024-06-17 | 164343.75 | 2024-06-26 11:41 | -123486.75 | VIJAY MOHITE
Pile Breaking -DCW | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 10 | 500 | 0 | 5000 | 0 | 2024-06-16 12:27 | Labour charges for Pile Breaking Work for Transformer Room. | 100 |  | 108392 | 2024-06-17 | 164343.75 | 2024-06-26 11:41 | -159343.75 | VIJAY MOHITE
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6649 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of JAN-2023 | 8.3333 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6649 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of FEB-2023 | 8.3333 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6649 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of MAR-2023 | 8.3333 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6649 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of APR-2023 | 8.3333 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6649 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of MAY-2023 | 8.3333 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6649 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of JUNE-2023 | 8.3333 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6649 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of JULY-2023 | 8.3333 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6649 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of AUG-2023 | 8.3333 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6649 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of SEPT-2023 | 8.3333 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6649 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of OCT-2023 | 8.3333 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6649 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of NOV-2023 | 8.3333 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | Head Office Expenses | 12 | 416.6666 | 0 | 416.6849 | 75 | 2023-03-31 | EPBAX Maintenance for the Month of DEC-2023 | 8.3337 |  | 98971 | 2023-03-31 | 4999.94 | 2023-04-05 15:50 | -4583.2551 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6649 | 75 | 2024-02-01 | JULY-2024 | 8.3333 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6649 | 75 | 2024-02-01 | AUG-2024 | 8.3333 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6649 | 75 | 2024-02-01 | SEPT-2024 | 8.3333 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6649 | 75 | 2024-02-01 | OCT-2024 | 8.3333 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6649 | 75 | 2024-02-01 | NOV-2024 | 8.3333 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6849 | 75 | 2024-02-01 | DEC-2024 | 8.3337 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2551 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6649 | 75 | 2024-02-01 | JAN-2024 | 8.3333 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6649 | 75 | 2024-02-01 | FEB-2024 | 8.3333 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6649 | 75 | 2024-02-01 | MAR-2024 | 8.3333 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6649 | 75 | 2024-02-01 | APR-2024 | 8.3333 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6649 | 75 | 2024-02-01 | MAY-2024 | 8.3333 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
EPABX System Maintenance | N/C | N/C | PARSN TECHNOLOGIES PVT LTD | 639 | 2023-03-20 | HO- AC Maintenance Work. - 1 No. | 12 | 416.6666 | 0 | 416.6649 | 75 | 2024-02-01 | JUNE-2024 | 8.3333 |  | 104912 | 2024-02-01 | 4999.94 | 2024-02-01 18:43 | -4583.2751 | PARSN TECHNOLOGIES PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | 40kva DG servicing kit | 12 | 736 | 0 | 735.9706 | 132.48 | 2024-06-08 | JUN-2024 | 8.333 | Report No- 000515 DT 07/06/2024 | 108210 | 2024-06-10 | 735.97 | 2024-06-24 12:28 | 0.00056 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2024-04-11 | Dec - 2023 | 8.3334 | Report No-18068 DT-25/12/2023 | 106967 | 2024-04-20 | 3499.95 | 2024-05-07 12:49 | -2624.943 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2024-04-11 | Jan - 2024 | 8.3334 | Report No-17942 DT-03/01/2024 | 106967 | 2024-04-20 | 3499.95 | 2024-05-07 12:49 | -2624.943 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2024-04-11 | Feb - 2024 | 8.3334 | Report No-000962 DT-06/02/2024 | 106967 | 2024-04-20 | 3499.95 | 2024-05-07 12:49 | -2624.943 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 874.923 | 157.48 | 2024-04-11 | Mar - 2024 | 8.3326 | Report No-000276 DT-26/03/2024 | 106967 | 2024-04-20 | 3499.95 | 2024-05-07 12:49 | -2625.027 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | 40kva DG servicing kit | 12 | 736 | 0 | 735.9706 | 132.48 | 2024-04-11 | APR-2024 | 8.333 | Report No-000295 DT-08/04/2024 | 106968 | 2024-04-20 | 735.97 | 2024-05-07 12:49 | 0.00056 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | 40kva DG servicing kit | 12 | 736 | 0 | 735.9706 | 132.48 | 2024-05-09 | MAY-2024 | 8.333 | Report No-000371 DT 08/05/2024 | 107491 | 2024-05-13 | 735.97 | 2024-06-15 11:45 | 0.00056 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 11.9999 | 875 | 0 | 874.9997 | 157.5 | 2023-07-20 | April - 2023 | 8.3334 | 125 KVA DG Set | 100777 | 2023-07-21 | 2625 | 2023-08-09 12:26 | -1750.0003 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 11.9999 | 875 | 0 | 874.9997 | 157.5 | 2023-07-20 | May - 2023 | 8.3334 | 125 KVA DG set | 100777 | 2023-07-21 | 2625 | 2023-08-09 12:26 | -1750.0003 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 11.9999 | 875 | 0 | 874.9997 | 157.5 | 2023-07-20 | June - 2023 | 8.3334 | 125 KVA DG set | 100777 | 2023-07-21 | 2625 | 2023-08-09 12:26 | -1750.0003 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2023-12-07 | Sep - 2023 | 8.3334 | Report No- 17508 DT 30/09/2023 | 103794 | 2023-12-11 | 4375.05 | 2024-01-16 15:00 | -3500.043 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2023-12-05 | Nov - 2023 | 8.3334 | Report No- 17958 DT 30/11/2023 | 103794 | 2023-12-11 | 4375.05 | 2024-01-16 15:00 | -3500.043 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2023-12-05 | Oct - 2023 | 8.3334 | Report No- 17446 DT 11/10/2023 | 103794 | 2023-12-11 | 4375.05 | 2024-01-16 15:00 | -3500.043 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2023-12-05 | July - 2023 | 8.3334 | Report No- 16530 DT 13/07/2023 | 103794 | 2023-12-11 | 4375.05 | 2024-01-16 15:00 | -3500.043 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2023-12-05 | Aug - 2023 | 8.3334 | Report No- 17516 DT 17/08/2023 | 103794 | 2023-12-11 | 4375.05 | 2024-01-16 15:00 | -3500.043 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | 40kva DG servicing kit | 12 | 736 | 0 | 735.9706 | 132.48 | 2024-07-10 | JUL-2024 | 8.333 | Report No-000680 DT 09.07.2024 | 109102 | 2024-07-15 | 735.97 | 2024-08-05 14:02 | 0.00056 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | 82.5 kva DG servicing kit | 12 | 897 | 0 | 896.6412 | 161.4 | 2024-07-10 | JUL-2024 | 8.33 | Report no-000682 DT 09.07.2024 | 109103 | 2024-07-15 | 896.64 | 2024-08-05 14:02 | 0.0012 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2023-12-05 | Jul - 2023 | 8.3334 | Report No- 16532 DT 13/07/2023 | 103793 | 2023-12-11 | 4375.05 | 2024-01-16 15:00 | -3500.043 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2023-12-05 | Aug - 2023 | 8.3334 | Report No- 17517 DT 17/08/2023 | 103793 | 2023-12-11 | 4375.05 | 2024-01-16 15:00 | -3500.043 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2023-12-05 | Sep - 2023 | 8.3334 | Report No- 17615 DT 23/09/2023 | 103793 | 2023-12-11 | 4375.05 | 2024-01-16 15:00 | -3500.043 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2023-12-05 | Nov - 2023 | 8.3334 | Report No- 17959 DT 30/11/2023 | 103793 | 2023-12-11 | 4375.05 | 2024-01-16 15:00 | -3500.043 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2023-12-07 | Oct - 2023 | 8.3334 | Report No- 17803 DT 21/10/2023 | 103793 | 2023-12-11 | 4375.05 | 2024-01-16 15:00 | -3500.043 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | 82.5 kva DG servicing kit | 12 | 897 | 0 | 896.6412 | 161.4 | 2024-05-23 | MAY-2024 | 8.33 | Report No- 000372 DT08/05/2024 | 107791 | 2024-05-27 | 896.64 | 2024-06-15 11:45 | 0.0012 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 11.9999 | 875 | 0 | 874.9997 | 157.5 | 2023-07-20 | Apr - 2023 | 8.3334 | 82.5 KVA DG set | 100778 | 2023-07-21 | 2625 | 2023-08-09 12:12 | -1750.0003 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 11.9999 | 875 | 0 | 874.9997 | 157.5 | 2023-07-20 | May - 2023 | 8.3334 | 82.5 KVA DG set | 100778 | 2023-07-21 | 2625 | 2023-08-09 12:12 | -1750.0003 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 11.9999 | 875 | 0 | 874.9997 | 157.5 | 2023-07-20 | Jun - 2023 | 8.3334 | 82.5 KVA DG set | 100778 | 2023-07-21 | 2625 | 2023-08-09 12:12 | -1750.0003 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2024-04-11 | Dec - 2023 | 8.3334 | Report No-18066 DT-25/12/2023 | 106773 | 2024-04-15 | 4396.59 | 2024-05-21 18:45 | -3521.583 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2024-04-11 | Feb - 2024 | 8.3334 | Report No-000961 DT-05/02/2024 | 106773 | 2024-04-15 | 4396.59 | 2024-05-21 18:45 | -3521.583 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 874.923 | 157.48 | 2024-04-11 | Mar - 2024 | 8.3326 | Report No-000994 DT-04/04/2024 | 106773 | 2024-04-15 | 4396.59 | 2024-05-21 18:45 | -3521.667 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | DG Service Work | 12 | 875 | 0 | 875.007 | 157.5 | 2024-04-11 | Jan - 2024 | 8.3334 | Report No-17941 DT-03/01/2024 | 106773 | 2024-04-15 | 4396.59 | 2024-05-21 18:45 | -3521.583 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | 82.5 kva DG servicing kit | 12 | 897 | 0 | 896.6412 | 161.4 | 2024-04-11 | APR-2024 | 8.33 | Report No-000294 DT-08/04/2024 | 106773 | 2024-04-15 | 4396.59 | 2024-05-21 18:45 | -3499.9488 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | 82.5 kva DG servicing kit | 12 | 897 | 0 | 896.6412 | 161.4 | 2024-06-08 | JUN-2024 | 8.33 | Report No- 16098 DT04/06/2024 | 108214 | 2024-06-10 | 896.64 | 2024-06-24 12:31 | 0.0012 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | 125kva DG servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-06-08 | JUN-2024 | 8.33 | Report No-16097 DT 04/06/2024 | 108213 | 2024-06-10 | 919.63 | 2024-06-24 12:29 | 0.002 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 12 | 650 | 0 | 650.0052 | 117 | 2024-04-11 | Dec - 2023 | 8.3334 | Report No-18067 DT-25/12/2023 | 106969 | 2024-04-20 | 2599.97 | 2024-05-07 12:49 | -1949.9648 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 12 | 650 | 0 | 650.0052 | 117 | 2024-04-11 | Feb - 2024 | 8.3334 | Report No-000963 DT-06/02/2024 | 106969 | 2024-04-20 | 2599.97 | 2024-05-07 12:49 | -1949.9648 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 12 | 650 | 0 | 649.9428 | 116.98 | 2024-04-11 | Mar - 2024 | 8.3326 | Report No-000277 DT-26/03/2024 | 106969 | 2024-04-20 | 2599.97 | 2024-05-07 12:49 | -1950.0272 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 12 | 650 | 0 | 650.0052 | 117 | 2024-04-11 | Jan - 2024 | 8.3334 | Report No-17943 DT-03/01/2024 | 106969 | 2024-04-20 | 2599.97 | 2024-05-07 12:49 | -1949.9648 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | 125kva DG servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-04-11 | APR-2024 | 8.33 | Report No-000293 DT-08/04/2024 | 106970 | 2024-04-20 | 919.63 | 2024-05-07 12:49 | 0.002 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | 125kva DG servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-05-09 | MAY-2024 | 8.33 | Report No-00373 DT 08/05/2024 | 107490 | 2024-05-13 | 919.63 | 2024-06-15 11:45 | 0.002 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 11.9999 | 650 | 0 | 649.9998 | 117 | 2023-07-20 | Apr - 2023 | 8.3334 | 40 KVA DG Set | 100779 | 2023-07-21 | 1950 | 2023-08-09 12:27 | -1300.0002 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 11.9999 | 650 | 0 | 649.9998 | 117 | 2023-07-20 | May - 2023 | 8.3334 | 40 KVA DG Set | 100779 | 2023-07-21 | 1950 | 2023-08-09 12:27 | -1300.0002 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 11.9999 | 650 | 0 | 649.9998 | 117 | 2023-07-20 | Jun - 2023 | 8.3334 | 40 KVA DG Set | 100779 | 2023-07-21 | 1950 | 2023-08-09 12:27 | -1300.0002 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 12 | 650 | 0 | 650.0052 | 117 | 2023-12-05 | Jul - 2023 | 8.3334 | Report No- 16531 DT 13/07/2023 | 103792 | 2023-12-11 | 3250.05 | 2024-01-16 15:53 | -2600.0448 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 12 | 650 | 0 | 650.0052 | 117 | 2023-12-05 | Aug - 2023 | 8.3334 | Report No- 17518 DT 17/08/2023 | 103792 | 2023-12-11 | 3250.05 | 2024-01-16 15:53 | -2600.0448 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 12 | 650 | 0 | 650.0052 | 117 | 2023-12-05 | Oct - 2023 | 8.3334 | Report No- 17447 DT 11/10/2023 | 103792 | 2023-12-11 | 3250.05 | 2024-01-16 15:53 | -2600.0448 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 12 | 650 | 0 | 650.0052 | 117 | 2023-12-05 | Nov - 2023 | 8.3334 | Report No- 17957 DT 30/11/2023 | 103792 | 2023-12-11 | 3250.05 | 2024-01-16 15:53 | -2600.0448 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | DG Service Work | 12 | 650 | 0 | 650.0052 | 117 | 2023-12-07 | Sep - 2023 | 8.3334 | Report No- 17508 DT 30/09/2023 | 103792 | 2023-12-11 | 3250.05 | 2024-01-16 15:53 | -2600.0448 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | 125kva DG servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-07-10 | JUL-2024 | 8.33 | Report No-000679 DT 09.07.2024 | 109101 | 2024-07-15 | 919.63 | 2024-08-05 14:01 | 0.002 | MEGAPOWER SOLUTION PVT LTD
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 3rd Floor Staircase Flooring Work | 98.4 | 8 | 0 | 787.2 | 141.7 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Tread for Regular Staircase (ST-02). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12693.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Staircase Flooring Work | 98.4 | 8 | 0 | 787.2 | 141.7 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Tread for Regular Staircase (ST-02). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12693.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 3rd Floor Fire Staircase Flooring Work | 26.6 | 8 | 0 | 212.8 | 38.3 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Skirting for Fire Staircase (ST-01). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -13267.6 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Staircase Flooring Work | 98.4 | 8 | 0 | 787.2 | 141.7 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Tread for Regular Staircase (ST-02). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12693.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 131.2 | 8 | 0 | 1049.6 | 188.92 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Tread for Fire Staircase (ST-01). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12430.8 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 115 | 8 | 0 | 920 | 165.6 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Skirting for Fire Staircase (ST-01). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12560.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Staircase Flooring Work | 62.5 | 8 | 0 | 500 | 90 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish for skirting for Regular Staircase (ST-02). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12980.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Staircase Flooring Work | 62.5 | 8 | 0 | 500 | 90 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish for skirting for Regular Staircase (ST-02). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12980.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Fire Staircase Flooring Work | 131.2 | 8 | 0 | 1049.6 | 188.92 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Tread for Fire Staircase (ST-01). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12430.8 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Staircase Flooring Work | 98.4 | 8 | 0 | 787.2 | 141.7 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Tread for Regular Staircase (ST-02). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12693.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Fire Staircase Flooring Work | 42.75 | 8 | 0 | 342 | 61.56 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Tread for Fire Staircase (ST-01). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -13138.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Fire Staircase Flooring Work | 134.375 | 8 | 0 | 1075 | 193.5 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Tread for Fire Staircase (ST-01). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12405.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 131.2 | 8 | 0 | 1049.6 | 188.92 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Tread for Fire Staircase (ST-01). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12430.8 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 115 | 8 | 0 | 920 | 165.6 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Skirting for Fire Staircase (ST-01). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12560.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 3rd Floor Staircase Flooring Work | 62.5 | 8 | 0 | 500 | 90 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish for skirting for Regular Staircase (ST-02). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12980.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Fire Staircase Flooring Work | 62.375 | 8 | 0 | 499 | 89.82 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Skirting for Fire Staircase (ST-01). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12981.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Fire Staircase Flooring Work | 36.75 | 8 | 0 | 294 | 52.92 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Skirting for Fire Staircase (ST-01). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -13186.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Fire Staircase Flooring Work | 115 | 8 | 0 | 920 | 165.6 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish work for Skirting for Fire Staircase (ST-01). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12560.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Staircase Flooring Work | 62.5 | 8 | 0 | 500 | 90 | 2023-05-08 | Charges of Sadarahalli Granite Edge Polish for skirting for Regular Staircase (ST-02). | 100 |  | 99520 | 2023-05-08 | 13480.4 | 2023-06-10 10:37 | -12980.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Fire Staircase Flooring Work | 140.1 | 85 | 0 | 11908.5 | 2143.54 | 2023-06-09 | Material Supply charges of Sadarahalli Granite for Staircase Tread Fire Staircase (ST-01). | 100 |  | 100025 | 2023-06-09 | 22225.3 | 2023-06-20 16:53 | -10316.8 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Staircase Flooring Work | 82.1 | 8 | 0 | 656.8 | 118.22 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish for skirting for Regular Staircase (ST-02). | 100 |  | 100025 | 2023-06-09 | 22225.3 | 2023-06-20 16:53 | -21568.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Fire Staircase Flooring Work | 20.125 | 8 | 0 | 161 | 28.98 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for Fire Staircase (ST-01). | 100 |  | 100025 | 2023-06-09 | 22225.3 | 2023-06-20 16:53 | -22064.3 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Staircase Flooring Work | 128 | 8 | 0 | 1024 | 184.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for Regular Staircase (ST-02). | 100 |  | 100025 | 2023-06-09 | 22225.3 | 2023-06-20 16:53 | -21201.3 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 99.7059 | 85 | 0 | 8475.0015 | 1525.5 | 2023-06-09 | Material Supply charges of Sadarahalli Granite for Staircase Tread Fire Staircase (ST-01). | 100 |  | 100025 | 2023-06-09 | 22225.3 | 2023-06-20 16:53 | -13750.2985 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Staircase Flooring Work | 19.9 | 85 | 0 | 1691.5 | 304.48 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Skirting Regular Staircase (ST-02). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -117147 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Fire Staircase Flooring Work | 39.4 | 85 | 0 | 3349 | 602.82 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work Fire Staircase (ST-01). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -115489.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Staircase Flooring Work | 19.9 | 85 | 0 | 1691.5 | 304.48 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Skirting Regular Staircase (ST-02). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -117147 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Staircase Flooring Work | 50.4 | 85 | 0 | 4284 | 771.12 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -114554.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Fire Staircase Flooring Work | 28.3 | 85 | 0 | 2405.5 | 433 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work Fire Staircase (ST-01). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -116433 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 188.8 | 85 | 0 | 16048 | 2888.64 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Fire Staircase (ST-01). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -102790.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Staircase Flooring Work | 50.4 | 85 | 0 | 4284 | 771.12 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -114554.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Staircase Flooring Work | 50.4 | 85 | 0 | 4284 | 771.12 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -114554.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Staircase Flooring Work | 50.4 | 85 | 0 | 4284 | 771.12 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -114554.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 28.3 | 85 | 0 | 2405.5 | 433 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work Fire Staircase (ST-01). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -116433 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 3rd Floor Staircase Flooring Work | 19.9 | 85 | 0 | 1691.5 | 304.48 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Skirting Regular Staircase (ST-02). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -117147 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 188.8 | 85 | 0 | 16048 | 2888.64 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Fire Staircase (ST-01). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -102790.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 3rd Floor Staircase Flooring Work | 50.4 | 85 | 0 | 4284 | 771.12 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -114554.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 28.3 | 85 | 0 | 2405.5 | 433 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work Fire Staircase (ST-01). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -116433 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Fire Staircase Flooring Work | 188.8 | 85 | 0 | 16048 | 2888.64 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Fire Staircase (ST-01). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -102790.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 3rd Floor Fire Staircase Flooring Work | 98.4 | 85 | 0 | 8364 | 1505.52 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Fire Staircase (ST-01). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -110474.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Staircase Flooring Work | 24.7 | 85 | 0 | 2099.5 | 377.92 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Skirting Regular Staircase (ST-02). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -116739 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Fire Staircase Flooring Work | 252.7 | 85 | 0 | 21479.5 | 3866.32 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Fire Staircase (ST-01). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -97359 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Staircase Flooring Work | 19.9 | 85 | 0 | 1691.5 | 304.48 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Skirting Regular Staircase (ST-02). | 100 |  | 99458 | 2023-05-06 | 118838.5 | 2023-06-10 10:38 | -117147 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Fire Staircase Flooring Work | 96.9 | 85 | 0 | 8236.5 | 1482.58 | 2023-06-26 11:40 | Material Supply charges of Sadarahalli Granite for Staircase Riser Fire Staircase (ST-01). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -86530 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 71 | 85 | 0 | 6035 | 1086.3 | 2023-06-26 11:41 | Material Supply charges of Sadarahalli Granite for Staircase Riser Fire Staircase (ST-01). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -88731.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Fire Staircase Flooring Work | 71 | 85 | 0 | 6035 | 1086.3 | 2023-06-26 11:41 | Material Supply charges of Sadarahalli Granite for Staircase Riser Fire Staircase (ST-01). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -88731.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 71 | 85 | 0 | 6035 | 1086.3 | 2023-06-26 11:41 | Material Supply charges of Sadarahalli Granite for Staircase Riser Fire Staircase (ST-01). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -88731.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Staircase Flooring Work | 102 | 85 | 0 | 8670 | 1560.6 | 2023-06-26 11:41 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -86096.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 140.1 | 85 | 0 | 11908.5 | 2143.54 | 2023-06-26 11:41 | Material Supply charges of Sadarahalli Granite for Staircase Tread Fire Staircase (ST-01). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -82858 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 3rd Floor Fire Staircase Flooring Work | 6.5 | 85 | 0 | 552.5 | 99.46 | 2023-06-26 11:41 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work Fire Staircase (ST-01). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -94214 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Staircase Flooring Work | 72.3 | 85 | 0 | 6145.5 | 1106.2 | 2023-06-26 11:41 | Material Supply charges of Sadarahalli Granite for Staircase Riser Regular Staircase (ST-02). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -88621 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Fire Staircase Flooring Work | 189.1 | 85 | 0 | 16073.5 | 2893.24 | 2023-06-26 11:40 | Material Supply charges of Sadarahalli Granite for Staircase Tread Fire Staircase (ST-01). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -78693 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Staircase Flooring Work | 105.1 | 85 | 0 | 8933.5 | 1608.04 | 2023-06-26 11:41 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -85833 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F- Bldg Stilt Floor Staircase Flooring Work | 53.3 | 85 | 0 | 4530.5 | 815.5 | 2023-06-26 11:41 | Material Supply charges of Sadarahalli Granite for Staircase Riser Regular Staircase (ST-02). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -90236 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Staircase Flooring Work | 136.6 | 85 | 0 | 11611 | 2089.98 | 2023-06-26 11:41 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 100288 | 2023-06-26 | 94766.5 | 2023-07-19 12:11 | -83155.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 3rd Floor Staircase Flooring Work | 53.3 | 85 | 0 | 4530.5 | 815.5 | 2024-06-09 13:40 | Material Supply charges of Sadarahalli Granite for Staircase Riser Regular Staircase (ST-02). | 100 |  | 108221 | 2024-06-10 | 35483.7 | 2024-07-15 15:21 | -30953.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Fire Staircase Flooring Work | 0.075 | 8 | 0 | 0.6 | 0.1 | 2024-06-09 13:40 | Charges of Sadarahalli Granite Edge Polish work for Tread for Fire Staircase (ST-01). | 100 |  | 108221 | 2024-06-10 | 35483.7 | 2024-07-15 15:21 | -35483.1 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Staircase Flooring Work | 105.1 | 85 | 0 | 8933.5 | 1608.04 | 2024-06-09 13:40 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 108221 | 2024-06-10 | 35483.7 | 2024-07-15 15:21 | -26550.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Staircase Flooring Work | 53.3 | 85 | 0 | 4530.5 | 815.5 | 2024-06-09 13:40 | Material Supply charges of Sadarahalli Granite for Staircase Riser Regular Staircase (ST-02). | 100 |  | 108221 | 2024-06-10 | 35483.7 | 2024-07-15 15:21 | -30953.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 3rd Floor Staircase Flooring Work | 105.1 | 85 | 0 | 8933.5 | 1608.04 | 2024-06-09 13:40 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 108221 | 2024-06-10 | 35483.7 | 2024-07-15 15:21 | -26550.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 40.3941 | 85 | 0 | 3433.4985 | 618.04 | 2024-06-09 13:40 | Material Supply charges of Sadarahalli Granite for Staircase Tread Fire Staircase (ST-01). | 100 |  | 108221 | 2024-06-10 | 35483.7 | 2024-07-15 15:21 | -32050.2015 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 1st Floor Staircase Flooring Work | 3.1 | 85 | 0 | 263.5 | 47.44 | 2024-06-09 13:40 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 108221 | 2024-06-10 | 35483.7 | 2024-07-15 15:21 | -35220.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg 2nd Floor Staircase Flooring Work | 53.3 | 85 | 0 | 4530.5 | 815.5 | 2024-06-09 13:40 | Material Supply charges of Sadarahalli Granite for Staircase Riser Regular Staircase (ST-02). | 100 |  | 108221 | 2024-06-10 | 35483.7 | 2024-07-15 15:21 | -30953.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 644 | 2023-03-29 | F-Bldg LG Floor Fire Staircase Flooring Work | 40.95 | 8 | 0 | 327.6 | 58.96 | 2024-06-09 13:40 | Charges of Sadarahalli Granite Edge Polish work for Skirting for Fire Staircase (ST-01). | 100 |  | 108221 | 2024-06-10 | 35483.7 | 2024-07-15 15:21 | -35156.1 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
300sqmm x 3.5C Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 60 | 99 | 0 | 5940 | 1069.2 | 2024-06-07 15:04 | Labour Charges for 300 sqmm x 3.5C Cable Laying work. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -51283.46 | LAXMI ELECTRICALS ENTERPRISES
3Cx95 sqmm Cable Laying | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 40 | 121 | 0 | 4840 | 871.2 | 2024-06-07 15:04 | Labour charges for Laying of 3C x 95 sqmm cable. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -52383.46 | LAXMI ELECTRICALS ENTERPRISES
4 Way Feeder Pillar | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 1 | 2750 | 0 | 2750 | 495 | 2024-06-07 15:04 | Labour charges for Fixing of 4 way Feeder pillar. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -54473.46 | LAXMI ELECTRICALS ENTERPRISES
Touchproof Jointing Kit (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 1 | 2750 | 0 | 2750 | 495 | 2024-06-07 15:04 | Labour charges for Fixing of 300 sqmm Touchproof jointing kit. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -54473.46 | LAXMI ELECTRICALS ENTERPRISES
End Termination 300sqmm X 3.5 core cable (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 12 | 1870 | 0 | 22440 | 4039.2 | 2024-06-07 15:04 | Providing and fixing of 300 Sqmm x 3.5 C end termination. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -34783.46 | LAXMI ELECTRICALS ENTERPRISES
6 way Feeder Piller (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 2 | 3300 | 0 | 6600 | 1188 | 2024-06-07 15:04 | Labour charges for fixing of 6 Way Feeder piller. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -50623.46 | LAXMI ELECTRICALS ENTERPRISES
Gland Plate Hole Making (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 14 | 100 | 0 | 1400 | 252 | 2024-06-07 15:04 | Labour charges for Gland Plate Hole Making work. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -55823.46 | LAXMI ELECTRICALS ENTERPRISES
95 sqmm Touchproof Jointing Kit (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 2 | 2750 | 0 | 5500 | 990 | 2024-06-07 15:04 | Labour charges for fixing of 95 sqmm Touchproof Jointing Kit. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -51723.46 | LAXMI ELECTRICALS ENTERPRISES
95 sqmm Indoor Jointing Kit (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 0.722 | 6930 | 0 | 5003.46 | 900.62 | 2024-06-07 15:04 | Providing and Fixing of 95 sqmm indoor jointing kit (M+L). | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -52220 | LAXMI ELECTRICALS ENTERPRISES
Excavation & Filling. | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 140 | 176 | 0 | 24640 | 0 | 2023-09-11 | Labour charges for 3 feet Excavation and Filling work (Backside Old Cable removing work) | 100 |  | 101803 | 2023-09-11 | 90695 | 2023-10-23 12:37 | -66055 | LAXMI ELECTRICALS
Full round pipe | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 25 | 55 | 0 | 1375 | 0 | 2023-09-11 | Labour charges for Fixing of 8 inch Full Round pipe (2m- 1Pipe) | 100 |  | 101803 | 2023-09-11 | 90695 | 2023-10-23 12:37 | -89320 | LAXMI ELECTRICALS
300 sqmm Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 420 | 154 | 0 | 64680 | 0 | 2023-09-11 | Labour charges for 3C x 300 sqmm Cable Laying work. | 100 |  | 101803 | 2023-09-11 | 90695 | 2023-10-23 12:37 | -26015 | LAXMI ELECTRICALS
300 sqmm Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 190 | 154 | 0 | 29260 | 5266.8 | 2024-07-03 14:58 | Labour charges for 3C x 300 sqmm Cable Laying work. | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -13787.73 | ADITI POWER CARE AND ENTERPRISES
End Termination 300sqmm X 3.5 core cable (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 4 | 1870 | 0 | 7480 | 1346.4 | 2024-07-03 15:02 | Providing and fixing of 300 Sqmm x 3.5 C end termination. | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -35567.73 | ADITI POWER CARE AND ENTERPRISES
Excavation & Filling. | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 6 | 176 | 0 | 1056 | 190.08 | 2024-07-03 15:07 | Labour charges for 3 feet Excavation and Filling work (Backside Old Cable removing work) | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -41991.73 | ADITI POWER CARE AND ENTERPRISES
95 sqmm Touchproof Jointing Kit (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 1 | 2750 | 0 | 2750 | 495 | 2024-07-03 15:02 | Labour charges for fixing of 95 sqmm Touchproof Jointing Kit. | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -40297.73 | ADITI POWER CARE AND ENTERPRISES
95 sqmm Indoor Jointing Kit (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 0.361 | 6930 | 0 | 2501.73 | 450.32 | 2024-07-03 15:10 | Providing and Fixing of 95 sqmm indoor jointing kit (M+L). | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -40546 | ADITI POWER CARE AND ENTERPRISES
300 sqmm Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 115 | 154 | 0 | 17710 | 3187.8 | 2024-07-29 17:10 | Labour charges for 3C x 300 sqmm Cable Laying work. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -82170 | ADITI POWER CARE AND ENTERPRISES
LT Earthing Set (m+l) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 7 | 4400 | 0 | 30800 | 5544 | 2024-07-29 17:10 | Supply and Labour Charges for fixing of LT Earthing set including Funnel, GI Patti, Salt, Coal,etc | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -69080 | ADITI POWER CARE AND ENTERPRISES
300sqmm x 3.5C Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 340 | 99 | 0 | 33660 | 6058.8 | 2024-07-29 17:10 | Labour Charges for 300 sqmm x 3.5C Cable Laying work. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -66220 | ADITI POWER CARE AND ENTERPRISES
Touchproof Jointing Kit (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 1 | 2750 | 0 | 2750 | 495 | 2024-07-29 17:10 | Labour charges for Fixing of 300 sqmm Touchproof jointing kit. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -97130 | ADITI POWER CARE AND ENTERPRISES
End Termination 300sqmm X 3.5 core cable (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 8 | 1870 | 0 | 14960 | 2692.8 | 2024-07-29 17:10 | Providing and fixing of 300 Sqmm x 3.5 C end termination. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -84920 | ADITI POWER CARE AND ENTERPRISES
Rabit Shifting Work | N/C | N/C | BASSAPPA CHAVAN | 646 | 2023-03-31 | E-Bldg Rabit Shifting Work - 1 No. | 50 | 400 | 0 | 20000 | 0 | 2024-04-08 | Charges for Rabit shifting work Tractor Trips (Loading & Unloading) for E-Bldg | 100 |  | 106710 | 2024-04-08 | 20000 | 2024-06-10 11:28 | 0 | GANESH MAHADU LONDHE
Rabit Shifting Work | N/C | N/C | BASSAPPA CHAVAN | 646 | 2023-03-31 | E-Bldg Rabit Shifting Work - 1 No. | 47 | 400 | 0 | 18800 | 0 | 2024-01-08 | Charges for Rabit shifting work Tractor Trips (Loading & Unloading) for E-Bldg | 100 |  | 104501 | 2024-01-08 | 18800 | 2024-02-05 11:47 | 0 | RATHOD RUKMANA KESHAPPA
Rabit Shifting Work | N/C | N/C | BASSAPPA CHAVAN | 646 | 2023-03-31 | E-Bldg Rabit Shifting Work - 1 No. | 63 | 400 | 0 | 25200 | 0 | 2024-04-08 16:11 | Charges for Rabit shifting work Tractor Trips (Loading & Unloading) for E-Bldg | 100 |  | 106682 | 2024-04-08 | 25200 | 1900-01-01 | 0 | RATHOD RUKMANA KESHAPPA
Rabit Shifting Work | N/C | N/C | BASSAPPA CHAVAN | 646 | 2023-03-31 | E-Bldg Rabit Shifting Work - 1 No. | 13 | 400 | 0 | 5200 | 0 | 2023-08-02 | Charges for Rabit shifting work Tractor Trips (Loading & Unloading) for E-Bldg | 100 |  | 100992 | 2023-08-04 | 5200 | 1900-01-01 | 0 | NAMANNA RATHOD
Rabit Shifting Work | N/C | N/C | BASSAPPA CHAVAN | 646 | 2023-03-31 | E-Bldg Rabit Shifting Work - 1 No. | 62 | 400 | 0 | 24800 | 0 | 2023-12-22 | Charges for Rabit shifting work Tractor Trips (Loading & Unloading) for E-Bldg | 100 |  | 104102 | 2023-12-25 | 24800 | 1900-01-01 | 0 | SHIVAM ENTERPRISES
Rabit Shifting Work | N/C | N/C | BASSAPPA CHAVAN | 646 | 2023-03-31 | E-Bldg Rabit Shifting Work - 1 No. | 30 | 400 | 0 | 12000 | 0 | 2023-04-21 | Charges for Rabit shifting work Tractor Trips (Loading & Unloading) for E-Bldg | 100 |  | 99269 | 2023-04-22 | 12000 | 2023-07-07 11:25 | 0 | BASSAPPA CHAVAN
Rabit Shifting Work | N/C | N/C | BASSAPPA CHAVAN | 647 | 2023-03-31 | F-Bldg Rabit Shifting Work - 1 No. | 34 | 400 | 0 | 13600 | 0 | 2023-06-30 | Charges for Rabit shifting work Tractor Trips (Loading & Unloading) for F-Bldg | 100 |  | 100378 | 2023-07-01 | 13600 | 2023-07-11 13:09 | 0 | BASSAPPA CHAVAN
PCC Work | N/C | N/C | PRAKASH SAHU | 648 | 2023-04-03 | F Building Lift Pit Area Soling & PCC Work | 157.98 | 6 | 0 | 947.88 | 0 | 2023-04-19 | Charges for PCC work of F Building lift pit area. | 100 |  | 99239 | 2023-04-20 | 1974.75 | 2023-07-24 12:29 | -1026.87 | PRAKASH SAHU
Soling Work-BC- | N/C | N/C | PRAKASH SAHU | 648 | 2023-04-03 | F Building Lift Pit Area Soling & PCC Work | 157.98 | 6.5 | 0 | 1026.87 | 0 | 2023-04-19 | Charges for Soling work of F Building lift pit area. | 100 |  | 99239 | 2023-04-20 | 1974.75 | 2023-07-24 12:29 | -947.88 | PRAKASH SAHU
Groove Cutting | N/C | N/C | PRAKASH SAHU | 648 | 2023-04-03 | Groove Cutting For AC Pipe Line | 150 | 20 | 0 | 3000 | 0 | 2023-10-07 09:28 | Labour Charges for Groove Cutting work for AC Pipe line in F Building OPD Area | 100 |  | 102434 | 2023-10-09 | 3000 | 2023-10-23 12:31 | 0 | PRABHURAM VERMA
Murum filling Labour BC | N/C | N/C | PRAKASH SAHU | 649 | 2023-04-03 | F Building Lift Pit Murum Filling work - 1 No. | 527 | 3.5 | 0 | 1844.5 | 0 | 2023-05-17 | Charges for Murum Filling work for F Building lift pit area. | 100 |  | 99697 | 2023-05-18 | 1844.5 | 2023-07-11 13:08 | 0 | PRAKASH SAHU
Murum filling Labour BC | N/C | N/C | PRAKASH SAHU | 649 | 2023-04-03 | F Building Lift Pit Murum Filling work - 1 No. | 572.68 | 3.5 | 0 | 2004.38 | 0 | 2024-07-17 | Charges for Murum Filling work for F Building lift pit area. | 100 |  | 109235 | 2024-07-22 | 2004.38 | 1900-01-01 | 0 | PRAKASH SAHU
Earthing work(m+l)- BC | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 650 | 2023-04-06 | F Building Earthing Work(Temporary earthing work) 1 No. | 4 | 4800 | 0 | 19200 | 3456 | 2023-10-03 | Labour and Material Charges for Earthing work with excavation,Fixing and Supply of Salt,Coal,GI Pipe with Funnel,GI Plate,GI Wire etc material for Elevator. | 100 |  | 102214 | 2023-10-04 | 28800 | 2023-11-01 14:24 | -9600 | HARISH CHANDRA JADHAV ELECTRICALS
Earthing work(m+l)- BC | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 650 | 2023-04-06 | F Building Earthing Work(Temporary earthing work) 1 No. | 2 | 4800 | 0 | 9600 | 1728 | 2023-10-03 | Labour and Material Charges for Earthing work of meter room including Excavation supply of Coal,Salt,GI Pipe with funnel,GI Plate,GI Wire etc. | 100 |  | 102214 | 2023-10-04 | 28800 | 2023-11-01 14:24 | -19200 | HARISH CHANDRA JADHAV ELECTRICALS
B.O.C.W. Act Registration &Compliance. | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 651 | 2023-04-07 | Contract Labour act Registration & Compliance | 81 | 350 | 0 | 28350 | 5103 | 2024-04-08 | BOCW Registration under Contract Labour Act Registration from 1st March 2024 to 31st December 2024. | 100 |  | 106655 | 2024-04-08 | 28350 | 2024-04-09 14:47 | 0 | NIKISHA CONSULTANCY SERVICES
B.O.C.W. Act Registration &Compliance. | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 651 | 2023-04-07 | Contract Labour act Registration & Compliance | 294 | 350 | 0 | 102900 | 18522 | 2024-04-08 | BOCW Registration under Contract Labour Act Registration from 1st March 2024 to 31st December 2024. | 100 |  | 106656 | 2024-04-08 | 234150 | 2024-04-09 14:47 | -131250 | NIKISHA CONSULTANCY SERVICES
Registration of Company (RC) | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 651 | 2023-04-07 | Contract Labour act Registration & Compliance | 375 | 350 | 0 | 131250 | 23625 | 2024-04-08 | Company Registration (RC) under contract Labour Act Registration from 1st March 2024 to 31st December 2025. | 100 |  | 106656 | 2024-04-08 | 234150 | 2024-04-09 14:47 | -102900 | NIKISHA CONSULTANCY SERVICES
B.O.C.W. Act Registration &Compliance. | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 651 | 2023-04-07 | Contract Labour act Registration & Compliance | 1 | 34000 | 0 | 34000 | 6120 | 2023-04-10 | BOCW Registration under contract Labour Act Registration for the year- 2023 (136 Nos x 250) | 100 |  | 99110 | 2023-04-11 | 106250 | 2023-04-11 11:50 | -72250 | NIKISHA CONSULTANCY SERVICES
Registration of Company (RC) | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 651 | 2023-04-07 | Contract Labour act Registration & Compliance | 1 | 72250 | 0 | 72250 | 13005 | 2023-04-10 | Company Registration (RC) under contract Labour Act Registration for the year 2023 (289 Nos x 250) | 100 |  | 99110 | 2023-04-11 | 106250 | 2023-04-11 11:50 | -34000 | NIKISHA CONSULTANCY SERVICES
Bobcat Hiring Charges | N/C | N/C | GANESH MAHADU LONDHE | 652 | 2023-04-07 | STP-265 KLD Murum Backfilling Work - 1 No. | 28 | 850 | 0 | 23800 | 0 | 2023-05-16 | Bobcat Hiring charges for levelling work for Old STP 265 KLD Murrum Backfilling work. | 100 |  | 99675 | 2023-05-17 | 23800 | 2023-06-10 10:41 | 0 | GANESH MAHADU LONDHE
Spreading & Levelling Work | N/C | N/C | GANESH MAHADU LONDHE | 652 | 2023-04-07 | STP-265 KLD Murum Backfilling Work - 1 No. | 465 | 15 | 0 | 6975 | 0 | 2023-07-05 | Labour Charges for Spreading and Levelling work for Old STP 265 KLD. | 100 |  | 100532 | 2023-07-07 | 6975 | 2023-07-26 12:26 | 0 | SHIVAM ENTERPRISES
RCC Work - DCH | N/C | N/C | VIJAY MOHITE | 653 | 2023-04-08 | STP-265 KLD RCC Work (L) | 1 | 400000 | 0 | 400000 | 0 | 2023-10-07 17:07 | Labour Charges for PCC Work below raft Slab, Raft Box, RCC Pardi, Beam, Slab, Steel work and shuttering work included for 265 KLD STP of D & E-Bldg. | 100 |  | 102419 | 2023-10-07 | 400000 | 2023-10-11 19:10 | 0 | VIJAY MOHITE
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 24th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 9.8 | 8 | 0 | 78.4 | 14.12 | 2024-01-07 | Charges and Quantity Diff. of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -22002.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor- ST-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for Parking Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 9.8 | 8 | 0 | 78.4 | 14.12 | 2024-01-07 | Charges and Quantity Diff. of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -22002.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-01 Flooring Work | 19.7 | 8 | 0 | 157.6 | 28.36 | 2024-01-07 | Charges and Quantity Diff. of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21923.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for Parking Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Stilt Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 9.8 | 8 | 0 | 78.4 | 14.12 | 2024-01-07 | Charges and Quantity Diff. of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -22002.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor - ST-02 Flooring Work | 94.2 | 8 | 0 | 753.6 | 135.64 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Skirting for Parking Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21327.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 113.8 | 85 | 0 | 9673 | 1741.14 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work for Parking Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -199333.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-06-09 13:51 | Material Supply charges of Sadarahalli Granite for Parking Staircase Skirting Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -207009 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 49.4 | 85 | 0 | 4199 | 755.82 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204807.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Fire Staircase-01 Flooring Work | 20 | 85 | 0 | 1700 | 306 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90893.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 24th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bdlg 5th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 24th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 5th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 17.25 | 85 | 0 | 1466.25 | 263.92 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -91127.65 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 1.19 | 85 | 0 | 101.15 | 18.2 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -92492.75 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Regular Staircase-02 Flooring Work | 23.5 | 85 | 0 | 1997.5 | 359.56 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Regular Staircase (ST-02). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90596.4 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-07-08 | Material Supply charges of Sadarahalli Granite for Staircase Skirting work D-Bldg Fire Staircase (ST-01). | 100 |  | 108939 | 2024-07-08 | 92593.9 | 2024-07-24 17:11 | -90621.9 | SONA MARBLE
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 18.87 | 85 | 0 | 1603.95 | 288.72 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -117912 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 5th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-10-20 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 102916 | 2023-10-23 | 119515.95 | 2023-12-02 12:18 | -109689.95 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -319987.35 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -320216.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -319987.35 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -320216.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Regular Staircase-02 Flooring Work | 9.4 | 85 | 0 | 799 | 143.82 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -329014.35 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -320216.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -319987.35 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -320216.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 96.73 | 85 | 0 | 8222.05 | 1479.96 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -321591.3 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bdlg 5th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -115779 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 7.3059 | 85 | 0 | 621.0015 | 111.78 | 2023-08-03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 100999 | 2023-08-04 | 125375.5 | 2023-09-04 11:38 | -124754.4985 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 22 | 85 | 0 | 1870 | 336.6 | 2023-06-08 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -44763.1 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-06-05 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -42187.6 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 5th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-06-05 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -42187.6 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 5th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-06-05 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -42187.6 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-06-05 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -42187.6 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Stilt Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 92.6 | 8 | 0 | 740.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish for skirting for Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34786.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 93.1 | 8 | 0 | 744.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish for skirting for Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34782.4 | PAPPU BAGELA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:21 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:36 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Regular Staircase-02 Flooring Work | 42.9 | 85 | 0 | 3646.5 | 656.38 | 2023-09-18 16:48 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -125086 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 49.5 | 85 | 0 | 4207.5 | 757.36 | 2023-09-18 16:36 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -124525 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-09-18 16:43 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -124287 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:21 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-09-18 16:43 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -124287 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:36 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bdlg 5th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-09-18 16:24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 101950 | 2023-09-20 | 128732.5 | 2023-12-02 12:18 | -122145 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Stilt Fire Staircase-01 Flooring Work | 16.3059 | 85 | 0 | 1386.0015 | 249.48 | 2023-05-05 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99461 | 2023-05-06 | 1386 | 2023-06-10 10:37 | 0.0015 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bdlg 5th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 5th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 92.6 | 8 | 0 | 740.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish for skirting for Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34786.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 92.6 | 8 | 0 | 740.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish for skirting for Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34786.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 94.1 | 8 | 0 | 752.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for skirting for D-Bldg Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34774.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Regular Staircase-02 Flooring Work | 95.3 | 8 | 0 | 762.4 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish work for Skirting for D-Bldg Regular Staircase (ST-02). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34764.8 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 92.6 | 8 | 0 | 740.8 | 0 | 2024-03-09 | Charges of Sadarahalli Granite Edge Polish for skirting for Fire Staircase (ST-01). | 100 |  | 105893 | 2024-03-11 | 35527.2 | 2024-03-18 12:11 | -34786.4 | PAPPU BAGELA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-06-08 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -42187.6 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 52.875 | 8 | 0 | 423 | 76.14 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46210.1 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-06-05 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -42187.6 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-06-05 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -42187.6 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-06-09 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 100026 | 2023-06-09 | 46633.1 | 2023-06-20 16:53 | -46003.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 5th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 2nd Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 54.4824 | 85 | 0 | 4631.004 | 833.58 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -138592.496 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 3 | 85 | 0 | 255 | 45.9 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -142968.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 3rd Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 4th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-06-02 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 99880 | 2023-06-03 | 143223.5 | 2023-06-20 16:53 | -136636 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 22.8 | 85 | 0 | 1938 | 348.84 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Parking Staircase skirting Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -207068.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 22.8 | 85 | 0 | 1938 | 348.84 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Parking Staircase skirting Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -207068.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor- ST-02 Flooring Work | 49.4 | 85 | 0 | 4199 | 755.82 | 2024-06-09 13:44 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204807.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-02 Flooring Work | 100 | 85 | 0 | 8500 | 1530 | 2024-06-09 13:58 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -200506.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-02 Flooring Work | 50 | 85 | 0 | 4250 | 765 | 2024-06-09 14:03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204756.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-02 Flooring Work | 58.1 | 85 | 0 | 4938.5 | 888.94 | 2024-06-09 13:44 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204068 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-02 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-06-09 13:51 | Material Supply charges of Sadarahalli Granite for Parking Staircase Skirting Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -207034.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 61 | 85 | 0 | 5185 | 933.3 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -203821.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-01 Flooring Work | 100 | 85 | 0 | 8500 | 1530 | 2024-06-09 13:58 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work for Parking Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -200506.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 49.4 | 85 | 0 | 4199 | 755.82 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204807.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 113.8 | 85 | 0 | 9673 | 1741.14 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work for Parking Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -199333.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 49.4 | 85 | 0 | 4199 | 755.82 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204807.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-01 Flooring Work | 72.3 | 85 | 0 | 6145.5 | 1106.2 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -202861 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 23.1 | 85 | 0 | 1963.5 | 353.44 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Parking Staircase skirting Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -207043 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor - ST-02 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-06-09 13:51 | Material Supply charges of Sadarahalli Granite for Parking Staircase Skirting Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -207034.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-02 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-06-09 13:51 | Material Supply charges of Sadarahalli Granite for Parking Staircase Skirting Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -207034.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Stilt Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2024-06-09 13:58 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204561 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-01 Flooring Work | 50 | 85 | 0 | 4250 | 765 | 2024-06-09 14:03 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work for Parking Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204756.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 113.8 | 85 | 0 | 9673 | 1741.14 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work for Parking Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -199333.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Stilt Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2024-06-09 13:58 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -199180.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 49.4 | 85 | 0 | 4199 | 755.82 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204807.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 22.8 | 85 | 0 | 1938 | 348.84 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Parking Staircase skirting Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -207068.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor - ST-02 Flooring Work | 113 | 85 | 0 | 9605 | 1728.9 | 2024-06-09 13:44 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -199401.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-02 Flooring Work | 113 | 85 | 0 | 9605 | 1728.9 | 2024-06-09 13:44 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -199401.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor - ST-02 Flooring Work | 49.4 | 85 | 0 | 4199 | 755.82 | 2024-06-09 13:44 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204807.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-02 Flooring Work | 49.4 | 85 | 0 | 4199 | 755.82 | 2024-06-09 13:44 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204807.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 113.8 | 85 | 0 | 9673 | 1741.14 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work for Parking Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -199333.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 22.8 | 85 | 0 | 1938 | 348.84 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Parking Staircase skirting Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -207068.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-02 Flooring Work | 113 | 85 | 0 | 9605 | 1728.9 | 2024-06-09 13:44 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -199401.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor- ST-02 Flooring Work | 113 | 85 | 0 | 9605 | 1728.9 | 2024-06-09 13:44 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -199401.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-02 Flooring Work | 49.4 | 85 | 0 | 4199 | 755.82 | 2024-06-09 13:44 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -204807.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 113.6 | 85 | 0 | 9656 | 1738.08 | 2024-06-09 13:42 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work for Parking Fire Staircase (ST-01). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -199350.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-02 Flooring Work | 113 | 85 | 0 | 9605 | 1728.9 | 2024-06-09 13:44 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -199401.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor- ST-02 Flooring Work | 23.2 | 85 | 0 | 1972 | 354.96 | 2024-06-09 13:51 | Material Supply charges of Sadarahalli Granite for Parking Staircase Skirting Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -207034.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-02 Flooring Work | 40 | 85 | 0 | 3400 | 612 | 2024-06-09 14:03 | Material Supply charges of Sadarahalli Granite for Parking Staircase Riser Regular Staircase (ST-02). | 100 |  | 108222 | 2024-06-10 | 209006.5 | 2024-07-15 15:22 | -205606.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 55.5 | 85 | 0 | 4717.5 | 849.16 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -170533 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 5.8 | 85 | 0 | 493 | 88.74 | 2023-12-30 | Material Supply charges and Quantity Diff. of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174757.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 5.8 | 85 | 0 | 493 | 88.74 | 2023-12-30 | Material Supply charges and Quantity Diff. of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174757.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-12-31 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174620.9 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-01 Flooring Work | 9 | 85 | 0 | 765 | 137.7 | 2023-12-30 | Material Supply charges and Quantity Diff. of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174485.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-12-31 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174620.9 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 105.5941 | 85 | 0 | 8975.4985 | 1615.6 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -166275.0015 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bdlg 5th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-12-31 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174620.9 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 28 | 85 | 0 | 2380 | 428.4 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -172870.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 24th Fire Staircase-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Stilt Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 5.8 | 85 | 0 | 493 | 88.74 | 2023-12-30 | Material Supply charges and Quantity Diff. of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174757.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-02 Flooring Work | 116.3 | 85 | 0 | 9885.5 | 1779.4 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -165365 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor - ST-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 24th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-12-31 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174620.9 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-01 Flooring Work | 116.3 | 85 | 0 | 9885.5 | 1779.4 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -165365 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Stilt Fire Staircase-01 Flooring Work | 61 | 85 | 0 | 5185 | 933.3 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -170065.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-12-31 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174620.9 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-12-31 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174620.9 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 5.8 | 85 | 0 | 493 | 88.74 | 2023-12-30 | Material Supply charges and Quantity Diff. of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174757.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 5.8 | 85 | 0 | 493 | 88.74 | 2023-12-30 | Material Supply charges and Quantity Diff. of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174757.5 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor- ST-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 24th Fire Staircase-01 Flooring Work | 86.82 | 85 | 0 | 7379.7 | 1328.34 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -167870.8 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-12-31 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174620.9 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2023-12-31 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -174620.9 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Regular Staircase-02 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
sadarali Granite Tread (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 77.5 | 85 | 0 | 6587.5 | 1185.76 | 2023-12-30 | Material Supply charges of Sadarahalli Granite for Parking Staircase Tread Fire Staircase (ST-01). | 100 |  | 104249 | 2024-01-01 | 175250.5 | 2024-01-23 14:22 | -168663 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for Parking Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 24th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Stilt Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-02 Flooring Work | 118.1 | 8 | 0 | 944.8 | 170.06 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for Parking Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21136 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 1st Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg LG Floor ST-01 Flooring Work | 118.1 | 8 | 0 | 944.8 | 170.06 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21136 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 9.8 | 8 | 0 | 78.4 | 14.12 | 2024-01-07 | Charges and Quantity Diff. of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -22002.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for Parking Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 9.8 | 8 | 0 | 78.4 | 14.12 | 2024-01-07 | Charges and Quantity Diff. of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -22002.4 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Regular Staircase-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish for Tread for Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg P1 Floor - ST-02 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for Parking Regular Staircase (ST-02). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
S. Halli Edge Polish- BCo | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 78.7 | 8 | 0 | 629.6 | 113.32 | 2024-01-07 | Charges of Sadarahalli Granite Edge Polish work for Tread for D-Bldg Fire Staircase (ST-01). | 100 |  | 104376 | 2024-01-08 | 22080.8 | 2024-02-02 14:54 | -21451.2 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 12th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -320216.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bdlg 5th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -320216.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -320216.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -319987.35 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 6th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -319987.35 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 19th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 20th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -319987.35 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -320216.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 17th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -319987.35 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 8th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 10th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -319987.35 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -319987.35 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 115.6 | 85 | 0 | 9826 | 1768.68 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -319987.35 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 21st Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Riser work D-Bldg Fire Staircase (ST-01). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Flooring (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 22nd Regular Staircase-02 Flooring Work | 112.9 | 85 | 0 | 9596.5 | 1727.38 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Flooring work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -320216.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 9th Regular Staircase-02 Flooring Work | 52.3 | 85 | 0 | 4445.5 | 800.2 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -325367.85 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Riser (M) | N/C | N/C | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA | 654 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 32.927 | 85 | 0 | 2798.795 | 503.78 | 2023-11-24 | Material Supply charges of Sadarahalli Granite for Staircase Tread work D-Bldg Regular Staircase (ST-02). | 100 |  | 103495 | 2023-11-25 | 329813.35 | 2023-12-25 15:39 | -327014.555 | SAINATH GRANITES & MARBLES PROP REDDY CHAVVA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 5th Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 5th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 1st Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132956.8 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 1st Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 4th Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 1st Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 3rd Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 3rd Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 3rd Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 4th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 2nd Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 2nd Fire Staircase-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-09-13 12:09 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132953.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 2nd Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 4th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-09-13 11:50 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -132089.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 5th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-09-13 12:05 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 101854 | 2023-09-15 | 135788.8 | 2023-09-30 11:24 | -133270.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121284.8 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 14th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 15th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 1st Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121281.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 2nd Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121281.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 1st Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121598.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bdlg 5th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121281.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 4th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121598.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 6th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121281.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bdlg 5th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121598.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 3rd Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121598.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121598.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121598.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 5th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bdlg 5th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -120504 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -120417.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 3rd Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -120504 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 1st Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 3rd Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 4th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121281.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 1st Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -120504 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 4th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 3rd Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121281.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 2nd Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 2nd Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -120504 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 4th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -120504 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 2nd Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121598.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 6th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121598.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -120417.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 6th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -120504 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121284.8 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121284.8 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 10th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121598.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -120417.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 56.46 | 40 | 0 | 2258.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121858.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2023-10-10 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 102496 | 2023-10-11 | 124116.8 | 2023-10-28 11:59 | -121598.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 15th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 16th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 15th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 16th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg Stilt Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215372.8 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 19th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 16th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 21st Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 91.04 | 40 | 0 | 3641.6 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214563.2 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 13th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 88.32 | 40 | 0 | 3532.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214672 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 91.04 | 40 | 0 | 3641.6 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214563.2 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 19th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 9th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 19th Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215372.8 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 91.04 | 40 | 0 | 3641.6 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214563.2 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 91.04 | 40 | 0 | 3641.6 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214563.2 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 91.04 | 40 | 0 | 3641.6 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214563.2 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 7th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 12th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 12th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 17th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 12th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 19th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214505.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg LG Floor ST-01 Flooring Work | 94.48 | 40 | 0 | 3779.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214425.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 13th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 20th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 21st Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 20th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214505.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 20th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215372.8 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 19th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 13th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 20th Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215372.8 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 10th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 21st Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 21st Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214505.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 22nd Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 11th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 11th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 11th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 20th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg LG Floor ST-01 Flooring Work | 110.24 | 40 | 0 | 4409.6 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -213795.2 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 19th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 21st Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 22nd Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 10th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 8th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 9th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg Stilt Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 21st Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215372.8 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 17th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 15th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 17th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -214592 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 20th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215686.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 7th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 8th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-01-13 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 104558 | 2024-01-15 | 218204.8 | 2024-01-23 14:18 | -215369.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg Ground Floor- ST-01 Flooring Work | 74.08 | 40 | 0 | 2963.2 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102408 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 10th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 21st Fire Staircase-01 Flooring Work | 75.28 | 40 | 0 | 3011.2 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102360 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 75.28 | 40 | 0 | 3011.2 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102360 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 9th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 18th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg Stilt Fire Staircase-01 Flooring Work | 75.28 | 40 | 0 | 3011.2 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102360 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P1 Floor- ST-01 Flooring Work | 74.08 | 40 | 0 | 2963.2 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102408 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P2 Floor - ST-01 Flooring Work | 74.08 | 40 | 0 | 2963.2 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102408 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P3 Floor ST-01 Flooring Work | 74.96 | 40 | 0 | 2998.4 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102372.8 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 11th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 12th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 6th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 19th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg LG Floor ST-01 Flooring Work | 174.56 | 40 | 0 | 6982.4 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -98388.8 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bdlg 5th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 14th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 16th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 17th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 12th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 18th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 21st Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 13th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 1st Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 20th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 10th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 22nd Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 6th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 9th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 7th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 8th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg P5 Floor - ST-01 Flooring Work | 74.08 | 40 | 0 | 2963.2 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102408 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 11th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 16th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 17th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 8th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 19th Fire Staircase-01 Flooring Work | 75.28 | 40 | 0 | 3011.2 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102360 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 13th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 20th Fire Staircase-01 Flooring Work | 75.28 | 40 | 0 | 3011.2 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102360 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 7th Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 1st Fire Staircase-01 Flooring Work | 18.82 | 40 | 0 | 752.8 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Fire Staircase (ST-01) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -104618.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 15th Regular Staircase-02 Flooring Work | 76.24 | 40 | 0 | 3049.6 | 0 | 2024-03-06 | Labour charges for Fixing of Sadarahalli Granite Skirting work for D-Bldg Regular Staircase (ST-02) | 100 |  | 105873 | 2024-03-11 | 105371.2 | 2024-03-20 15:37 | -102321.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 22nd Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -39731.2 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -39731.2 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -40512 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -40508.8 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 22nd Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -39644.8 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -40825.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Regular Staircase-02 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -40825.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Fire Staircase-01 Flooring Work | 70.8 | 40 | 0 | 2832 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -40512 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -40825.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Regular Staircase-02 Flooring Work | 90.32 | 40 | 0 | 3612.8 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -39731.2 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Regular Staircase-02 Flooring Work | 70.88 | 40 | 0 | 2835.2 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Riser work for D-Bldg Regular Staircase (ST-02) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -40508.8 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -39644.8 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 24th Fire Staircase-01 Flooring Work | 92.48 | 40 | 0 | 3699.2 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Flooring work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -39644.8 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 655 | 2023-04-10 | D-Bldg 23rd Fire Staircase-01 Flooring Work | 62.96 | 40 | 0 | 2518.4 | 0 | 2024-07-28 | Labour charges for Fixing of Sadarahalli Granite Tread work for D-Bldg Fire Staircase (ST-01) | 100 |  | 109408 | 2024-07-29 | 43344 | 2024-08-05 14:01 | -40825.6 | PAPPU BAGELA
MS Square Pipe (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 397.17 | 15 | 0 | 5957.55 | 1072.36 | 2023-07-29 | Labour charges for Fixing of Vertical Square pipe for door support & Horizontal square pipe 40x40mm for New Labour camp at P1 floor Podium. | 100 |  | 100910 | 2023-07-29 | 5957.55 | 2023-08-21 13:37 | 0 | PRESSMET ENTERPRISES
GI Sheet Fixing (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 3926 | 5 | 0 | 19630 | 0 | 2023-07-11 | Labour charges for fixing of GI sheet including tapping screw for New Labour camp work at P1 floor Podium. | 100 |  | 100637 | 2023-07-12 | 19630 | 1900-01-01 | 0 | PARTH ENTERPRISES
MS Square Pipe (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 1236 | 15 | 0 | 18540 | 0 | 2024-01-30 | Labour charges for Fixing of Vertical Square pipe for door support & Horizontal square pipe 40x40mm for New Labour camp at P1 floor Podium. | 100 |  | 105003 | 2024-02-05 | 21791 | 2024-03-12 14:17 | -3251 | SURESH RANGNATH SHITOLE
MS Square Pipe (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 216.7333 | 15 | 0 | 3250.9995 | 0 | 2024-01-30 | Labour charges for Fixing of Vertical Square pipe for door support & Horizontal square pipe 40x40mm for New Labour camp at P1 floor Podium. | 100 |  | 105003 | 2024-02-05 | 21791 | 2024-03-12 14:17 | -18540.0005 | SURESH RANGNATH SHITOLE
MS Square Pipe (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 786 | 15 | 0 | 11790 | 0 | 2024-04-12 | Labour charges for Fixing of Vertical Square pipe for door support & Horizontal square pipe 40x40mm for New Labour camp at P1 floor Podium. | 100 |  | 106778 | 2024-04-15 | 12690 | 2024-05-28 19:15 | -900 | SURESH RANGNATH SHITOLE
MS Square Pipe (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 60 | 15 | 0 | 900 | 0 | 2024-04-12 | Labour charges for Fixing of Vertical Square pipe for door support & Horizontal square pipe 40x40mm for New Labour camp at P1 floor Podium. | 100 |  | 106778 | 2024-04-15 | 12690 | 2024-05-28 19:15 | -11790 | SURESH RANGNATH SHITOLE
MS Square Pipe (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 168 | 15 | 0 | 2520 | 0 | 2023-10-11 | Labour charges for Fixing of Vertical Square pipe for door support & Horizontal square pipe 40x40mm for New Labour camp at P1 floor Podium. | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102556 | 2023-10-12 | 2520 | 2023-11-24 10:34 | 0 | PAWAR SHIVAPPA TARANAIK
GI Sheet Fixing (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 4967.4 | 5 | 0 | 24837 | 0 | 2023-05-10 | Labour charges for fixing of GI sheet including tapping screw for New Labour camp work at P1 floor Podium. | 100 |  | 99569 | 2023-05-10 | 24837 | 2023-05-15 18:32 | 0 | IZHAR MANSOOR SHAIKH
GI Sheet Fixing (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 928.4 | 5 | 0 | 4642 | 0 | 2024-08-05 | Labour charges for fixing of GI sheet including tapping screw for New Labour camp work at P1 floor Podium. | 100 |  | 109610 | 2024-08-05 | 4642 | 1900-01-01 | 0 | SURESH RANGNATH SHITOLE
MS Square Pipe (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 580 | 15 | 0 | 8700 | 0 | 2023-08-05 | Labour charges for Fixing of Vertical Square pipe for door support & Horizontal square pipe 40x40mm for New Labour camp at P1 floor Podium. | 100 |  | 101044 | 2023-08-05 | 8700 | 1900-01-01 | 0 | SURESH RANGNATH SHITOLE
MS Square Pipe (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 530 | 15 | 0 | 7950 | 0 | 2023-08-05 | Labour charges for Fixing of Vertical Square pipe for door support & Horizontal square pipe 40x40mm for New Labour camp at P1 floor Podium. | 100 |  | 101045 | 2023-08-05 | 7950 | 2023-09-12 13:01 | 0 | SURESH RANGNATH SHITOLE
MS Square Pipe (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 304 | 15 | 0 | 4560 | 0 | 2023-08-07 | Labour charges for Fixing of Vertical Square pipe for door support & Horizontal square pipe 40x40mm for New Labour camp at P1 floor Podium. | 100 |  | 101072 | 2023-08-07 | 4560 | 2023-09-12 13:01 | 0 | SURESH RANGNATH SHITOLE
GI Sheet Fixing (L) | N/C | N/C | PRESSMET ENTERPRISES | 656 | 2023-04-10 | Arcadia-Labour Camp at Podium Fabrication Work | 129 | 5 | 0 | 645 | 116.1 | 2023-12-18 | Labour charges for fixing of GI sheet including tapping screw for New Labour camp work at P1 floor Podium. | 100 |  | 104047 | 2023-12-18 | 645 | 1900-01-01 | 0 | SURESH RANGNATH SHITOLE
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 27.5 | 40 | 0 | 1100 | 0 | 2023-08-12 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101218 | 2023-08-12 | 3000 | 2023-08-12 14:27 | -1900 | PAWAR SHIVAPPA TARANAIK
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Fire Staircase Flooring Work | 28.25 | 40 | 0 | 1130 | 0 | 2023-08-12 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101218 | 2023-08-12 | 3000 | 2023-08-12 14:27 | -1870 | PAWAR SHIVAPPA TARANAIK
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 19.25 | 40 | 0 | 770 | 0 | 2023-08-12 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101218 | 2023-08-12 | 3000 | 2023-08-12 14:27 | -2230 | PAWAR SHIVAPPA TARANAIK
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 19.68 | 40 | 0 | 787.2 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22174.2 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Fire Staircase Flooring Work | 29.535 | 40 | 0 | 1181.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -21780 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Fire Staircase Flooring Work | 21.66 | 40 | 0 | 866.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22095 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 21.66 | 40 | 0 | 866.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22095 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Fire Staircase Flooring Work | 19.68 | 40 | 0 | 787.2 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22174.2 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Staircase Flooring Work | 9.375 | 40 | 0 | 375 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22586.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Staircase Flooring Work | 9.375 | 40 | 0 | 375 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22586.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 19.68 | 40 | 0 | 787.2 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22174.2 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 21.66 | 40 | 0 | 866.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22095 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Staircase Flooring Work | 7.56 | 40 | 0 | 302.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22659 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Staircase Flooring Work | 9.375 | 40 | 0 | 375 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22586.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Staircase Flooring Work | 14.76 | 40 | 0 | 590.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22371 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Staircase Flooring Work | 9.375 | 40 | 0 | 375 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22586.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Fire Staircase Flooring Work | 14.76 | 40 | 0 | 590.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22371 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Staircase Flooring Work | 7.56 | 40 | 0 | 302.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22659 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Staircase Flooring Work | 14.76 | 40 | 0 | 590.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Tread work Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22371 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Staircase Flooring Work | 7.56 | 40 | 0 | 302.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22659 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Fire Staircase Flooring Work | 0.07 | 40 | 0 | 2.8 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22958.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Staircase Flooring Work | 14.76 | 40 | 0 | 590.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22371 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Staircase Flooring Work | 20.67 | 40 | 0 | 826.8 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22134.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 0.82 | 40 | 0 | 32.8 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22928.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Fire Staircase Flooring Work | 3.99 | 40 | 0 | 159.6 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22801.8 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Staircase Flooring Work | 16.245 | 40 | 0 | 649.8 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22311.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Fire Staircase Flooring Work | 37.905 | 40 | 0 | 1516.2 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -21445.2 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Staircase Flooring Work | 7.56 | 40 | 0 | 302.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22659 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 9.07 | 40 | 0 | 362.8 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22598.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Fire Staircase Flooring Work | 26.58 | 40 | 0 | 1063.2 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -21898.2 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Staircase Flooring Work | 7.56 | 40 | 0 | 302.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22659 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Staircase Flooring Work | 19.2 | 40 | 0 | 768 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22193.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Staircase Flooring Work | 16.245 | 40 | 0 | 649.8 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Riser work Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22311.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Fire Staircase Flooring Work | 17.25 | 40 | 0 | 690 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22271.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Fire Staircase Flooring Work | 24.03 | 40 | 0 | 961.2 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22000.2 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Staircase Flooring Work | 16.245 | 40 | 0 | 649.8 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22311.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Staircase Flooring Work | 12.315 | 40 | 0 | 492.6 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22468.8 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Staircase Flooring Work | 14.76 | 40 | 0 | 590.4 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22371 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 17.25 | 40 | 0 | 690 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22271.4 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Staircase Flooring Work | 16.245 | 40 | 0 | 649.8 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22311.6 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 17.25 | 40 | 0 | 690 | 0 | 2024-05-06 16:10 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Fire Staircase (ST-01). | 100 |  | 107414 | 2024-05-07 | 22961.4 | 1900-01-01 | -22271.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Staircase Flooring Work | 42.84 | 40 | 0 | 1713.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -145401 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Staircase Flooring Work | 117.13 | 40 | 0 | 4685.2 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -142429.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Staircase Flooring Work | 83.64 | 40 | 0 | 3345.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143769 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Staircase Flooring Work | 92.055 | 40 | 0 | 3682.2 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143432.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Staircase Flooring Work | 83.64 | 40 | 0 | 3345.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143769 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Fire Staircase Flooring Work | 83.64 | 40 | 0 | 3345.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143769 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Staircase Flooring Work | 42.84 | 40 | 0 | 1713.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -145401 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Staircase Flooring Work | 83.64 | 40 | 0 | 3345.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Tread work Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143769 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Fire Staircase Flooring Work | 97.75 | 40 | 0 | 3910 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143204.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Fire Staircase Flooring Work | 122.74 | 40 | 0 | 4909.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -142205 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 122.74 | 40 | 0 | 4909.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -142205 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 122.74 | 40 | 0 | 4909.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -142205 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 111.52 | 40 | 0 | 4460.8 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -142653.8 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Staircase Flooring Work | 42.84 | 40 | 0 | 1713.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -145401 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Staircase Flooring Work | 53.125 | 40 | 0 | 2125 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -144989.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Staircase Flooring Work | 108.8 | 40 | 0 | 4352 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -142762.6 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Staircase Flooring Work | 42.84 | 40 | 0 | 1713.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -145401 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Staircase Flooring Work | 92.055 | 40 | 0 | 3682.2 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Riser work Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143432.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Fire Staircase Flooring Work | 136.17 | 40 | 0 | 5446.8 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -141667.8 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Staircase Flooring Work | 69.785 | 40 | 0 | 2791.4 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -144323.2 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Staircase Flooring Work | 92.055 | 40 | 0 | 3682.2 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143432.4 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 160.48 | 40 | 0 | 6419.2 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -140695.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 3rd Floor Fire Staircase Flooring Work | 22.61 | 40 | 0 | 904.4 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -146210.2 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Fire Staircase Flooring Work | 160.48 | 40 | 0 | 6419.2 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -140695.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Staircase Flooring Work | 53.125 | 40 | 0 | 2125 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -144989.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Fire Staircase Flooring Work | 111.52 | 40 | 0 | 4460.8 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -142653.8 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Staircase Flooring Work | 53.125 | 40 | 0 | 2125 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -144989.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 111.52 | 40 | 0 | 4460.8 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -142653.8 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 97.75 | 40 | 0 | 3910 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143204.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Fire Staircase Flooring Work | 167.365 | 40 | 0 | 6694.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -140420 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Fire Staircase Flooring Work | 97.75 | 40 | 0 | 3910 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143204.6 | PAPPU BAGELA
Sadarali Granite Riser (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F- Bldg Stilt Floor Staircase Flooring Work | 92.055 | 40 | 0 | 3682.2 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Riser work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143432.4 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Fire Staircase Flooring Work | 150.62 | 40 | 0 | 6024.8 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -141089.8 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Fire Staircase Flooring Work | 160.48 | 40 | 0 | 6419.2 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -140695.4 | PAPPU BAGELA
Sadarali Granite Skirting (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 1st Floor Staircase Flooring Work | 53.125 | 40 | 0 | 2125 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Skirting work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -144989.6 | PAPPU BAGELA
Sadarali Granite Tread (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg 2nd Floor Staircase Flooring Work | 83.64 | 40 | 0 | 3345.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Tread work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -143769 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Fire Staircase Flooring Work | 214.795 | 40 | 0 | 8591.8 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Fire Staircase (ST-01). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -138522.8 | PAPPU BAGELA
Sadarali Granite Flooring (L) | N/C | N/C | PAPPU BAGELA | 657 | 2023-04-10 | F-Bldg LG Floor Staircase Flooring Work | 42.84 | 40 | 0 | 1713.6 | 0 | 2023-08-03 18:34 | Labour charges of Sadarahalli Granite Staircase Flooring work for F-Bldg Common Regular Staircase (ST-02). | 100 |  | 101002 | 2023-08-04 | 147114.6 | 2023-08-17 11:26 | -145401 | PAPPU BAGELA
Hamali & Varai | N/C | N/C | Samiksha Enterprises | 659 | 2023-04-12 | All Site Structure Removing & Shifting Work | 1 | 20000 | 0 | 20000 | 0 | 2023-05-17 18:07 | Charges for One Boat Club Sample flat & Sales office renovation work. | 100 |  | 99682 | 2023-05-17 | 30000 | 2023-06-15 13:14 | -10000 | Samiksha Enterprises
Loading & unloding Dld | N/C | N/C | Samiksha Enterprises | 659 | 2023-04-12 | All Site Structure Removing & Shifting Work | 1 | 10000 | 0 | 10000 | 0 | 2023-05-17 18:07 | Charges for One Boat Club Site all Structure removing & Shifting work. | 100 |  | 99682 | 2023-05-17 | 30000 | 2023-06-15 13:14 | -20000 | Samiksha Enterprises
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 660 | 2023-04-12 | F-Bldg 3rd Floor Lift Wall BBM & Sand Face Plaster Work | 2 | 2000 | 0 | 4000 | 0 | 2023-05-02 | Labour charges for Applying Sand Face Plaster for Lift Wall (Lift-01 & Lift-02) F-Bldg. | 100 |  | 99389 | 2023-05-03 | 20000 | 2023-06-10 10:36 | -16000 | K RAMU RATHOD
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 660 | 2023-04-12 | F-Bldg 2nd Floor Lift Wall BBM & Sand Face Plaster Work | 2 | 2000 | 0 | 4000 | 0 | 2023-05-02 | Labour charges for Applying Sand Face Plaster for Lift Wall (Lift-01 & Lift-02) F-Bldg. | 100 |  | 99389 | 2023-05-03 | 20000 | 2023-06-10 10:36 | -16000 | K RAMU RATHOD
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 660 | 2023-04-12 | F-Bldg 1st Floor Lift Wall BBM & Sand Face Plaster Work | 2 | 2000 | 0 | 4000 | 0 | 2023-05-02 | Labour charges for Applying Sand Face Plaster for Lift Wall (Lift-01 & Lift-02) F-Bldg. | 100 |  | 99389 | 2023-05-03 | 20000 | 2023-06-10 10:36 | -16000 | K RAMU RATHOD
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 660 | 2023-04-12 | F-Bldg Stilt Floor Lift Wall BBM & Sand Face Plaster Work | 2 | 2000 | 0 | 4000 | 0 | 2023-05-02 | Labour charges for Applying Sand Face Plaster for Lift Wall (Lift-01 & Lift-02) F-Bldg. | 100 |  | 99389 | 2023-05-03 | 20000 | 2023-06-10 10:36 | -16000 | K RAMU RATHOD
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 660 | 2023-04-12 | F-Bldg LG. Floor Lift Wall BBM & Sand Face Plaster Work | 2 | 2000 | 0 | 4000 | 0 | 2023-05-02 | Labour charges for Applying Sand Face Plaster for Lift Wall (Lift-01 & Lift-02) F-Bldg. | 100 |  | 99389 | 2023-05-03 | 20000 | 2023-06-10 10:36 | -16000 | K RAMU RATHOD
Expansion Joint (L) | N/C | N/C | AQUARIUS WATERPROOFING | 661 | 2023-04-12 | Expansion Joint 4th Fl- Betn E & F-Bldg | 27.752 | 247.5 | 0 | 6868.62 | 1236.36 | 2024-02-18 12:18 | Labour Charges for-Cleaning and Grinding + Apply EG-100 as primer coat upto 300mm + Fixing of Perma Butyl tape 100mm + Neoproof RC-202 + 50 gsm fleece. | 100 |  | 105374 | 2024-02-19 | 20451.42 | 2024-03-16 10:58 | -13582.8 | AQUARIUS WATERPROOFING
Expansion Joint (L) | N/C | N/C | AQUARIUS WATERPROOFING | 661 | 2023-04-12 | Expansion Joint Work P5 Fl- Betn D&Podium | 27.44 | 247.5 | 0 | 6791.4 | 1222.46 | 2024-02-18 12:18 | Labour Charges for-Cleaning and Grinding + Apply EG-100 as primer coat upto 300mm + Fixing of Perma Butyl tape 100mm + Neoproof RC-202 + 50 gsm fleece. | 100 |  | 105374 | 2024-02-19 | 20451.42 | 2024-03-16 10:58 | -13660.02 | AQUARIUS WATERPROOFING
Expansion Joint (L) | N/C | N/C | AQUARIUS WATERPROOFING | 661 | 2023-04-12 | Expansion Joint P5 Fl- Betn Podium & E | 27.44 | 247.5 | 0 | 6791.4 | 1222.46 | 2024-02-18 12:18 | Labour Charges for-Cleaning and Grinding + Apply EG-100 as primer coat upto 300mm + Fixing of Perma Butyl tape 100mm + Neoproof RC-202 + 50 gsm fleece. | 100 |  | 105374 | 2024-02-19 | 20451.42 | 2024-03-16 10:58 | -13660.02 | AQUARIUS WATERPROOFING
Expansion Joint (M) | N/C | N/C | AQUARIUS WATERPROOFING | 663 | 2023-04-12 | Expansion Joint Work P5 Fl- Betn D&Podium | 34.3 | 577.5 | 0 | 19808.25 | 3565.48 | 2024-02-18 12:03 | Material Supply Charges for- EG-100 + Perma Butyl tape 100mm + Neoproof RC-202 + 50 gsm fleece for Expansion joint treatment. | 100 |  | 105373 | 2024-02-19 | 59649.98 | 2024-03-16 10:58 | -39841.73 | AQUARIUS WATERPROOFING
Expansion Joint (M) | N/C | N/C | AQUARIUS WATERPROOFING | 663 | 2023-04-12 | Expansion Joint P5 Fl- Betn Podium & E | 34.3 | 577.5 | 0 | 19808.25 | 3565.48 | 2024-02-18 12:03 | Material Supply Charges for- EG-100 + Perma Butyl tape 100mm + Neoproof RC-202 + 50 gsm fleece for Expansion joint treatment. | 100 |  | 105373 | 2024-02-19 | 59649.98 | 2024-03-16 10:58 | -39841.73 | AQUARIUS WATERPROOFING
Expansion Joint (M) | N/C | N/C | AQUARIUS WATERPROOFING | 663 | 2023-04-12 | Expansion Joint 4th Fl- Betn E & F-Bldg | 34.69 | 577.5 | 0 | 20033.475 | 3606.02 | 2024-02-18 12:03 | Material Supply Charges for- EG-100 + Perma Butyl tape 100mm + Neoproof RC-202 + 50 gsm fleece for Expansion joint treatment. | 100 |  | 105373 | 2024-02-19 | 59649.98 | 2024-03-16 10:58 | -39616.505 | AQUARIUS WATERPROOFING
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 24th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 13th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 15th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 22nd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 10th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 11th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 4th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 6th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 17th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 2nd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 19th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 20th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 8th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 9th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg Stilt Fl Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork and Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 18th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 5th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 23rd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 21st Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 16th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 7th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 12th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 14th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 1st Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 3rd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-07-01 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108686 | 2024-07-01 | 50000 | 2024-08-05 13:57 | -48000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 9th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 20th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 16th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 19th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 1st Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 3rd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 14th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 23rd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg Stilt Fl Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork and Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 12th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 18th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 21st Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 7th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 22nd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 24th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 17th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 2nd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 5th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 4th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 6th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 11th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 8th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 10th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 13th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 15th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2023-12-23 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104108 | 2023-12-25 | 50000 | 2024-01-16 14:56 | -48000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P5 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-01-05 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104364 | 2024-01-08 | 12000 | 2024-01-23 14:18 | -10000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P3 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-01-05 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104364 | 2024-01-08 | 12000 | 2024-01-23 14:18 | -10000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P2 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-01-05 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104364 | 2024-01-08 | 12000 | 2024-01-23 14:18 | -10000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg Ground Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-01-05 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104364 | 2024-01-08 | 12000 | 2024-01-23 14:18 | -10000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P1 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-01-05 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104364 | 2024-01-08 | 12000 | 2024-01-23 14:18 | -10000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg LG Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-01-05 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 104364 | 2024-01-08 | 12000 | 2024-01-23 14:18 | -10000 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg parking P1-Fl RCC Wall-Sand Face Plaster 1.1m Ht - | 1502.408 | 20 | 0 | 30048.16 | 0 | 2023-09-30 | Labour charges for Single Coat Sand face Plaster work on Wall for D-Bldg Parking. | 100 |  | 102153 | 2023-10-02 | 44710.66 | 2023-10-11 11:10 | -14662.5 | K RAMU RATHOD
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg parking P1-Fl RCC Wall-Sand Face Plaster 1.1m Ht - | 586.5 | 25 | 0 | 14662.5 | 0 | 2023-09-30 | Labour charges for Single Coat Sand face Plaster work on Column for D-Bldg Parking. | 100 |  | 102153 | 2023-10-02 | 44710.66 | 2023-10-11 11:10 | -30048.16 | K RAMU RATHOD
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg parking G.Fl RCC Wall-Sand Face Plaster 1.1m Ht - 1 | 1058.4 | 20 | 0 | 21168 | 0 | 2023-07-04 | Labour charges for Single Coat Sand face Plaster work on Wall for D-Bldg Parking. | 100 | Total Quantity- 80% of 1323 .024 Sq.ft = 1058.4 | 100460 | 2023-07-05 | 41502 | 2023-07-19 11:55 | -20334 | K RAMU RATHOD
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg parking P2-Fl RCC Wall-Sand Face Plaster 1.1m Ht - | 1016.7 | 20 | 0 | 20334 | 0 | 2023-07-04 | Labour charges for Single Coat Sand face Plaster work on Wall for D-Bldg Parking. | 100 | Total Quantity - 80% of 1270.90 Sq.ft | 100460 | 2023-07-05 | 41502 | 2023-07-19 11:55 | -21168 | K RAMU RATHOD
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg parking P2-Fl RCC Wall-Sand Face Plaster 1.1m Ht - | 489.88 | 20 | 0 | 9797.6 | 1763.56 | 2023-09-23 | Labour charges for Single Coat Sand face Plaster work on Wall for D-Bldg Parking. | 100 |  | 102060 | 2023-09-25 | 21539 | 2023-10-11 11:10 | -11741.4 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg parking P5 Floor RCC Wall-Sand Face Plaster 1.1m Ht-( | 587.07 | 20 | 0 | 11741.4 | 2113.46 | 2023-09-23 | Labour charges for Single Coat Sand face Plaster work on Wall for D-Bldg Parking. | 100 |  | 102060 | 2023-09-25 | 21539 | 2023-10-11 11:10 | -9797.6 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg parking P3 Floor RCC Wall-Sand Face Plaster 1.1m Ht | 1661.36 | 25 | 0 | 41534 | 7476.12 | 2023-08-25 18:56 | Labour charges for Single Coat Sand face Plaster work on Column for D-Bldg Parking. | 100 |  | 101445 | 2023-08-26 | 78277.2 | 2023-09-12 12:47 | -36743.2 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg parking P3 Floor RCC Wall-Sand Face Plaster 1.1m Ht | 1837.16 | 20 | 0 | 36743.2 | 6613.78 | 2023-08-25 18:56 | Labour charges for Single Coat Sand face Plaster work on Wall for D-Bldg Parking. | 100 |  | 101445 | 2023-08-26 | 78277.2 | 2023-09-12 12:47 | -41534 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg Ground Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-05-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107376 | 2024-05-07 | 12000 | 2024-05-28 19:05 | -10000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P5 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-05-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107376 | 2024-05-07 | 12000 | 2024-05-28 19:05 | -10000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P1 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-05-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107376 | 2024-05-07 | 12000 | 2024-05-28 19:05 | -10000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P3 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-05-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107376 | 2024-05-07 | 12000 | 2024-05-28 19:05 | -10000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P2 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-05-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107376 | 2024-05-07 | 12000 | 2024-05-28 19:05 | -10000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg LG Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-05-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107376 | 2024-05-07 | 12000 | 2024-05-28 19:05 | -10000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 21st Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 7th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 4th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 6th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 19th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 17th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 24th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 16th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 10th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg parking P1-Fl RCC Wall-Sand Face Plaster 1.1m Ht - | 176 | 20 | 0 | 3520 | 633.6 | 2024-03-04 | Labour charges for Single Coat Sand face Plaster work on Wall for D-Bldg Parking. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -50000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 13th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 15th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 22nd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 12th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 5th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 11th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 8th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 9th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 1st Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 3rd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 18th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 2nd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg Stilt Fl Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork and Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 20th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 14th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg 23rd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-03-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105854 | 2024-03-11 | 53520 | 2024-03-26 14:54 | -51520 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P2 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-08-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 109516 | 2024-08-05 | 12000 | 1900-01-01 | -10000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg Ground Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-08-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 109516 | 2024-08-05 | 12000 | 1900-01-01 | -10000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg LG Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-08-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 109516 | 2024-08-05 | 12000 | 1900-01-01 | -10000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P5 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-08-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 109516 | 2024-08-05 | 12000 | 1900-01-01 | -10000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P1 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-08-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 109516 | 2024-08-05 | 12000 | 1900-01-01 | -10000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster (No.) | N/C | N/C | K RAMU RATHOD | 664 | 2023-04-12 | D-Bldg P3 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-08-04 | Labour charges for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 109516 | 2024-08-05 | 12000 | 1900-01-01 | -10000 | SHUBHAM SURENDRA BAHADUR SINGH
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 42.73 | 2400 | 0 | 102552 | 18459.36 | 2024-03-14 14:48 | Charges for 500mm dia Boring with Hydraulic Rotary Rig through weathered/ Hard Strata with all equipment,labour,tools,tackle etc. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -539548 | MASKE PILE FOUNDATION
Pile Concreting Work | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 235.25 | 200 | 0 | 47050 | 8469 | 2024-03-14 14:48 | Charges for Concreting work for Piling including all equipment,labour,tools,tackle etc. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -595050 | MASKE PILE FOUNDATION
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 192.52 | 1600 | 0 | 308032 | 55445.76 | 2024-03-14 14:48 | Charges for 500mm dia Boring with Hydraulic Rotary Rig through all strata excluding weathered/ Hard Strata with all equipment,labour,tools,tackle etc. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -334068 | MASKE PILE FOUNDATION
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 15.48 | 1600 | 0 | 24768 | 4458.24 | 2024-03-15 15:05 | Charges for 500mm dia Boring with Hydraulic Rotary Rig through all strata excluding weathered/ Hard Strata with all equipment,labour,tools,tackle etc. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -617332 | MASKE PILE FOUNDATION
Reinforcement for Piling-BC | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 235.25 | 200 | 0 | 47050 | 8469 | 2024-03-14 14:48 | Charges for Reinforcement work for Piling. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -595050 | MASKE PILE FOUNDATION
Mobilisation - DEn | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 1 | 100000 | 0 | 100000 | 18000 | 2024-03-14 14:48 | Charges for One Time Transportation including crane for Club House piling work. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -542100 | MASKE PILE FOUNDATION
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 5.27 | 2400 | 0 | 12648 | 2276.64 | 2024-03-15 15:05 | Charges for 500mm dia Boring with Hydraulic Rotary Rig through weathered/ Hard Strata with all equipment,labour,tools,tackle etc. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -629452 | MASKE PILE FOUNDATION
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-304-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-101-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-102-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-103-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-303-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-503-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-301-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-106-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-602-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-202-2BHK(Near Refuse Area) Brickbat Waterproofing | 27.472 | 18 | 0 | 494.496 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -93293.284 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-401-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-403-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-402-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-205-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-701-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-305-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-601-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-107-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-401-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-006-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-104-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-007-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-106-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-104-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-303-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-001-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-003-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-401-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-404-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-004-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-403-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-403-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-802-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-05-05 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54627.784 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1504-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54869.72 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-703-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-05-05 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54883.624 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1804-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54869.72 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-703-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-05-05 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54658.92 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-701-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-05-05 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54627.784 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-701-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-05-05 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54627.784 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1502-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54830.96 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-502-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-05-05 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54658.92 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-801-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-05-05 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54627.784 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-704-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-05-05 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54658.92 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-804-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-05-05 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54883.624 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1401-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54830.96 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1603-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54869.72 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-601-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-05-05 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54658.92 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1602-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54830.96 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1703-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54869.72 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1802-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54830.96 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-501-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-05-05 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54658.92 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-802-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-05-05 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54627.784 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1403-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54624.824 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1404-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54869.72 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1402-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54830.96 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1503-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54869.72 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-605-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18426.096 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-607-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18912.48 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-507-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18667.584 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-705-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18873.72 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-706-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18873.72 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-607-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18667.584 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-606-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18873.72 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-608-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18912.48 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-508-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18667.584 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18426.096 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18426.096 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18873.72 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-507-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18912.48 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-707-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18912.48 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18873.72 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-605-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18873.72 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-608-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18667.584 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-606-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18426.096 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-508-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18912.48 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-708-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104384 | 2024-01-08 | 19741.68 | 2024-02-05 11:44 | -18912.48 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-805-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-02-25 20:10 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105576 | 2024-02-26 | 8173.68 | 2024-03-28 12:37 | -6858.096 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-806-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-02-25 20:10 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105576 | 2024-02-26 | 8173.68 | 2024-03-28 12:37 | -6858.096 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-808-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-02-25 20:10 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105576 | 2024-02-26 | 8173.68 | 2024-03-28 12:37 | -7099.584 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-806-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-02-25 19:31 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105576 | 2024-02-26 | 8173.68 | 2024-03-28 12:37 | -7305.72 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-808-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-02-25 19:31 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105576 | 2024-02-26 | 8173.68 | 2024-03-28 12:37 | -7344.48 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-807-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-02-25 20:10 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105576 | 2024-02-26 | 8173.68 | 2024-03-28 12:37 | -7099.584 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-805-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-02-25 19:31 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105576 | 2024-02-26 | 8173.68 | 2024-03-28 12:37 | -7305.72 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-807-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-02-25 19:31 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105576 | 2024-02-26 | 8173.68 | 2024-03-28 12:37 | -7344.48 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-706-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29383.48 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-407-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-05-16 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29907.104 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-907-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-05-16 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29648.304 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-408-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29907.104 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-905-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-05-16 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29854.44 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-906-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-05-16 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29406.816 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-605-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29651.264 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-508-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29907.104 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-607-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29907.104 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29651.264 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-906-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-05-16 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29854.44 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-405-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29651.264 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-705-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29383.48 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-107-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-17 12:57 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23464.71 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-005-3BHK Brickbat Waterproofing | 81.845 | 18 | 0 | 1473.21 | 0 | 2023-10-17 13:07 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -22820.7 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-001-3BHK Brickbat Waterproofing | 81.845 | 18 | 0 | 1473.21 | 0 | 2023-10-17 13:07 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -22820.7 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-002-3BHK Brickbat Waterproofing | 130.95 | 18 | 0 | 2357.1 | 0 | 2023-10-17 13:07 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -21936.81 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-003-2BHK Brickbat Waterproofing | 114.96 | 18 | 0 | 2069.28 | 0 | 2023-10-17 13:07 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -22224.63 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-007-2BHK Brickbat Waterproofing | 71.85 | 18 | 0 | 1293.3 | 0 | 2023-10-17 13:07 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23000.61 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-106-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2023-10-17 13:15 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -22978.326 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-105-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2023-10-17 13:15 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -22978.326 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-004-2BHK Brickbat Waterproofing | 71.85 | 18 | 0 | 1293.3 | 0 | 2023-10-17 13:07 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23000.61 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-103-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-17 12:57 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23464.71 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-105-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-17 12:57 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23425.95 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-108-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-10-17 13:15 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23219.814 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-008-2BHK Brickbat Waterproofing | 71.85 | 18 | 0 | 1293.3 | 0 | 2023-10-17 13:07 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23000.61 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-104-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-17 12:57 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23464.71 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-101-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-17 12:57 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23425.95 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-102-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-17 12:57 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23425.95 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-108-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-17 12:57 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23464.71 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-106-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-17 12:57 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23425.95 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-006-3BHK Brickbat Waterproofing | 81.845 | 18 | 0 | 1473.21 | 0 | 2023-10-17 13:07 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -22820.7 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-107-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-10-17 13:15 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 102744 | 2023-10-18 | 24293.91 | 2023-11-06 16:12 | -23219.814 | PRABHURAM VERMA
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-701-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 19:58 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1002-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:21 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-806-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-602-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-802-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-802-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1005-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:10 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-606-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-26 19:23 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-606-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-607-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-805-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-702-2BHK(Near Refuse Area) Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-801-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-803-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-704-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-601-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-603-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-801-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1003-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:49 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1005-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:49 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-604-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-802-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-804-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-901-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1004-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:21 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-803-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-902-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-705-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1001-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:49 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-806-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-905-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-906-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-908-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-701-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-706-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1003-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1005-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-706-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1001-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:21 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-508-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-701-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-703-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-903-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-607-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-908-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-507-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-708-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-704-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-902-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-501-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-605-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-706-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-708-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-906-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-601-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-26 19:23 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-705-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-908-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-701-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-702-2BHK(Near Refuse Area) Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-608-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-707-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-801-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1002-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1001-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-703-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-905-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-702-2BHK(Near Refuse Area) Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-706-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-906-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-907-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-903-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-708-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-504-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-707-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1208-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1206-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1605-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1605-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1805-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1807-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1305-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1307-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1808-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1605-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1607-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1808-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1205-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1406-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1408-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1606-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1606-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1206-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1106-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1708-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1106-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1107-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1308-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1306-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1505-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1708-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1506-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1706-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1108-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1505-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1205-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1506-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1505-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1507-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1806-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1608-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1108-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1705-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1307-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1706-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1606-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1608-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1105-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1406-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1507-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1306-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1405-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1605-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1608-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1205-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1806-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1207-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1508-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1106-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1506-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1508-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1705-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1706-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1306-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1607-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1805-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1105-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1406-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1208-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1206-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1305-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1505-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1705-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1707-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1205-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1407-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1506-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1805-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1108-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1405-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1406-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1806-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1405-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1107-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1408-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1405-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1107-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1507-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1707-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1308-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1105-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1201-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-06-28 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48150.724 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1003-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-902-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1704-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-06-30 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48147.764 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-903-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-06-29 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48406.564 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-804-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-002-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-06-29 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48150.724 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1003-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-06-28 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48406.564 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1104-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-06-28 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48406.564 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1302-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-06-29 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48150.724 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1203-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1004-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-06-28 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48406.564 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1204-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-06-28 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48406.564 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1303-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-06-29 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48406.564 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1204-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-901-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1201-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-302-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2023-11-08 23:58 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19732.87 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-303-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2023-11-08 23:58 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19771.63 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-201-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2023-11-08 23:38 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19285.246 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-203-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-11-08 23:38 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19526.734 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-008-2BHK Brickbat Waterproofing | 43.11 | 18 | 0 | 775.98 | 0 | 2023-11-08 23:47 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19824.85 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-304-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2023-11-08 23:58 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19771.63 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-208-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-11-08 23:38 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19526.734 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-006-3BHK Brickbat Waterproofing | 49.107 | 18 | 0 | 883.926 | 0 | 2023-11-08 23:47 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19716.904 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-308-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2023-11-08 23:58 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19771.63 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-301-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2023-11-08 23:58 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19732.87 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-206-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2023-11-08 23:38 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19285.246 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-004-2BHK Brickbat Waterproofing | 43.11 | 18 | 0 | 775.98 | 0 | 2023-11-08 23:47 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19824.85 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-306-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2023-11-08 23:58 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19732.87 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-205-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2023-11-08 23:38 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19285.246 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-005-3BHK Brickbat Waterproofing | 49.107 | 18 | 0 | 883.926 | 0 | 2023-11-08 23:47 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19716.904 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-305-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2023-11-08 23:58 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19732.87 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-902-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1104-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:14 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-206-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:35 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-305-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-901-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1201-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1003-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1204-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1304-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:15 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-802-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1004-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-804-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:27 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1004-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-207-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:35 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-205-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-207-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1101-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:14 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-902-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:27 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1001-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-306-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:35 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-307-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1302-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:15 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-701-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:27 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1101-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1303-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-504-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-502-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-803-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-804-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1003-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-801-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1102-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:14 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-901-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:27 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1301-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1001-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-601-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-208-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1303-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:15 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-801-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:27 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1302-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1304-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-205-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:35 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-308-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:35 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-602-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-306-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-308-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1104-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-603-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-803-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:27 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-602-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-27 16:48 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-503-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-504-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-904-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-704-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:27 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-904-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:27 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-502-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-903-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-903-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:27 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-208-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:35 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-206-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-601-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-27 16:48 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1103-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:14 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-703-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:27 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-802-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:27 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1002-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-307-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:35 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-305-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:35 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-503-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1201-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:14 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1103-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1203-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:14 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1002-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1202-2BHK(Near Refuse Area) IPS Screeding Work-(Flat) | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:14 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1301-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-02-26 20:15 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80505.36 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1102-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80057.736 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1203-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-02-26 20:40 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80299.224 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-501-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-501-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-02-26 21:42 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80302.184 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1204-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-02-26 20:15 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80544.12 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-604-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-26 21:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1403-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1603-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1302-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1604-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1803-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1102-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1104-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1502-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1702-2BHK(Near Refuse Area) Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1703-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1802-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1804-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1301-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1402-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1201-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1301-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1504-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1703-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1502-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1701-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1101-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1802-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-906-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-907-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1007-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:49 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1002-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:10 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-704-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-904-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1005-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:21 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-604-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1007-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:21 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-803-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1002-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:49 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-607-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-26 19:23 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-806-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-805-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1008-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:49 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1001-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:10 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-903-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-605-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-807-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-808-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-603-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-806-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-801-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1003-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:21 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-606-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1006-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:49 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-602-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-26 19:23 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-605-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-26 19:23 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-904-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-902-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-502-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-601-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-904-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-503-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-602-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-905-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-807-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-603-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-26 19:23 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-902-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1006-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1006-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:21 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1004-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:49 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-805-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1006-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:10 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-807-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-808-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-804-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-901-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-901-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61005 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-705-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-705-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-707-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-808-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-907-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-12-26 18:34 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61270 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-604-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-26 19:23 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1004-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-608-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:07 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1008-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-12-26 18:21 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61625 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-901-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-26 19:00 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61535 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-805-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-703-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-802-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-804-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-905-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-12-28 20:02 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61275 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-608-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-12-26 19:23 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105180 | 2024-02-10 | 61800 | 2024-02-19 15:21 | -61100 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-305-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-006-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-008-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-208-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-302-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-406-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-007-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-101-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-108-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-405-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-004-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-005-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-102-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-208-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-408-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-206-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-103-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-204-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-307-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-104-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-102-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1305-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1306-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1207-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1407-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1807-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1508-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1207-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1407-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1606-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1806-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1607-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1706-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1708-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1308-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1106-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1307-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50465 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1105-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1305-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50375 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1208-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1408-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1805-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49845 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1807-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50110 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1206-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1705-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -50115 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1707-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1808-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 105896 | 2024-03-11 | 50640 | 2024-03-28 12:41 | -49940 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-008-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-107-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-103-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-208-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-302-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-106-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-108-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-003-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-004-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-205-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-007-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-005-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-206-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-002-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-204-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-403-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-404-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-001-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-006-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-201-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-401-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-304-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-207-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-203-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-101-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-301-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-402-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-104-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-105-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.2 | 1300 | 0 | 260 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -30160 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-303-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-02-25 15:36 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 106036 | 2024-03-12 | 30420 | 2024-03-18 12:06 | -29380 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-603-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-27 16:48 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-604-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-02-27 16:48 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 105612 | 2024-02-28 | 81373.32 | 2024-03-18 12:04 | -80558.024 | PRABHURAM VERMA
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-401-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-004-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-303-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-305-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-507-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-001-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-006-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-204-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-308-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-401-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-008-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-107-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-105-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-303-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-304-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-306-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-207-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-303-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-207-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-005-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-106-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-407-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-206-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-405-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-407-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-201-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-203-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-206-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-104-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-105-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-301-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-302-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-003-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-205-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-006-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-502-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-006-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-103-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-002-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-002-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-004-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-001-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-201-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-302-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-002-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-504-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-007-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-106-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-404-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-406-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-402-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-201-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-501-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-106-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-307-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-007-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-101-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-301-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-005-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-205-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-306-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-507-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-508-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-403-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-005-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-404-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-405-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-301-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-205-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-301-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-104-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-101-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-106-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-306-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-408-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-501-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-203-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-001-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-508-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-204-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-403-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-304-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-504-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-102-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-403-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-502-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-102-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-305-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-101-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-108-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-008-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-105-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-404-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-208-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-305-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-107-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-205-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-402-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-407-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-503-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-202-2BHK(Near Refuse Area) Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-402-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-203-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-307-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-302-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-401-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-503-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-103-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-202-2BHK(Near Refuse Area) Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-207-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-308-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-501-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-405-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-502-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-105-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-202-2BHK(Near Refuse Area) Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-401-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-402-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-206-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-406-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-107-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-201-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-408-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-406-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74011.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-002-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-108-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-202-2BHK(Near Refuse Area) Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73741.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-003-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2023-09-27 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73836.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-001-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-09-27 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74271.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-308-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74361.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-003-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-304-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -74006.15 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-306-3BHK Core Cutting Work | 2.91 | 265 | 0 | 771.15 | 138.8 | 2023-09-27 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 102118 | 2023-09-29 | 74536.15 | 2023-10-20 11:02 | -73765 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-601-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-16 18:55 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 104040 | 2023-12-18 | 1060 | 1900-01-01 | -795 | GANGAPRASAD K VARMA
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-606-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-16 18:55 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 104040 | 2023-12-18 | 1060 | 1900-01-01 | -795 | GANGAPRASAD K VARMA
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-602-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-16 18:55 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 104040 | 2023-12-18 | 1060 | 1900-01-01 | -795 | GANGAPRASAD K VARMA
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-605-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2023-12-16 18:55 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 104040 | 2023-12-18 | 1060 | 1900-01-01 | -795 | GANGAPRASAD K VARMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-705-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-05-16 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29406.816 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-706-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-05-16 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29406.816 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-407-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29907.104 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29651.264 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-905-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-05-16 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29406.816 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-405-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-05-16 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29651.264 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-406-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-05-16 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29651.264 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-406-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29651.264 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-608-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29907.104 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-606-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29651.264 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-507-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-05-16 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29907.104 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-907-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-05-16 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29893.2 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-908-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-05-16 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29893.2 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-707-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-05-16 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29648.304 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-708-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-05-16 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29648.304 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-908-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-05-16 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29648.304 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-408-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-05-16 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107648 | 2024-05-20 | 30722.4 | 2024-06-10 11:25 | -29907.104 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-702-2BHK(Near Refuse Area) IPS Screeding Work-(Flat) | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-302-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-502-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-307-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-008-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-004-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-101-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-108-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-007-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-104-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-001-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-201-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-203-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-201-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-203-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-404-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-101-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-301-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-302-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-208-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-202-2BHK(Near Refuse Area) IPS Screeding Work-(Flat) | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-403-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-402-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-603-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-501-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-704-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-003-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-204-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-402-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-404-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-604-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-404-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-302-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-103-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-301-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-306-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-308-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-005-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-108-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-502-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-503-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-504-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-008-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-304-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-501-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-006-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-107-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-204-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-203-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-401-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-402-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-604-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-207-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-005-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-07 18:43 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92716.644 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-201-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-601-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-603-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-602-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92472.196 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-703-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 20:09 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-304-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:14 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-504-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-07 20:24 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92713.684 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-204-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92958.58 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-206-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-07 19:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92919.82 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-103-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-303-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-07 18:38 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104382 | 2024-01-08 | 93787.78 | 2024-01-23 14:23 | -92972.484 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-204-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-11-08 23:38 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19526.734 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-001-3BHK Brickbat Waterproofing | 49.107 | 18 | 0 | 883.926 | 0 | 2023-11-08 23:47 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19716.904 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-002-3BHK Brickbat Waterproofing | 32.74 | 18 | 0 | 589.32 | 0 | 2023-11-08 23:47 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -20011.51 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-207-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-11-08 23:38 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19526.734 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-007-2BHK Brickbat Waterproofing | 43.11 | 18 | 0 | 775.98 | 0 | 2023-11-08 23:47 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19824.85 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-307-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2023-11-08 23:58 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 103401 | 2023-11-09 | 20600.83 | 2023-12-02 12:17 | -19771.63 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-407-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2023-12-08 16:48 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104075 | 2023-12-21 | 11355.96 | 2023-12-22 11:34 | -10281.864 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-406-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2023-12-08 16:42 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104075 | 2023-12-21 | 11355.96 | 2023-12-22 11:34 | -10488 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-408-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2023-12-08 16:42 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104075 | 2023-12-21 | 11355.96 | 2023-12-22 11:34 | -10526.76 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-405-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2023-12-08 16:42 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104075 | 2023-12-21 | 11355.96 | 2023-12-22 11:34 | -10488 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-105-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 187.2 | 2023-12-08 16:19 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 104075 | 2023-12-21 | 11355.96 | 2023-12-22 11:34 | -10315.96 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-405-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2023-12-08 16:48 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104075 | 2023-12-21 | 11355.96 | 2023-12-22 11:34 | -10040.376 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-407-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2023-12-08 16:42 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 104075 | 2023-12-21 | 11355.96 | 2023-12-22 11:34 | -10526.76 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-105-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2023-12-08 16:05 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 104075 | 2023-12-21 | 11355.96 | 2023-12-22 11:34 | -10284.824 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-105-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2023-12-08 15:48 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 104075 | 2023-12-21 | 11355.96 | 2023-12-22 11:34 | -10284.824 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-406-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2023-12-08 16:48 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104075 | 2023-12-21 | 11355.96 | 2023-12-22 11:34 | -10040.376 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-408-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2023-12-08 16:48 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 104075 | 2023-12-21 | 11355.96 | 2023-12-22 11:34 | -10281.864 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1701-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-06-30 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -47906.276 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1004-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1103-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1703-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-06-30 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48147.764 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1803-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-06-30 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48147.764 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1903-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-06-30 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48392.66 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1102-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-06-29 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48150.724 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1203-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-06-28 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48406.564 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1002-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-802-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-903-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1801-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-06-30 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -47906.276 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1301-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-06-29 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48150.724 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1904-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-06-30 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48392.66 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1902-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-06-30 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48353.9 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-902-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-06-29 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48150.724 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1802-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-06-30 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -47906.276 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-803-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-904-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1001-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-06-28 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48150.724 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1304-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-06-29 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48406.564 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1901-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-06-30 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48353.9 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1102-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1104-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1002-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-06-28 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48150.724 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1101-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-06-28 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48150.724 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1103-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-06-28 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48406.564 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-901-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-06-29 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48150.724 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-904-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-06-29 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48406.564 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1101-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-801-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-29 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48181.86 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1804-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-06-30 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108679 | 2024-07-01 | 49221.86 | 2024-08-05 14:02 | -48147.764 | PRABHURAM VERMA
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1902-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109593 | 2024-08-05 | 1050 | 1900-01-01 | -875 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-2301-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109593 | 2024-08-05 | 1050 | 1900-01-01 | -875 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-2302-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109593 | 2024-08-05 | 1050 | 1900-01-01 | -875 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1901-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109593 | 2024-08-05 | 1050 | 1900-01-01 | -875 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1904-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109593 | 2024-08-05 | 1050 | 1900-01-01 | -875 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1903-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109593 | 2024-08-05 | 1050 | 1900-01-01 | -875 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1804-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1801-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1201-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1302-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1401-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1103-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1404-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1202-2BHK(Near Refuse Area) Core Cutting Work | 0.6667 | 265 | 0 | 176.6755 | 31.8 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52125.0045 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1803-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1504-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1102-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1303-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1204-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1501-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1704-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1401-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1702-2BHK(Near Refuse Area) Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1801-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1601-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1803-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1702-2BHK(Near Refuse Area) Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1704-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1202-2BHK(Near Refuse Area) Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1404-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1801-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1504-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1503-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1502-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1302-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1501-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1101-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1701-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1304-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1703-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1203-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1201-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1201-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1401-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1603-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1202-2BHK(Near Refuse Area) Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1303-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1604-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1101-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1802-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1601-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1702-2BHK(Near Refuse Area) Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1103-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1404-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1502-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1601-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1007-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1501-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1503-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1203-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1403-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1102-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1103-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1604-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1403-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1601-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1602-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1804-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1801-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1802-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 18:05 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1503-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1704-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1304-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1303-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1401-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1402-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1603-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1402-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1104-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1101-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1701-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1008-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1102-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1301-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1301-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1302-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 94.5 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51776.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1304-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 16:53 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1204-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1602-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-03-08 17:04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52126.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1202-2BHK(Near Refuse Area) Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1402-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:22 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1104-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1203-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-03-08 17:48 | Labour Charges for 5 Inch Dia Vertical Core Cutting work in Slab for E Building Common toilet Commode and Shower area & Attached toilet Commode and Shower area-1no each (2BHK) Commode 1Nos & Shower 2Nos (3BHK) | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51601.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1602-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 5" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1602-3BHK Core Cutting Work | 1 | 265 | 0 | 265 | 47.7 | 2024-03-08 17:40 | Labour Charges for 5 Inch Dia Horizontal Core Cutting work in Non Structural wall for E Building Common toilet above ventilator & Attched toilet above ventilator 1 Nos each(2BHK) Commode 1Nos & Above Ventilator of Common & Attached toilet 1Nos each(3BHK). | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -52036.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1501-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1701-3BHK Core Cutting Work | 3 | 265 | 0 | 795 | 143.1 | 2024-03-08 18:18 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51506.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 2" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1204-2BHK Core Cutting Work | 2 | 265 | 0 | 530 | 95.4 | 2024-03-08 18:35 | Labour Charges for 2 Inch Dia Horizontal Core Cutting work in Non structural wall for Kitchen (2nos) and Common Basin (1 Nos) of E Building internal flat. | 100 |  | 107267 | 2024-05-03 | 52301.68 | 2024-05-03 15:31 | -51771.68 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1906-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109596 | 2024-08-05 | 1050 | 1900-01-01 | -875 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1905-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109596 | 2024-08-05 | 1050 | 1900-01-01 | -875 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-2208-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109596 | 2024-08-05 | 1050 | 1900-01-01 | -875 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1908-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109596 | 2024-08-05 | 1050 | 1900-01-01 | -875 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1907-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109596 | 2024-08-05 | 1050 | 1900-01-01 | -875 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Core Cutting 6" BCE | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-2207-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2024-08-04 | Labour Charges for 6 inch Dia Vertical Core Cutting work in slab for E Building Living Balcony. | 100 |  | 109596 | 2024-08-05 | 1050 | 1900-01-01 | -875 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1008-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-06-02 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40848.824 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-705-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40851.784 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-706-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40851.784 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-707-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41107.624 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-606-3BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-608-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41107.624 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-405-3BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-406-3BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-607-2BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1007-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-06-02 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41093.72 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40851.784 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-606-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40851.784 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-507-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41107.624 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-605-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40851.784 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-607-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41107.624 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1006-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-06-02 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41054.96 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-708-2BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1006-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-06-02 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40607.336 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-608-2BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1005-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 156.24 | 2024-06-02 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41054.96 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-705-3BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-706-3BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-407-2BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-408-2BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1008-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 149.26 | 2024-06-02 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41093.72 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-508-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41107.624 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-708-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41107.624 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-708-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-06-02 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41107.624 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-508-2BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-707-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-06-02 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -41107.624 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 192.8 | 2024-06-02 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40851.784 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-605-3BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-507-2BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-707-2BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-02 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40622.92 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1005-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 236.8 | 2024-06-02 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40607.336 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1007-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 193.34 | 2024-06-02 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107930 | 2024-06-03 | 41922.92 | 2024-06-15 11:52 | -40848.824 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-508-2BHK Brickbat Waterproofing | 14.918 | 18 | 0 | 268.524 | 48.34 | 2024-06-23 14:04 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18695.136 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-606-3BHK IPS Screeding Work | 14.466 | 15 | 0 | 216.99 | 39.06 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18746.67 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-608-2BHK IPS Screeding Work | 13.82 | 15 | 0 | 207.3 | 37.32 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18756.36 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-608-2BHK Int Flat Chemical Grouting Work | 101.912 | 2 | 0 | 203.824 | 36.68 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18759.836 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-705-3BHK IPS Screeding Work | 14.466 | 15 | 0 | 216.99 | 39.06 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18746.67 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-805-3BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-23 15:07 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -17663.66 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-807-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-23 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -17944.54 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-405-3BHK Brickbat Waterproofing | 18.272 | 18 | 0 | 328.896 | 59.2 | 2024-06-23 12:53 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18634.764 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-705-3BHK Int Flat Chemical Grouting Work | 133.892 | 2 | 0 | 267.784 | 48.2 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18695.876 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-706-3BHK Int Flat Chemical Grouting Work | 133.892 | 2 | 0 | 267.784 | 48.2 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18695.876 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-707-2BHK Int Flat Chemical Grouting Work | 101.912 | 2 | 0 | 203.824 | 36.68 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18759.836 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-806-3BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-23 15:07 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -17663.66 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-507-2BHK Brickbat Waterproofing | 14.918 | 18 | 0 | 268.524 | 48.34 | 2024-06-23 14:04 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18695.136 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-407-2BHK IPS Screeding Work | 13.82 | 15 | 0 | 207.3 | 37.32 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18756.36 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-607-2BHK IPS Screeding Work | 13.82 | 15 | 0 | 207.3 | 37.32 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18756.36 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-405-3BHK IPS Screeding Work | 14.466 | 15 | 0 | 216.99 | 39.06 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18746.67 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK IPS Screeding Work | 14.466 | 15 | 0 | 216.99 | 39.06 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18746.67 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK Int Flat Chemical Grouting Work | 133.892 | 2 | 0 | 267.784 | 48.2 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18695.876 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-807-2BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-23 15:07 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -17663.66 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-706-3BHK IPS Screeding Work | 14.466 | 15 | 0 | 216.99 | 39.06 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18746.67 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK Int Flat Chemical Grouting Work | 133.892 | 2 | 0 | 267.784 | 48.2 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18695.876 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK Brickbat Waterproofing | 18.272 | 18 | 0 | 328.896 | 59.2 | 2024-06-23 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18634.764 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-808-2BHK IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 234 | 2024-06-23 15:07 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -17663.66 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-407-2BHK Brickbat Waterproofing | 14.918 | 18 | 0 | 268.524 | 48.34 | 2024-06-23 12:53 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18695.136 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-505-3BHK IPS Screeding Work | 14.466 | 15 | 0 | 216.99 | 39.06 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18746.67 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-507-2BHK IPS Screeding Work | 13.82 | 15 | 0 | 207.3 | 37.32 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18756.36 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-707-2BHK IPS Screeding Work | 13.82 | 15 | 0 | 207.3 | 37.32 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18756.36 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-605-3BHK IPS Screeding Work | 14.466 | 15 | 0 | 216.99 | 39.06 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18746.67 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-605-3BHK Int Flat Chemical Grouting Work | 133.892 | 2 | 0 | 267.784 | 48.2 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18695.876 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-607-2BHK Int Flat Chemical Grouting Work | 101.912 | 2 | 0 | 203.824 | 36.68 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18759.836 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-606-3BHK Int Flat Chemical Grouting Work | 133.892 | 2 | 0 | 267.784 | 48.2 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18695.876 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-406-3BHK IPS Screeding Work | 14.466 | 15 | 0 | 216.99 | 39.06 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18746.67 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-408-2BHK IPS Screeding Work | 13.82 | 15 | 0 | 207.3 | 37.32 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18756.36 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-806-3BHK IPS Screeding Work | 14.466 | 15 | 0 | 216.99 | 39.06 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18746.67 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-805-3BHK IPS Screeding Work | 14.466 | 15 | 0 | 216.99 | 39.06 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18746.67 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-508-2BHK IPS Screeding Work | 13.82 | 15 | 0 | 207.3 | 37.32 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18756.36 | PRASHANT KASHINATH NETAKE
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-708-2BHK IPS Screeding Work | 13.82 | 15 | 0 | 207.3 | 37.32 | 2024-06-23 14:52 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18756.36 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-805-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-23 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -17624.74 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-806-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-23 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -17624.74 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-507-2BHK Int Flat Chemical Grouting Work | 101.912 | 2 | 0 | 203.824 | 36.68 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18759.836 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-506-3BHK Brickbat Waterproofing | 18.272 | 18 | 0 | 328.896 | 59.2 | 2024-06-23 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18634.764 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-508-2BHK Int Flat Chemical Grouting Work | 101.912 | 2 | 0 | 203.824 | 36.68 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18759.836 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-708-2BHK Int Flat Chemical Grouting Work | 101.912 | 2 | 0 | 203.824 | 36.68 | 2024-06-22 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18759.836 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-406-3BHK Brickbat Waterproofing | 18.272 | 18 | 0 | 328.896 | 59.2 | 2024-06-23 12:53 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18634.764 | PRASHANT KASHINATH NETAKE
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-408-2BHK Brickbat Waterproofing | 14.918 | 18 | 0 | 268.524 | 48.34 | 2024-06-23 12:53 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -18695.136 | PRASHANT KASHINATH NETAKE
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-808-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-23 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 108548 | 2024-06-24 | 18963.66 | 2024-07-11 10:26 | -17944.54 | PRASHANT KASHINATH NETAKE
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-604-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-05-05 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54658.92 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-704-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-05-05 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54883.624 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-704-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-05-05 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54883.624 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-804-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-05-05 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54883.624 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1601-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54830.96 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1503-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54624.824 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1403-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54869.72 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1702-2BHK(Near Refuse Area) IPS Screeding Work-(Flat) | 57.864 | 15 | 0 | 867.96 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54830.96 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1704-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54869.72 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1803-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54869.72 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-801-3BHK Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-05-05 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54627.784 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1604-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54624.824 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-504-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-05-05 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54658.92 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-803-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-05-05 | Ghadai work with Hammer,Chisel,Breaker,etc.to Prepare Plain Floor Surface,including cleaning, shifting debris at one place including all lead & lift with all tools & equipments required. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54883.624 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1801-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54830.96 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-603-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-05-05 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54658.92 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1604-2BHK IPS Screeding Work | 55.28 | 15 | 0 | 829.2 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54869.72 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-503-2BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-05-05 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54658.92 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-703-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-05-05 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54883.624 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-803-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-05-05 | Labour Charges for Chemical Grouting work for internal flat of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54883.624 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1502-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54383.336 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1504-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54624.824 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1601-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54383.336 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1401-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54383.336 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1603-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54624.824 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1501-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54830.96 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1402-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54383.336 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1404-2BHK Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54624.824 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1501-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54383.336 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1602-3BHK Brickbat Waterproofing | 73.088 | 18 | 0 | 1315.584 | 0 | 2024-05-05 | Labour Charges for Brickbat Waterproofing work for E Building Toilet Sunk 200mm & Living terrace and Dry Balcony 150mm Sunk. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54383.336 | PRABHURAM VERMA
IPS W/P | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-1701-3BHK IPS Screeding Work | 57.864 | 15 | 0 | 867.96 | 0 | 2024-05-05 | Labour Charges for IPS Screeding waterproofing work in Master toilet & Common toilet of E Building | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54830.96 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-602-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-05-05 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54658.92 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | GANGAPRASAD K VARMA | 666 | 2023-04-14 | E-701-3BHK IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-05-05 | Labour Charges for IPS Seal Pack work for E Building. | 100 |  | 107382 | 2024-05-07 | 55698.92 | 2024-06-06 12:21 | -54658.92 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-807-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-23 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -11406.4 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1005-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-06-02 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107924 | 2024-06-03 | 12450.38 | 2024-06-15 11:52 | -10842.444 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-707-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-06-02 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107924 | 2024-06-03 | 12450.38 | 2024-06-15 11:52 | -11635.084 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1006-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-06-02 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107924 | 2024-06-03 | 12450.38 | 2024-06-15 11:52 | -10842.444 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1006-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-06-02 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107924 | 2024-06-03 | 12450.38 | 2024-06-15 11:52 | -11177.372 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-708-2BHK Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 146.76 | 2024-06-02 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107924 | 2024-06-03 | 12450.38 | 2024-06-15 11:52 | -11635.084 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1008-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-06-02 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107924 | 2024-06-03 | 12450.38 | 2024-06-15 11:52 | -11234.22 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1008-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-06-02 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107924 | 2024-06-03 | 12450.38 | 2024-06-15 11:52 | -11137.596 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1005-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-06-02 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107924 | 2024-06-03 | 12450.38 | 2024-06-15 11:52 | -11177.372 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1007-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-06-02 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107924 | 2024-06-03 | 12450.38 | 2024-06-15 11:52 | -11137.596 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1007-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-06-02 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107924 | 2024-06-03 | 12450.38 | 2024-06-15 11:52 | -11234.22 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-302-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80219.55 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-604-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80342.31 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-401-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80285.462 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-601-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80285.462 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-602-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80285.462 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-601-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-07 19:44 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -79950.534 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-701-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80285.462 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-302-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -79950.534 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-501-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -79950.534 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-401-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -79950.534 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-502-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -79950.534 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-103-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-202-2BHK(Near Refuse Area) Chemical WP Before Brickbat WP | 27.472 | 22 | 0 | 604.384 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80954.086 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-305-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -79950.534 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-003-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-007-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-005-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80219.55 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-106-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80219.55 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-404-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-403-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-204-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-404-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80342.31 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-504-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80342.31 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-306-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -79950.534 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-704-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 20:05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-602-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-07 19:44 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -79950.534 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-001-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80219.55 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-108-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-201-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80219.55 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-203-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-403-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-401-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80219.55 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-402-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80219.55 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-004-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-006-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80219.55 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-107-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-304-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-504-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-501-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80285.462 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-703-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80342.31 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-701-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-07 20:05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -79950.534 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-703-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 20:05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-008-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-402-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -79950.534 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-101-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80219.55 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-303-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-104-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-304-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80539.35 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-404-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-604-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 19:44 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-603-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 19:44 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-402-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80285.462 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-307-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-308-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-103-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80342.31 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-506-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31186.332 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-608-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31243.18 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-706-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31186.332 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-605-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-01-07 19:44 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -30851.404 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-506-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -30851.404 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-705-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31186.332 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-707-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31243.18 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-505-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -30851.404 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-507-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31146.556 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-606-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-01-07 19:44 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -30851.404 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-705-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-01-07 20:05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -30851.404 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-608-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-01-07 19:44 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31146.556 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-607-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-01-07 19:44 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31146.556 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-706-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-01-07 20:05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -30851.404 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-505-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31186.332 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-606-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31186.332 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-707-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-01-07 20:05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31146.556 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-508-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31146.556 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-708-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-01-07 20:05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31146.556 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-708-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31243.18 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-605-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31186.332 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-607-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31243.18 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-508-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31243.18 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-507-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105451 | 2024-02-21 | 32459.34 | 2024-02-21 13:09 | -31243.18 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1004-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42592.9 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1802-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-06-30 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42004.084 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1803-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-06-30 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42299.236 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1002-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42273.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1902-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-06-30 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42339.012 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1904-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-06-30 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42395.86 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1104-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42592.9 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1201-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42273.1 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1302-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42273.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-2003-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-06-30 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42395.86 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1301-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42273.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-2001-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-06-30 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42339.012 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-901-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42273.1 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1204-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42592.9 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1804-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-06-30 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42299.236 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-002-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42273.1 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1003-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42592.9 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1102-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42273.1 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1103-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42592.9 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1304-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42592.9 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1703-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-06-30 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42299.236 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1901-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-06-30 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42339.012 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1101-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42273.1 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1303-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42592.9 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-902-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42273.1 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-904-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42592.9 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1704-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-06-30 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42299.236 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-2002-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-06-30 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42339.012 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1203-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42592.9 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1001-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42273.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1701-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-06-30 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42004.084 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1903-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-06-30 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42395.86 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-2004-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-06-30 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42395.86 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1801-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-06-30 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42004.084 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-903-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-29 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108680 | 2024-07-01 | 43612.02 | 2024-07-26 12:47 | -42592.9 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-105-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2023-12-08 15:57 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104076 | 2023-12-21 | 12158.7 | 2023-12-22 11:32 | -10819.78 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-406-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2023-12-08 16:38 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104076 | 2023-12-21 | 12158.7 | 2023-12-22 11:32 | -10550.764 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-405-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2023-12-08 16:28 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104076 | 2023-12-21 | 12158.7 | 2023-12-22 11:32 | -10885.692 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-405-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2023-12-08 16:38 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104076 | 2023-12-21 | 12158.7 | 2023-12-22 11:32 | -10550.764 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-408-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2023-12-08 16:38 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104076 | 2023-12-21 | 12158.7 | 2023-12-22 11:32 | -10845.916 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-407-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2023-12-08 16:28 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104076 | 2023-12-21 | 12158.7 | 2023-12-22 11:32 | -10942.54 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-406-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2023-12-08 16:28 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104076 | 2023-12-21 | 12158.7 | 2023-12-22 11:32 | -10885.692 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-407-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2023-12-08 16:38 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104076 | 2023-12-21 | 12158.7 | 2023-12-22 11:32 | -10845.916 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-408-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2023-12-08 16:28 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104076 | 2023-12-21 | 12158.7 | 2023-12-22 11:32 | -10942.54 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-303-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-11-09 00:06 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 103402 | 2023-11-09 | 9956.68 | 2023-12-02 12:17 | -8740.52 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-302-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-11-09 00:06 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 103402 | 2023-11-09 | 9956.68 | 2023-12-02 12:17 | -8683.672 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-304-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-11-09 00:06 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 103402 | 2023-11-09 | 9956.68 | 2023-12-02 12:17 | -8740.52 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-306-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-11-09 00:06 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 103402 | 2023-11-09 | 9956.68 | 2023-12-02 12:17 | -8683.672 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-301-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-11-09 00:06 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 103402 | 2023-11-09 | 9956.68 | 2023-12-02 12:17 | -8683.672 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-305-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-11-09 00:06 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 103402 | 2023-11-09 | 9956.68 | 2023-12-02 12:17 | -8683.672 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-307-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-11-09 00:06 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 103402 | 2023-11-09 | 9956.68 | 2023-12-02 12:17 | -8740.52 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-308-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-11-09 00:06 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 103402 | 2023-11-09 | 9956.68 | 2023-12-02 12:17 | -8740.52 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-605-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26306.94 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-706-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26306.94 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-905-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-05-16 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26372.852 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-607-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26626.74 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-508-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26626.74 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-405-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26306.94 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-407-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26626.74 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-905-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-05-16 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26037.924 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-907-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-05-16 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26333.076 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-705-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26306.94 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-907-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-05-16 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26429.7 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-505-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26306.94 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-507-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26626.74 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-906-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-05-16 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26372.852 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-908-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-05-16 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26429.7 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-908-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-05-16 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26333.076 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-606-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26306.94 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-608-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26626.74 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-906-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-05-16 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26037.924 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-406-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26306.94 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-408-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26626.74 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-506-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-05-16 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107649 | 2024-05-20 | 27645.86 | 2024-06-10 11:25 | -26306.94 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-208-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-26 21:22 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17845.2 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-502-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-26 21:27 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17525.4 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-306-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-26 21:22 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17525.4 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-601-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-26 21:27 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17525.4 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-602-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-26 21:27 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17525.4 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-603-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-26 21:27 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17845.2 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-206-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-26 21:22 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17525.4 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-307-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-26 21:22 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17845.2 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-503-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-26 21:27 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17845.2 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-205-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-26 21:22 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17525.4 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-207-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-26 21:22 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17845.2 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-305-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-26 21:22 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17525.4 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-501-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-26 21:27 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17525.4 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-504-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-26 21:27 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17845.2 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-308-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-26 21:22 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17845.2 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-604-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-26 21:27 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 105613 | 2024-02-28 | 18864.32 | 2024-03-18 12:04 | -17845.2 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1102-3BHK Chemical WP Before Brickbat WP | 56.6432 | 22 | 0 | 1246.1504 | 224.3 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21457.6196 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1103-2BHK Chemical WP Before Brickbat WP | 46.2458 | 22 | 0 | 1017.4076 | 183.14 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21686.3624 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-901-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-02-26 17:03 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21095.834 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-902-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-02-26 17:03 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21095.834 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-903-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-02-26 17:03 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21390.986 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1101-3BHK Chemical WP Before Brickbat WP | 56.6432 | 22 | 0 | 1246.1504 | 224.3 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21457.6196 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1104-2BHK Chemical WP Before Brickbat WP | 46.2458 | 22 | 0 | 1017.4076 | 183.14 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21686.3624 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1302-3BHK Chemical WP Before Brickbat WP | 56.6432 | 22 | 0 | 1246.1504 | 224.3 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21457.6196 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-904-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-02-26 17:03 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21390.986 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1304-2BHK Chemical WP Before Brickbat WP | 46.2458 | 22 | 0 | 1017.4076 | 183.14 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21686.3624 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1002-3BHK Chemical WP Before Brickbat WP | 56.6432 | 22 | 0 | 1246.1504 | 224.3 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21457.6196 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1004-2BHK Chemical WP Before Brickbat WP | 46.2458 | 22 | 0 | 1017.4076 | 183.14 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21686.3624 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1201-3BHK Chemical WP Before Brickbat WP | 56.6432 | 22 | 0 | 1246.1504 | 224.3 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21457.6196 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1003-2BHK Chemical WP Before Brickbat WP | 46.2458 | 22 | 0 | 1017.4076 | 183.14 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21686.3624 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1301-3BHK Chemical WP Before Brickbat WP | 56.6432 | 22 | 0 | 1246.1504 | 224.3 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21457.6196 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1303-2BHK Chemical WP Before Brickbat WP | 46.2458 | 22 | 0 | 1017.4076 | 183.14 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21686.3624 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1001-3BHK Chemical WP Before Brickbat WP | 56.6432 | 22 | 0 | 1246.1504 | 224.3 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21457.6196 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1203-2BHK Chemical WP Before Brickbat WP | 46.2458 | 22 | 0 | 1017.4076 | 183.14 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21686.3624 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1204-2BHK Chemical WP Before Brickbat WP | 46.2458 | 22 | 0 | 1017.4076 | 183.14 | 2024-02-26 17:41 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105602 | 2024-02-26 | 22703.77 | 1900-01-01 | -21686.3624 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-806-3BHK Chemical WP Before Brickbat WP | 18.272 | 22 | 0 | 401.984 | 72.36 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12023.536 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-707-2BHK Int Flat Chemical Grouting Work | 101.912 | 2 | 0 | 203.824 | 36.68 | 2024-06-23 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12221.696 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-707-2BHK Chemical WP Before Brickbat WP | 14.918 | 22 | 0 | 328.196 | 59.08 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12097.324 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-808-2BHK Chemical WP Before Brickbat WP | 14.918 | 22 | 0 | 328.196 | 59.08 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12097.324 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-808-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-23 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -11406.4 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-406-3BHK Chemical WP Before Brickbat WP | 18.272 | 22 | 0 | 401.984 | 72.36 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12023.536 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-508-2BHK Chemical WP Before Brickbat WP | 14.918 | 22 | 0 | 328.196 | 59.08 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12097.324 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-606-3BHK Chemical WP Before Brickbat WP | 18.272 | 22 | 0 | 401.984 | 72.36 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12023.536 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-705-3BHK Chemical WP Before Brickbat WP | 18.272 | 22 | 0 | 401.984 | 72.36 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12023.536 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-805-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-23 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -11086.6 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-605-3BHK Chemical WP Before Brickbat WP | 18.272 | 22 | 0 | 401.984 | 72.36 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12023.536 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-805-3BHK Chemical WP Before Brickbat WP | 18.272 | 22 | 0 | 401.984 | 72.36 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12023.536 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-807-2BHK Chemical WP Before Brickbat WP | 14.918 | 22 | 0 | 328.196 | 59.08 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12097.324 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-505-3BHK Chemical WP Before Brickbat WP | 18.272 | 22 | 0 | 401.984 | 72.36 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12023.536 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-507-2BHK Chemical WP Before Brickbat WP | 14.918 | 22 | 0 | 328.196 | 59.08 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12097.324 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-708-2BHK Chemical WP Before Brickbat WP | 14.918 | 22 | 0 | 328.196 | 59.08 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12097.324 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-806-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-23 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -11086.6 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-407-2BHK Chemical WP Before Brickbat WP | 14.918 | 22 | 0 | 328.196 | 59.08 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12097.324 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-607-2BHK Chemical WP Before Brickbat WP | 14.918 | 22 | 0 | 328.196 | 59.08 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12097.324 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-706-3BHK Chemical WP Before Brickbat WP | 18.272 | 22 | 0 | 401.984 | 72.36 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12023.536 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-408-2BHK Chemical WP Before Brickbat WP | 14.918 | 22 | 0 | 328.196 | 59.08 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12097.324 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-608-2BHK Chemical WP Before Brickbat WP | 14.918 | 22 | 0 | 328.196 | 59.08 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12097.324 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-405-3BHK Chemical WP Before Brickbat WP | 18.272 | 22 | 0 | 401.984 | 72.36 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12023.536 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-506-3BHK Chemical WP Before Brickbat WP | 18.272 | 22 | 0 | 401.984 | 72.36 | 2024-06-23 15:37 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12023.536 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-708-2BHK Int Flat Chemical Grouting Work | 101.912 | 2 | 0 | 203.824 | 36.68 | 2024-06-23 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 108549 | 2024-06-24 | 12425.52 | 2024-08-05 14:00 | -12221.696 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-002-3BHK Chemical WP Before Brickbat WP | 130.952 | 22 | 0 | 2880.944 | 0 | 2023-10-17 12:53 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -59214.316 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-102-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60487.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-203-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60782.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-106-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60487.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-201-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60487.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-104-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60879.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-101-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60487.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-208-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60879.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-208-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60782.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-007-2BHK Chemical WP Before Brickbat WP | 114.96 | 22 | 0 | 2529.12 | 0 | 2023-10-17 12:53 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -59566.14 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-105-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60822.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-202-2BHK(Near Refuse Area) Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60822.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-204-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60782.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-206-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60487.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-004-2BHK Chemical WP Before Brickbat WP | 114.96 | 22 | 0 | 2529.12 | 0 | 2023-10-17 12:53 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -59566.14 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-203-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60879.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-205-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60822.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-003-2BHK Chemical WP Before Brickbat WP | 114.96 | 22 | 0 | 2529.12 | 0 | 2023-10-17 12:53 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -59566.14 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-201-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60822.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-206-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60822.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-207-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60782.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-008-2BHK Chemical WP Before Brickbat WP | 114.96 | 22 | 0 | 2529.12 | 0 | 2023-10-17 12:53 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -59566.14 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-204-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60879.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-106-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60822.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-108-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60879.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-107-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60782.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-108-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60782.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-101-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60822.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-102-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60822.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-104-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60782.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-205-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60487.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-207-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60879.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-006-3BHK Chemical WP Before Brickbat WP | 130.952 | 22 | 0 | 2880.944 | 0 | 2023-10-17 12:53 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -59214.316 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-005-3BHK Chemical WP Before Brickbat WP | 130.952 | 22 | 0 | 2880.944 | 0 | 2023-10-17 12:53 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -59214.316 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-105-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60487.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-107-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-17 12:10 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60879.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-001-3BHK Chemical WP Before Brickbat WP | 130.952 | 22 | 0 | 2880.944 | 0 | 2023-10-17 12:53 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -59214.316 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-103-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2023-10-17 12:39 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 102743 | 2023-10-18 | 62095.26 | 2023-11-03 15:41 | -60782.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-503-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80342.31 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-303-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-502-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80285.462 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-301-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -79950.534 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-503-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-01-07 19:29 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80245.686 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-403-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-01-07 18:51 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80342.31 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-603-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80342.31 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-704-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-01-07 18:59 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80342.31 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-301-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-07 18:28 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 104645 | 2024-01-20 | 81558.47 | 2024-02-10 10:50 | -80219.55 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-808-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-02-25 19:22 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105584 | 2024-02-26 | 10819.78 | 2024-03-28 12:36 | -9506.996 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-806-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-02-25 19:22 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105584 | 2024-02-26 | 10819.78 | 2024-03-28 12:36 | -9211.844 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-806-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-02-25 19:12 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105584 | 2024-02-26 | 10819.78 | 2024-03-28 12:36 | -9546.772 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-805-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 229.14 | 2024-02-25 19:12 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105584 | 2024-02-26 | 10819.78 | 2024-03-28 12:36 | -9546.772 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-807-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-02-25 19:12 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105584 | 2024-02-26 | 10819.78 | 2024-03-28 12:36 | -9603.62 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-805-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 289.42 | 2024-02-25 19:22 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105584 | 2024-02-26 | 10819.78 | 2024-03-28 12:36 | -9211.844 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-807-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 236.3 | 2024-02-25 19:22 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 105584 | 2024-02-26 | 10819.78 | 2024-03-28 12:36 | -9506.996 | PRASHANT KASHINATH NETAKE
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-808-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 218.9 | 2024-02-25 19:12 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105584 | 2024-02-26 | 10819.78 | 2024-03-28 12:36 | -9603.62 | PRASHANT KASHINATH NETAKE
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-802-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-05-05 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49170.34 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1604-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49293.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1401-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -48901.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1502-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -48901.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1402-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -48901.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1503-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49293.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1503-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49196.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1504-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49196.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1802-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49236.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1602-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49236.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1404-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49196.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1603-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49293.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1604-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49196.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1803-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49293.1 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-804-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-05-05 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49490.14 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-801-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-05-05 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49170.34 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-701-3BHK Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-05-05 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49170.34 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1702-2BHK(Near Refuse Area) Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49236.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1601-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -48901.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1602-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -48901.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1502-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49236.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1703-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49293.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1504-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49293.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1704-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49293.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1401-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49236.252 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-803-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-05-05 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49490.14 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1403-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49293.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1403-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49196.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1404-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49293.1 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-703-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-05-05 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49490.14 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1603-2BHK Chemical WP Before Brickbat WP | 59.672 | 22 | 0 | 1312.784 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49196.476 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1501-3BHK Chemical WP Before Brickbat WP | 73.088 | 22 | 0 | 1607.936 | 0 | 2024-05-05 | Labour and material Charges for Chemical waterproofing work before brickbat waterproofing for E Building internal flat. | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -48901.324 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1402-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49236.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1501-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49236.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1701-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49236.252 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-704-2BHK Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-05-05 | Material Supply Charges for- Chemical Grouting work for E Building internal Flats | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49490.14 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1804-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49293.1 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1601-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49236.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1801-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-05-05 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 107384 | 2024-05-07 | 50509.26 | 2024-06-06 12:22 | -49236.252 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-801-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1001-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1003-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1004-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1201-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1202-2BHK(Near Refuse Area) Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-901-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1102-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1302-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1301-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-904-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-804-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-701-3BHK Chemical Waterproofing | 14.466 | 22 | 0 | 318.252 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -31751.128 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-903-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-703-2BHK Chemical Waterproofing | 13.82 | 22 | 0 | 304.04 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -31765.34 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-902-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1103-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1104-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1304-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-704-2BHK Chemical Waterproofing | 13.82 | 22 | 0 | 304.04 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -31765.34 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-803-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1002-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1303-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-702-2BHK(Near Refuse Area) Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1101-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-802-3BHK Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-02-25 22:25 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30796.372 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1203-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | GANGAPRASAD K VARMA | 667 | 2023-04-14 | E-1204-2BHK Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-02-25 22:36 | Labour and Material Charges for Chemical Waterproofing work for Common toilet & Master toilet of E Building | 100 |  | 105583 | 2024-02-26 | 32069.38 | 1900-01-01 | -30853.22 | PRABHURAM VERMA
Plumbing Groove. | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-Bldg Plumbing Groove in Toilet & Kitch | 1300 | 50 | 0 | 65000 | 11700 | 2023-09-16 | Charges for Making of Groove on Concrete wall in toilet and kitchen of E Building from stilt to 2nd Floor for internal plumbing PPRC & ASTM Pipe. | 100 |  | 101925 | 2023-09-18 | 65000 | 2023-10-20 10:59 | 0 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-002-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-204-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-205-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-001-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-005-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-106-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-107-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-108-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-004-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-105-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-006-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-007-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-008-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-101-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-102-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-104-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-103-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-206-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-207-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-003-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-10-18 23:52 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 102793 | 2023-10-19 | 96000 | 2023-11-01 14:27 | -91200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-708-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-606-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-707-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-605-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-706-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-608-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-603-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-602-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-601-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-604-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-705-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-701-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-607-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-702-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-703-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-16 18:44 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 104038 | 2023-12-18 | 72000 | 1900-01-01 | -67200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-306-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-304-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-504-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:48 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-506-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:48 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-308-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-401-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-402-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-507-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:48 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-202-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-406-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-303-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-404-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-501-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:48 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-407-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-305-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-503-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:48 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-505-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:48 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-307-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-508-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:48 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-208-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-301-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-502-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:48 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-302-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-405-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-403-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-408-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-12-10 16:35 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103824 | 2023-12-11 | 124800 | 2023-12-25 15:34 | -120000 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-802-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-905-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-805-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-906-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1007-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1306-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-801-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-803-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1202-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-804-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1008-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1307-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1401-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-907-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-808-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1101-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1005-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1108-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1205-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1407-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-704-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-807-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-904-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1106-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1308-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1104-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1303-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1003-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1201-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1204-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1403-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1404-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1208-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-902-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-903-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1301-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1305-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1002-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-908-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-806-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1107-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1206-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1203-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1405-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1406-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1408-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1102-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1304-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1001-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1004-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1402-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1207-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1006-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1105-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-901-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:22 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1103-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1302-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-03-02 17:27 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 105728 | 2024-03-04 | 273600 | 2024-03-16 10:54 | -268800 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Plumbing Groove. | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-Bldg Plumbing Groove in Toilet & Kitch | 72.26 | 50 | 0 | 3613 | 650.34 | 2023-12-31 17:58 | Charges for Making of Groove on Concrete wall in toilet and kitchen of E Building from stilt to 2nd Floor for internal plumbing PPRC & ASTM Pipe. | 100 |  | 104254 | 2024-01-01 | 3613 | 2024-02-19 15:28 | 0 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-201-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-11-03 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103251 | 2023-11-04 | 9600 | 2023-12-19 10:48 | -4800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-203-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2023-11-03 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 103251 | 2023-11-04 | 9600 | 2023-12-19 10:48 | -4800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Plumbing Groove. | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-Bldg Plumbing Groove in Toilet & Kitch | 88 | 50 | 0 | 4400 | 792 | 2023-11-07 | Charges for Making of Groove on Concrete wall in toilet and kitchen of E Building from stilt to 2nd Floor for internal plumbing PPRC & ASTM Pipe. | 100 |  | 103382 | 2023-11-08 | 4400 | 2023-12-02 12:17 | 0 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1501-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1508-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1604-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1606-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1608-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1806-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1504-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1805-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1506-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1708-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1807-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1901-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1908-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1503-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1706-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1703-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1904-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1905-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1803-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1603-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1605-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1505-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1507-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1601-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1707-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1801-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1702-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1502-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1705-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1906-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1907-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1602-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1701-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1802-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1607-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1903-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1804-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1808-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1902-3BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 668 | 2023-04-15 | E-1704-2BHK Internal Plumbing Work (L) | 0.8 | 6000 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for- PVC,PPRC and ASTM Pipe internal plumbing work of E Building. | 100 |  | 108196 | 2024-06-10 | 192000 | 2024-06-24 12:07 | -187200 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 669 | 2023-04-15 | E-Bldg External Plumbing Work (L) | 1 | 2000 | 0 | 2000 | 360 | 2023-11-06 | Labour Charges for Exteral plumbing Rainwater line work of E Building | 100 |  | 103344 | 2023-11-07 | 2000 | 2023-12-02 12:17 | 0 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Rainwater Line | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 669 | 2023-04-15 | E-Bldg External Plumbing Work (L) | 40 | 2000 | 0 | 80000 | 14400 | 2024-03-02 17:11 | Labour Charges for Exteral plumbing Rainwater line work of E Building | 100 |  | 105737 | 2024-03-04 | 80000 | 2024-03-16 10:54 | 0 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 669 | 2023-04-15 | E-Bldg External Plumbing Work (L) | 33 | 2000 | 0 | 66000 | 11880 | 2023-12-10 16:51 | Labour Charges for Exteral plumbing Rainwater line work of E Building | 100 |  | 103825 | 2023-12-11 | 66000 | 2023-12-25 15:35 | 0 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 669 | 2023-04-15 | E-Bldg External Plumbing Work (L) | 30 | 2000 | 0 | 60000 | 10800 | 2023-10-19 00:03 | Labour Charges for Exteral plumbing Rainwater line work of E Building | 100 |  | 102838 | 2023-10-20 | 60000 | 2023-11-01 14:27 | 0 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Purlin 50x50x5 fixing (L)- SOS | N/C | N/C | PRESSMET ENTERPRISES | 670 | 2023-04-18 | F-Bldg Barrication Work | 441.6 | 15 | 0 | 6624 | 0 | 2023-10-06 | Labour charges for fixing of Purlin (Angle- 50x50x5) for GI Sheet support F-Bldg Barrication work. | 100 |  | 102404 | 2023-10-07 | 6624 | 2023-10-28 12:00 | 0 | SURESH RANGNATH SHITOLE
Fabrication work (L) | N/C | N/C | PRESSMET ENTERPRISES | 670 | 2023-04-18 | F-Bldg Barrication Work | 134.4 | 15 | 0 | 2016 | 0 | 2023-05-10 | Labour charges for Fixing of 100mm C-Channel vertical pole for F-Bldg Barrication work. | 100 |  | 99571 | 2023-05-10 | 2016 | 2023-05-15 18:32 | 0 | IZHAR MANSOOR SHAIKH
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 671 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 1500 | 7.5 | 0 | 11250 | 2025 | 2023-09-13 | Material Supply charges for External Texture Painting work for F-Bldg LG Floor Parking Area. | 100 |  | 101857 | 2023-09-15 | 11250 | 1900-01-01 | 0 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 671 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 1500 | 7.5 | 0 | 11250 | 2025 | 2023-08-16 | Material Supply charges for External Texture Painting work for F-Bldg LG Floor Parking Area. | 100 |  | 101288 | 2023-08-17 | 11250 | 2023-09-01 11:43 | 0 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | MANSI ENTERPRISES | 671 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 2382 | 7.5 | 0 | 17865 | 3215.7 | 2023-08-19 | Material Supply charges for External Texture Painting work for F-Bldg LG Floor Parking Area. | 100 |  | 101354 | 2023-08-21 | 17865 | 2023-09-01 11:42 | 0 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | MANSI ENTERPRISES | 671 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 5979.43 | 2.25 | 0 | 13453.7175 | 2421.66 | 2023-09-20 | Material Supply charges of 1st Coat Acrylic Paint for F-Bldg LG Floor Int. Parking Area. | 100 |  | 101985 | 2023-09-20 | 19433.15 | 2023-09-30 11:54 | -5979.4325 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | MANSI ENTERPRISES | 671 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 5979.43 | 1 | 0 | 5979.43 | 1076.3 | 2023-09-20 | Material Supply charges of 1 Coat Water Base Primer for F-Bldg LG Floor Int. Parking Area. | 100 |  | 101985 | 2023-09-20 | 19433.15 | 2023-09-30 11:54 | -13453.72 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | MANSI ENTERPRISES | 672 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 5381.487 | 1.5 | 0 | 8072.2305 | 1453 | 2023-09-20 | Labour charges for Applying 1st coat Acrylic Paint for Elevation walls with crack filling.including crack sill proper cleaning/scrapping all required tools,equipments,transporation of raw material done contractor for F-Bldg LG Floor Int. Parking Area. | 100 |  | 101986 | 2023-09-20 | 8072.23 | 2023-09-30 11:54 | 0.0005 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 672 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 2382.069 | 7.25 | 0 | 17270.0003 | 3108.6 | 2023-08-19 | Labour Charges for Applying Texture Paint including joint putty, Grinding and Touchup for F-Bldg LG Floor Int. Parking Area. | 100 |  | 101355 | 2023-08-21 | 30857 | 2023-09-01 11:42 | -13586.9998 | VEER BHADRA ENTERPRISES
Scaffolding work | No category | N/C | MANSI ENTERPRISES | 672 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 3882 | 3.5 | 0 | 13587 | 2445.66 | 2023-08-19 | Labour Charges for Scaffolding Fixing and Removing work for F-Bldg LG Floor Int. Parking Area. | 100 |  | 101355 | 2023-08-21 | 30857 | 2023-09-01 11:42 | -17270 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | MANSI ENTERPRISES | 672 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 2000 | 1 | 0 | 2000 | 360 | 2024-04-07 | Labour charges for Applying Water Base Primer one coat including proper cleaning. all tools & equipments i.e. sand paper,Brush,Patra,Roller,Ghodi etc for F-Bldg LG Floor Int. Parking Area. | 100 |  | 106657 | 2024-04-08 | 2750 | 1900-01-01 | -750 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | MANSI ENTERPRISES | 672 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 500 | 1.5 | 0 | 750 | 135 | 2024-04-07 | Labour charges for Applying 1st coat Acrylic Paint for Elevation walls with crack filling.including crack sill proper cleaning/scrapping all required tools,equipments,transporation of raw material done contractor for F-Bldg LG Floor Int. Parking Area. | 100 |  | 106657 | 2024-04-08 | 2750 | 1900-01-01 | -2000 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 672 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 1500 | 7.25 | 0 | 10875 | 1957.5 | 2023-08-16 | Labour Charges for Applying Texture Paint including joint putty, Grinding and Touchup for F-Bldg LG Floor Int. Parking Area. | 100 |  | 101290 | 2023-08-17 | 10875 | 2023-09-01 11:43 | 0 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 672 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 1500 | 7.25 | 0 | 10875 | 1957.5 | 2023-09-13 | Labour Charges for Applying Texture Paint including joint putty, Grinding and Touchup for F-Bldg LG Floor Int. Parking Area. | 100 |  | 101855 | 2023-09-15 | 10875 | 2023-10-11 11:11 | 0 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (L) | N/C | N/C | MANSI ENTERPRISES | 672 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 80 | 1.5 | 0 | 120 | 21.6 | 2024-06-02 | Labour charges for Applying 1st coat Acrylic Paint for Elevation walls with crack filling.including crack sill proper cleaning/scrapping all required tools,equipments,transporation of raw material done contractor for F-Bldg LG Floor Int. Parking Area. | 100 |  | 107931 | 2024-06-03 | 8948.25 | 2024-06-15 17:59 | -8828.25 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (L) | N/C | N/C | MANSI ENTERPRISES | 672 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 3000 | 1.5 | 0 | 4500 | 810 | 2024-06-02 | Labour charges for Applying 2nd coat Acrylic Paint for Elevation walls with crack filling.including crack sill proper cleaning/scrapping all required tools & equipments & transporation of raw material to be done by contractor for F-Bldg LG Int. Parking. | 100 |  | 107931 | 2024-06-03 | 8948.25 | 2024-06-15 17:59 | -4448.25 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | MANSI ENTERPRISES | 672 | 2023-04-25 | F-Bldg LG. Fl Int. SideTexture Painting Work | 597 | 7.25 | 0 | 4328.25 | 779.08 | 2024-06-02 | Labour Charges for Applying Texture Paint including joint putty, Grinding and Touchup for F-Bldg LG Floor Int. Parking Area. | 100 |  | 107931 | 2024-06-03 | 8948.25 | 2024-06-15 17:59 | -4620 | VEER BHADRA ENTERPRISES
Brickwork 9" - ULT | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | Transformer Room- Brickwork & Plaster Above Plinth Beam (L) | 290.22 | 21 | 0 | 6094.62 | 1097.04 | 2023-08-21 | Labour charges for 9 inch Fly ash Brickwork above Plinth Beam for transformer room outer peripheri. | 100 |  | 101364 | 2023-08-22 | 17341.62 | 2023-09-04 11:40 | -11247 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - UTR | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg STP- 8" Blockwork & Plaster Work (L) | 243.9 | 20 | 0 | 4878 | 878.04 | 2023-08-21 | Labour Charges for sand face plaster with proper joint preparation between RCC & Blockwork using chiken mesh etc complete. | 100 |  | 101364 | 2023-08-22 | 17341.62 | 2023-09-04 11:40 | -12463.62 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - UTR | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 318.45 | 20 | 0 | 6369 | 1146.42 | 2023-08-21 | Labour Charges for sand face plaster with proper joint preparation between RCC & Blockwork using chiken mesh etc complete. | 100 |  | 101364 | 2023-08-22 | 17341.62 | 2023-09-04 11:40 | -10972.62 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - UTR | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 1273.808 | 20 | 0 | 25476.16 | 4585.7 | 2023-07-31 | Labour Charges for sand face plaster with proper joint preparation between RCC & Blockwork using chiken mesh etc complete. | 100 |  | 100924 | 2023-07-31 | 52432.12 | 2023-08-09 13:02 | -26955.96 | JAI SEVALAL CONSTRUCTION
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg STP- 8" Blockwork & Plaster Work (L) | 213.65 | 20 | 0 | 4273 | 769.14 | 2023-07-31 | Charges for Construction of 8 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 100924 | 2023-07-31 | 52432.12 | 2023-08-09 13:02 | -48159.12 | JAI SEVALAL CONSTRUCTION
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 158.5 | 20 | 0 | 3170 | 570.6 | 2023-07-31 | Charges for Construction of 8 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 100924 | 2023-07-31 | 52432.12 | 2023-08-09 13:02 | -49262.12 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - UTR | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg STP- 8" Blockwork & Plaster Work (L) | 975.648 | 20 | 0 | 19512.96 | 3512.34 | 2023-07-31 | Labour Charges for sand face plaster with proper joint preparation between RCC & Blockwork using chiken mesh etc complete. | 100 |  | 100924 | 2023-07-31 | 52432.12 | 2023-08-09 13:02 | -32919.16 | JAI SEVALAL CONSTRUCTION
8" Blockwork Rate Diff. | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 158.5 | 1 | 0 | 158.5 | 28.54 | 2024-04-08 | Rate Differance Charges for 8 inch Block work. | 100 |  | 106706 | 2024-04-08 | 158.5 | 1900-01-01 | 0 | JAI SEVALAL CONSTRUCTION
8" Blockwork Rate Diff. | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 635.944 | 1 | 0 | 635.944 | 114.46 | 2023-12-28 18:31 | Rate Differance Charges for 8 inch Block work. | 100 |  | 104227 | 2024-01-01 | 7495.91 | 1900-01-01 | -6859.966 | JAI SEVALAL CONSTRUCTION
8" Blockwork Rate Diff. | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg STP- 8" Blockwork & Plaster Work (L) | 490.928 | 1 | 0 | 490.928 | 88.36 | 2023-12-28 18:31 | Rate Differance Charges for 8 inch Block work. | 100 |  | 104227 | 2024-01-01 | 7495.91 | 1900-01-01 | -7004.982 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster Rate Diff. - DCH | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 1273.808 | 5 | 0 | 6369.04 | 1146.42 | 2023-12-28 18:31 | Rate Differance Charges for Sand Face Plaster with proper joint preparation between RCC & Blockwork using Chiken mesh etc complete. | 100 |  | 104227 | 2024-01-01 | 7495.91 | 1900-01-01 | -1126.87 | JAI SEVALAL CONSTRUCTION
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 635.944 | 20 | 0 | 12718.88 | 0 | 2023-07-04 | Charges for Construction of 8 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 100462 | 2023-07-05 | 20718.88 | 2023-07-26 12:27 | -8000 | K RAMU RATHOD
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg STP- 8" Blockwork & Plaster Work (L) | 400 | 20 | 0 | 8000 | 0 | 2023-07-04 | Charges for Construction of 8 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 100462 | 2023-07-05 | 20718.88 | 2023-07-26 12:27 | -12718.88 | K RAMU RATHOD
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-08-17 | 4) JULY 2023 | 8.3333 |  | 101295 | 2023-08-17 | 39999.84 | 2023-08-17 17:35 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-06-08 | 1) APRIL 2023 | 8.3333 |  | 100013 | 2023-06-08 | 39999.84 | 2023-06-08 18:41 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-06-08 | 2) MAY 2023 | 8.3333 |  | 100014 | 2023-06-08 | 39999.84 | 2023-06-08 18:42 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-07-19 | 3) JUNE 2023 | 8.3333 |  | 100761 | 2023-07-19 | 39999.84 | 2023-07-19 17:40 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-10-25 | 6) SEPT. 2023 | 8.3333 | ONLINE AND OFFLINE BRANDING SOCAIL MEDIA CREATIVES BILL FOR THE MONTH OF SEPT 2023 | 102982 | 2023-10-25 | 39999.84 | 2023-10-26 18:15 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-10-03 | 5) AUGUST 2023 | 8.3333 |  | 102200 | 2023-10-03 | 39999.84 | 2023-10-03 16:26 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2024-01-03 | 9) DEC. 2023 | 8.3333 | MONTHLY MEDIA ONLINE SOCIAL PLATFORM MARKETINGF ACTIVITY, BRANDING, SALES PROMOTION ETC. MONTLY BASIS CHARGES @40,000/- + TAX PER MONTH AS 01/06/2023 TO 31/03/2024. | 104312 | 2024-01-03 | 39999.84 | 2024-01-06 10:22 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2024-02-15 | 10) JANUARY 2024 | 8.3333 | RETAINERSHIP CHAREGES FOR SOCIAL MEDIA FOR THE MONTH OF JAN 2024 | 105326 | 2024-02-15 | 39999.84 | 2024-02-20 16:32 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-11-04 | 7) OCT. 2023 | 8.3333 | RETAINER BILL FOR THE MONTH OF OCT 2023 | 103279 | 2023-11-04 | 39999.84 | 2023-11-09 11:35 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2023-12-01 | 8) NOV. 2023 | 8.3333 | MOTHLY MEDIA ONLINE CHARGES SOCIAL PLATFORM ACTIVITY, BRANDING, SALES PROMOTION ETC. MONTLY BASIS CHARGES @40,000/- + TAX FOR THE MONTH OF NOVEMBER 2023 | 103568 | 2023-12-01 | 39999.84 | 2023-12-01 13:13 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2024-03-13 | 11) FEBRUARY 2024 | 8.3333 | MONTHLY MEDIA ONLINE SOCIAL PLATFORM MARKETINGF ACTIVITY, BRANDING, SALES PROMOTION ETC. MONTLY BASIS CHARGES @40,000/- + TAX PER MONTH | 106042 | 2024-03-13 | 39999.84 | 2024-03-16 12:20 | 0 | GOOD OLD DELIGHT
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 677 | 2023-05-08 | BRANDING Branding | 12 | 40000 | 0 | 40001.76 | 7200.32 | 2024-04-10 | 12) MARCH 2024 | 8.3337 | MONTHLY MEDIA/ MARKETING SOCIAL/ DIGITAL MONTHLY RETAINERSHIP CHARGES @ 40000 + TAX | 106736 | 2024-04-10 | 40001.76 | 2024-04-11 16:09 | 0 | GOOD OLD DELIGHT
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 1.0112 | 500000 | 7 | 505600 | 91009.26 | 2024-02-22 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 | ONLINE SOCIAL DIGITAL MEDIA / MARKETING BRANDING WITH LED GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY EXPENSES + TAX FOR THE MONTH OF JAN 2024 | 105462 | 2024-02-23 | 505607 | 2024-02-26 16:05 | -7 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 1.0106 | 500000 | -16 | 505300 | 90951.12 | 2024-03-12 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 | ONLINE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATAION THROUGH FACEBOOK | 106040 | 2024-03-12 | 505284 | 2024-03-16 12:24 | 16 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.8257 | 500000 | -1 | 412850 | 74312.82 | 2024-04-05 | FACEBOOK LEAD GENERATION CAMPAING | 100 | FACEBOOK LEAD GENERATION CAMPAING | 106482 | 2024-04-05 | 612849 | 2024-04-08 18:48 | -199999 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.4 | 500000 | 0 | 200000 | 36000 | 2024-04-03 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 | FACEBOOK MNTHLY CHARGES | 106482 | 2024-04-05 | 612849 | 2024-04-08 18:48 | -412849 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.0742 | 500000 | 1 | 37100 | 6678.18 | 2024-04-05 | FACEBOOK LEAD GENERATION CAMPAING | 100 | https://docs.google.com/spreadsheets/d/1le5wjd4-aYETQreQpqytmVzetCnuU7Rf_6dGsZAO-w0/edit?usp=sharing | 106483 | 2024-04-05 | 37101 | 2024-04-08 18:48 | -1 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.8929 | 500000 | 11 | 446450 | 80362.98 | 2024-01-05 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 | FACEBOOK PAID CAMPAING BILL FOR THE MONTH OF JAN 2024. | 104349 | 2024-01-05 | 446450 | 2024-01-06 10:19 | 0 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.925 | 500000 | -12 | 462500 | 83247.84 | 2023-06-09 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 100036 | 2023-06-09 | 462488 | 2023-06-09 13:16 | 12 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.2526 | 500000 | -19 | 126300 | 22730.58 | 2023-06-09 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 100037 | 2023-06-09 | 126281 | 2023-06-09 13:16 | 19 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.7375 | 500000 | -11 | 368750 | 66373.02 | 2023-06-09 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 100038 | 2023-06-09 | 368739 | 2023-06-09 13:17 | 11 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.6446 | 500000 | 0 | 322300 | 58014 | 2023-07-15 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 100704 | 2023-07-15 | 322300 | 2023-07-17 18:51 | 0 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.3127 | 500000 | -20 | 156350 | 28139.4 | 2023-07-15 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 100708 | 2023-07-15 | 156330 | 2023-07-17 18:52 | 20 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.1598 | 500000 | 0 | 79900 | 14382 | 2023-07-15 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 100709 | 2023-07-15 | 79900 | 2023-07-17 18:51 | 0 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.7572 | 500000 | 8 | 378600 | 68149.44 | 2023-09-07 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 101720 | 2023-09-07 | 378608 | 2023-09-09 11:15 | -8 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.76 | 500000 | 13 | 380000 | 68402.34 | 2023-09-07 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 101721 | 2023-09-07 | 380013 | 2023-09-09 11:15 | -13 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.6241 | 500000 | -22 | 312050 | 56165.04 | 2023-08-09 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 101145 | 2023-08-09 | 312028 | 2023-08-10 13:15 | 22 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.79 | 500000 | -14 | 395000 | 71097.48 | 2023-08-09 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 101146 | 2023-08-09 | 394986 | 2023-08-10 13:16 | 14 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.5229 | 500000 | 4 | 261450 | 47061.72 | 2023-10-05 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 102306 | 2023-10-05 | 261454 | 2023-10-05 14:31 | -4 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.1436 | 500000 | -6 | 71800 | 12922.92 | 2023-10-05 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 102301 | 2023-10-05 | 71794 | 2023-10-05 14:30 | 6 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.7261 | 500000 | -22 | 363050 | 65345.04 | 2023-10-05 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 102302 | 2023-10-05 | 363028 | 2023-10-05 14:30 | 22 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.008 | 500000 | 0 | 4000 | 720 | 2023-10-05 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 |  | 102303 | 2023-10-05 | 4000 | 2023-10-05 14:30 | 0 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.2815 | 500000 | -24 | 140750 | 25330.68 | 2023-12-02 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 | ONLINE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM FOR THE MONTH OF OCT2023 | 103593 | 2023-12-02 | 140726 | 2023-12-04 10:35 | 24 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.5362 | 500000 | -1 | 268100 | 48257.82 | 2023-12-02 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 | ONLINE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM FOR THE MONTH OF OCT 2023 | 103594 | 2023-12-02 | 268099 | 2023-12-04 10:35 | 1 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
FaceBook Paid Campaign | N/C | N/C | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED | 678 | 2023-05-09 | ONLINE / DIGITAL Social / Digital Activity | 0.5035 | 500000 | 7 | 251750 | 45316.26 | 2023-12-02 | ONLIE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM MONTHLY TARGATED RS. 500000/- + TAX PER MONTH AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 | 100 | ONLINE SOCIAL, DIGITAL MEDIA / MARKETING BRANDING WITH LEAD GENERATION THROUGH FACEBOOK DIGITAL PLATFORM FOR THE MONTH OF NOV 2023 | 103595 | 2023-12-02 | 251757 | 2023-12-04 10:35 | -7 | FACEBOOK INDIA ONLINE SERVICES PRIVATE LIMITED
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 4710.88 | 10 | 0 | 47108.8 | 8479.58 | 2024-07-20 18:32 | Schedule for RCC Work | 100 |  | 109264 | 2024-07-22 | 203575.4 | 2024-08-05 13:58 | -156466.6 | RITU ENTERPRISES
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 15646.66 | 10 | 0 | 156466.6 | 28163.98 | 2024-07-20 18:32 | Schedule for RCC Work | 100 |  | 109264 | 2024-07-22 | 203575.4 | 2024-08-05 13:58 | -47108.8 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2074.3997 | 155 | 0 | 321531.9535 | 57875.76 | 2023-12-25 16:21 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 104182 | 2023-12-25 | 321531.95 | 2024-01-02 11:45 | 0.0035 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 15.2727 | 165 | 0 | 2519.9955 | 0 | 2023-10-11 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102547 | 2023-10-12 | 2520 | 2023-11-06 16:15 | -0.0045 | PAWAR SHIVAPPA TARANAIK
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1230.6667 | 165 | -0.01 | 203060.0055 | 36550.8 | 2024-02-03 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | Debit for Rebaring (Challan No- 8,15,26,36,98) | 105063 | 2024-02-05 | 203060 | 2024-02-29 16:55 | 0.0055 | AVCON TECHNICS PVT LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 437 | 140 | 0 | 61180 | 11012.4 | 2023-09-08 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | Debit For Rebaring -12mm - 266 Nos, 230 Rs. each | 101747 | 2023-09-08 | 61180 | 1900-01-01 | 0 | AVCON TECHNICS PVT LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 208.2143 | 140 | 0 | 29150.002 | 5247 | 2023-08-08 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | Debit for rebaring at 1st slab 12mm having Quantity-115 Nos.,16mm having Quantity 6 no. for tie beam | 101112 | 2023-08-08 | 29150 | 2023-09-12 12:48 | 0.002 | AVCON TECHNICS PVT LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 104.9286 | 140 | 0 | 14690.004 | 2644.2 | 2023-07-27 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | Debit For Rebaring for D Bldg 1st slab 12 mm Bars having Qunatity - 58 nos X 230 Rs = 13340 16 mm Bars having Qunatity - 3 nos X 450 Rs =1350 Rs ,total- 14690 Rs. | 100879 | 2023-07-28 | 14690 | 2023-08-30 11:56 | 0.004 | AVCON TECHNICS PVT LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1400 | 140 | 0 | 196000 | 35280 | 2023-07-25 12:17 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 100835 | 2023-07-25 | 196000 | 2023-08-09 12:23 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1400 | 140 | 0 | 196000 | 35280 | 2023-10-02 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 102187 | 2023-10-03 | 196000 | 2023-10-17 12:47 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 42.8571 | 140 | 0.01 | 5999.994 | 0 | 2023-11-09 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | for Slab Chipping at Joint | 103404 | 2023-11-09 | 12000 | 2023-12-19 10:47 | -6000.006 | PRAKASH SAHU
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 38.7097 | 155 | 0 | 6000.0035 | 0 | 2023-11-09 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | for Slab Chipping at Joint | 103404 | 2023-11-09 | 12000 | 2023-12-19 10:47 | -5999.9965 | PRAKASH SAHU
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2800 | 155 | 0 | 434000 | 78120 | 2023-11-02 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 103204 | 2023-11-02 | 434000 | 2023-11-23 11:38 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1932 | 140 | 0 | 270480 | 48686.4 | 2023-08-07 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 101083 | 2023-08-08 | 270480 | 2023-08-14 14:32 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 580.69 | 155 | 0 | 90006.95 | 16201.26 | 2024-02-19 17:24 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 105552 | 2024-02-26 | 159059.95 | 2024-04-04 16:27 | -69053 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 26.39 | 140 | 0 | 3694.6 | 665.02 | 2024-02-19 17:24 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 105552 | 2024-02-26 | 159059.95 | 2024-04-04 16:27 | -155365.35 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 226.7896 | 255.45 | 0 | 57933.4033 | 10428.02 | 2024-02-19 18:32 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (Girder Slab) | 100 |  | 105552 | 2024-02-26 | 159059.95 | 2024-04-04 16:27 | -101126.5467 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 45 | 165 | 0 | 7425 | 1336.5 | 2024-02-19 17:24 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 105552 | 2024-02-26 | 159059.95 | 2024-04-04 16:27 | -151634.95 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1345 | 155 | 0 | 208475 | 37525.5 | 2023-12-04 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | =Total work done quantity in 4th ramp =1681 ,we have relesed 80 % Bill of that quantity | 103788 | 2023-12-11 | 208475 | 2023-12-16 17:30 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1200 | 140 | 0 | 168000 | 30240 | 2023-09-13 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 101829 | 2023-09-13 | 168000 | 2023-09-20 12:00 | 0 | RITU ENTERPRISES
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1789.2 | 10 | 0 | 17892 | 3220.56 | 2023-07-27 | Schedule for RCC Work | 100 | Debit For D Building LG Floor drive way Dressing leveling & Trimixing Concreting Work Having Area 3578.55 Sq.ft X 5 Rs. = 17892 Rs. | 100878 | 2023-07-28 | 17892 | 2023-09-04 19:05 | 0 | JAI SAIRAM CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 36.37 | 165 | 0 | 6001.05 | 0 | 2024-02-02 17:58 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | 5th slab chipping work | 106051 | 2024-03-14 | 6001.05 | 2024-03-18 12:06 | 0 | PRAKASH SAHU
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1333.33 | 165 | 0 | 219999.45 | 39599.9 | 2024-01-21 12:30 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | D building podium 4th to 5th slab ramp | 104685 | 2024-01-22 | 219999.45 | 2024-02-19 15:20 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2660.645 | 165 | 0 | 439006.425 | 79021.16 | 2023-10-11 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 102506 | 2023-10-11 | 439006.43 | 1900-01-01 | -0.005 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3419.66 | 10 | 0 | 34196.6 | 6155.38 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -86753.4 | AVCON TECHNICS PVT LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3419.66 | 10 | 0 | 34196.6 | 6155.38 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -86753.4 | AVCON TECHNICS PVT LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1836.02 | 10 | 0 | 18360.2 | 3304.84 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -102589.8 | AVCON TECHNICS PVT LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3419.66 | 10 | 0 | 34196.6 | 6155.38 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -86753.4 | AVCON TECHNICS PVT LTD
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-806-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-02-25 20:37 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105577 | 2024-02-26 | 5500 | 2024-03-28 12:37 | -5225 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-805-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-02-25 20:33 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105577 | 2024-02-26 | 5500 | 2024-03-28 12:37 | -4400 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-805-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-02-25 20:37 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105577 | 2024-02-26 | 5500 | 2024-03-28 12:37 | -5225 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-806-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-02-25 20:33 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105577 | 2024-02-26 | 5500 | 2024-03-28 12:37 | -4400 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-807-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-02-25 20:37 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105577 | 2024-02-26 | 5500 | 2024-03-28 12:37 | -5225 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-806-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-02-25 20:15 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105577 | 2024-02-26 | 5500 | 2024-03-28 12:37 | -5225 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-807-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-02-25 20:33 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105577 | 2024-02-26 | 5500 | 2024-03-28 12:37 | -4400 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-808-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-02-25 20:33 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105577 | 2024-02-26 | 5500 | 2024-03-28 12:37 | -4400 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-606-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-607-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-607-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-508-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-706-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-506-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-708-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-608-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-705-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-706-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-507-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-507-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-508-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-707-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-707-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-505-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-606-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-706-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-605-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-606-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-505-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-506-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1501-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1701-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:34 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1202-2BHK(Near Refuse Area) Bore Packing Work,Perma Eazee | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 14:57 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-108-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-208-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-006-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-207-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-105-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-004-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-003-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-206-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-005-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-205-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-104-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-002-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-103-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-101-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-006-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-204-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-207-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-103-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-002-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-003-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-106-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-001-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-008-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-108-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-205-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-106-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-204-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-001-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-007-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-101-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-104-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-203-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-004-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-102-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-005-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-201-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-007-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-206-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-008-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-105-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-107-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-107-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-201-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-10-17 15:27 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23815 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-102-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-203-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-208-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-10-17 15:10 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 102745 | 2023-10-18 | 24035 | 2023-11-03 15:40 | -23210 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1402-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 14:57 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1802-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 15:04 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1303-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1304-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1704-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:34 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1603-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1202-2BHK(Near Refuse Area) Bore Packing Work,Perma Eazee | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1702-2BHK(Near Refuse Area) Bore Packing Work,Perma Eazee | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 15:04 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1004-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1401-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1601-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1602-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1801-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:34 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1803-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:34 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1403-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1301-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1402-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1802-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:34 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1404-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1702-2BHK(Near Refuse Area) Bore Packing Work,Perma Eazee | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:34 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1502-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1803-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 15:04 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1103-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1402-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1002-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1203-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1204-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1404-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1604-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1401-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1403-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 14:57 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1104-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1101-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1703-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:34 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1302-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1404-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 14:57 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1401-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 14:57 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1201-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1701-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 15:04 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1703-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 15:04 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1704-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 15:04 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1003-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1403-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1501-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1503-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1804-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 15:04 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1102-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-05-13 15:12 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35475 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1504-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-05-13 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -36025 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1801-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-05-13 15:04 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35200 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1804-2BHK Bore Packing Work,Perma Eazee Coat | 2 | 275 | 0 | 550 | 0 | 2024-05-13 15:34 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107564 | 2024-05-13 | 36300 | 2024-07-26 12:46 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-803-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-902-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:17 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-903-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 20:47 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1004-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1103-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-903-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-801-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 20:47 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1201-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-901-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:17 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-904-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 20:47 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1303-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-602-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1104-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-501-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-802-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-901-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1004-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1304-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-601-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1002-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1204-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-702-2BHK(Near Refuse Area) Bore Packing Work,Perma Eazee C | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-901-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 20:47 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-503-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-504-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-704-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1301-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1302-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1001-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-804-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1003-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1102-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1104-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1301-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-703-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-801-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:17 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1101-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1102-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1303-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-802-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:17 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1302-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-502-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-902-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 20:47 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1201-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1203-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-902-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1001-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-803-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 20:47 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1003-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1304-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-701-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-904-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1001-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:17 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-802-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 20:47 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-804-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 20:47 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1101-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1103-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 20:52 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-801-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1002-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-1203-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-02-26 21:00 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -34925 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-603-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-604-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-02-26 21:07 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105614 | 2024-02-28 | 36025 | 2024-03-18 12:04 | -35750 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-905-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-05-19 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -6325 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-906-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-05-19 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -6325 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-907-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-05-19 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -5500 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-805-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-05-19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -6325 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-906-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-05-19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -6325 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-808-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-05-19 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -6325 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-908-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-05-19 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -5500 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-705-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-608-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-406-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-505-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-605-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-406-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:19 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-407-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:19 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-506-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 17:39 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-405-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-605-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-705-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22825 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-708-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:29 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-405-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:19 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-408-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-01-07 17:19 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 104381 | 2024-01-08 | 23100 | 2024-02-09 11:06 | -22000 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-403-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-305-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-09 00:31 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9295 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-307-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-09 00:31 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9295 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-301-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-303-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-307-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-401-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-402-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-308-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-09 00:31 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9295 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-302-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-09 00:31 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9295 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-304-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-09 00:31 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9295 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-302-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-304-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-406-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-408-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-301-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-09 00:31 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9295 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-405-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-306-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-308-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-407-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-303-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-09 00:31 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9295 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-305-3BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-404-2BHK Bore Packing Work,Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-09 00:23 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9900 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-306-3BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-09 00:31 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 103407 | 2023-11-09 | 10120 | 2024-01-23 14:22 | -9295 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-502-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-102-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-602-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-604-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-703-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-301-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-403-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:51 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-603-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-702-2BHK(Near Refuse Area) Bore Packing Work,Perma Eazee C | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-302-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-101-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-502-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-701-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-201-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-602-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-404-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:51 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-202-2BHK(Near Refuse Area) Bore Packing Work,Perma Eazee C | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-206-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-501-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-701-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-601-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-401-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:51 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-001-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-501-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-002-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-305-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-402-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-503-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-402-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:51 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-105-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-504-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-601-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-704-2BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 17:59 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23100 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-306-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-005-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-205-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-106-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-401-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-702-2BHK(Near Refuse Area) Bore Packing Work,Perma Eazee C | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-006-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2024-01-07 18:05 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 105177 | 2024-02-10 | 24200 | 2024-02-10 11:26 | -23925 | PRABHURAM VERMA
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-806-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-06-02 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107934 | 2024-06-03 | 4400 | 2024-06-24 12:15 | -4125 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-708-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 148.5 | 2024-06-02 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107934 | 2024-06-03 | 4400 | 2024-06-24 12:15 | -3575 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-805-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-06-02 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107934 | 2024-06-03 | 4400 | 2024-06-24 12:15 | -4125 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-707-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 148.5 | 2024-06-02 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107934 | 2024-06-03 | 4400 | 2024-06-24 12:15 | -3575 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-808-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 148.5 | 2024-06-02 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107934 | 2024-06-03 | 4400 | 2024-06-24 12:15 | -3575 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-706-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-06-02 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107934 | 2024-06-03 | 4400 | 2024-06-24 12:15 | -4125 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-705-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-06-02 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107934 | 2024-06-03 | 4400 | 2024-06-24 12:15 | -4125 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-807-2BHK Bore Packing Work,Perma Eazee Coat | 3 | 275 | 0 | 825 | 148.5 | 2024-06-02 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107934 | 2024-06-03 | 4400 | 2024-06-24 12:15 | -3575 | PRASHANT KASHINATH NETAKE
2"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-905-3BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-05-19 | Labour charges for 2 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -6325 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-905-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-05-19 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -5500 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-907-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-05-19 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -6325 | PRASHANT KASHINATH NETAKE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-908-2BHK Bore Packing Work,Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2024-05-19 | Labour charges for 6 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -6325 | PRASHANT KASHINATH NETAKE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | GANGAPRASAD K VARMA | 680 | 2023-05-13 | E-906-3BHK Bore Packing Work,Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2024-05-19 | Labour charges for 5 inch Bore Packing with Perma Eazee coat for E-Bldg Internal Flats | 100 |  | 107668 | 2024-05-20 | 6600 | 2024-06-10 11:25 | -5500 | PRASHANT KASHINATH NETAKE
Water Testing report - SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 12 | 1000 | 0 | 3000 | 540 | 2024-06-11 | Drinking water for Month of MAY-2024 (6 x 1000) | 25 |  | 108302 | 2024-06-11 | 16000 | 2024-06-27 18:36 | -13000 | EHS Matrix Private Limited
Stack Monitoring Report SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 12 | 900 | 0 | 2700 | 486 | 2024-06-11 | DG Stack Monitoring Report for Month of MAY-2024 (5 x 900) | 25 |  | 108302 | 2024-06-11 | 16000 | 2024-06-27 18:36 | -13300 | EHS Matrix Private Limited
NOise Test Day SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 32 | 100 | 0 | 800 | 144 | 2024-06-11 | Noise Test Day for Month of MAY-2024 (10 x 125) | 25 |  | 108302 | 2024-06-11 | 16000 | 2024-06-27 18:36 | -15200 | EHS Matrix Private Limited
Noise Test Night SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 32 | 100 | 0 | 800 | 144 | 2024-06-11 | Noise Test Night for Month of MAY-2024 (10 x 125) | 25 |  | 108302 | 2024-06-11 | 16000 | 2024-06-27 18:36 | -15200 | EHS Matrix Private Limited
Air Test SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 12 | 1500 | 0 | 4500 | 810 | 2024-06-11 | Ambient Air Test for Month of MAY-2024 (5 x 1500) | 25 |  | 108302 | 2024-06-11 | 16000 | 2024-06-27 18:36 | -11500 | EHS Matrix Private Limited
Effluent Sample | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 4 | 1200 | 0 | 1200 | 216 | 2024-06-11 | Treated Effluent Sample for STP for Month of MAY-2024 (2 x 1000) | 25 |  | 108302 | 2024-06-11 | 16000 | 2024-06-27 18:36 | -14800 | EHS Matrix Private Limited
Soil Analysis Test- SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 8 | 1500 | 0 | 3000 | 540 | 2024-06-11 | Soil Analysis Test for Month of MAY-2024 (4 x 1500) | 25 |  | 108302 | 2024-06-11 | 16000 | 2024-06-27 18:36 | -13000 | EHS Matrix Private Limited
Water Testing report - SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 8 | 1000 | 0 | 2000 | 360 | 2023-06-20 | Drinking water for Month of MAY-2023 (6 x 1000) | 25 |  | 100220 | 2023-06-20 | 17100 | 2023-06-22 13:52 | -15100 | EHS Matrix Private Limited
Air Test SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 16 | 1500 | 0 | 6000 | 1080 | 2023-06-20 | Ambient Air Test for Month of MAY-2023 (5 x 1500) | 25 |  | 100220 | 2023-06-20 | 17100 | 2023-06-22 13:52 | -11100 | EHS Matrix Private Limited
NOise Test Day SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 32 | 100 | 0 | 800 | 144 | 2023-06-20 | Noise Test Day for Month of MAY-2023 (10 x 125) | 25 |  | 100220 | 2023-06-20 | 17100 | 2023-06-22 13:52 | -16300 | EHS Matrix Private Limited
Noise Test Night SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 32 | 100 | 0 | 800 | 144 | 2023-06-20 | Noise Test Night for Month of MAY-2023 (10 x 125) | 25 |  | 100220 | 2023-06-20 | 17100 | 2023-06-22 13:52 | -16300 | EHS Matrix Private Limited
Stack Monitoring Report SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 8 | 900 | 0 | 1800 | 324 | 2023-06-20 | DG Stack Monitoring Report for Month of MAY-2023 (5 x 900) | 25 |  | 100220 | 2023-06-20 | 17100 | 2023-06-22 13:52 | -15300 | EHS Matrix Private Limited
Soil Analysis Test- SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 12 | 1500 | 0 | 4500 | 810 | 2023-06-20 | Soil Analysis Test for Month of MAY-2023 (4 x 1500) | 25 |  | 100220 | 2023-06-20 | 17100 | 2023-06-22 13:52 | -12600 | EHS Matrix Private Limited
Sewage Water Analysis | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 4 | 1200 | 0 | 1200 | 216 | 2023-06-20 | Untreated Effluent Sample for STP for Month of MAY-2023 (2 x 1000) | 25 |  | 100220 | 2023-06-20 | 17100 | 2023-06-22 13:52 | -15900 | EHS Matrix Private Limited
Air Test SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 16 | 1500 | 0 | 6000 | 1080 | 2023-12-01 | Ambient Air Test for Month of NOV-2023 (5 x 1500) | 25 |  | 103550 | 2023-12-01 | 16000 | 2023-12-16 17:31 | -10000 | EHS Matrix Private Limited
NOise Test Day SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 32 | 100 | 0 | 800 | 144 | 2023-12-01 | Noise Test Day for Month of NOV-2023 (10 x 125) | 25 |  | 103550 | 2023-12-01 | 16000 | 2023-12-16 17:31 | -15200 | EHS Matrix Private Limited
Stack Monitoring Report SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 12 | 900 | 0 | 2700 | 486 | 2023-12-01 | DG Stack Monitoring Report for Month of NOV-2023 (5 x 900) | 25 |  | 103550 | 2023-12-01 | 16000 | 2023-12-16 17:31 | -13300 | EHS Matrix Private Limited
Soil Analysis Test- SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 4 | 1500 | 0 | 1500 | 270 | 2023-12-01 | Soil Analysis Test for Month of NOV-2023 (4 x 1500) | 25 |  | 103550 | 2023-12-01 | 16000 | 2023-12-16 17:31 | -14500 | EHS Matrix Private Limited
Water Testing report - SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 12 | 1000 | 0 | 3000 | 540 | 2023-12-01 | Drinking water for Month of NOV-2023 (6 x 1000) | 25 |  | 103550 | 2023-12-01 | 16000 | 2023-12-16 17:31 | -13000 | EHS Matrix Private Limited
Sewage Water Analysis | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 4 | 1200 | 0 | 1200 | 216 | 2023-12-01 | Untreated Effluent Sample for STP for Month of NOV-2023 (2 x 1000) | 25 |  | 103550 | 2023-12-01 | 16000 | 2023-12-16 17:31 | -14800 | EHS Matrix Private Limited
Noise Test Night SOS | N/C | N/C | EHS Matrix Private Limited | 681 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water | 32 | 100 | 0 | 800 | 144 | 2023-12-01 | Noise Test Night for Month of NOV-2023 (10 x 125) | 25 |  | 103550 | 2023-12-01 | 16000 | 2023-12-16 17:31 | -15200 | EHS Matrix Private Limited
IPS W/P | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | Transformer Room- Floor IPS Waterproofing | 350.2 | 15 | 0 | 5253 | 945.54 | 2024-03-02 19:15 | Labour charges for IPS Waterproofing Work for Transformer Room. | 100 |  | 105729 | 2024-03-04 | 5253 | 2024-03-23 12:18 | 0 | JAI SEVALAL CONSTRUCTION
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | Transformer Room- Terrace Brickbat W/P Work | 522.3431 | 24 | 0 | 12536.2344 | 0 | 2024-05-05 12:15 | Labour charges for Terrace Brickbat Waterproofing work for Transformer Room. | 100 |  | 107393 | 2024-05-07 | 12536.23 | 2024-06-06 12:22 | 0.0044 | PRABHURAM VERMA
Int. Ghotai Plaster- UWR | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | Transformer Room- Trench Int. Face Ghotai Work | 499.76 | 15 | 0 | 7496.4 | 1349.36 | 2023-12-28 18:35 | Labour charges for Internal Ghotai Plaster work for Int. face- vertical, Both wall- Top & Horizontal for Transformer Room. | 100 |  | 104233 | 2024-01-01 | 7496.4 | 2024-02-05 11:29 | 0 | JAI SEVALAL CONSTRUCTION
IPS W/P | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | D-Lift No.-1,2,3-IPS Waterproofing in pits | 100.21 | 15 | 0 | 1503.15 | 0 | 2024-07-24 | Labour Charges for IPS Waterproofing work for D-Bldg Lift Pit No- 1, 2, 3. | 100 |  | 109386 | 2024-07-29 | 16705.53 | 1900-01-01 | -15202.38 | AJAY KUMAR GUPTA
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | D-Bldg 2nd Floor Refuge Area Waterproofing Work | 211.144 | 24 | 0 | 5067.456 | 0 | 2024-07-23 | Labour Charges for Refuge Area Brickbat Waterproofing work. | 100 |  | 109386 | 2024-07-29 | 16705.53 | 1900-01-01 | -11638.074 | AJAY KUMAR GUPTA
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | D-Bldg 7th Floor Refuge Area Waterproofing Work | 211.144 | 24 | 0 | 5067.456 | 0 | 2024-07-23 | Labour Charges for Refuge Area Brickbat Waterproofing work. | 100 |  | 109386 | 2024-07-29 | 16705.53 | 1900-01-01 | -11638.074 | AJAY KUMAR GUPTA
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | D-Bldg 12th Floor Refuge Area Waterproofing Work | 211.144 | 24 | 0 | 5067.456 | 0 | 2024-07-23 | Labour Charges for Refuge Area Brickbat Waterproofing work. | 100 |  | 109386 | 2024-07-29 | 16705.53 | 1900-01-01 | -11638.074 | AJAY KUMAR GUPTA
Int Plumbing CP & Sanitary Fittings. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 685 | 2023-05-30 | 1st Fl- Int. Plumbing Work (L) | 12 | 1440 | 0 | 17280 | 3110.4 | 2024-07-15 | Labour Charges for internal plumbing CP & Sanitary fittings work of F Building | 100 |  | 109117 | 2024-07-15 | 18720 | 1900-01-01 | -1440 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing CP & Sanitary Fittings. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 685 | 2023-05-30 | LG Fl- Int. Plumbing Work (L) | 1 | 1440 | 0 | 1440 | 259.2 | 2024-07-15 | Labour Charges for internal plumbing CP & Sanitary fittings work of F Building | 100 |  | 109117 | 2024-07-15 | 18720 | 1900-01-01 | -17280 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 685 | 2023-05-30 | LG Fl- Int. Plumbing Work (L) | 0.8 | 2160 | 0 | 1728 | 311.04 | 2023-07-10 | Labour Charges for internal plumbing PPRC work of F Building | 100 |  | 100614 | 2023-07-11 | 21168 | 2023-09-20 11:58 | -19440 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 685 | 2023-05-30 | 1st Fl- Int. Plumbing Work (L) | 9 | 2160 | 0 | 19440 | 3499.2 | 2023-07-10 | Labour Charges for internal plumbing PPRC work of F Building | 100 |  | 100614 | 2023-07-11 | 21168 | 2023-09-20 11:58 | -1728 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 685 | 2023-05-30 | 1st Fl- Int. Plumbing Work (L) | 3 | 2160 | 0 | 6480 | 1166.4 | 2024-06-06 | Labour Charges for internal plumbing PPRC work of F Building | 100 |  | 108190 | 2024-06-10 | 6912 | 2024-07-05 11:40 | -432 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Int Plumbing PPRC Work. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 685 | 2023-05-30 | LG Fl- Int. Plumbing Work (L) | 0.2 | 2160 | 0 | 432 | 77.76 | 2024-06-06 | Labour Charges for internal plumbing PPRC work of F Building | 100 |  | 108190 | 2024-06-10 | 6912 | 2024-07-05 11:40 | -6480 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rising Main Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | LG Fl- External Plumbing Work (L) | 1 | 480 | 0 | 480 | 86.4 | 2024-06-06 | Labour Charges for F Building External plumbing Rising main line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -28176 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 1st Fl- External Plumbing Work (L) | 2.4 | 480 | 0 | 1152 | 207.36 | 2024-06-06 | Labour Charges for F Building External plumbing Rainwater line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -27504 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rising Main Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 2nd Fl- External Plumbing Work (L) | 10 | 480 | 0 | 4800 | 864 | 2024-06-06 | Labour Charges for F Building External plumbing Rising main line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -23856 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | Stilt Fl- External Plumbing Work (L) | 0.6 | 480 | 0 | 288 | 51.84 | 2024-06-06 | Labour Charges for F Building External plumbing Rainwater line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -28368 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | LG Fl- External Plumbing Work (L) | 0.2 | 480 | 0 | 96 | 17.28 | 2024-06-06 | Labour Charges for F Building External plumbing Rainwater line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -28560 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Gully Trap & Chamber. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 2nd Fl- External Plumbing Work (L) | 8.4 | 240 | 0 | 2016 | 362.88 | 2024-06-06 | Labour Charges for F Building External plumbing Gully trap and Chamber work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -26640 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Duct Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 2nd Fl- External Plumbing Work (L) | 2 | 480 | 0 | 960 | 172.8 | 2024-06-06 | Labour Charges for F Building External plumbing Duct line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -27696 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Gully Trap & Chamber. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | Stilt Fl- External Plumbing Work (L) | 3 | 240 | 0 | 720 | 129.6 | 2024-06-06 | Labour Charges for F Building External plumbing Gully trap and Chamber work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -27936 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 2nd Fl- External Plumbing Work (L) | 2 | 480 | 0 | 960 | 172.8 | 2024-06-06 | Labour Charges for F Building External plumbing Rainwater line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -27696 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Duct Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 3rd Fl- External Plumbing Work (L) | 1.8 | 480 | 0 | 864 | 155.52 | 2024-06-06 | Labour Charges for F Building External plumbing Duct line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -27792 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rising Main Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | Stilt Fl- External Plumbing Work (L) | 3 | 480 | 0 | 1440 | 259.2 | 2024-06-06 | Labour Charges for F Building External plumbing Rising main line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -27216 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Gully Trap & Chamber. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | LG Fl- External Plumbing Work (L) | 0.2 | 240 | 0 | 48 | 8.64 | 2024-06-06 | Labour Charges for F Building External plumbing Gully trap and Chamber work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -28608 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Duct Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | Stilt Fl- External Plumbing Work (L) | 0.6 | 480 | 0 | 288 | 51.84 | 2024-06-06 | Labour Charges for F Building External plumbing Duct line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -28368 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Gully Trap & Chamber. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 3rd Fl- External Plumbing Work (L) | 7.4 | 240 | 0 | 1776 | 319.68 | 2024-06-06 | Labour Charges for F Building External plumbing Gully trap and Chamber work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -26880 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Duct Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | LG Fl- External Plumbing Work (L) | 0.2 | 480 | 0 | 96 | 17.28 | 2024-06-06 | Labour Charges for F Building External plumbing Duct line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -28560 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 3rd Fl- External Plumbing Work (L) | 1.8 | 480 | 0 | 864 | 155.52 | 2024-06-06 | Labour Charges for F Building External plumbing Rainwater line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -27792 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Gully Trap & Chamber. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 1st Fl- External Plumbing Work (L) | 2.4 | 240 | 0 | 576 | 103.68 | 2024-06-06 | Labour Charges for F Building External plumbing Gully trap and Chamber work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -28080 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Duct Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 1st Fl- External Plumbing Work (L) | 2.4 | 480 | 0 | 1152 | 207.36 | 2024-06-06 | Labour Charges for F Building External plumbing Duct line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -27504 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rising Main Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 1st Fl- External Plumbing Work (L) | 12 | 480 | 0 | 5760 | 1036.8 | 2024-06-06 | Labour Charges for F Building External plumbing Rising main line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -22896 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rising Main Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 3rd Fl- External Plumbing Work (L) | 9 | 480 | 0 | 4320 | 777.6 | 2024-06-06 | Labour Charges for F Building External plumbing Rising main line work. | 100 |  | 108191 | 2024-06-10 | 28656 | 2024-07-05 11:41 | -24336 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Gully Trap & Chamber. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 1st Fl- External Plumbing Work (L) | 9.6 | 240 | 0 | 2304 | 414.72 | 2023-12-09 17:11 | Labour Charges for F Building External plumbing Gully trap and Chamber work. | 100 |  | 103819 | 2023-12-11 | 9792 | 2023-12-25 15:38 | -7488 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
OHWT Distribution. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 2nd Fl- External Plumbing Work (L) | 1.6 | 480 | 0 | 768 | 138.24 | 2023-12-09 17:11 | Labour Charges for F Building External plumbing OHWT Distribution work. | 100 |  | 103819 | 2023-12-11 | 9792 | 2023-12-25 15:38 | -9024 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Gully Trap & Chamber. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 3rd Fl- External Plumbing Work (L) | 1.6 | 240 | 0 | 384 | 69.12 | 2023-12-09 17:11 | Labour Charges for F Building External plumbing Gully trap and Chamber work. | 100 |  | 103819 | 2023-12-11 | 9792 | 2023-12-25 15:38 | -9408 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Gully Trap & Chamber. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 2nd Fl- External Plumbing Work (L) | 1.6 | 240 | 0 | 384 | 69.12 | 2023-12-09 17:11 | Labour Charges for F Building External plumbing Gully trap and Chamber work. | 100 |  | 103819 | 2023-12-11 | 9792 | 2023-12-25 15:38 | -9408 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
OHWT Distribution. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | LG Fl- External Plumbing Work (L) | 0.8 | 480 | 0 | 384 | 69.12 | 2023-12-09 17:11 | Labour Charges for F Building External plumbing OHWT Distribution work. | 100 |  | 103819 | 2023-12-11 | 9792 | 2023-12-25 15:38 | -9408 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
OHWT Distribution. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 3rd Fl- External Plumbing Work (L) | 1.6 | 480 | 0 | 768 | 138.24 | 2023-12-09 17:11 | Labour Charges for F Building External plumbing OHWT Distribution work. | 100 |  | 103819 | 2023-12-11 | 9792 | 2023-12-25 15:38 | -9024 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Gully Trap & Chamber. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | LG Fl- External Plumbing Work (L) | 0.8 | 240 | 0 | 192 | 34.56 | 2023-12-09 17:11 | Labour Charges for F Building External plumbing Gully trap and Chamber work. | 100 |  | 103819 | 2023-12-11 | 9792 | 2023-12-25 15:38 | -9600 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
OHWT Distribution. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 1st Fl- External Plumbing Work (L) | 9.6 | 480 | 0 | 4608 | 829.44 | 2023-12-09 17:11 | Labour Charges for F Building External plumbing OHWT Distribution work. | 100 |  | 103819 | 2023-12-11 | 9792 | 2023-12-25 15:38 | -5184 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Duct Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 2nd Fl- External Plumbing Work (L) | 8 | 480 | 0 | 3840 | 691.2 | 2023-10-12 12:25 | Labour Charges for F Building External plumbing Duct line work. | 100 |  | 102590 | 2023-10-13 | 26880 | 2023-10-28 11:58 | -23040 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 2nd Fl- External Plumbing Work (L) | 8 | 480 | 0 | 3840 | 691.2 | 2023-10-12 12:30 | Labour Charges for F Building External plumbing Rainwater line work. | 100 |  | 102590 | 2023-10-13 | 26880 | 2023-10-28 11:58 | -23040 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Duct Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 3rd Fl- External Plumbing Work (L) | 7.2 | 480 | 0 | 3456 | 622.08 | 2023-10-12 12:25 | Labour Charges for F Building External plumbing Duct line work. | 100 |  | 102590 | 2023-10-13 | 26880 | 2023-10-28 11:58 | -23424 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | Stilt Fl- External Plumbing Work (L) | 2.4 | 480 | 0 | 1152 | 207.36 | 2023-10-12 12:30 | Labour Charges for F Building External plumbing Rainwater line work. | 100 |  | 102590 | 2023-10-13 | 26880 | 2023-10-28 11:58 | -25728 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Duct Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | Stilt Fl- External Plumbing Work (L) | 2.4 | 480 | 0 | 1152 | 207.36 | 2023-10-12 12:25 | Labour Charges for F Building External plumbing Duct line work. | 100 |  | 102590 | 2023-10-13 | 26880 | 2023-10-28 11:58 | -25728 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 1st Fl- External Plumbing Work (L) | 9.6 | 480 | 0 | 4608 | 829.44 | 2023-10-12 12:30 | Labour Charges for F Building External plumbing Rainwater line work. | 100 |  | 102590 | 2023-10-13 | 26880 | 2023-10-28 11:58 | -22272 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Duct Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | LG Fl- External Plumbing Work (L) | 0.8 | 480 | 0 | 384 | 69.12 | 2023-10-12 12:25 | Labour Charges for F Building External plumbing Duct line work. | 100 |  | 102590 | 2023-10-13 | 26880 | 2023-10-28 11:58 | -26496 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | LG Fl- External Plumbing Work (L) | 0.8 | 480 | 0 | 384 | 69.12 | 2023-10-12 12:30 | Labour Charges for F Building External plumbing Rainwater line work. | 100 |  | 102590 | 2023-10-13 | 26880 | 2023-10-28 11:58 | -26496 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Duct Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 1st Fl- External Plumbing Work (L) | 9.6 | 480 | 0 | 4608 | 829.44 | 2023-10-12 12:25 | Labour Charges for F Building External plumbing Duct line work. | 100 |  | 102590 | 2023-10-13 | 26880 | 2023-10-28 11:58 | -22272 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Rainwater Line. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 686 | 2023-05-31 | 3rd Fl- External Plumbing Work (L) | 7.2 | 480 | 0 | 3456 | 622.08 | 2023-10-12 12:30 | Labour Charges for F Building External plumbing Rainwater line work. | 100 |  | 102590 | 2023-10-13 | 26880 | 2023-10-28 11:58 | -23424 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
2 core x 1.5 sqmm cable for PA System (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Building Fire Alarm System Work | 86 | 40 | 0 | 2408 | 433.44 | 2023-12-04 | After Installation & Pressure Testing | 70 | Installed on 24/11/2023 | 103626 | 2023-12-04 | 2408 | 2024-01-02 11:45 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 40 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 9.1996 | 423 | 0 | 2724.0016 | 490.32 | 2024-02-12 | After Installation & Pressure Testing | 70 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -174455.9984 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 40 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 9.2009 | 423 | 0 | 972.9952 | 175.14 | 2024-02-12 | After Final Noc | 25 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -176207.0048 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 40mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 300 | 0 | 375 | 67.5 | 2024-02-12 | After Final Noc | 25 | For F Building | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -176805 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 40mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 300 | 0 | 1050 | 189 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -176130 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 25 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 294.8987 | 282 | 0 | 58213.0034 | 10478.34 | 2024-02-12 | After Installation & Pressure Testing | 70 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -118966.9966 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 25 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 294.8936 | 282 | 0 | 20789.9988 | 3742.2 | 2024-02-12 | After Final Noc | 25 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -156390.0012 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 32 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 55.4002 | 352.5 | 0 | 13669.9994 | 2460.6 | 2024-02-12 | After Installation & Pressure Testing | 70 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -163510.0007 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 32 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 55.3986 | 352.5 | 0 | 4882.0016 | 878.76 | 2024-02-12 | After Final Noc | 25 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -172297.9984 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 100 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 84.4008 | 775.5 | 0.03 | 45816.9743 | 8247.06 | 2024-02-12 | After Installation & Pressure Testing | 70 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -131363.0257 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 100 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 84.3997 | 775.5 | 0.01 | 16362.9918 | 2945.34 | 2024-02-12 | After Final Noc | 25 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -160817.0082 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 50 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 22.999 | 564 | -0.01 | 9080.0052 | 1634.4 | 2024-02-12 | After Installation & Pressure Testing | 70 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -168099.9948 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 50 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 23 | 564 | 0 | 3243 | 583.74 | 2024-02-12 | After Final Noc | 25 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -173937 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Starter (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 1410 | 0 | 352.5 | 63.46 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -84457 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signage Fire Hose Reel (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 3.9991 | 329 | 0.01 | 920.9927 | 165.78 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -83888.5073 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signage Fire Hose Reel (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 4 | 329 | 0 | 329 | 59.22 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -84480.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Starter (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 1410 | 0 | 987 | 177.66 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -83822.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Cable 2.5 sqmm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 39.9865 | 42.3 | 0 | 1184.0003 | 213.12 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -83625.4997 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Cable 2.5 sqmm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 42.3 | 0 | 423 | 76.14 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -84386.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.0159 | 45 | 0 | 6773.0009 | 1219.14 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -78036.4992 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.0222 | 45 | 0 | 2418.9997 | 435.42 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -82390.5002 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
7.5 HP Booster Pump- (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3290 | 0 | 2303 | 414.54 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -82506.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
7.5 HP Booster Pump- (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3290 | 0 | 822.5 | 148.06 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -83987 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 130 | 200 | 0 | 18200 | 3276 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -66609.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 130 | 200 | 0 | 6500 | 1170 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -78309.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215 | 188 | 0 | 28294 | 5092.92 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -56515.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
GI Single Fire Hose Box (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 1034 | 0 | 1292.5 | 232.66 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -83517 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215 | 188 | 0 | 10105 | 1818.9 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -74704.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
GI Single Fire Hose Box (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 1034 | 0 | 3619 | 651.42 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -81190.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 300 | 0 | 75 | 13.5 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -84734.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 300 | 0 | 210 | 37.8 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -84599.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm cable for PA System (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Building Fire Alarm System Work | 291.5 | 40 | 0 | 8162 | 1469.16 | 2023-08-21 | After Installation & Pressure Testing | 70 |  | 101362 | 2023-08-21 | 8162 | 2023-09-20 11:59 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm cable for PA System (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Building Fire Alarm System Work | 566 | 40 | 0 | 15848 | 2852.64 | 2023-09-23 | After Installation & Pressure Testing | 70 |  | 102046 | 2023-09-23 | 15848 | 2023-10-11 11:03 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm cable for PA System (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 311 | 80 | 0 | 17416 | 3134.88 | 2023-08-21 | Against Material Supply | 70 |  | 101363 | 2023-08-21 | 17416 | 2023-09-20 11:59 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm cable for PA System (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1000 | 80 | 0 | 56000 | 10080 | 2023-09-16 | Against Material Supply | 70 | Challan No- 16617 | 101922 | 2023-09-18 | 56000 | 2023-10-11 11:03 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5.0008 | 2650 | -0.03 | 3313.03 | 596.34 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105280 | 2024-02-12 | 13251 | 2024-03-18 12:02 | -9937.97 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5.0038 | 2650 | 0 | 663.0035 | 119.34 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105280 | 2024-02-12 | 13251 | 2024-03-18 12:02 | -12587.9965 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 2650 | 0 | 9275 | 1669.5 | 2024-02-12 | Against Material Supply | 70 | For F Building | 105280 | 2024-02-12 | 13251 | 2024-03-18 12:02 | -3976 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signage Fire Hose Reel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 3.9987 | 6392 | 0.02 | 1277.9845 | 230.04 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -465513.0155 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Fire Alarm Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 215000 | 0 | 150500 | 27090 | 2023-12-04 | Against Material Supply | 70 | Challan No-17080 DT 23/11/2023 | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -180705 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Control Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 3300 | 0 | 2310 | 415.8 | 2023-12-04 | Against Material Supply | 70 |  | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -328895 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fault Isolator Base / Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 2500 | 0 | 1750 | 315 | 2023-12-04 | Against Material Supply | 70 |  | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -329455 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Manual call point (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 2850 | 0 | 1995 | 359.1 | 2023-12-04 | Against Material Supply | 70 |  | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -329210 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Conventional Sounder cum Strobe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 5 | 1900 | 0 | 6650 | 1197 | 2023-12-04 | Against Material Supply | 70 | Challan No-17080 DT 23/11/2023 | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -324555 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable smoke detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 100 | 2400 | 0 | 168000 | 30240 | 2023-12-04 | Against Material Supply | 70 | Challan No-17080 | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -163205 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 6 | 3600 | 0 | 15120 | 2721.6 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 4/07/2024 Against D Building Pump Room | 109135 | 2024-07-16 | 17360 | 1900-01-01 | -2240 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3200 | 0 | 2240 | 403.2 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 Against D Building | 109135 | 2024-07-16 | 17360 | 1900-01-01 | -15120 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 380 | 0 | 10640 | 1915.2 | 2024-04-08 | Against Material Supply | 70 |  | 106673 | 2024-04-08 | 42112 | 2024-04-10 17:55 | -31472 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 90 | 0 | 2520 | 453.6 | 2024-04-08 | Against Material Supply | 70 |  | 106673 | 2024-04-08 | 42112 | 2024-04-10 17:55 | -39592 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 1034 | 0 | 28952 | 5211.36 | 2024-04-08 | Against Material Supply | 70 |  | 106673 | 2024-04-08 | 42112 | 2024-04-10 17:55 | -13160 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
GI Single Fire Hose Box (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 17930 | 0 | 62755 | 11295.9 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -404036 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
GI Single Fire Hose Box (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 17930 | 0 | 22412.5 | 4034.26 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -444378.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
GI Single Fire Hose Box (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 17930 | 0 | 4482.5 | 806.86 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -462308.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215 | 90 | 0 | 13545 | 2438.1 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -453246 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.0222 | 90 | 0 | 4837.9995 | 870.84 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -461953.0005 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
7.5 HP Booster Pump- (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 45590 | 0 | 31913 | 5744.34 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -434878 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
7.5 HP Booster Pump- (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 45590 | 0 | 11397.5 | 2051.56 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -455393.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
7.5 HP Booster Pump- (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 45590 | 0 | 2279.5 | 410.32 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -464511.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215 | 1034 | 0 | 155617 | 28011.06 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -311174 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.0019 | 1034 | 0.01 | 55577.9912 | 10004.04 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -411213.0088 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.0097 | 1034 | 0 | 11116.0015 | 2000.88 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -455674.9985 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Starter (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 6241 | 0 | 4368.7 | 786.36 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -462422.3 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Starter (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 6241 | 0 | 1560.25 | 280.84 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -465230.75 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Starter (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 6241 | 0 | 312.05 | 56.16 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -466478.95 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signage Fire Hose Reel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 4.0001 | 6392 | -0.05 | 17898.0474 | 3221.64 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -448892.9526 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 130 | 380 | 0 | 34580 | 6224.4 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -432211 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 130 | 380 | 0 | 12350 | 2223 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -454441 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 130 | 380 | 0 | 2470 | 444.6 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -464321 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Cable 2.5 sqmm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 122 | 0 | 244 | 43.92 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -466547 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3800 | 0 | 2660 | 478.8 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -464131 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3800 | 0 | 950 | 171 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -465841 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3800 | 0 | 190 | 34.2 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -466601 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.1111 | 90 | 0 | 968 | 174.24 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -465823 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Cable 2.5 sqmm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 122 | 0 | 3416 | 614.88 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -463375 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Cable 2.5 sqmm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 122 | 0 | 1220 | 219.6 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -465571 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signage Fire Hose Reel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 4 | 6392 | 0 | 6392 | 1150.56 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -460399 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Upright (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 30 | 450 | 0 | 9450 | 1701 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/07/2024 Total Received-400 -We have released 338 Nos from D Building Remaining Qty released from F Building (Balance for amendment 32 Nos) | 109419 | 2024-07-29 | 40950 | 1900-01-01 | -31500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Repeater Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 45000 | 0 | 31500 | 5670 | 2024-07-29 | Against Material Supply | 70 | Challan No-18179 DT 27/7/2024 | 109419 | 2024-07-29 | 40950 | 1900-01-01 | -9450 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Heat Detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 2350 | 0 | 1645 | 296.1 | 2024-06-02 | Against Material Supply | 70 | CH NO-18053 DT 16/04/2024 | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -30520 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable smoke detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 5 | 2400 | 0 | 8400 | 1512 | 2024-06-02 | Against Material Supply | 70 | CH NO-18053 DT 16/04/2024 | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -23765 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
6W Ceiling Speakers (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 15 | 1250 | 0 | 13125 | 2362.5 | 2024-06-02 | Against Material Supply | 70 | CH NO-18053 DT 16/04/2024 and CH NO-17969 DT 30/03/2024 | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -19040 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Talk Back System (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 4 | 800 | 0 | 2240 | 403.2 | 2024-06-02 | Against Material Supply | 70 | CH NO-18053 DT 16/04/2024 | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -29925 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fault Isolator Base / Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 3 | 2500 | 0 | 5250 | 945 | 2024-06-02 | Against Material Supply | 70 |  | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -26915 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Handheld Microphone (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 2150 | 0 | 1505 | 270.9 | 2024-06-02 | Against Material Supply | 70 | CH NO-18290 DT 24/05/2024 | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -30660 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI Pipe C Class 80mm dia.(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 35 | 1000 | 0 | 24500 | 4410 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-10/06/2024 | 108186 | 2024-06-10 | 39529 | 2024-06-26 11:43 | -15029 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher ABC 4Kg (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 6 | 1645 | 0 | 6909 | 1243.62 | 2024-06-10 | Against Material Supply | 70 | DC-18325 DT-31/05/2024 | 108186 | 2024-06-10 | 39529 | 2024-06-26 11:43 | -32620 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher 4.5Kg CO2 (IS15683:2006(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 2 | 5800 | 0 | 8120 | 1461.6 | 2024-06-10 | Against Material Supply | 70 | DC-18325 DT-31/05/2024 | 108186 | 2024-06-10 | 39529 | 2024-06-26 11:43 | -31409 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 90 | 0 | 2520 | 453.6 | 2024-07-01 | Against Material Supply | 70 | Challan No-18491 DT-25/06/2024 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -70042 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 1034 | 0 | 28952 | 5211.36 | 2024-07-01 | Against Material Supply | 70 | challan No-18491 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -43610 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler Alarm Valve 150mm dia (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 43500 | 0 | 30450 | 5481 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT-27/06/2024 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -42112 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 380 | 0 | 10640 | 1915.2 | 2024-07-01 | Against Material Supply | 70 | Challan No-18491DT-25/06/2024 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -61922 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Telephone Jack/Receiver (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 5500 | 0 | 3850 | 693 | 2024-05-13 | Against Material Supply | 70 | CHALLAN NO-18140 | 107563 | 2024-05-13 | 86559.9 | 2024-05-28 19:02 | -82709.9 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Talkback Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 66504 | 0 | 46552.8 | 8379.5 | 2024-05-13 | Against Material Supply | 70 | CHALLAN NO-18140 | 107563 | 2024-05-13 | 86559.9 | 2024-05-28 19:02 | -40007.1 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Digital Signal Based Voice Alarm Controller (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 51653 | 0 | 36157.1 | 6508.28 | 2024-05-13 | Against Material Supply | 70 | CHALLAN NO-18140 | 107563 | 2024-05-13 | 86559.9 | 2024-05-28 19:02 | -50402.8 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Bed Elevator | N/C | N/C | OTIS ELEVATOR COMPANY (INDIA) LIMITED | 689 | 2023-06-02 | F Building Lift Work (L) | 1 | 2275000 | 0 | 227500 | 40950 | 2024-05-25 | After handover | 10 |  | 107766 | 2024-05-25 | 227500 | 2024-06-04 15:24 | 0 | OTIS ELEVATOR COMPANY (INDIA) LIMITED
Bed Elevator | N/C | N/C | OTIS ELEVATOR COMPANY (INDIA) LIMITED | 689 | 2023-06-02 | F Building Lift Work (L) | 1 | 2275000 | 0 | 1023750 | 184275 | 2024-02-07 | Before manufacturing | 45 |  | 105146 | 2024-02-08 | 1023750 | 2024-02-08 18:14 | 0 | OTIS ELEVATOR COMPANY (INDIA) LIMITED
Bed Elevator | N/C | N/C | OTIS ELEVATOR COMPANY (INDIA) LIMITED | 689 | 2023-06-02 | F Building Lift Work (L) | 1 | 2275000 | 0 | 113750 | 20475 | 2024-02-07 | Advance along with work order | 5 |  | 105147 | 2024-02-08 | 113750 | 2024-02-08 18:14 | 0 | OTIS ELEVATOR COMPANY (INDIA) LIMITED
Bed Elevator | N/C | N/C | OTIS ELEVATOR COMPANY (INDIA) LIMITED | 689 | 2023-06-02 | F Building Lift Work (L) | 1 | 2275000 | 0 | 910000 | 163800 | 2023-12-21 | After material receipt at site | 40 |  | 104121 | 2023-12-25 | 910000 | 2024-03-11 11:05 | 0 | OTIS ELEVATOR COMPANY (INDIA) LIMITED
Horizontal 6" Core cutting | N/C | N/C | AJAY KUMAR GUPTA | 690 | 2023-06-05 | F-Bldg Core Cutting For Fire Fighting Work | 3 | 265 | 0 | 795 | 0 | 2023-08-03 16:38 | Labour charges for 6 inch Horizontal Core Cutting work for F-Bldg 1st, 2nd & 3rd Floor for Fire Fighting and Internal Plumbing work. | 100 |  | 101001 | 2023-08-04 | 20935 | 2023-09-04 11:40 | -20140 | AJAY KUMAR GUPTA
Horizontal 3" Core cutting | N/C | N/C | AJAY KUMAR GUPTA | 690 | 2023-06-05 | D-Bldg Core Cutting For Fire Fighting Work | 76 | 265 | 0 | 20140 | 0 | 2023-08-03 16:38 | Labour charges for 3 inch Horizontal core cutting work for D-Bldg internal flat, & refuse area for fire fighting and internal plumbing work. | 100 |  | 101001 | 2023-08-04 | 20935 | 2023-09-04 11:40 | -795 | AJAY KUMAR GUPTA
Drain Piping 32mm (M+L) | N/C | N/C | WEATHERSPELL AIRCON ENGINEERS PVT LTD | 691 | 2023-06-05 | F-Bldg 1st Floor AC Work | 68 | 225 | 0 | 10710 | 1927.8 | 2023-09-25 | After Receipt of Material at site within 15 days | 70 | Invoice No- 76 Remaining Quantity - 4 Mtrs ,Rate-225 Rs. So, 4 X 225 = 900 Rs. Released from other item due to less Work Order Quantity | 102067 | 2023-09-25 | 257250 | 2023-11-22 18:27 | -246540 | WEATHERSPELL AIRCON ENGINEERS PVT LTD
Drain Piping 32mm (M+L) | N/C | N/C | WEATHERSPELL AIRCON ENGINEERS PVT LTD | 691 | 2023-06-05 | F-Bldg 1st Floor AC Work | 68 | 225 | 0 | 4590 | 826.2 | 2023-09-25 | After material installation & Final NOC | 30 | Invoice No- 76 Remaining Quantity - 4 Mtrs ,Rate-225 Rs. So, 4 X 225 = 900 Rs. Released from other item due to less Work Order Quantity | 102067 | 2023-09-25 | 257250 | 2023-11-22 18:27 | -252660 | WEATHERSPELL AIRCON ENGINEERS PVT LTD
Drain Piping 25mm (M+L) | N/C | N/C | WEATHERSPELL AIRCON ENGINEERS PVT LTD | 691 | 2023-06-05 | F-Bldg 1st Floor AC Work | 30 | 150 | 0 | 3150 | 567 | 2023-09-25 | After Receipt of Material at site within 15 days | 70 | Invoice No- 76 | 102067 | 2023-09-25 | 257250 | 2023-11-22 18:27 | -254100 | WEATHERSPELL AIRCON ENGINEERS PVT LTD
Drain Piping 25mm (M+L) | N/C | N/C | WEATHERSPELL AIRCON ENGINEERS PVT LTD | 691 | 2023-06-05 | F-Bldg 1st Floor AC Work | 30 | 150 | 0 | 1350 | 243 | 2023-09-25 | After material installation & Final NOC | 30 | Invoice No- 76 | 102067 | 2023-09-25 | 257250 | 2023-11-22 18:27 | -255900 | WEATHERSPELL AIRCON ENGINEERS PVT LTD
4C 1.5 sq.mm Copper Armoured Cable (M+L) | N/C | N/C | WEATHERSPELL AIRCON ENGINEERS PVT LTD | 691 | 2023-06-05 | F-Bldg 1st Floor AC Work | 275 | 150 | 0 | 28875 | 5197.5 | 2023-09-25 | After Receipt of Material at site within 15 days | 70 | Invoice No- 76 | 102067 | 2023-09-25 | 257250 | 2023-11-22 18:27 | -228375 | WEATHERSPELL AIRCON ENGINEERS PVT LTD
4C 1.5 sq.mm Copper Armoured Cable (M+L) | N/C | N/C | WEATHERSPELL AIRCON ENGINEERS PVT LTD | 691 | 2023-06-05 | F-Bldg 1st Floor AC Work | 275 | 150 | 0 | 12375 | 2227.5 | 2023-09-25 | After material installation & Final NOC | 30 | Invoice No- 76 | 102067 | 2023-09-25 | 257250 | 2023-11-22 18:27 | -244875 | WEATHERSPELL AIRCON ENGINEERS PVT LTD
Drain Piping 25mm (M+L) | N/C | N/C | WEATHERSPELL AIRCON ENGINEERS PVT LTD | 691 | 2023-06-05 | F-Bldg 1st Floor AC Work | 8.5714 | 150 | 0 | 899.997 | 162 | 2023-09-25 | After Receipt of Material at site within 15 days | 70 | Invoice No- 76 Remaining Quantity - 4 Mtrs For PVC Drain Pipe 32mm,Rate-225 Rs. So, 4 X 225 = 900 Rs. Released from this labour due to less Work Order Quantity for 32mm drain pipe | 102067 | 2023-09-25 | 257250 | 2023-11-22 18:27 | -256350.003 | WEATHERSPELL AIRCON ENGINEERS PVT LTD
Refrigerant Piping (L+M) | N/C | N/C | WEATHERSPELL AIRCON ENGINEERS PVT LTD | 691 | 2023-06-05 | F-Bldg 1st Floor AC Work | 217 | 900 | 0 | 136710 | 24607.8 | 2023-09-25 | After Receipt of Material at site within 15 days | 70 | Invoice No- 76 | 102067 | 2023-09-25 | 257250 | 2023-11-22 18:27 | -120540 | WEATHERSPELL AIRCON ENGINEERS PVT LTD
Refrigerant Piping (L+M) | N/C | N/C | WEATHERSPELL AIRCON ENGINEERS PVT LTD | 691 | 2023-06-05 | F-Bldg 1st Floor AC Work | 217 | 900 | 0 | 58590 | 10546.2 | 2023-09-25 | After material installation & Final NOC | 30 | Invoice No- 76 | 102067 | 2023-09-25 | 257250 | 2023-11-22 18:27 | -198660 | WEATHERSPELL AIRCON ENGINEERS PVT LTD
GI Sheet Fixing (L) | N/C | N/C | PRESSMET ENTERPRISES | 692 | 2023-06-05 | D-Bldg Temporary GI Sheet Roofing in Open duct | 252 | 5 | 0 | 1260 | 0 | 2023-07-12 | Labour charges for fixing of GI Sheet including tapping screw for temporary roofing in open duct area for D-Bldg. | 100 |  | 100655 | 2023-07-12 | 1260 | 2023-07-19 12:16 | 0 | PARTH ENTERPRISES
MS Pipe (L) | N/C | N/C | PRESSMET ENTERPRISES | 692 | 2023-06-05 | D-Bldg Temporary GI Sheet Roofing in Open duct | 287.23 | 15 | 0 | 4308.45 | 0 | 2024-03-11 | Labour charges for fixing of MS Squate pipe 40mm x 40mm for temporary roofing in open duct area for D-Bldg. | 100 |  | 106959 | 2024-04-19 | 5238.45 | 2024-04-25 11:26 | -930 | SURESH RANGNATH SHITOLE
GI Sheet Fixing (L) | N/C | N/C | PRESSMET ENTERPRISES | 692 | 2023-06-05 | D-Bldg Temporary GI Sheet Roofing in Open duct | 186 | 5 | 0 | 930 | 0 | 2024-03-11 | Labour charges for fixing of GI Sheet including tapping screw for temporary roofing in open duct area for D-Bldg. | 100 |  | 106959 | 2024-04-19 | 5238.45 | 2024-04-25 11:26 | -4308.45 | SURESH RANGNATH SHITOLE
MS Pipe Fixing (L) | N/C | N/C | PRESSMET ENTERPRISES | 692 | 2023-06-05 | D,E,Podium-Parking- Edge Barrication Work | 187 | 15 | 0 | 2805 | 0 | 2023-10-09 | Labour Charges for Fixing of MS Square pipe 40x40x2mm for Edge Barrication work of Podium, D& E Parking area. | 100 |  | 102485 | 2023-10-11 | 2805 | 1900-01-01 | 0 | SURESH RANGNATH SHITOLE
MS Pipe Fixing (L) | N/C | N/C | PRESSMET ENTERPRISES | 692 | 2023-06-05 | D,E,Podium-Parking- Edge Barrication Work | 564 | 15 | 0 | 8460 | 1522.8 | 2023-09-26 | Labour Charges for Fixing of MS Square pipe 40x40x2mm for Edge Barrication work of Podium, D& E Parking area. | 100 |  | 102109 | 2023-09-27 | 8460 | 1900-01-01 | 0 | SURESH RANGNATH SHITOLE
MS Pipe Fixing (L) | N/C | N/C | PRESSMET ENTERPRISES | 692 | 2023-06-05 | D,E,Podium-Parking- Edge Barrication Work | 1195 | 15 | 0 | 17925 | 0 | 2023-12-18 | Labour Charges for Fixing of MS Square pipe 40x40x2mm for Edge Barrication work of Podium, D& E Parking area. | 100 |  | 104091 | 2023-12-23 | 17925 | 2023-12-25 15:44 | 0 | SURESH RANGNATH SHITOLE
Sand Face Plaster - ULT | N/C | N/C | K RAMU RATHOD | 693 | 2023-06-07 | Transformer Room-Internal Single Coat-Sand Face Plaster Work | 759.19 | 20 | 0 | 15183.8 | 2733.08 | 2023-12-28 18:29 | Labour Charges for Sand Face Single plaster work for internal side of transformer room. | 100 |  | 104225 | 2024-01-01 | 15183.8 | 2024-01-23 14:19 | 0 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - ULT | N/C | N/C | K RAMU RATHOD | 693 | 2023-06-07 | Transformer Room-External Single Coat-Sand Face Plaster Work | 353.7 | 20 | 0 | 7074 | 1273.32 | 2024-01-17 16:44 | Labour Charges for Sand Face single coat plaster work for External side of transformer room. | 100 |  | 104677 | 2024-01-22 | 9323 | 2024-02-05 11:35 | -2249 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - ULT | N/C | N/C | K RAMU RATHOD | 693 | 2023-06-07 | Transformer Room-Internal Single Coat-Sand Face Plaster Work | 112.45 | 20 | 0 | 2249 | 404.82 | 2024-01-17 16:44 | Labour Charges for Sand Face Single plaster work for internal side of transformer room. | 100 |  | 104677 | 2024-01-22 | 9323 | 2024-02-05 11:35 | -7074 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - ULT | N/C | N/C | K RAMU RATHOD | 693 | 2023-06-07 | Transformer Room-External Single Coat-Sand Face Plaster Work | 483.26 | 20 | 0 | 9665.2 | 1739.74 | 2024-03-15 | Labour Charges for Sand Face single coat plaster work for External side of transformer room. | 100 | weigh bridge & south side balance plaster consider | 106938 | 2024-04-19 | 18867 | 2024-04-25 11:28 | -9201.8 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - ULT | N/C | N/C | K RAMU RATHOD | 693 | 2023-06-07 | Transformer Room-Internal Single Coat-Sand Face Plaster Work | 460.09 | 20 | 0 | 9201.8 | 1656.32 | 2024-03-15 | Labour Charges for Sand Face Single plaster work for internal side of transformer room. | 100 | Parapet inner side & weigh bridge side | 106938 | 2024-04-19 | 18867 | 2024-04-25 11:28 | -9665.2 | JAI SEVALAL CONSTRUCTION
Rough Plaster- ULT | N/C | N/C | K RAMU RATHOD | 694 | 2023-06-07 | Transformer Room- Cable Trench Ext. Face Rough Plaster Work | 759.19 | 15 | 0 | 11387.85 | 2049.82 | 2024-03-19 | Labour Charges for Rough plaster work for Transformer room Cable trench. | 100 |  | 106269 | 2024-03-20 | 28164.72 | 1900-01-01 | -16776.87 | JAI SEVALAL CONSTRUCTION
Brickwork 15" -DLd | N/C | N/C | K RAMU RATHOD | 694 | 2023-06-07 | Transformer Room- Cable Trench 15" Thk Brickwork | 204.83 | 24 | 0 | 4915.92 | 884.86 | 2024-03-20 | Labour Charges for 15 inch Brickwork for Transformer room Cable trench. | 100 |  | 106269 | 2024-03-20 | 28164.72 | 1900-01-01 | -23248.8 | JAI SEVALAL CONSTRUCTION
Rough Plaster- ULT | N/C | N/C | K RAMU RATHOD | 694 | 2023-06-07 | Transformer Room- Cable Trench Int. Face Rough Plaster Work | 790.73 | 15 | 0 | 11860.95 | 2134.98 | 2024-03-19 | Labour Charges for Rough plaster work for Transformer room Cable trench. | 100 |  | 106269 | 2024-03-20 | 28164.72 | 1900-01-01 | -16303.77 | JAI SEVALAL CONSTRUCTION
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 694 | 2023-06-07 | Transformer Room G Fl. to 1st Slab & Parapet -8" Blockwork | 771.81 | 20 | 0 | 15436.2 | 2778.52 | 2024-01-17 16:46 | Labour Charges for 8 inch Blockwork for Transformer room main wall Ground to 1st Slab. | 100 |  | 104678 | 2024-01-22 | 15436.2 | 2024-02-05 11:36 | 0 | JAI SEVALAL CONSTRUCTION
Brickwork 15" -DLd | N/C | N/C | K RAMU RATHOD | 694 | 2023-06-07 | Transformer Room- Cable Trench 15" Thk Brickwork | 476 | 24 | 0 | 11424 | 2056.32 | 2023-12-02 19:01 | Labour Charges for 15 inch Brickwork for Transformer room Cable trench. | 100 |  | 103620 | 2023-12-04 | 11424 | 1900-01-01 | 0 | JAI SEVALAL CONSTRUCTION
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | LG Floor D-Parking Ceiling Painting Work | 3461 | 1 | 0 | 3461 | 622.98 | 2024-06-01 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 108485 | 2024-06-22 | 6922 | 2024-06-27 15:20 | -3461 | SHUBHAM SURENDRA BAHADUR SINGH
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | LG Floor D-Parking Ceiling Painting Work | 3461 | 1 | 0 | 3461 | 622.98 | 2024-06-01 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 108485 | 2024-06-22 | 6922 | 2024-06-27 15:20 | -3461 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | Ground Floor D-Parking Ceiling Painting Work | 790 | 1 | 0 | 790 | 142.2 | 2024-01-15 | Labour Charges for Scrapping work and water base primer for Ceiling paint of D Building parking area. | 100 |  | 107233 | 2024-04-30 | 8952.86 | 2024-05-03 13:20 | -8162.86 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P5 Floor D-Parking Ceiling Painting Work | 626.21 | 1 | 0 | 626.21 | 112.72 | 2024-01-15 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 107233 | 2024-04-30 | 8952.86 | 2024-05-03 13:20 | -8326.65 | AAKRUTI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P1 Floor D-Parking Ceiling Painting Work | 1776 | 1 | 0 | 1776 | 319.68 | 2024-01-15 | Labour Charges for Scrapping work and water base primer for Ceiling paint of D Building parking area. | 100 |  | 107233 | 2024-04-30 | 8952.86 | 2024-05-03 13:20 | -7176.86 | AAKRUTI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P3 Floor D-Parking Ceiling Painting Work | 1927 | 1 | 0 | 1927 | 346.86 | 2024-01-15 | Labour Charges for Scrapping work and water base primer for Ceiling paint of D Building parking area. | 100 |  | 107233 | 2024-04-30 | 8952.86 | 2024-05-03 13:20 | -7025.86 | AAKRUTI ENTERPRISES
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P5 Floor D-Parking Ceiling Painting Work | 626.21 | 1 | 0 | 626.21 | 112.72 | 2024-01-15 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 107233 | 2024-04-30 | 8952.86 | 2024-05-03 13:20 | -8326.65 | AAKRUTI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P2 Floor D-Parking Ceiling Painting Work | 1927 | 1 | 0 | 1927 | 346.86 | 2024-01-15 | Labour Charges for Scrapping work and water base primer for Ceiling paint of D Building parking area. | 100 |  | 107233 | 2024-04-30 | 8952.86 | 2024-05-03 13:20 | -7025.86 | AAKRUTI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P5 Floor D-Parking Ceiling Painting Work | 1280.44 | 1 | 0 | 1280.44 | 230.48 | 2024-01-15 | Labour Charges for Scrapping work and water base primer for Ceiling paint of D Building parking area. | 100 |  | 107233 | 2024-04-30 | 8952.86 | 2024-05-03 13:20 | -7672.42 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | Ground Floor D-Parking Ceiling Painting Work | 790 | 1 | 0 | 790 | 142.2 | 2023-11-08 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 107234 | 2024-04-30 | 14148 | 2024-05-03 13:20 | -13358 | AAKRUTI ENTERPRISES
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P1 Floor D-Parking Ceiling Painting Work | 1776 | 1 | 0 | 1776 | 319.68 | 2023-11-08 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 107234 | 2024-04-30 | 14148 | 2024-05-03 13:20 | -12372 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P5 Floor D-Parking Ceiling Painting Work | 654 | 1 | 0 | 654 | 117.72 | 2023-11-08 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 107234 | 2024-04-30 | 14148 | 2024-05-03 13:20 | -13494 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P2 Floor D-Parking Ceiling Painting Work | 1927 | 1 | 0 | 1927 | 346.86 | 2023-11-08 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 107234 | 2024-04-30 | 14148 | 2024-05-03 13:20 | -12221 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P3 Floor D-Parking Ceiling Painting Work | 1927 | 1 | 0 | 1927 | 346.86 | 2023-11-08 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 107234 | 2024-04-30 | 14148 | 2024-05-03 13:20 | -12221 | AAKRUTI ENTERPRISES
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P5 Floor D-Parking Ceiling Painting Work | 654 | 1 | 0 | 654 | 117.72 | 2023-11-08 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 107234 | 2024-04-30 | 14148 | 2024-05-03 13:20 | -13494 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P1 Floor D-Parking Ceiling Painting Work | 1776 | 1 | 0 | 1776 | 319.68 | 2023-11-08 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 107234 | 2024-04-30 | 14148 | 2024-05-03 13:20 | -12372 | AAKRUTI ENTERPRISES
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | Ground Floor D-Parking Ceiling Painting Work | 790 | 1 | 0 | 790 | 142.2 | 2023-11-08 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 107234 | 2024-04-30 | 14148 | 2024-05-03 13:20 | -13358 | AAKRUTI ENTERPRISES
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P2 Floor D-Parking Ceiling Painting Work | 1927 | 1 | 0 | 1927 | 346.86 | 2023-11-08 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 107234 | 2024-04-30 | 14148 | 2024-05-03 13:20 | -12221 | AAKRUTI ENTERPRISES
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P3 Floor D-Parking Ceiling Painting Work | 1927 | 1 | 0 | 1927 | 346.86 | 2023-11-08 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 107234 | 2024-04-30 | 14148 | 2024-05-03 13:20 | -12221 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | LG Floor D-Parking Ceiling Painting Work | 1730 | 1 | 0 | 1730 | 311.4 | 2024-06-16 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 108487 | 2024-06-22 | 1730 | 2024-06-27 15:20 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P5 Floor D-Parking Ceiling Painting Work | 5122 | 1 | 0 | 5122 | 921.96 | 2023-10-03 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -87314 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P1 Floor D-Parking Ceiling Painting Work | 7108 | 1 | 0 | 7108 | 1279.44 | 2023-10-03 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -85328 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P3 Floor D-Parking Ceiling Painting Work | 7712 | 1 | 0 | 7712 | 1388.16 | 2023-10-03 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -84724 | AAKRUTI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P1 Floor D-Parking Ceiling Painting Work | 7108 | 1 | 0 | 7108 | 1279.44 | 2023-10-03 | Labour Charges for Scrapping work and water base primer for Ceiling paint of D Building parking area. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -85328 | AAKRUTI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P3 Floor D-Parking Ceiling Painting Work | 7712 | 1 | 0 | 7712 | 1388.16 | 2023-10-03 | Labour Charges for Scrapping work and water base primer for Ceiling paint of D Building parking area. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -84724 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P2 Floor D-Parking Ceiling Painting Work | 7712 | 1 | 0 | 7712 | 1388.16 | 2023-10-03 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -84724 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P5 Floor D-Parking Ceiling Painting Work | 5122 | 1 | 0 | 5122 | 921.96 | 2023-10-03 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -87314 | AAKRUTI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | Ground Floor D-Parking Ceiling Painting Work | 3158 | 1 | 0 | 3158 | 568.44 | 2023-10-03 | Labour Charges for Scrapping work and water base primer for Ceiling paint of D Building parking area. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -89278 | AAKRUTI ENTERPRISES
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P1 Floor D-Parking Ceiling Painting Work | 7108 | 1 | 0 | 7108 | 1279.44 | 2023-10-03 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -85328 | AAKRUTI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P2 Floor D-Parking Ceiling Painting Work | 7712 | 1 | 0 | 7712 | 1388.16 | 2023-10-03 | Labour Charges for Scrapping work and water base primer for Ceiling paint of D Building parking area. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -84724 | AAKRUTI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P5 Floor D-Parking Ceiling Painting Work | 5122 | 1 | 0 | 5122 | 921.96 | 2023-10-03 | Labour Charges for Scrapping work and water base primer for Ceiling paint of D Building parking area. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -87314 | AAKRUTI ENTERPRISES
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P3 Floor D-Parking Ceiling Painting Work | 7712 | 1 | 0 | 7712 | 1388.16 | 2023-10-03 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -84724 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | Ground Floor D-Parking Ceiling Painting Work | 3158 | 1 | 0 | 3158 | 568.44 | 2023-10-03 | Labour Charges for 1 Coat putty for 100 % area of Ceiling of D Building parking. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -89278 | AAKRUTI ENTERPRISES
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | P2 Floor D-Parking Ceiling Painting Work | 7712 | 1 | 0 | 7712 | 1388.16 | 2023-10-03 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -84724 | AAKRUTI ENTERPRISES
Joint Filling with Putty | N/C | N/C | AAKRUTI ENTERPRISES | 697 | 2023-06-09 | Ground Floor D-Parking Ceiling Painting Work | 3158 | 1 | 0 | 3158 | 568.44 | 2023-10-03 | Labour Charges for Joint filling with putty for Ceiling paint of D Building parking area. | 100 |  | 102216 | 2023-10-04 | 92436 | 2023-10-28 12:11 | -89278 | AAKRUTI ENTERPRISES
ACP Cladding (L)-BCo | N/C | N/C | DREAMTREE EXPERIENCE | 699 | 2023-06-12 | F-Bldg Elevation & Signage work | 5314 | 50 | 0 | 265700 | 47826 | 2023-12-08 | Labour charges for fixing of 4mm thick ACP Cladding with Aluminium Framing (Size- 85 x 37) for F-Bldg Doctors hub Signage work. | 100 | GANGA ALTUS DR HUB BRANDING | 103877 | 2023-12-11 | 482750 | 2023-12-12 10:32 | -217050 | DREAMTREE EXPERIENCE
UV Print on Fabric | N/C | N/C | DREAMTREE EXPERIENCE | 699 | 2023-06-12 | F-Bldg Elevation & Signage work | 1447 | 150 | 0 | 217050 | 39069 | 2023-12-08 | Labour charges for UV print on Fabric for F-Bldg Doctors hub Signage work. | 100 | GANGA ALTUS DR HUB BRANDING | 103877 | 2023-12-11 | 482750 | 2023-12-12 10:32 | -265700 | DREAMTREE EXPERIENCE
UV Print on Fabric (M) | N/C | N/C | DREAMTREE EXPERIENCE | 700 | 2023-06-12 | F-Bldg Elevation & Signage work | 1447 | 700 | 0 | 1012900 | 182322 | 2023-12-08 | Material Supply charges for UV print on Fabric for F-Bldg Doctors hub Signage work. | 100 | GANGA ALTUS DR HUB BRANDING | 103776 | 2023-12-11 | 1181980 | 2023-12-11 12:56 | -169080 | DREAMTREE EXPERIENCE
ACP Cladding (M)-BCo | N/C | N/C | DREAMTREE EXPERIENCE | 700 | 2023-06-12 | F-Bldg Elevation & Signage work | 5314 | 20 | 0 | 106280 | 19130.4 | 2023-12-08 | ADDITIONAL CHARGES ON ACP @ 20RS PER SQFT | 100 | GANGA ALTUS DR HUB BRANDING | 103776 | 2023-12-11 | 1181980 | 2023-12-11 12:56 | -1075700 | DREAMTREE EXPERIENCE
ACP Cladding (M)-BCo | N/C | N/C | DREAMTREE EXPERIENCE | 700 | 2023-06-12 | F-Bldg Elevation & Signage work | 314 | 200 | 0 | 62800 | 11304 | 2023-12-08 | Material Supply charges of 4mm thick ACP Cladding with Aluminium Framing (Size- 85 x 37) for F-Bldg Doctors hub Signage work. | 100 | GANGA ALTUS DR HUB BRANDING | 103776 | 2023-12-11 | 1181980 | 2023-12-11 12:56 | -1119180 | DREAMTREE EXPERIENCE
ACP Cladding (M)-BCo | N/C | N/C | DREAMTREE EXPERIENCE | 700 | 2023-06-12 | F-Bldg Elevation & Signage work | 5000 | 200 | 0 | 1000000 | 180000 | 2023-10-04 | Material Supply charges of 4mm thick ACP Cladding with Aluminium Framing (Size- 85 x 37) for F-Bldg Doctors hub Signage work. | 100 |  | 102247 | 2023-10-04 | 1000000 | 2023-10-05 16:54 | 0 | DREAMTREE EXPERIENCE
Inlet & Outlet provision -cc | N/C | N/C | SAI PLUMBING WORKS | 701 | 2023-06-17 | D-704-2BHK Customer changes | 0.9 | 1000 | 0 | 900 | 162 | 2023-12-19 11:57 | Labour Charges for Provision of Extra Water Inlet and outlet for Dry Balcony Sink. | 100 |  | 104094 | 2023-12-25 | 4500 | 2024-02-02 14:28 | -3600 | SAI PLUMBING WORKS
Inlet & Outlet provision -cc | N/C | N/C | SAI PLUMBING WORKS | 701 | 2023-06-17 | D-1106-3BHK Customer changes | 0.9 | 1000 | 0 | 900 | 162 | 2023-12-19 11:57 | Labour Charges for Provision of Extra Water Inlet and outlet for Dry Balcony Sink. | 100 |  | 104094 | 2023-12-25 | 4500 | 2024-02-02 14:28 | -3600 | SAI PLUMBING WORKS
Inlet & Outlet provision -cc | N/C | N/C | SAI PLUMBING WORKS | 701 | 2023-06-17 | D-1003-2BHK Customer changes | 0.9 | 1000 | 0 | 900 | 162 | 2023-12-19 11:57 | Labour Charges for Provision of Extra Water Inlet and outlet for Dry Balcony Sink. | 100 |  | 104094 | 2023-12-25 | 4500 | 2024-02-02 14:28 | -3600 | SAI PLUMBING WORKS
Inlet & Outlet provision -cc | N/C | N/C | SAI PLUMBING WORKS | 701 | 2023-06-17 | D-703-2BHK Customer changes | 0.9 | 1000 | 0 | 900 | 162 | 2023-12-19 11:57 | Labour Charges for Provision of Extra Water Inlet and outlet for Dry Balcony Sink. | 100 |  | 104094 | 2023-12-25 | 4500 | 2024-02-02 14:28 | -3600 | SAI PLUMBING WORKS
Inlet & Outlet provision -cc | N/C | N/C | SAI PLUMBING WORKS | 701 | 2023-06-17 | D-1103-2BHK Customer changes | 0.9 | 1000 | 0 | 900 | 162 | 2023-12-19 11:57 | Labour Charges for Provision of Extra Water Inlet and outlet for Dry Balcony Sink. | 100 |  | 104094 | 2023-12-25 | 4500 | 2024-02-02 14:28 | -3600 | SAI PLUMBING WORKS
Plumbing Groove. | N/C | N/C | SAI PLUMBING WORKS | 705 | 2023-06-17 | D-Bldg Plumbing Groove in Toilet & Kitchen 13th to 24th floo | 152.46 | 30 | 0 | 4573.8 | 823.28 | 2023-11-04 | Charges for Making of Plumbing Groove on Concrete wall in toilet and kitchen of D Building 13th floor to 24th floor. | 100 |  | 103294 | 2023-11-06 | 4573.8 | 2023-11-22 11:30 | 0 | SAI PLUMBING WORKS
Groove Cutting Rate Diff. | N/C | N/C | SAI PLUMBING WORKS | 705 | 2023-06-17 | D-Bldg Plumbing Groove in Toilet & Kitchen 13th to 24th floo | 2457.68 | 20 | 0 | 49153.6 | 8847.64 | 2023-12-15 | Labour charges and rate diff. for Plumbing Groove on concrete wall in toilet & Kitchen of D-Bldg 13th to 24th Floor. | 100 |  | 104028 | 2023-12-18 | 62875 | 2023-12-25 15:34 | -13721.4 | SAI PLUMBING WORKS
Plumbing Groove. | N/C | N/C | SAI PLUMBING WORKS | 705 | 2023-06-17 | D-Bldg Plumbing Groove in Toilet & Kitchen 13th to 24th floo | 457.38 | 30 | 0 | 13721.4 | 2469.86 | 2023-12-15 | Charges for Making of Plumbing Groove on Concrete wall in toilet and kitchen of D Building 13th floor to 24th floor. | 100 |  | 104028 | 2023-12-18 | 62875 | 2023-12-25 15:34 | -49153.6 | SAI PLUMBING WORKS
Plumbing Groove. | N/C | N/C | SAI PLUMBING WORKS | 705 | 2023-06-17 | D-Bldg Plumbing Groove in Toilet & Kitchen 13th to 24th floo | 294.23 | 30 | 0 | 8826.9 | 0 | 2023-09-13 19:03 | Charges for Making of Plumbing Groove on Concrete wall in toilet and kitchen of D Building 13th floor to 24th floor. | 100 |  | 101861 | 2023-09-15 | 8826.9 | 2023-09-30 12:04 | 0 | PRABHURAM VERMA
Plumbing Groove. | N/C | N/C | SAI PLUMBING WORKS | 705 | 2023-06-17 | D-Bldg Plumbing Groove in Toilet & Kitchen 13th to 24th floo | 471.14 | 30 | 0 | 14134.2 | 2544.16 | 2023-10-11 | Charges for Making of Plumbing Groove on Concrete wall in toilet and kitchen of D Building 13th floor to 24th floor. | 100 |  | 102544 | 2023-10-12 | 14134.2 | 2023-10-28 11:36 | 0 | SAI PLUMBING WORKS
Plumbing Groove. | N/C | N/C | SAI PLUMBING WORKS | 705 | 2023-06-17 | D-Bldg Plumbing Groove in Toilet & Kitchen 13th to 24th floo | 322.8 | 30 | 0 | 9684 | 1743.12 | 2024-05-12 | Charges for Making of Plumbing Groove on Concrete wall in toilet and kitchen of D Building 13th floor to 24th floor. | 100 |  | 107505 | 2024-05-13 | 9684 | 2024-06-04 15:22 | 0 | SAI PLUMBING WORKS
Plumbing Groove. | N/C | N/C | SAI PLUMBING WORKS | 705 | 2023-06-17 | D-Bldg Plumbing Groove in Toilet & Kitchen 13th to 24th floo | 1082.47 | 30 | 0 | 32474.1 | 5845.34 | 2023-09-13 19:02 | Charges for Making of Plumbing Groove on Concrete wall in toilet and kitchen of D Building 13th floor to 24th floor. | 100 |  | 101862 | 2023-09-15 | 32474.1 | 2023-09-30 12:06 | 0 | SAI PLUMBING WORKS
Inlet & Outlet provision -cc | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 711 | 2023-06-20 | E-806-3BHK Customer Changes | 0.8 | 1000 | 0 | 800 | 144 | 2024-03-02 17:18 | Labour charges for Provision of Extra Water Inlet and outlet for Dry Balcony sink. | 100 |  | 105731 | 2024-03-04 | 800 | 2024-03-16 10:54 | 0 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Inlet & Outlet provision -cc | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 711 | 2023-06-20 | E-305-3BHK Customer changes | 0.8 | 1000 | 0 | 800 | 144 | 2023-12-10 16:32 | Labour charges for Provision of Extra Water Inlet and outlet for Dry Balcony sink. | 100 |  | 103822 | 2023-12-11 | 800 | 2023-12-25 15:35 | 0 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Inlet & Outlet provision -cc | N/C | N/C | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE) | 711 | 2023-06-20 | E-102-3BHK Customer Changes | 0.8 | 1000 | 0 | 800 | 144 | 2023-12-14 19:04 | Labour charges for Provision of Extra Water Inlet and outlet for Dry Balcony sink. | 100 |  | 104044 | 2023-12-18 | 800 | 1900-01-01 | 0 | TEJAS ENTERPRISES ( PROP. RAMESH SOMUSE)
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Stilt Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Labour charges for Ghadai Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Stilt Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Material supply charges for Chemical Grouting Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg 3rd Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Material supply charges for Chemical Grouting Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Lift Pit- Brickbat W/P Work | 30.506 | 18 | 0 | 549.108 | 0 | 2024-07-12 16:08 | Labour charges for Brickbat waterproofing work for F-Bldg Lift Pit (Base) 01 & 02. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4581.582 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg 3rd Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Labour charges for Chemical Grouting Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg 3rd Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Labour charges for Ghadai Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Stilt Fl Chemical Grouting Work (Office Bet 2ST) | 168.67 | 2 | 0 | 337.34 | 0 | 2024-07-12 15:55 | Labour charges for Chemical Grouting Work for F-bldg Stilt & 3rd Floor office between both staircase. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -4793.35 | PRABHURAM VERMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Lift Pit- Chemical W/P Work | 116.252 | 22 | 0 | 2557.544 | 0 | 2024-07-12 16:08 | Material and Labour charges for Chemical Waterproofing work for F-Bldg Lift Walls. | 100 |  | 109089 | 2024-07-15 | 5130.69 | 1900-01-01 | -2573.146 | PRABHURAM VERMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Lift Pit- Chemical W/P Work | 465.008 | 22 | 0 | 10230.176 | 0 | 2023-08-17 17:51 | Material and Labour charges for Chemical Waterproofing work for F-Bldg Lift Walls. | 100 |  | 101316 | 2023-08-18 | 12426.61 | 2023-09-04 11:45 | -2196.434 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | GANGAPRASAD K VARMA | 712 | 2023-06-22 | F-Bldg Lift Pit- Brickbat W/P Work | 122.024 | 18 | 0 | 2196.432 | 0 | 2023-08-17 15:22 | Labour charges for Brickbat waterproofing work for F-Bldg Lift Pit (Base) 01 & 02. | 100 |  | 101316 | 2023-08-18 | 12426.61 | 2023-09-04 11:45 | -10230.178 | PRABHURAM VERMA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | Parking- Meter Room Flooring Work (L) | 149.488 | 22 | 0 | 3288.736 | 0 | 2023-09-13 12:27 | Labour charges for Fixing of Vitrified Flooring (600 x 600) for F-Bldg LG Floor Meter room area | 100 |  | 101860 | 2023-09-15 | 4307.08 | 2023-09-30 12:11 | -1018.344 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | Parking- Meter Room Flooring Work (L) | 46.288 | 22 | 0 | 1018.336 | 0 | 2023-09-13 12:27 | Labour charges for fixing of Skirting (600 x 600) for F-Bldg LG Floor Meter Room area. | 100 |  | 101860 | 2023-09-15 | 4307.08 | 2023-09-30 12:11 | -3288.744 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F-Bldg 3rd Floor- Int Flooring Work | 143.3695 | 18 | 0 | 2580.651 | 0 | 2023-09-21 10:52 | Labour Charges for- Vitrified flooring fixing & Floor Guard laying with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 102012 | 2023-09-21 | 7430.74 | 2023-09-30 12:12 | -4850.089 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F- Bldg Stilt Floor- Int. Flooring Work | 143.3695 | 18 | 0 | 2580.651 | 0 | 2023-09-21 10:52 | Labour Charges for- Vitrified flooring fixing & Floor Guard laying with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 102012 | 2023-09-21 | 7430.74 | 2023-09-30 12:12 | -4850.089 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F-Bldg 3rd Floor- Skirting Work | 51.578 | 22 | 0 | 1134.716 | 0 | 2023-09-21 10:52 | Labour Charges for- Vitrified Skirting fixing work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 102012 | 2023-09-21 | 7430.74 | 2023-09-30 12:12 | -6296.024 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F- Bldg Stilt Floor- Skirting Work | 51.578 | 22 | 0 | 1134.716 | 0 | 2023-09-21 10:52 | Labour Charges for- Vitrified Skirting fixing work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 102012 | 2023-09-21 | 7430.74 | 2023-09-30 12:12 | -6296.024 | PAPPU BAGELA
Vitrified Flooring - BRE | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F- Bldg Stilt Floor- Int. Flooring Work | 4352.35 | 22 | 0 | 95751.7 | 0 | 2024-04-17 17:12 | Labour charges for (600 x 600 mm) Vitrified Flooring work with Floor Guard Laying & Acid wash, Including Proper Fixing with line, level, right angle & joint filling for Stilt Floor at F-Bldg | 100 |  | 106990 | 2024-04-22 | 100857.5 | 2024-05-15 14:39 | -5105.8 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F-Bldg LG Floor- Bio-Waste Room- Flooring & Dado Work | 126.32 | 23 | 0 | 2905.36 | 0 | 2024-04-17 17:13 | Labour charges for Dado Fixing (300mm x 600mm) work with proper line level,joint filling,right angle,etc. for Biowaste Room. | 100 |  | 106990 | 2024-04-22 | 100857.5 | 2024-05-15 14:39 | -97952.14 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F-Bldg LG Floor- Bio-Waste Room- Flooring & Dado Work | 100.02 | 22 | 0 | 2200.44 | 0 | 2024-04-17 17:13 | Labour charges for Vitrified Flooring (600mm x 600mm) Fixing work with Floor Guard sheet laying with proper line level,joint filling,right angle,etc. for Bio-waste Room. | 100 |  | 106990 | 2024-04-22 | 100857.5 | 2024-05-15 14:39 | -98657.06 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F.Bldg Stilt Floor Toilet Dado | 391.87 | 23 | 0 | 9013.01 | 0 | 2024-04-22 16:36 | Labour charges for (300 x600 mm) Dado fixing for Common toilet with proper line, level, joint filling, right angle, etc for Stilt Floor F-Bldg | 100 |  | 107109 | 2024-04-25 | 12694.32 | 2024-05-15 14:39 | -3681.31 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F-Bldg 3rd Floor- Skirting Work | 9.102 | 22 | 0 | 200.244 | 0 | 2024-04-22 11:32 | Labour Charges for- Vitrified Skirting fixing work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 107109 | 2024-04-25 | 12694.32 | 2024-05-15 14:39 | -12494.076 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F- Bldg Stilt Floor- Int. Flooring Work | 25.3005 | 18 | 0 | 455.409 | 0 | 2024-04-22 11:32 | Labour Charges for- Vitrified flooring fixing & Floor Guard laying with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 107109 | 2024-04-25 | 12694.32 | 2024-05-15 14:39 | -12238.911 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F- Bldg Stilt Floor- Skirting Work | 9.102 | 22 | 0 | 200.244 | 0 | 2024-04-22 11:32 | Labour Charges for- Vitrified Skirting fixing work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 107109 | 2024-04-25 | 12694.32 | 2024-05-15 14:39 | -12494.076 | PAPPU BAGELA
Ceramic Flooring - BRE | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F.Bldg Stilt Floor Toilet Flooring Work | 80.73 | 21 | 0 | 1695.33 | 0 | 2024-04-22 16:37 | Labour Charges for (300 x 300mm) Ceramic Flooring work for Common Toilet with proper line, level, joint Filling, Right angle, etc for Stilt Floor at F-Bldg. | 100 |  | 107109 | 2024-04-25 | 12694.32 | 2024-05-15 14:39 | -10998.99 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F-Bldg 3rd Floor- Int Flooring Work | 25.3005 | 18 | 0 | 455.409 | 0 | 2024-04-22 11:32 | Labour Charges for- Vitrified flooring fixing & Floor Guard laying with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 107109 | 2024-04-25 | 12694.32 | 2024-05-15 14:39 | -12238.911 | PAPPU BAGELA
Schedule & Quality | No category | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F-Bldg 3rd Floor- Int Flooring Work | 168.67 | 2 | 0 | 337.34 | 0 | 2024-04-22 11:32 | Labour Charges for- Schedule & Quality of F Building vitrified flooring work office area between both staircase. | 100 |  | 107109 | 2024-04-25 | 12694.32 | 2024-05-15 14:39 | -12356.98 | PAPPU BAGELA
Schedule & Quality | No category | N/C | PAPPU BAGELA | 717 | 2023-07-03 | F- Bldg Stilt Floor- Int. Flooring Work | 168.67 | 2 | 0 | 337.34 | 0 | 2024-04-22 11:32 | Labour Charges for- Schedule & Quality of F Building vitrified flooring work office area between both staircase. | 100 |  | 107109 | 2024-04-25 | 12694.32 | 2024-05-15 14:39 | -12356.98 | PAPPU BAGELA
Kota Flooring (L)- BCO | N/C | N/C | R.M.Marbles | 718 | 2023-07-03 | Parking- Service Room- Kota Flooring Work (M+L) | 251.12 | 40 | 0 | 10044.8 | 0 | 2023-09-21 12:17 | Labour charges for fixing of kota Flooring for oxygen piping room (service room) including material shifting, cutting, grinding, fixing, floor guard sheet laying, removing & acid wash. | 100 |  | 102013 | 2023-09-21 | 10044.8 | 2023-09-30 12:13 | 0 | PAPPU BAGELA
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2203-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2208-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2306-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2308-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2405-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2304-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2101-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2404-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2106-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2302-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2202-2BHK(Near Refuse Area) Flat Electrical Work | 1 | 12683 | 0 | 4439.05 | 799.02 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145345.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2204-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2402-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2303-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2207-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2102-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2407-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2408-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2103-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2105-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2107-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2307-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2305-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2401-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2403-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2201-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2108-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2205-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2206-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2301-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2104-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2024-07-30 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -145354.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2406-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2024-07-30 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 109576 | 2024-08-05 | 149784.95 | 1900-01-01 | -144821.25 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1805-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2002-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1806-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2001-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2005-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2006-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2003-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1903-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1907-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1801-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1904-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1908-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1902-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1802-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1803-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1808-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1901-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1905-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1804-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1807-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2004-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2007-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-2008-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-12-23 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -108301.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1906-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-12-23 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 104111 | 2023-12-25 | 112732.2 | 1900-01-01 | -107768.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-107-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1102-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1703-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-005-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-101-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-108-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-304-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-705-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1401-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1508-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-301-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-303-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-502-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-702-2BHK(Near Refuse Area) Flat Electrical Work | 1 | 12683 | 0 | 4439.05 | 799.02 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674110.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-908-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1305-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1602-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1704-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1708-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-206-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-308-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-405-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-501-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-603-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-703-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-704-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-901-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-907-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1104-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1308-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1603-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1707-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-604-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1002-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1005-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1008-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1501-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1502-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-205-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-504-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-701-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-706-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-708-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1003-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1108-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-102-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-106-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-207-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-601-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-607-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1101-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1403-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1406-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-001-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-07 10:31 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-001-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2023-11-08 | Internal Wiring Work | 30 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674294.6 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-004-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-103-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-305-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-404-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-408-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-802-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-006-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-302-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-904-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-906-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1105-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1303-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1307-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-401-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-402-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-806-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-808-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1203-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1205-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1208-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1301-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-007-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-008-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-306-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-503-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-003-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-104-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-505-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-507-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-707-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-805-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-807-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1608-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-208-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-506-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1001-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1004-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1007-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1405-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1207-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1302-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1604-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1705-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1706-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-605-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1404-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1503-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-002-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-07 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-202-2BHK(Near Refuse Area) Flat Electrical Work | 1 | 12683 | 0 | 4439.05 | 799.02 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674110.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1107-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1201-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1202-2BHK(Near Refuse Area) Flat Electrical Work | 1 | 12683 | 0 | 4439.05 | 799.02 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674110.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1506-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-403-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-406-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-905-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1106-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1304-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1306-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-203-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-608-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1006-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1103-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1407-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1408-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1702-2BHK(Near Refuse Area) Flat Electrical Work | 1 | 12683 | 0 | 4439.05 | 799.02 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674110.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-606-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-902-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1504-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-407-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-801-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1204-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1605-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1606-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-803-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-804-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1206-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1607-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1701-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-602-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-307-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-508-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-903-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1402-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1505-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1507-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-1601-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-105-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-201-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-11-08 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -673585.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 719 | 2023-07-03 | E-204-2BHK Flat Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-11-08 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 103380 | 2023-11-08 | 678549.2 | 1900-01-01 | -674118.55 | HARISH CHANDRA JADHAV ELECTRICALS
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1101-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 24 | 0 | 142.656 | 25.68 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145723.794 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1101-3BHK Flooring & Tiling Work | 125.13 | 17 | 0 | 2127.21 | 382.9 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -143739.24 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1103-2BHK Flooring & Tiling Work-(Flat) | 107.6925 | 17 | 0 | 1830.7725 | 329.54 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144035.6775 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-501-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2024-03-10 15:00 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -137297.362 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 24 | 0 | 235.584 | 42.4 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145630.866 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1102-3BHK Flooring & Tiling Work | 125.13 | 17 | 0 | 2127.21 | 382.9 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -143739.24 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1104-2BHK Flooring & Tiling Work-(Flat) | 107.6925 | 17 | 0 | 1830.7725 | 329.54 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144035.6775 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-503-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.02 | 2024-03-10 15:00 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139344.082 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-504-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.02 | 2024-03-10 15:00 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139344.082 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1201-3BHK Toilet Dado Work | 249.168 | 24 | 0 | 5980.032 | 1076.4 | 2024-03-10 15:15 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139886.418 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-704-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145650.498 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1202-2BHK(Near Refuse Area) Comm Passage Wash Basin Dado W | 5.944 | 24 | 0 | 142.656 | 25.68 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145723.794 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-502-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2024-03-10 15:00 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -137297.362 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 22 | 0 | 1411.344 | 254.04 | 2024-03-10 15:08 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144455.106 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-701-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145735.682 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145735.682 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-03-10 15:26 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -143864.37 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1501-3BHK Flooring & Tiling Work | 125.13 | 19 | 0 | 2377.47 | 427.94 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -143488.98 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145735.682 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1103-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 24 | 0 | 235.584 | 42.4 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145630.866 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Flooring & Tiling Work-(Flat) | 107.6925 | 17 | 0 | 1830.7725 | 329.54 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144035.6775 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-402-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2024-03-10 15:00 | Labour Charges for- Vitrified Flooring work with floor guard laying. Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -138368.498 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Toilet Dado Work | 245.416 | 24 | 0 | 5889.984 | 1060.2 | 2024-03-10 15:15 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139976.466 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-603-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145650.498 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1204-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 24 | 0 | 235.584 | 42.4 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145630.866 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-601-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145735.682 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145735.682 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1202-2BHK(Near Refuse Area) Flooring & Tiling Work | 54.2475 | 17 | 0 | 922.2075 | 166 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144944.2425 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1203-2BHK Flooring & Tiling Work-(Flat) | 107.6925 | 17 | 0 | 1830.7725 | 329.54 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144035.6775 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1204-2BHK Flooring & Tiling Work-(Flat) | 107.6925 | 17 | 0 | 1830.7725 | 329.54 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144035.6775 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Flooring & Tiling Work | 61.568 | 22 | 0 | 1354.496 | 243.82 | 2024-03-10 15:08 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144511.954 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Toilet Dado Work | 249.168 | 24 | 0 | 5980.032 | 1076.4 | 2024-03-10 15:15 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139886.418 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1101-3BHK Toilet Dado Work | 249.168 | 24 | 0 | 5980.032 | 1076.4 | 2024-03-10 15:15 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139886.418 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1204-2BHK Toilet Dado Work | 245.416 | 24 | 0 | 5889.984 | 1060.2 | 2024-03-10 15:19 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139976.466 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145650.498 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 24 | 0 | 235.584 | 42.4 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145630.866 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-704-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.92 | 2024-03-17 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -85271.15 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1303-2BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-03-17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -87126.254 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-601-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2024-03-17 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -79140.462 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-601-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-03-17 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -84386.35 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-503-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.92 | 2024-03-17 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -85271.15 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-701-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2024-03-17 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -79140.462 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-502-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-03-17 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -84386.35 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-701-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-03-17 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -84386.35 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1302-3BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-03-17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -87126.254 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-602-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-03-17 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -84386.35 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1403-2BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-03-17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -87126.254 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1301-3BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-03-17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -87126.254 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-703-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.02 | 2024-03-17 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -81187.182 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-704-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.02 | 2024-03-17 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -81187.182 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-602-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2024-03-17 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -79140.462 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-504-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.92 | 2024-03-17 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -85271.15 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-604-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.02 | 2024-03-17 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -81187.182 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-501-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-03-17 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -84386.35 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1404-2BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-03-17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -87126.254 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-603-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.02 | 2024-03-17 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -81187.182 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-703-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.92 | 2024-03-17 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -85271.15 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1304-2BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-03-17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -87126.254 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1401-3BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-03-17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -87126.254 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-604-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.92 | 2024-03-17 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -85271.15 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-603-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.92 | 2024-03-17 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -85271.15 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1402-3BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-03-17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 107231 | 2024-04-30 | 87709.55 | 2024-05-03 13:16 | -87126.254 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301506.35 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-501-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301227.35 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-101-3BHK Vitrified Skirting | 166.16 | 18 | 0 | 2990.88 | 538.36 | 2024-02-10 20:40 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -300238.55 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-204-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 395.02 | 2024-02-10 20:40 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301034.87 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-301-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2024-02-10 17:26 | Labour Charges for- Vitrified Flooring work with floor guard laying. Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -295731.478 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-404-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 1027.28 | 2024-02-10 17:26 | Labour Charges for- Vitrified Flooring work with floor guard laying. Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297522.358 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-402-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303110.55 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-404-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303033.11 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-02-10 19:02 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302694.742 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-02-10 19:05 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302646.134 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Toilet Dado Work | 245.416 | 22 | 0 | 5399.152 | 971.84 | 2024-02-10 19:17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297830.278 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-401-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301494.294 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-704-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301506.35 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-703-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 22 | 0 | 1411.344 | 254.04 | 2024-02-10 20:34 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301818.086 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-203-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 395.02 | 2024-02-10 20:40 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301034.87 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-301-3BHK Vitrified Skirting | 166.16 | 18 | 0 | 2990.88 | 538.36 | 2024-02-10 20:40 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -300238.55 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-404-2BHK Toilet Dado Work | 245.416 | 20 | 0 | 4908.32 | 883.5 | 2024-02-10 19:11 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -298321.11 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Toilet Dado Work | 249.168 | 22 | 0 | 5481.696 | 986.7 | 2024-02-10 19:17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297747.734 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-503-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 22 | 0 | 1411.344 | 254.04 | 2024-02-10 18:35 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301818.086 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-002-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303110.55 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-201-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303110.55 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1204-2BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-02-10 19:05 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302646.134 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-402-3BHK Toilet Dado Work | 249.168 | 20 | 0 | 4983.36 | 897 | 2024-02-10 19:11 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -298246.07 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Flooring & Tiling Work | 61.568 | 22 | 0 | 1354.496 | 243.82 | 2024-02-10 20:34 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301874.934 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-703-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301506.35 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-404-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 395.02 | 2024-02-10 20:40 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301034.87 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-601-3BHK Flooring & Tiling Work | 61.568 | 22 | 0 | 1354.496 | 243.82 | 2024-02-10 20:34 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301874.934 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-603-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 22 | 0 | 1411.344 | 254.04 | 2024-02-10 20:34 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301818.086 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-601-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301227.35 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-201-3BHK Vitrified Skirting | 166.16 | 18 | 0 | 2990.88 | 538.36 | 2024-02-10 20:40 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -300238.55 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Toilet Dado Work | 249.168 | 22 | 0 | 5481.696 | 986.7 | 2024-02-10 19:17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297747.734 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-303-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303033.11 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-02-10 19:02 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302694.742 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-604-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 22 | 0 | 1411.344 | 254.04 | 2024-02-10 20:34 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301818.086 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-701-3BHK Flooring & Tiling Work | 61.568 | 22 | 0 | 1354.496 | 243.82 | 2024-02-10 20:34 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301874.934 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-603-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301506.35 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-401-3BHK Flooring & Tiling Work | 61.568 | 20 | 0 | 1231.36 | 221.64 | 2024-02-10 18:35 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301998.07 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-103-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303033.11 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-504-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-02-10 18:47 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303013.478 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Toilet Dado Work | 245.416 | 22 | 0 | 5399.152 | 971.84 | 2024-02-10 19:17 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297830.278 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-704-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 22 | 0 | 1411.344 | 254.04 | 2024-02-10 20:34 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301818.086 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-604-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301506.35 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-101-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2024-02-10 17:26 | Labour Charges for- Vitrified Flooring work with floor guard laying. Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -295731.478 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-204-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 1027.28 | 2024-02-10 17:26 | Labour Charges for- Vitrified Flooring work with floor guard laying. Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297522.358 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-003-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303033.11 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1102-3BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-02-10 19:05 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302646.134 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-602-3BHK Toilet Dado Work | 249.168 | 22 | 0 | 5481.696 | 986.7 | 2024-02-10 19:11 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297747.734 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-604-2BHK Toilet Dado Work | 245.416 | 22 | 0 | 5399.152 | 971.84 | 2024-02-10 19:11 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297830.278 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-004-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303033.11 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-02-10 19:02 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302694.742 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301227.35 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301227.35 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301506.35 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-502-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-02-10 20:37 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301227.35 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-503-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-02-10 18:47 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303013.478 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-02-10 19:02 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302694.742 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-02-10 19:02 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302694.742 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-504-2BHK Toilet Dado Work | 245.416 | 22 | 0 | 5399.152 | 971.84 | 2024-02-10 19:11 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297830.278 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-403-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 1027.28 | 2024-02-10 17:26 | Labour Charges for- Vitrified Flooring work with floor guard laying. Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297522.358 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-502-3BHK Flooring & Tiling Work | 61.568 | 22 | 0 | 1354.496 | 243.82 | 2024-02-10 18:35 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301874.934 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-202-2BHK(Near Refuse Area) Comm Passage Wash Basin Dado Wo | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303110.55 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-301-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303110.55 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-501-3BHK Flooring & Tiling Work | 61.568 | 22 | 0 | 1354.496 | 243.82 | 2024-02-10 18:35 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -301874.934 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-603-2BHK Toilet Dado Work | 245.416 | 22 | 0 | 5399.152 | 971.84 | 2024-02-10 19:11 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297830.278 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-701-3BHK Toilet Dado Work | 249.168 | 22 | 0 | 5481.696 | 986.7 | 2024-02-10 19:11 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -297747.734 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-403-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303033.11 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-02-10 19:02 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302694.742 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-02-10 19:05 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302646.134 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1203-2BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-02-10 19:05 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302646.134 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-204-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-02-10 18:47 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for common passage at wash Basin E-bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -303033.11 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-404-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2024-02-10 18:53 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302961.782 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-02-10 19:02 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 105248 | 2024-02-12 | 303229.43 | 2024-02-21 11:28 | -302694.742 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-001-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2023-12-14 15:01 | Labour Charges for- Vitrified Flooring work with floor guard laying. Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -166382.138 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-201-3BHK Flooring & Tiling Work | 61.568 | 20 | 0 | 1231.36 | 221.64 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172648.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-302-3BHK Toilet Dado Work | 249.168 | 20 | 0 | 4983.36 | 897 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168896.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-304-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-703-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173345.402 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-301-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173550.018 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-204-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172386.754 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-002-3BHK Vitrified Skirting | 166.16 | 18 | 0 | 2990.88 | 538.36 | 2023-12-14 15:05 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -170889.21 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-002-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173550.018 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-104-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 20 | 0 | 1283.04 | 230.94 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172597.05 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-003-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 395.02 | 2023-12-14 15:05 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -171685.53 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-603-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173345.402 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-203-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172386.754 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-704-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173345.402 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-201-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172144.954 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-001-3BHK Vitrified Skirting | 166.16 | 18 | 0 | 2990.88 | 538.36 | 2023-12-14 15:05 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -170889.21 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-102-3BHK Toilet Dado Work | 249.168 | 20 | 0 | 4983.36 | 897 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168896.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-103-2BHK Toilet Dado Work | 245.416 | 20 | 0 | 4908.32 | 883.5 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168971.77 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-201-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173550.018 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-104-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-002-3BHK Toilet Dado Work | 249.168 | 20 | 0 | 4983.36 | 897 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168896.73 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-204-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173612.442 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-404-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-701-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173345.402 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-304-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173612.442 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-001-3BHK Flooring & Tiling Work | 61.568 | 20 | 0 | 1231.36 | 221.64 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172648.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-003-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 20 | 0 | 1283.04 | 230.94 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172597.05 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-101-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173550.018 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-102-3BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-304-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172386.754 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-004-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 20 | 0 | 1283.04 | 230.94 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172597.05 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-302-3BHK Flooring & Tiling Work | 61.568 | 20 | 0 | 1231.36 | 221.64 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172648.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-201-3BHK Toilet Dado Work | 249.168 | 20 | 0 | 4983.36 | 897 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168896.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-101-3BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-004-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 1027.28 | 2023-12-14 15:01 | Labour Charges for- Vitrified Flooring work with floor guard laying. Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168173.018 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-004-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 395.02 | 2023-12-14 15:05 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -171685.53 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-304-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 20 | 0 | 1283.04 | 230.94 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172597.05 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-203-2BHK Toilet Dado Work | 245.416 | 20 | 0 | 4908.32 | 883.5 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168971.77 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-302-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173550.018 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-002-3BHK Flooring & Tiling Work | 61.568 | 20 | 0 | 1231.36 | 221.64 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172648.73 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-103-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173612.442 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-103-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-502-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173345.402 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-601-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173345.402 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-002-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172144.954 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-303-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172386.754 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-002-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2023-12-14 15:01 | Labour Charges for- Vitrified Flooring work with floor guard laying. Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -166382.138 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-004-2BHK Toilet Dado Work | 245.416 | 20 | 0 | 4908.32 | 883.5 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168971.77 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-301-3BHK Toilet Dado Work | 249.168 | 20 | 0 | 4983.36 | 897 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168896.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-101-3BHK Toilet Dado Work | 249.168 | 20 | 0 | 4983.36 | 897 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168896.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-104-2BHK Toilet Dado Work | 245.416 | 20 | 0 | 4908.32 | 883.5 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168971.77 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-104-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173612.442 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-001-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172144.954 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-101-3BHK Flooring & Tiling Work | 61.568 | 20 | 0 | 1231.36 | 221.64 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172648.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-001-3BHK Toilet Dado Work | 249.168 | 20 | 0 | 4983.36 | 897 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168896.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-602-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173345.402 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-604-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173345.402 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-101-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172144.954 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-003-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 1027.28 | 2023-12-14 15:01 | Labour Charges for- Vitrified Flooring work with floor guard laying. Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168173.018 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-103-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 20 | 0 | 1283.04 | 230.94 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172597.05 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-301-3BHK Flooring & Tiling Work | 61.568 | 20 | 0 | 1231.36 | 221.64 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172648.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-303-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 20 | 0 | 1283.04 | 230.94 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172597.05 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-003-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173612.442 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-003-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-503-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173345.402 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-504-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173345.402 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-204-2BHK Toilet Dado Work | 245.416 | 20 | 0 | 4908.32 | 883.5 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168971.77 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-001-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173550.018 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-203-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173612.442 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-001-3BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-401-3BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 16:37 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-302-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172144.954 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-501-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173345.402 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-003-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172386.754 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-201-3BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-203-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-402-3BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-003-2BHK Toilet Dado Work | 245.416 | 20 | 0 | 4908.32 | 883.5 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168971.77 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-202-2BHK(Near Refuse Area) Toilet Dado Work | 249.168 | 20 | 0 | 4983.36 | 897 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168896.73 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-204-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-403-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 16:30 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-104-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172386.754 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-301-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172144.954 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-004-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173612.442 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-001-3BHK Living Terrace Skirting | 2.427 | 17 | 0 | 41.259 | 7.42 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47263.531 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-203-2BHK Living Terrace Skirting | 1.968 | 17 | 0 | 33.456 | 6.02 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47271.334 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Flooring & Tiling Work-(Flat) | 14.359 | 17 | 0 | 244.103 | 43.94 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47060.687 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-303-2BHK Living Terrace Skirting | 1.968 | 17 | 0 | 33.456 | 6.02 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47271.334 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Flooring & Tiling Work-(Flat) | 8.019 | 24 | 0 | 192.456 | 34.64 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47112.334 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Flooring & Tiling Work-(Flat) | 8.019 | 24 | 0 | 192.456 | 34.64 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47112.334 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-502-3BHK Vitrified Skirting | 20.77 | 20 | 0 | 415.4 | 74.78 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46889.39 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-701-3BHK Vitrified Skirting | 20.77 | 20 | 0 | 415.4 | 74.78 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46889.39 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-002-3BHK Living Terrace Skirting | 2.427 | 17 | 0 | 41.259 | 7.42 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47263.531 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Flooring & Tiling Work | 7.696 | 22 | 0 | 169.312 | 30.48 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47135.478 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Kitchen Dado Work | 3.038 | 22 | 0 | 66.836 | 12.04 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47237.954 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-502-3BHK Living Terrace Skirting | 2.427 | 19 | 0 | 46.113 | 8.3 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47258.677 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Living Terrace Skirting | 2.427 | 19 | 0 | 46.113 | 8.3 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47258.677 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Flooring & Tiling Work | 7.696 | 22 | 0 | 169.312 | 30.48 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47135.478 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Toilet Dado Work | 30.677 | 22 | 0 | 674.894 | 121.48 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46629.896 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Toilet Dado Work | 31.146 | 22 | 0 | 685.212 | 123.34 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46619.578 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-302-3BHK Vitrified Skirting | 20.77 | 18 | 0 | 373.86 | 67.3 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46930.93 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-403-2BHK Vitrified Skirting | 15.24 | 18 | 0 | 274.32 | 49.38 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47030.47 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Flooring & Tiling Work | 16.684 | 15 | 0 | 250.26 | 45.04 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47054.53 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-404-2BHK Living Terrace Skirting | 1.968 | 17 | 0 | 33.456 | 6.02 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47271.334 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-603-2BHK Living Terrace Skirting | 1.968 | 19 | 0 | 37.392 | 6.74 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47267.398 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Kitchen Dado Work | 3.038 | 22 | 0 | 66.836 | 12.04 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47237.954 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-303-2BHK Vitrified Skirting | 15.24 | 18 | 0 | 274.32 | 49.38 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47030.47 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-304-2BHK Vitrified Skirting | 15.24 | 18 | 0 | 274.32 | 49.38 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47030.47 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Vitrified Skirting | 15.24 | 22 | 0 | 335.28 | 60.36 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46969.51 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-103-2BHK Vitrified Skirting | 15.24 | 18 | 0 | 274.32 | 49.38 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47030.47 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-104-2BHK Vitrified Skirting | 15.24 | 18 | 0 | 274.32 | 49.38 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47030.47 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-601-3BHK Vitrified Skirting | 20.77 | 20 | 0 | 415.4 | 74.78 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46889.39 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-704-2BHK Vitrified Skirting | 15.24 | 20 | 0 | 304.8 | 54.86 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46999.99 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Living Terrace Skirting | 2.427 | 21 | 0 | 50.967 | 9.18 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47253.823 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Living Terrace Skirting | 1.968 | 21 | 0 | 41.328 | 7.44 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47263.462 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-503-2BHK Living Terrace Skirting | 1.968 | 19 | 0 | 37.392 | 6.74 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47267.398 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-602-3BHK Living Terrace Skirting | 2.427 | 19 | 0 | 46.113 | 8.3 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47258.677 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Toilet Dado Work | 31.146 | 24 | 0 | 747.504 | 134.56 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46557.286 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Flooring & Tiling Work | 7.696 | 22 | 0 | 169.312 | 30.48 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47135.478 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Toilet Dado Work | 30.677 | 22 | 0 | 674.894 | 121.48 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46629.896 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Vitrified Flooring Work | 66.946 | 18 | 0 | 1205.028 | 216.9 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46099.762 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Living Terrace Skirting | 1.968 | 19 | 0 | 37.392 | 6.74 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47267.398 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Toilet Dado Work | 31.146 | 22 | 0 | 685.212 | 123.34 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46619.578 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Vitrified Flooring Work | 50.956 | 16 | 0 | 815.296 | 146.76 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46489.494 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-101-3BHK Vitrified Skirting | 20.77 | 18 | 0 | 373.86 | 67.3 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46930.93 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-204-2BHK Vitrified Skirting | 15.24 | 18 | 0 | 274.32 | 49.38 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47030.47 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Vitrified Skirting | 20.77 | 20 | 0 | 415.4 | 74.78 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46889.39 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Flooring & Tiling Work-(Flat) | 14.359 | 15 | 0 | 215.385 | 38.78 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47089.405 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Vitrified Flooring Work | 66.946 | 16 | 0 | 1071.136 | 192.8 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46233.654 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-401-3BHK Vitrified Skirting | 20.77 | 18 | 0 | 373.86 | 67.3 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46930.93 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Vitrified Flooring Work | 66.946 | 18 | 0 | 1205.028 | 216.9 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46099.762 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-504-2BHK Vitrified Skirting | 15.24 | 20 | 0 | 304.8 | 54.86 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46999.99 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-602-3BHK Vitrified Skirting | 20.77 | 20 | 0 | 415.4 | 74.78 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46889.39 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Flooring & Tiling Work-(Flat) | 14.359 | 17 | 0 | 244.103 | 43.94 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47060.687 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-402-3BHK Living Terrace Skirting | 2.427 | 17 | 0 | 41.259 | 7.42 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47263.531 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Living Terrace Skirting | 2.427 | 19 | 0 | 46.113 | 8.3 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47258.677 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Kitchen Dado Work | 3.038 | 22 | 0 | 66.836 | 12.04 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47237.954 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-002-3BHK Vitrified Skirting | 20.77 | 18 | 0 | 373.86 | 67.3 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46930.93 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-404-2BHK Vitrified Skirting | 15.24 | 18 | 0 | 274.32 | 49.38 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47030.47 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Vitrified Flooring Work | 50.956 | 16 | 0 | 815.296 | 146.76 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46489.494 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Vitrified Skirting | 20.77 | 20 | 0 | 415.4 | 74.78 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46889.39 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-004-2BHK Living Terrace Skirting | 1.968 | 17 | 0 | 33.456 | 6.02 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47271.334 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-501-3BHK Living Terrace Skirting | 2.427 | 19 | 0 | 46.113 | 8.3 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47258.677 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Living Terrace Skirting | 1.968 | 19 | 0 | 37.392 | 6.74 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47267.398 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Flooring & Tiling Work | 7.696 | 24 | 0 | 184.704 | 33.24 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47120.086 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Kitchen Dado Work | 3.038 | 24 | 0 | 72.912 | 13.12 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47231.878 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Kitchen Dado Work | 3.038 | 22 | 0 | 66.836 | 12.04 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47237.954 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Toilet Dado Work | 30.677 | 22 | 0 | 674.894 | 121.48 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46629.896 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Flooring & Tiling Work-(Flat) | 8.019 | 22 | 0 | 176.418 | 31.76 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47128.372 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-503-2BHK Vitrified Skirting | 15.24 | 20 | 0 | 304.8 | 54.86 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46999.99 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Vitrified Skirting | 15.24 | 20 | 0 | 304.8 | 54.86 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46999.99 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-101-3BHK Living Terrace Skirting | 2.427 | 17 | 0 | 41.259 | 7.42 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47263.531 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Kitchen Dado Work | 3.038 | 24 | 0 | 72.912 | 13.12 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47231.878 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Vitrified Flooring Work | 66.946 | 16 | 0 | 1071.136 | 192.8 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46233.654 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-004-2BHK Vitrified Skirting | 15.24 | 18 | 0 | 274.32 | 49.38 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47030.47 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-703-2BHK Vitrified Skirting | 15.24 | 20 | 0 | 304.8 | 54.86 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46999.99 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Flooring & Tiling Work | 16.684 | 15 | 0 | 250.26 | 45.04 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47054.53 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-302-3BHK Living Terrace Skirting | 2.427 | 17 | 0 | 41.259 | 7.42 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47263.531 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-703-2BHK Living Terrace Skirting | 1.968 | 19 | 0 | 37.392 | 6.74 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47267.398 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Living Terrace Skirting | 2.427 | 19 | 0 | 46.113 | 8.3 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47258.677 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Kitchen Dado Work | 3.038 | 22 | 0 | 66.836 | 12.04 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47237.954 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Flooring & Tiling Work-(Flat) | 8.019 | 22 | 0 | 176.418 | 31.76 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47128.372 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-604-2BHK Vitrified Skirting | 15.24 | 20 | 0 | 304.8 | 54.86 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46999.99 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-003-2BHK Living Terrace Skirting | 1.968 | 17 | 0 | 33.456 | 6.02 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47271.334 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Flooring & Tiling Work | 16.684 | 15 | 0 | 250.26 | 45.04 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47054.53 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Flooring & Tiling Work | 16.684 | 15 | 0 | 250.26 | 45.04 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47054.53 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Flooring & Tiling Work-(Flat) | 14.359 | 15 | 0 | 215.385 | 38.78 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47089.405 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Living Terrace Skirting | 1.968 | 21 | 0 | 41.328 | 7.44 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47263.462 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-201-3BHK Living Terrace Skirting | 2.427 | 17 | 0 | 41.259 | 7.42 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47263.531 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Flooring & Tiling Work | 7.696 | 22 | 0 | 169.312 | 30.48 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47135.478 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Kitchen Dado Work | 3.038 | 22 | 0 | 66.836 | 12.04 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47237.954 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Kitchen Dado Work | 3.038 | 22 | 0 | 66.836 | 12.04 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47237.954 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-001-3BHK Vitrified Skirting | 20.77 | 18 | 0 | 373.86 | 67.3 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46930.93 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Toilet Dado Work | 280.314 | 22 | 0 | 6166.908 | 1110.04 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -41137.882 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Vitrified Skirting | 20.77 | 22 | 0 | 456.94 | 82.24 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46847.85 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-201-3BHK Vitrified Skirting | 20.77 | 18 | 0 | 373.86 | 67.3 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46930.93 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-304-2BHK Living Terrace Skirting | 1.968 | 17 | 0 | 33.456 | 6.02 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47271.334 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Living Terrace Skirting | 2.427 | 19 | 0 | 46.113 | 8.3 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47258.677 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Vitrified Flooring Work | 66.946 | 16 | 0 | 1071.136 | 192.8 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46233.654 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-402-3BHK Vitrified Skirting | 20.77 | 18 | 0 | 373.86 | 67.3 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46930.93 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Vitrified Skirting | 20.77 | 20 | 0 | 415.4 | 74.78 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46889.39 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Vitrified Skirting | 20.77 | 20 | 0 | 415.4 | 74.78 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46889.39 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Living Terrace Skirting | 2.427 | 21 | 0 | 50.967 | 9.18 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47253.823 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-103-2BHK Living Terrace Skirting | 1.968 | 17 | 0 | 33.456 | 6.02 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47271.334 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Flooring & Tiling Work-(Flat) | 8.019 | 22 | 0 | 176.418 | 31.76 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47128.372 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Flooring & Tiling Work-(Flat) | 8.019 | 22 | 0 | 176.418 | 31.76 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47128.372 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-501-3BHK Vitrified Skirting | 20.77 | 20 | 0 | 415.4 | 74.78 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46889.39 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Vitrified Skirting | 15.24 | 20 | 0 | 304.8 | 54.86 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46999.99 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-301-3BHK Living Terrace Skirting | 2.427 | 17 | 0 | 41.259 | 7.42 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47263.531 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-701-3BHK Living Terrace Skirting | 2.427 | 19 | 0 | 46.113 | 8.3 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47258.677 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-704-2BHK Living Terrace Skirting | 1.968 | 19 | 0 | 37.392 | 6.74 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47267.398 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Living Terrace Skirting | 1.968 | 19 | 0 | 37.392 | 6.74 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47267.398 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Flooring & Tiling Work | 7.696 | 24 | 0 | 184.704 | 33.24 | 2024-06-27 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47120.086 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Kitchen Dado Work | 3.038 | 24 | 0 | 72.912 | 13.12 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47231.878 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Toilet Dado Work | 30.677 | 24 | 0 | 736.248 | 132.52 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46568.542 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Kitchen Dado Work | 3.038 | 22 | 0 | 66.836 | 12.04 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47237.954 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-002-3BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-004-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-004-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172386.754 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-204-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 20 | 0 | 1283.04 | 230.94 | 2023-12-14 15:23 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172597.05 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-303-2BHK Toilet Dado Work | 245.416 | 20 | 0 | 4908.32 | 883.5 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168971.77 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-304-2BHK Toilet Dado Work | 245.416 | 20 | 0 | 4908.32 | 883.5 | 2023-12-14 15:39 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -168971.77 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-303-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2023-12-14 15:45 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173612.442 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-301-3BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-302-3BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-303-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2023-12-14 15:54 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -173394.01 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-103-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-12-14 16:42 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 103986 | 2023-12-18 | 173880.09 | 2023-12-22 11:31 | -172386.754 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Vitrified Flooring Work | 50.956 | 18 | 0 | 917.208 | 165.1 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46387.582 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Toilet Dado Work | 30.677 | 22 | 0 | 674.894 | 121.48 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46629.896 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Vitrified Flooring Work | 50.956 | 16 | 0 | 815.296 | 146.76 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46489.494 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Vitrified Flooring Work | 50.956 | 16 | 0 | 815.296 | 146.76 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46489.494 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Vitrified Skirting | 20.77 | 22 | 0 | 456.94 | 82.24 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46847.85 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-603-2BHK Vitrified Skirting | 15.24 | 20 | 0 | 304.8 | 54.86 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46999.99 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Vitrified Skirting | 15.24 | 20 | 0 | 304.8 | 54.86 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46999.99 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Flooring & Tiling Work | 16.684 | 17 | 0 | 283.628 | 51.06 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47021.162 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Flooring & Tiling Work | 16.684 | 17 | 0 | 283.628 | 51.06 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47021.162 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Flooring & Tiling Work-(Flat) | 14.359 | 15 | 0 | 215.385 | 38.78 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47089.405 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-401-3BHK Living Terrace Skirting | 2.427 | 17 | 0 | 41.259 | 7.42 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47263.531 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Living Terrace Skirting | 1.968 | 19 | 0 | 37.392 | 6.74 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47267.398 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Flooring & Tiling Work-(Flat) | 14.359 | 15 | 0 | 215.385 | 38.78 | 2024-06-27 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47089.405 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-204-2BHK Living Terrace Skirting | 1.968 | 17 | 0 | 33.456 | 6.02 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47271.334 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-203-2BHK Vitrified Skirting | 15.24 | 18 | 0 | 274.32 | 49.38 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47030.47 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-301-3BHK Vitrified Skirting | 20.77 | 18 | 0 | 373.86 | 67.3 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46930.93 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Vitrified Skirting | 15.24 | 20 | 0 | 304.8 | 54.86 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46999.99 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-403-2BHK Living Terrace Skirting | 1.968 | 17 | 0 | 33.456 | 6.02 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47271.334 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-604-2BHK Living Terrace Skirting | 1.968 | 19 | 0 | 37.392 | 6.74 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47267.398 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Toilet Dado Work | 30.677 | 24 | 0 | 736.248 | 132.52 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46568.542 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Toilet Dado Work | 31.146 | 22 | 0 | 685.212 | 123.34 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46619.578 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-104-2BHK Living Terrace Skirting | 1.968 | 17 | 0 | 33.456 | 6.02 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47271.334 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-504-2BHK Living Terrace Skirting | 1.968 | 19 | 0 | 37.392 | 6.74 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47267.398 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-601-3BHK Living Terrace Skirting | 2.427 | 19 | 0 | 46.113 | 8.3 | 2024-06-27 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47258.677 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Kitchen Dado Work | 3.038 | 24 | 0 | 72.912 | 13.12 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Kitchen Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47231.878 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Toilet Dado Work | 31.146 | 24 | 0 | 747.504 | 134.56 | 2024-06-27 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46557.286 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Vitrified Flooring Work | 50.956 | 18 | 0 | 917.208 | 165.1 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46387.582 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Vitrified Flooring Work | 66.946 | 16 | 0 | 1071.136 | 192.8 | 2024-06-27 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46233.654 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-003-2BHK Vitrified Skirting | 15.24 | 18 | 0 | 274.32 | 49.38 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling. | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -47030.47 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Vitrified Skirting | 15.24 | 22 | 0 | 335.28 | 60.36 | 2024-06-27 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108671 | 2024-07-01 | 47304.79 | 2024-07-11 10:29 | -46969.51 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1203-2BHK Toilet Dado Work | 245.416 | 24 | 0 | 5889.984 | 1060.2 | 2024-03-10 15:19 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139976.466 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-604-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145650.498 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 24 | 0 | 142.656 | 25.68 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145723.794 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1104-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 24 | 0 | 235.584 | 42.4 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145630.866 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145650.498 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145650.498 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 22 | 0 | 1411.344 | 254.04 | 2024-03-10 15:08 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144455.106 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Toilet Dado Work | 245.416 | 24 | 0 | 5889.984 | 1060.2 | 2024-03-10 15:15 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139976.466 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1203-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 24 | 0 | 235.584 | 42.4 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145630.866 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1104-2BHK Toilet Dado Work | 245.416 | 24 | 0 | 5889.984 | 1060.2 | 2024-03-10 15:15 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139976.466 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1202-2BHK(Near Refuse Area) Toilet Dado Work | 249.168 | 24 | 0 | 5980.032 | 1076.4 | 2024-03-10 15:15 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139886.418 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Toilet Dado Work | 249.168 | 24 | 0 | 5980.032 | 1076.4 | 2024-03-10 15:15 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139886.418 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 24 | 0 | 142.656 | 25.68 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145723.794 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-602-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145735.682 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145650.498 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-03-10 15:26 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144143.37 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1103-2BHK Toilet Dado Work | 245.416 | 24 | 0 | 5889.984 | 1060.2 | 2024-03-10 15:15 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -139976.466 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-703-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145650.498 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1102-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 24 | 0 | 142.656 | 25.68 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145723.794 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1201-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 24 | 0 | 142.656 | 25.68 | 2024-03-10 15:25 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145723.794 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Flooring & Tiling Work-(Flat) | 107.6925 | 17 | 0 | 1830.7725 | 329.54 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144035.6775 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-702-2BHK(Near Refuse Area) Comm Passage Wash Basin Dado Wo | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145735.682 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-03-10 15:26 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144143.37 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Flooring & Tiling Work | 125.13 | 17 | 0 | 2127.21 | 382.9 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -143739.24 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Flooring & Tiling Work | 125.13 | 17 | 0 | 2127.21 | 382.9 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -143739.24 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1201-3BHK Flooring & Tiling Work | 125.13 | 17 | 0 | 2127.21 | 382.9 | 2024-03-10 15:28 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -143739.24 | SHIVAM CONSTRUCTION
Dado Work - BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-03-10 15:23 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Common Passage Wash Basin E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -145735.682 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-03-10 15:26 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -143864.37 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Flooring & Tiling Work | 61.568 | 22 | 0 | 1354.496 | 243.82 | 2024-03-10 15:08 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 107229 | 2024-04-30 | 145866.45 | 2024-05-03 13:16 | -144511.954 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -84681.376 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -85752.512 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -86983.936 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -85752.512 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 1735.24 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -84681.376 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -85752.512 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.02 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -87799.232 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.02 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -87799.232 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 1542.44 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -85752.512 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 1320.78 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -86983.936 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.02 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -87799.232 | SHIVAM CONSTRUCTION
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 1174.02 | 2024-06-03 | Labour Charges for- Vitrified Flooring work with floor guard laying. IncludingProper Fixing with line,level,right angle & joint filling. | 100 |  | 107948 | 2024-06-03 | 94321.6 | 2024-06-24 12:11 | -87799.232 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1002-3BHK Flooring & Tiling Work | 61.568 | 24 | 0 | 1477.632 | 265.98 | 2024-06-03 17:30 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108012 | 2024-06-03 | 12069.12 | 2024-06-24 12:11 | -10591.488 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1102-3BHK Flooring & Tiling Work | 61.568 | 24 | 0 | 1477.632 | 265.98 | 2024-06-03 17:30 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108012 | 2024-06-03 | 12069.12 | 2024-06-24 12:11 | -10591.488 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1104-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 24 | 0 | 1539.648 | 277.14 | 2024-06-03 17:30 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108012 | 2024-06-03 | 12069.12 | 2024-06-24 12:11 | -10529.472 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 24 | 0 | 1539.648 | 277.14 | 2024-06-03 17:30 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108012 | 2024-06-03 | 12069.12 | 2024-06-24 12:11 | -10529.472 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 24 | 0 | 1539.648 | 277.14 | 2024-06-03 17:30 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108012 | 2024-06-03 | 12069.12 | 2024-06-24 12:11 | -10529.472 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1101-3BHK Flooring & Tiling Work | 61.568 | 24 | 0 | 1477.632 | 265.98 | 2024-06-03 17:30 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108012 | 2024-06-03 | 12069.12 | 2024-06-24 12:11 | -10591.488 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1103-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 24 | 0 | 1539.648 | 277.14 | 2024-06-03 17:30 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108012 | 2024-06-03 | 12069.12 | 2024-06-24 12:11 | -10529.472 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Flooring & Tiling Work | 61.568 | 24 | 0 | 1477.632 | 265.98 | 2024-06-03 17:30 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108012 | 2024-06-03 | 12069.12 | 2024-06-24 12:11 | -10591.488 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1204-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 24 | 0 | 1539.648 | 277.14 | 2024-06-09 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -98076.362 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1403-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 24 | 0 | 1539.648 | 277.14 | 2024-06-09 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -98076.362 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1404-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 17 | 0 | 1952.824 | 351.5 | 2024-06-09 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -97663.186 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-603-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99316.874 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1303-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 24 | 0 | 1539.648 | 277.14 | 2024-06-09 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -98076.362 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 73.4 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99208.274 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.52 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99285.386 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1302-3BHK Toilet Dado Work | 249.168 | 24 | 0 | 5980.032 | 1076.4 | 2024-06-09 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -93635.978 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99247.106 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-402-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99285.938 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99247.106 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-804-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99316.874 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1001-3BHK Vitrified Skirting | 166.16 | 22 | 0 | 3655.52 | 658 | 2024-06-09 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -95960.49 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1401-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-06-09 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -97346.986 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1203-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 24 | 0 | 1539.648 | 277.14 | 2024-06-09 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -98076.362 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1301-3BHK Toilet Dado Work | 249.168 | 24 | 0 | 5980.032 | 1076.4 | 2024-06-09 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -93635.978 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-803-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.92 | 2024-06-09 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -97177.61 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-904-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99316.874 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1403-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 17 | 0 | 1952.824 | 351.5 | 2024-06-09 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -97663.186 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1303-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 17 | 0 | 1952.824 | 351.5 | 2024-06-09 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -97663.186 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-502-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99247.106 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99247.106 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 482.8 | 2024-06-09 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -96933.77 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1402-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-06-09 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -97346.986 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1003-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 482.8 | 2024-06-09 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -96933.77 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-503-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99316.874 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-602-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99247.106 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1302-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-06-09 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -97346.986 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1304-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 17 | 0 | 1952.824 | 351.5 | 2024-06-09 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -97663.186 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1401-3BHK Flooring & Tiling Work | 61.568 | 24 | 0 | 1477.632 | 265.98 | 2024-06-09 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -98138.378 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-06-09 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -96292.81 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-501-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99247.106 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1201-3BHK Flooring & Tiling Work | 61.568 | 24 | 0 | 1477.632 | 265.98 | 2024-06-09 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -98138.378 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-703-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99316.874 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-902-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99247.106 | SHIVAM CONSTRUCTION
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1301-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-06-09 | Labour charges for fixing of Ceramic Flooring work & Floor Guard Laying work including proper fixing with proper line, level, right angle and joint filling for E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -97346.986 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1402-3BHK Flooring & Tiling Work | 61.568 | 24 | 0 | 1477.632 | 265.98 | 2024-06-09 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -98138.378 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-901-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-06-09 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -96292.81 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1404-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 24 | 0 | 1539.648 | 277.14 | 2024-06-09 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -98076.362 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-504-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99316.874 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-601-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99247.106 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1302-3BHK Flooring & Tiling Work | 61.568 | 24 | 0 | 1477.632 | 265.98 | 2024-06-09 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -98138.378 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1304-2BHK Toilet Dado Work | 245.416 | 24 | 0 | 5889.984 | 1060.2 | 2024-06-09 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -93726.026 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1304-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 24 | 0 | 1539.648 | 277.14 | 2024-06-09 | Labour charges for Fixing of Ceramic Dado work (300 x 600 mm) with including proper line, level, right angle & Joint Filling for E-bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -98076.362 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1004-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 59.52 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99285.386 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-903-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.92 | 2024-06-09 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -97177.61 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-701-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99247.106 | SHIVAM CONSTRUCTION
Ceramic Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-704-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2024-06-09 | Labour Charges for fixing of ceramic Skirting work for Living Terrace and Dry Balcony E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -99316.874 | SHIVAM CONSTRUCTION
Dado BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-1303-2BHK Toilet Dado Work | 245.416 | 24 | 0 | 5889.984 | 1060.2 | 2024-06-09 | Labour Charges for fixing of Ceramic Dado (300 x 600mm) with proper line, level, right angle and joint filling for Master Toilet & Common Toilet Area E-Bldg. | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -93726.026 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-801-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-06-09 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -96292.81 | SHIVAM CONSTRUCTION
Vitrified Skirting BC | N/C | N/C | SHIVAM CONSTRUCTION | 723 | 2023-07-12 | E-802-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-06-09 | Labour charges for Vitrified skirting work with cutting and Fixing in Line, Level, Right Angle & Proper Joint filling for E-Bldg | 100 |  | 108216 | 2024-06-10 | 99616.01 | 2024-06-24 12:10 | -96292.81 | SHIVAM CONSTRUCTION