## Work_Completion_Browse638585483
Work Completion Browse
Project : GANGA DHAM TOWERS
From Date : 01/08/2024 To date: 01/08/2024
Page 1 of 1
Total Records: 191 Records 1 to 191
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 2.25 | 0 | 325.305 | 58.56 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39575.025 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside FC Flr External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 2.25 | 0 | 159.93 | 28.78 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39740.4 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 2.25 | 0 | 159.93 | 28.78 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39740.4 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 2.25 | 0 | 159.93 | 28.78 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39740.4 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 2.25 | 0 | 374.535 | 67.42 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39525.795 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside FC Flr External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside FC Flr External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 2.25 | 0 | 374.535 | 67.42 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39525.795 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 2.25 | 0 | 325.305 | 58.56 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39575.025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside FC Flr External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside FC Flr External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 2.25 | 0 | 159.93 | 28.78 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39740.4 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 2.25 | 0 | 374.535 | 67.42 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39525.795 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 2.25 | 0 | 159.93 | 28.78 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39740.4 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES