## Work_Completion_Browse638585490
Work Completion Browse
Project : GANGA DHAM TOWERS
From Date : 01/08/2024 To date: 01/08/2024
Page 1 of 1
Total Records: 198 Records 1 to 198
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg North Side 27th Floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 3.5 | 0 | 582.61 | 104.86 | 2024-08-03 | Labour charges for Providing, Fixing and Removing of Scaffolding/Gandola for Texture Painting work. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31612.67 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 1.75 | 0 | 124.39 | 22.4 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32070.89 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 3.5 | 0 | 582.61 | 104.86 | 2024-08-03 | Labour charges for Providing, Fixing and Removing of Scaffolding/Gandola for Texture Painting work. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31612.67 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 3.5 | 0 | 582.61 | 104.86 | 2024-08-03 | Labour charges for Providing, Fixing and Removing of Scaffolding/Gandola for Texture Painting work. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31612.67 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 1.75 | 0 | 124.39 | 22.4 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32070.89 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 1.75 | 0 | 291.305 | 52.44 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31903.975 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 1.75 | 0 | 291.305 | 52.44 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31903.975 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 3.5 | 0 | 506.03 | 91.08 | 2024-08-03 | Labour charges for Providing, Fixing and Removing of Scaffolding/Gandola for Texture Painting work. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31689.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 3.5 | 0 | 506.03 | 91.08 | 2024-08-03 | Labour charges for Providing, Fixing and Removing of Scaffolding/Gandola for Texture Painting work. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31689.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 1.75 | 0 | 124.39 | 22.4 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32070.89 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 1.75 | 0 | 124.39 | 22.4 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32070.89 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 1.75 | 0 | 253.015 | 45.54 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31942.265 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 1.75 | 0 | 124.39 | 22.4 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32070.89 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 1.75 | 0 | 291.305 | 52.44 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31903.975 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 1.75 | 0 | 253.015 | 45.54 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31942.265 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES